## Introduction PLEASE READ!
Introduction
This workbook contains the Revised Draft 2024-2033 State Transportation Improvement Program (STIP).
The Full Draft STIP tab lists all projects in the Draft STIP, including those previously selected for funding through the Strategic Transportation Investments (STI) prioritization process, alternate critera projects (interstate maintenance, bridge, safety, and MPO direct attributal projects), exempt projects (such as congestion mitigation projects), transit projects, and others.
The Projects Eligible for Swaps tab is a subset of projects listed on the Full Draft STIP. Projects listed are eligible to be swapped with other projects, as long as both NCDOT and the Metropolitan Planning Organization (MPO) or Rural Planning Organization (RPO) in which the project is located agree to the swap AND the total cost of any project(s) swapped into the Draft STIP is less than 110% of the costs of project(s) swapped out. Please note that only STI funds needed for each phase (right-of-way, utilities, and construction) are listed on this tab. Projects listed on Full Draft STIP include the entire funding needed for each phase.
The Fund Sources tab lists the full title of the fund sources listed on the Full Draft STIP and Projects Eligible for Swaps tabs.
The Swap Projects Schedule Compare tab lists the same projects in the Projects Eligible for Swaps tab and provides the Prioritization score at the time the project was committed, along with a comparison of each project's schedule and committed/prioritization status in the current 2020-2029 STIP, the Draft 2024-2033 STIP released in April 2022, and the revised Draft 2024-2033 STIP released in August 2022.
Please use the filters on the column headers (Row 4) to filter and sort the information for your needs. Projects are initially sorted by County, Mode, Route, and Project ID.
Please note that ALL INFORMATION AND DATA is considered DRAFT and is SUBJECT TO CHANGE. The Final 2024-2033 STIP is anticipated to be presented to the Board of Transportation for approval in May 2023.
Last updated August 4, 2022

## Full Draft STIP
REVISED DRAFT 2024-2033 STATE TRANSPORTATION IMPROVEMENT PROGRAM
NOTES: COSTS AND SCHEDULES ARE AS OF AUGUST 4, 2022 AND ARE SUBJECT TO CHANGE. AMOUNTS SHOWN ARE PROJECT ESTIMATE AMOUNTS REMAINING. ANY AMOUNTS PROGRAMMED FOR ACTIVITIES OTHER THAN RIGHT-OF-WAY, UTILITIES, OR CONSTRUCTION ARE INCLUDED UNDER "OTHER ACTIVITIES".
BASIC PROJECT INFORMATION | [8 empty] | FISCAL YEAR PROJECT PHASE SCHEDULED TO START
COUNTY(S) | ROUTE/CITY | DESCRIPTION | MODE | DIVISION(S) | MPOs/RPOs | PROJECT ID | STI CATEGORY FUNDED | FUNDING SOURCE (SEE FUNDING SOURCES TAB FOR MORE INFO) | RIGHT-OF-WAY PROJECTED SCHEDULE | TOTAL REMAINING FUNDS NEEDED FOR RIGHT-OF-WAY | UTILITIES PROJECTED SCHEDULE | TOTAL REMAINING FUNDS NEEDED FOR UTILITIES | CONSTRUCTION PROJECTED SCHEDULE | TOTAL REMAINING FUNDS NEEDED FOR CONSTRUCTION | PROJECTED SCHEDULE FOR OTHER ACTIVITIES | TOTAL REMAINING FUNDS FOR OTHER ACTIVITIES | TOTAL REMAINING FUNDS NEEDED | COMMENT
ALAMANCE | BURLINGTON- ALAMANCE REGIONAL AIRPORT (BUY) | OBTAIN NAVIGATION EASEMENTS AND CLEAR OBSTRUCTIONS IN THE RUNWAY 24 APPROACH. | AVIATION | 7 | BURLINGTON-GRAHAM MPO | AV-5737 | DIVISION 7 | L, T | 2023 | 1200000 | [6 empty] | 1200000
ALAMANCE | BURLINGTON- ALAMANCE REGIONAL AIRPORT (BUY) | CONSTRUCT 100 FT PAVED OVERRUN AND MAKE SAFETY ENHANCEMENTS. | AVIATION | 7 | BURLINGTON-GRAHAM MPO | AV-5851 | DIVISION 7 | T |  |  |  |  | 2024 | 2080000 |  |  | 2080000
ALAMANCE | LEE AVENUE | WEST LEBANON AVENUE TO SR 1454 (WEST HAGGARD AVENUE) IN ELON. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | BURLINGTON-GRAHAM MPO | EB-5988 | DIVISION 7 | L, TA5200 | 2025 | 5000 |  |  | 2026 | 272000 | 2024 | 30000 | 307000
ALAMANCE | NC 49 / NC 54 (HARDEN STREET) | WEST PINE STREET TO NORTH MARSHALL STREET IN GRAHAM. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | BURLINGTON-GRAHAM MPO | EB-5887 | DIVISION 7 | L, TA5200 | 2023 | 44000 |  |  | 2023 | 105000 |  |  | 149000
ALAMANCE | US 70 (NORTH CHURCH STREET) | SR 1716 (GRAHAM-HOPEDALE ROAD) TO SR 1719 (SELLARS MILL ROAD) IN BURLINGTON. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | BURLINGTON-GRAHAM MPO | EB-5879 | DIVISION 7 | L, TA5200 | 2023 | 28000 |  |  | 2023 | 66000 | 2022 | 16000 | 110000
ALAMANCE | US 70 (NORTH CHURCH STREET) | BEAUMONT AVENUE TO SR 1716 (GRAHAM-HOPEDALE ROAD) IN BURLINGTON. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | BURLINGTON-GRAHAM MPO | EB-5885 | DIVISION 7 | L, TA5200 |  |  |  |  | 2023 | 120000 |  |  | 120000
ALAMANCE | I-40 / I-85 | SR 1007 (MEBANE-OAKS ROAD) IN MEBANE. INTERCHANGE IMPROVEMENTS. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | I-5711 | STATEWIDE MOBILITY | NHP, S(M) |  |  |  |  | 2020 | 13133000 |  |  | 13133000 | UNDER CONSTRUCTION; GARVEE BONDS: $2M FOR CONSTRUCTION - PAYBCK 2021-2035
ALAMANCE | I-40 / I-85 | 0.2 MILE EAST OF NC 49 TO 0.2 MILE EAST OF NC 54 IN GRAHAM. PAVEMENT REHABILITATION. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | I-5836 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION - CONSTRUCTION FUNDED UNDER I-5309
ALAMANCE | I-40 / I-85 | SR 1158 (HUFFMAN MILL ROAD) INTERCHANGE. CONSTRUCT ADDITIONAL LEFT TURN LANE ON I-40 WESTBOUND RAMP AND IMPROVE OPERATIONS AT SR 1308 (GARDEN ROAD) INTERSECTION. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | I-6009 | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1000000 |  |  | 1800000
ALAMANCE | I-40 / I-85 | SR 1981 (TROLLINGWOOD-HAWFIELDS ROAD) IN MEBANE. UPGRADE INTERCHANGE. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | I-6059 | DIVISION 7 | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7100000 |  |  | 7900000
ALAMANCE | I-40 /I-85 | EAST OF GUILFORD COUNTY LINE TO EAST OF NC 49. PAVEMENT REHABILITATION. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | I-5309 | STATEWIDE MOBILITY | [10 empty] | CONSTRUCTION COMPLETED - PROJECT COST INCLUDES I-5836 CONSTRUCTION
ALAMANCE | NC 119 | NC 119 RELOCATION, I-85 TO SOUTH OF SR 1918 (MRS. WHITE ROAD) IN MEBANE. FOUR-TO-SIX-LANE FACILITY ON NEW LOCATION. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-3109
ALAMANCE | NC 119 | NC 119 RELOCATION, I-40 / I-85 TO NORTH OF SR 1921 (MEBANE ROGERS ROAD). | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-3109A | REGION D | T |  |  |  |  | 2019 | 42967000 | 2021 | 360000 | 43327000 | UNDER CONSTRUCTION; BUILD NC BONDS: $14.14 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $282,000 FOR PRELIMINARY ENGINEERING AND $19.247 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
ALAMANCE | NC 119 | NC 119 RELOCATION, NORTH OF SR 1921 (MEBANE ROGERS ROAD) TO SOUTH OF SR 1918 (MRS. WHITE ROAD) | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-3109B | REGION D | T |  |  |  |  | 2021 | 6660000 |  |  | 6660000 | UNDER CONSTRUCTION; BUILD NC BONDS: $5.173 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
ALAMANCE | NC 119 | SR 1981 (TROLLINGWOOD-HAWFIELDS ROAD) / SR 2126 (OLD HILLSBOROUGH ROAD TO LOWES BOULEVARD IN MEBANE. WIDEN TO MULTILANES. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6013 | DIVISION 7 | T | 2023 | 5500000 | 2023 | 900000 | 2024 | 7200000 |  |  | 13600000 | IN PROGRESS
ALAMANCE | NC 49 (ROXBORO ROAD) | SR 1928 (WILKINS ROAD) AND SR 1927 (BASON ROAD). UPGRADE K-TYPE INTERSECTION. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6183 | DIVISION 7 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2900000 |  |  | 4500000
ALAMANCE | NC 54 | SR 1945 (RIVERBEND ROAD) / SR 2431 (JOHNSON STREET) TO SOUTH OF SR 2107 (WHITTEMORE ROAD) IN GRAHAM. IMPROVE SR 1945 (RIVERBEND ROAD) / SR 2431 (JOHNSON STREET) INTERSECTION, UPGRADE RAMP INTERSECTIONS AT I-40 / I-85, IMPROVE SR 2106 (WOODY ROAD) INTERSE | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6115 | REGION D
ALAMANCE | NC 54 (CHAPEL HILL ROAD) | SR 1445 (SOUTH O'NEAL STREET) IN BURLINGTON. RECONFIGURE INTERSECTION TO MAKE O'NEAL STREET THE THROUGH MOVEMENT WITH NC 54 EAST OF THE INTERSECTION. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6184 | DIVISION 7 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8400000 |  |  | 14600000
ALAMANCE | NC 54 (EAST HARDEN STREET) | NC 49 (EAST ELM STREET) IN GRAHAM. INTERSECTION IMPROVEMENTS. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6017 | DIVISION 7 | T | 2022 | 1700000 | 2022 | 643000 | 2023 | 2100000 |  |  | 4443000 | RIGHT-OF-WAY IN PROGRESS
ALAMANCE | NC 54 (EAST HARDEN STREET) | SR 1945 (RIVERBEND ROAD) / SR 2431 (JOHNSON STREET) INTERSECTIONIN GRAHAM. INTERSECTION IMPROVEMENTS. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6115A | DIVISION 7 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2000000 |  |  | 2700000
ALAMANCE | NC 54 (EAST HARDEN STREET) | I-40 / I-85 INTERCHANGE IN GRAHAM. UPGRADE RAMP INTERSECTIONS. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6115B | REGION D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5399000 |  |  | 6299000
ALAMANCE | NC 54 (EAST HARDEN STREET) | SR 2106 (WOODY DRIVE) IN GRAHAM. INTERSECTION IMPROVEMENTS. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6115C | REGION D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2100000 |  |  | 2900000
ALAMANCE | NC 54 (EAST HARDEN STREET) | SR 2106 (WOODY DRIVE) AND SR 2107 (WHITTEMORE ROAD) INTERSECTIONS IN GRAHAM. UPGRADE PIPE CULVERTS 000271 AND 000297. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6115D | REGION D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1600000 |  |  | 1900000
ALAMANCE | NC 54 (WEST HARDEN STREET) | NC 49 (MAPLE AVENUE) IN BURLINGTON. INSTALL DUAL LEFT TURN LANES IN WESTBOUND DIRECTION. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6131 | REGION D | T | 2025 | 4100000 | 2025 | 1100000 | 2026 | 3500000 |  |  | 8700000
ALAMANCE | NC 62 | SR 1430 (RAMADA ROAD) TO US 70 (CHURCH STREET) IN BURLINGTON. WIDEN TO MULTILANES. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-5844 | DIVISION 7 | T | 2024 | 13300000 | 2024 | 3400000 | 2025 | 8700000 |  |  | 25400000
ALAMANCE | NC 62 (ALAMANCE ROAD) | SR 1155 (HATCHERY ROAD) / BONNIE LANE INTERSECTION IN BURLINGTON. INSTALL TRAFFIC SIGNAL AND ADD TURN LANES. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6114 | REGION D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 900000 |  |  | 1800000
ALAMANCE | NC 87 (WEBB AVENUE) | SR 1515 (FLORA AVENUE). INSTALL TRAFFIC SIGNAL AND ADD TURN LANES. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6182 | DIVISION 7 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 180000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1100000 |  |  | 2480000
ALAMANCE | NEW ROUTE | NEW ROUTE, US 70 TO NC 100 IN ELON. CONSTRUCT MULTILANE FACILITY, PART ON NEW LOCATION. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-3110 | [11 empty] | PART B, GARVEE BOND FUNDING $10.5 MILLION; PAYBACK FY 2011 - FY 2022
ALAMANCE | NEW ROUTE | US 70 TO NORTH OF SR 1309 (WESTBROOK AVENUE) | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-3110A | [11 empty] | COMPLETE
ALAMANCE | NEW ROUTE | IMPROVEMENTS ON SR 1311 (COOK ROAD), SR 1309 (WESTBROOK AVENUE) TO NC 100, PART ON NEW LOCATION | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-3110B | PRE-STI (TRANSITION) | BG5200 |  |  |  |  | 2011 | 3444000 |  |  | 3444000 | COMPLETE. PART B, GARVEE BOND FUNDING $10.5 MILLION; PAYBACK FY 2011 - FY 2022
ALAMANCE | SR 1212 (POND ROAD) | REPLACE BRIDGE 000170 OVER PRONG OF ALAMANCE CREEK IN ALAMANCE. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | B-5347 | HIGHWAY FUND | [10 empty] | UNDER CONSTRUCTION
ALAMANCE | SR 1301 (BOONE STATION DRIVE) | SR 1301 (ST. MARKS CHURCH ROAD) / JAVA LANE AND GLIDWELL DRIVE / TIKI LANE IN BURLINGTON. INSTALL PEDESTRIAN SIGNALS AND CURB RAMPS, AND REVISE PAVEMENT MARKINGS. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | W-5807B | DIVISION 7 | HSIP |  |  |  |  | 2023 | 75000 |  |  | 75000
ALAMANCE | SR 1455 (EAST HAGGARD AVENUE) | NC 87 (WEST WEBB AVENUE) / NC 100 (UNIVERSITY DRIVE) IN ELON. IMPROVE INTERSECTION. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6214 | DIVISION 7 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5600000 |  |  | 11400000
ALAMANCE | SR 1716 (GRAHAM- HOPEDALE ROAD) | SR 1720 (WEST HANOVER ROAD) TO MORNINGSIDE DRIVE IN BURLINGTON. WIDEN TO MULTILANES WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6014 | DIVISION 7 | T | 2023 | 4700000 | 2023 | 1200000 | 2025 | 13200000 |  |  | 19100000
ALAMANCE | SR 1716 (NORTH MAIN STREET) | SR 2396 (WEST PARKER STREET) IN GRAHAM. IMPROVE INTERSECTION. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6132 | DIVISION 7 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1500000 |  |  | 2200000
ALAMANCE | SR 1928 (TROLLINGWOOD ROAD) | REPLACE BRIDGE 000068 OVER NCRR / NORFOLK SOUTHERN RAILROAD IN HAW RIVER. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | B-6052 | DIVISION 7 | S | 2024 | 500000 |  |  | 2026 | 2500000 |  |  | 3000000 | "S" FUNDS REFLECT STATE BRIDGE PROGRAM FUNDING
ALAMANCE | US 70 (NORTH CHURCH STREET) | SR 1817 (GRAHAM-HOPEDALE ROAD) IN BURLINGTON. INTERSECTION IMPROVEMENTS. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-5843 | DIVISION 7 | T |  |  |  |  | 2019 | 2167000 | 2021 | 810000 | 2977000 | UNDER CONSTRUCTION; BUILD NC BONDS: $654,000 FOR CONSTRUCTION - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), $627,000 FOR PRELIMINARY ENGINEERING AND $1.152 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
ALAMANCE | US 70 (SOUTH CHURCH STREET) | TARLETON AVENUE TO FIFTH STREET IN BURLINGTON. WIDEN AND CONSTRUCT CENTER TURN LANE. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6009 | REGION D | T | 2028 | 26600000 | 2028 | 5100000 | 2030 | 11700000 |  |  | 43400000
ALAMANCE | US 70 (SOUTH CHURCH STREET) | SR 1226 / SR 1311 (UNIVERSITY DRIVE) IN BURLINGTON. INTERSECTION IMPROVEMENTS, TO INCLUDE WIDENING OF US 70 TO MAINTAIN CONSISTENT CROSS-SECTION WITH PROJECT U-5752 IMPROVEMENTS. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6010 | REGION D | T | 2020 | 6000000 |  |  | 2022 | 16100000 |  |  | 22100000 | UNDER CONSTRUCTION
ALAMANCE | US 70 (SOUTH CHURCH STREET) | SR 1158 (HUFFMAN MILL ROAD) IN BURLINGTON. INTERSECTION IMPROVEMENTS. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6011 | REGION D | T | 2022 | 3000000 | 2022 | 600000 | 2025 | 2400000 |  |  | 6000000 | RIGHT OF WAY IN PROGRESS
ALAMANCE | VARIOUS | UPGRADE BURLINGTON-GRAHAM SIGNAL SYSTEM. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6015 | DIVISION 7 | T |  |  |  |  | 2021 | 6125000 |  |  | 6125000 | UNDER CONSTRUCTION; BUILD NC BONDS: $4.759 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
ALAMANCE | ALAMANACE COUNTY TRANSPORTATION | FUNDING FOR PREVENTIVE MAINTENANCE. | PUBLIC TRANSIT | 7 | BURLINGTON-GRAHAM MPO | TG-6811B | PUBLIC TRANSIT | FED, L | [6 empty] | 2020 | 46000 | 46000
ALAMANCE | ALAMANACE COUNTY TRANSPORTATION | ADMINISTRATION | PUBLIC TRANSIT | 7 | BURLINGTON-GRAHAM MPO | TK-6103 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 1424000 | 1424000 | FUNDS AUTHORIZED IN PROGRESS
ALAMANCE | ALAMANACE COUNTY TRANSPORTATION | OPERATING FOR ALAMANCE COUNTY TRANSPORTATION IN THE BURLINGTON URBAN AREA - THROUGH NCDOT | PUBLIC TRANSIT | 7 | BURLINGTON-GRAHAM MPO | TO-5214 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 7813000 | 7813000 | FUNDS AUTHORIZED IN PROGRESS
ALAMANCE | BURLINGTON | CAPITAL FOR PEDESTRIAN IMPROVEMENTS FOR FIXED ROUTR SERVICES | PUBLIC TRANSIT | 7 | BURLINGTON-GRAHAM MPO | TD-6322 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 60000 | 60000 | ADD PROJECT TD-6322 TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO.
ALAMANCE | BURLINGTON | ADA SERVICES | PUBLIC TRANSIT | 7 | BURLINGTON-GRAHAM MPO | TG-6812A | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 211000 | 211000 | ADD PROJECT TG-6812A TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO.
ALAMANCE | BURLINGTON | PLANNING FOR PLANNING FOR FIXED ROUTE SERVICE EXPANSION | PUBLIC TRANSIT | 7 | BURLINGTON-GRAHAM MPO | TP-5161 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 5000 | 5000 | ADD PROJECT TP-5161 TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO.
ALAMANCE | BURLINGTON | PLANNING FOR PLANNING FACILITY FEASIBILITY STUDY | PUBLIC TRANSIT | 7 | BURLINGTON-GRAHAM MPO | TP-5162 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 95000 | 95000 | ADD PROJECT TP-5162 TO STIP FOR FFY2019. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT REQUEST OF BGMPO.
ALAMANCE | LINK TRANSIT | OPERATING ASSISTANCE TO MAINTAIN CURRENT LEVEL OF SERVICE IN ADDITION TO SERVICE EXPANSION FOR WEEKEND SERVICE. | PUBLIC TRANSIT | 7 | BURLINGTON-GRAHAM MPO | TO-6170 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2021 | 4199000 | 4199000 | MOVE FUNDING FROM PREVIOUS YEARS TO FY 2021 AND FY 2022 AT THE REQUEST OF BGMPO.
ALAMANCE | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | OPERATING | PUBLIC TRANSIT | 7 | BURLINGTON-GRAHAM MPO | TO-5134 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 3806000 | 3806000 | FUNDS AUTHORIZED IN PROGRESS
ALAMANCE | REGIONAL TRANS. PIEDMONT AUTHORITY FOR | ROUTINE CAPITAL, PASSENGER AMENITIES, PARTS, EQUIPMENT, PREVENTIVE MAINTENANCE, AND CAPITAL COST OF CONTRACTING. | PUBLIC TRANSIT | 7 | BURLINGTON-GRAHAM MPO | TG-6137B | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 750000 | 750000
ALAMANCE | PIEDMONT CORRIDOR | GRAHAM TO HAW RIVER. SIDING AND CURVE REALIGNMENT. | RAIL | 7 | BURLINGTON-GRAHAM MPO | P-5205 | PRE-STI (TRANSITION) | [10 empty] | COMPLETED
ALAMANCE, CASWELL, GUILFOR D, ORANGE, ROCKINGHAM | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 7 | PIEDMONT TRIAD RPO, BURLINGTON-GRAHAM MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, GREENSBORO URBAN AREA MPO, HIGH POINT URBAN AREA MPO, TRIANGLE AREA RPO | W-5707REG | REGION D | HSIP | 2020 | 90000 |  |  | 2020 | 555000 |  |  | 645000
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | DIVISION 7 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | BIKE/PED | 7 | PIEDMONT TRIAD RPO, BURLINGTON-GRAHAM MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, GREENSBORO URBAN AREA MPO, HIGH POINT URBAN AREA MPO, TRIANGLE AREA RPO | BO-2407 | DIVISION 7 | S, TA |  |  |  |  | 2024 | 10000000 |  |  | 10000000
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 7. | HIGHWAY | 7 | PIEDMONT TRIAD RPO, BURLINGTON-GRAHAM MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, GREENSBORO URBAN AREA MPO, HIGH POINT URBAN AREA MPO, TRIANGLE AREA RPO | HS-2007 | DIVISION 7
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | VARIOUS SECONDARY ROUTES. INSTALL LONG-LIFE PAVEMENT MARKINGS. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO, GREENSBORO URBAN AREA MPO, PIEDMONT TRIAD RPO, TRIANGLE AREA RPO | HS-2007C | DIVISION 7 | HSIP |  |  |  |  | 2021 | 3455000 |  |  | 3455000
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | DIVISION 7 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | HIGHWAY | 7 | PIEDMONT TRIAD RPO, BURLINGTON-GRAHAM MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, GREENSBORO URBAN AREA MPO, HIGH POINT URBAN AREA MPO, TRIANGLE AREA RPO | R-5787 | DIVISION 7 | S, TA |  |  |  |  | 2020 | 3600000 |  |  | 3600000 | IN PROGRESS; "S" FUNDS REFLECT STATE HIGHWAY FUNDS
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | DIVISION 7 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | 7 | PIEDMONT TRIAD RPO, BURLINGTON-GRAHAM MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, GREENSBORO URBAN AREA MPO, HIGH POINT URBAN AREA MPO, TRIANGLE AREA RPO | W-5207 | [11 empty] | COMPLETED
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 7. | HIGHWAY | 7 | PIEDMONT TRIAD RPO, BURLINGTON-GRAHAM MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, GREENSBORO URBAN AREA MPO, HIGH POINT URBAN AREA MPO, TRIANGLE AREA RPO | W-5707 | [11 empty] | IN PROGRESS
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 7 | PIEDMONT TRIAD RPO, BURLINGTON-GRAHAM MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, GREENSBORO URBAN AREA MPO, HIGH POINT URBAN AREA MPO, TRIANGLE AREA RPO | W-5707DIV | DIVISION 7 | HSIP | 2020 | 90000 |  |  | 2020 | 555000 |  |  | 645000
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 7 | PIEDMONT TRIAD RPO, BURLINGTON-GRAHAM MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, GREENSBORO URBAN AREA MPO, HIGH POINT URBAN AREA MPO, TRIANGLE AREA RPO | W-5707SW | STATEWIDE MOBILITY | HSIP | 2020 | 120000 |  |  | 2020 | 740000 |  |  | 860000
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 7. | HIGHWAY | 7 | PIEDMONT TRIAD RPO, BURLINGTON-GRAHAM MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, GREENSBORO URBAN AREA MPO, HIGH POINT URBAN AREA MPO, TRIANGLE AREA RPO | W-5807 | [11 empty] | INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 7. | RAIL | 7 | PIEDMONT TRIAD RPO, BURLINGTON-GRAHAM MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, GREENSBORO URBAN AREA MPO, HIGH POINT URBAN AREA MPO, TRIANGLE AREA RPO | RC-2007 | DIVISION 7 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
ALAMANCE, CASWELL, GUILFORD, ORANGE, ROCKINGHAM | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 7. | RAIL | 7 | PIEDMONT TRIAD RPO, BURLINGTON-GRAHAM MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, GREENSBORO URBAN AREA MPO, HIGH POINT URBAN AREA MPO, TRIANGLE AREA RPO | RX-2007 | DIVISION 7
ALAMANCE, GUILFORD | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | OPERATING ASSISTANCE | PUBLIC TRANSIT | 7 | BURLINGTON-GRAHAM MPO | TO-5136 | PUBLIC TRANSIT | SMAP | [6 empty] | 2020 | 3268000 | 3268000 | FUNDS AUTHORIZED IN PROGRESS
ALAMANCE, ORANGE | I-40 / I-85 | EAST OF NC 54 IN GRAHAM IN ALAMANCE COUNTY TO WEST OF SR 1114 (BUCKHORN ROAD) IN ORANGE COUINTY. PAVEMENT REHABILITATION. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | I-5954 | STATEWIDE MOBILITY | [10 empty] | COMPLETED
ALEXANDER | ALEXANDER COUNTY | CONSTRUCT ACCESS ROAD INTO ALEXANDER INDUSTRIAL PARK. | HIGHWAY | 12 | GREATER HICKORY MPO | R-5870 | EXEMPT | ADHSL, T |  |  |  |  | 2021 | 1675000 |  |  | 1675000 | ARC PROJECT NO. 19094, AWARD AMOUNT = $1,500,000; $500,000 IS ECONOMIC DEVELOPMENT FUNDING
ALEXANDER | NC 127 | REPLACE BRIDGE 010001 OVER DUCK CREEK. | HIGHWAY | 12 | GREATER HICKORY MPO | B-5954 | REGION F | HFB | 2025 | 200000 |  |  | 2026 | 4701000 |  |  | 4901000
ALEXANDER | NC 16 | INTERSECTION OF NC 16 AND SR 1609 (COUNTY HOME ROAD). CONSTRUCT INTERSECTION IMPROVMENTS. | HIGHWAY | 12 | GREATER HICKORY MPO | R-5762 | DIVISION 12 | T | 2022 | 120000 |  |  | 2023 | 500000 |  |  | 620000
ALEXANDER | NC 16 | CATAWBA RIVER TO US 64 IN TAYLORSVILLE. UPGRADE AND MODERNIZE TWO-LANE ROADWAY. | HIGHWAY | 12 | GREATER HICKORY MPO | U-6151 | NOT FUNDED | T | NOT FUNDED | 17300000 | NOT FUNDED | 3500000 | NOT FUNDED | 55000000 |  |  | 75800000
ALEXANDER | SR 1348 | REPLACE BRIDGE 10291 OVER DUCK CREEK. | HIGHWAY | 12 | GREATER HICKORY MPO | BR-0201 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 1050000 |  |  | 1050000 | THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.12.R.88
ALEXANDER | US 64 | US 64 AND SR 1124. ADD LEFT TURN LANE ON WESTBOUND US 64/NC 90 | HIGHWAY | 12 | GREATER HICKORY MPO | U-6041 | DIVISION 12 | T | 2024 | 200000 | 2024 | 400000 | 2025 | 1450000 |  |  | 2050000
ALEXANDER, BURKE, CALDWELL, CATAWBA | OF CLEVELAND COUNTY TRANSPORTATION ADMIN. | REPLACEMENT - LIGHT TRANSIT VEHICLE | PUBLIC TRANSIT | 11, 12, 13 |  | TA-6507 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 920000 | 920000 | FUNDS AUTHORIZED IN PROGRESS
ALEXANDER, BURKE, CALDWELL, CATAWBA | REGIONAL TRANSPORTATION WESTERN PIEDMONT | REPLACEMENT VAN | PUBLIC TRANSIT | 11, 12, 13 |  | TA-6501 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 184000 | 184000 | FUNDS AUTHORIZED IN PROGRESS
ALEXANDER, BURKE, CALDWELL, CATAWBA | REGIONAL TRANSPORTATION WESTERN PIEDMONT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC | PUBLIC TRANSIT | 11, 12, 13 | GREATER HICKORY MPO | TG-4774 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 200000 | 200000 | FUNDS AUTHORIZED IN PROGRESS
ALEXANDER, BURKE, CALDWELL, CATAWBA | REGIONAL TRANSPORTATION WESTERN PIEDMONT | PREVENTIVE MAINTENANCE | PUBLIC TRANSIT | 11, 12, 13 | GREATER HICKORY MPO | TG-4774A | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2000000 | 2000000 | FUNDS AUTHORIZED IN PROGRESS
ALEXANDER, BURKE, CALDWELL, CATAWBA | REGIONAL TRANSPORTATION WESTERN PIEDMONT | OPERATING ASSISTANCE - ADA PARATRANSIT SERVICE | PUBLIC TRANSIT | 11, 12, 13 | GREATER HICKORY MPO | TG-4774B | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 444000 | 444000 | FUNDS AUTHORIZED IN PROGRESS
ALEXANDER, BURKE, CALDWELL, CATAWBA | REGIONAL TRANSPORTATION WESTERN PIEDMONT | ROUTINE CAPITAL - SERVICE VEHICLE | PUBLIC TRANSIT | 11, 12, 13 |  | TG-6142A | PUBLIC TRANSIT | 5311, L | [6 empty] | 2021 | 39000 | 39000 | FUNDS AUTHORIZED IN PROGRESS
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT COUNCIL OF GOVERNMENTS | PLANNING ASSISTANCE - 5303 | PUBLIC TRANSIT | 11, 12, 13 | GREATER HICKORY MPO | TP-5106 | PUBLIC TRANSIT | 5303, L, S | [6 empty] | 2020 | 401000 | 401000 | MODIFY FUNDING IN FY 21, FY 22, AND FY 23, CONSISTENT WITH FTA ALLOCATION FOR MPO REGION AND ADOPTED UPWP
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | REPLACEMENT VAN | PUBLIC TRANSIT | 11, 12, 13 | GREATER HICKORY MPO | TA-4929 | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 1893000 | 1893000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | PLANNING ASSISTANCE | PUBLIC TRANSIT | 11, 12, 13 | GREATER HICKORY MPO | TP-4733B | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 327000 | 327000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23 MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | OPERATING ASSISTANCE - ELDERLY AND DISABLED PERSONS | PUBLIC TRANSIT | 11, 12, 13 | GREATER HICKORY MPO | TQ-6507 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2020 | 1294000 | 1294000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, FY 23
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSPORTATION | REPLACEMENT BUS | PUBLIC TRANSIT | 11, 12, 13 | GREATER HICKORY MPO | TA-4927 | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 360000 | 360000 | FUNDS AUTHORIZED IN PROGRESS
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSPORTATION | EXPANSION BUS | PUBLIC TRANSIT | 11, 12, 13 | GREATER HICKORY MPO | TA-4928 | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2021 | 362000 | 362000
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSPORTATION | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC | PUBLIC TRANSIT | 11, 12, 13 |  | TG-6159 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 80000 | 80000 | FUNDS AUTHORIZED IN PROGRESS
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSPORTATION | ADMINISTRATION | PUBLIC TRANSIT | 11, 12, 13 |  | TK-5181 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 1420000 | 1420000 | FUNDS AUTHORIZED IN PROGRESS
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSPORTATION | OPERATING ASSISTANCE - NON-URBAN | PUBLIC TRANSIT | 11, 12, 13 | GREATER HICKORY MPO | TM-6108 | PUBLIC TRANSIT | 5316, L | [6 empty] | 2020 | 736000 | 736000 | FUNDS AUTHORIZED IN PROGRESS
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSPORTATION | OPERATING ASSISTANCE - SMALL-URBAN | PUBLIC TRANSIT | 11, 12, 13 | GREATER HICKORY MPO | TN-6109 | PUBLIC TRANSIT | 5317, L | [6 empty] | 2020 | 120000 | 120000 | FUNDS AUTHORIZED IN PROGRESS
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSPORTATION | OPERATING ASSISTANCE | PUBLIC TRANSIT | 11, 12, 13 | GREATER HICKORY MPO | TO-4733 | PUBLIC TRANSIT | 5307, L, SMAP | [6 empty] | 2020 | 4954000 | 4954000 | FUNDS AUTHORIZED IN PROGRESS
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSPORTATION | OPERATING ASSISTANCE | PUBLIC TRANSIT | 11, 12, 13 |  | TO-6109 | PUBLIC TRANSIT | 5311, L | [6 empty] | 2020 | 784000 | 784000 | FUNDS AUTHORIZED IN PROGRESS
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSPORTATION | PLANNING ASSISTANCE | PUBLIC TRANSIT | 11, 12, 13 | GREATER HICKORY MPO | TP-4733A | PUBLIC TRANSIT | 5307 | [6 empty] | 2020 | 210000 | 210000 | FUNDS AUTHORIZED IN PROGRESS
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSPORTATION | PREVENTIVE MAINTENANCE - PARATRANSIT | PUBLIC TRANSIT | 11, 12, 13 | GREATER HICKORY MPO | TQ-6503 | PUBLIC TRANSIT | 5310, L, S | [6 empty] | 2020 | 38000 | 38000 | FUNDS AUTHORIZED IN PROGRESS
ALEXANDER, BURKE, CALDWELL, CATAWBA | WESTERN PIEDMONT REGIONAL TRANSPORTATION | SAFETY & SECURITY | PUBLIC TRANSIT | 11, 12, 13 | GREATER HICKORY MPO | TS-5128 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 24000 | 24000 | FUNDS AUTHORIZED IN PROGRESS
ALEXANDER, CATAWBA | NC 127 | SR 1400 (CLONINGER MILL ROAD) TO SR 1156 (RICHEY ROAD). INCLUDES CONSTRUCTION OF RIGHT TURN LANE ON NC 127 AT SR 1146 (BETHLEHEM SCHOOL ROAD) (FORMERLY U-6040). UPGRADE TWO LANES AND PROVIDE SOME MULTI-LANE CURB AND GUTTER. | HIGHWAY | 12 | GREATER HICKORY MPO | R-3603
ALEXANDER, CATAWBA | NC 127 | SR 1400 (CLONINGER MILL ROAD) TO SR 1156 (RICHEY ROAD). | HIGHWAY | 12 | GREATER HICKORY MPO | R-3603A | DIVISION 12 | T | 2024 | 26900000 | 2024 | 100000 | 2026 | 55100000 |  |  | 82100000 | INCLUDES CONSTRUCTION OF RIGHT TURN LANE ON NC 127 AT SR 1146 (BETHLEHEM SCHOOL ROAD) (FORMERLY U-6040).
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | DIVISION 12 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | BIKE/PED | 12 | GASTON-CLEVELAND-LINCOLN MPO, GREATER HICKORY MPO, CHARLOTTE REGIONAL TPO | BO-2412 | DIVISION 12 | S, TA |  |  |  |  | 2024 | 4000000 |  |  | 4000000
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 12. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO, GREATER HICKORY MPO, CHARLOTTE REGIONAL TPO | HS-2012 | DIVISION 12 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | DIVISION 12 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO, GREATER HICKORY MPO, CHARLOTTE REGIONAL TPO | R-5792 | DIVISION 12 | S, TA |  |  |  |  | 2020 | 3500000 |  |  | 3500000 | UNDER CONSTRUCTION. "S" FUNDS ARE STATE HIGHWAY FUNDS
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | DIVISION 12 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO, GREATER HICKORY MPO, CHARLOTTE REGIONAL TPO | W-5212 | [11 empty] | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS; SEGMENT J: ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. STATE MATCH TO BE FUNDED WITH SPOT SAFETY FUNDS.
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 12. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO, GREATER HICKORY MPO, CHARLOTTE REGIONAL TPO | W-5712 | [11 empty] | IN PROGRESS
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO, GREATER HICKORY MPO, CHARLOTTE REGIONAL TPO | W-5712DIV | DIVISION 12 | HSIP | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO, GREATER HICKORY MPO, CHARLOTTE REGIONAL TPO | W-5712REG | REGION F | HSIP | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO, GREATER HICKORY MPO, CHARLOTTE REGIONAL TPO | W-5712SW | STATEWIDE MOBILITY | HSIP | 2020 | 160000 |  |  | 2020 | 960000 |  |  | 1120000
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 12. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO, GREATER HICKORY MPO, CHARLOTTE REGIONAL TPO | W-5812 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 12. | RAIL | 12 | GASTON-CLEVELAND-LINCOLN MPO, GREATER HICKORY MPO, CHARLOTTE REGIONAL TPO | RC-2012 | DIVISION 12 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
ALEXANDER, CATAWBA, CLEVELAND, GASTON, IREDELL, LINCOLN | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 12. | RAIL | 12 | GASTON-CLEVELAND-LINCOLN MPO, GREATER HICKORY MPO, CHARLOTTE REGIONAL TPO | RX-2012 | DIVISION 12 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
ALLEGHANY | SR 1422 | REPLACE BRIDGE 20035 OVER GLADE CREEK. | HIGHWAY | 11 | HIGH COUNTRY RPO | BR-0206 | HIGHWAY FUND | HFB |  |  |  |  | 2022 | 750000 |  |  | 750000 | THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.157
ALLEGHANY | SR 1433 | REPLACE BRIDGE 20133 OVER LITTLE RIVER. | HIGHWAY | 11 | HIGH COUNTRY RPO | BR-0207 | HIGHWAY FUND | HFB |  |  |  |  | 2022 | 500000 |  |  | 500000 | THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.159
ALLEGHANY | ALLEGHANY COUNTY | ADMINISTRATION | PUBLIC TRANSIT | 11 | HIGH COUNTRY RPO | TK-6105 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 620000 | 620000 | FUNDS AUTHORIZED IN PROGRESS
ANSON | NEW ROUTE - WADESBORO BYPASS | US 74 WEST OF WADESBORO TO US 74 EAST OF WADESBORO. CONSTRUCT FREEWAY ON NEW LOCATION. | HIGHWAY | 10 | ROCKY RIVER RPO | R-5878
ANSON | NEW ROUTE - WADESBORO BYPASS | US 74 WEST OF WADESBORO TO US 52 NORTH OF WADESBORO. CONSTRUCT FREEWAY ON NEW LOCATION. | HIGHWAY | 10 | ROCKY RIVER RPO | R-5878A | NOT FUNDED | NHP | NOT FUNDED | 4000000 | NOT FUNDED | 600000 | NOT FUNDED | 104300000 |  |  | 108900000
ANSON | NEW ROUTE - WADESBORO BYPASS | US 52 NORTH OF WADESBORO TO US 74 EAST OF WADESBORO. CONSTRUCT FREEWAY ON NEW LOCATION. | HIGHWAY | 10 | ROCKY RIVER RPO | R-5878B | REGION E | T | 2027 | 32400000 | 2027 | 1300000 | 2029 | 121799000 |  |  | 155499000
ANSON | SR 1142 (CITY POND ROAD) | REPLACE BRIDGE 030075 OVER NORTH FORK JONES CREEK. | HIGHWAY | 10 | ROCKY RIVER RPO | B-5809 | DIVISION 10 | BGOFF | 2020 | 105000 |  |  | 2022 | 1353000 |  |  | 1458000
ANSON | SR 1627 (PINKSTON ROAD) | REPLACE BRIDGE OVER WSSB RAILROAD. | HIGHWAY | 10 | ROCKY RIVER RPO | B-4410 | [11 empty] | LOCAL FUNDING PROVIDED BY TOWN OF ANSONVILLE
ANSON | SR 1627 (PINKSTON ROAD) | INSTALL WATERLINE IN TOWN OF ANSONVILLE PER UTILITY CONSTRUCTION AGREEMENT. | HIGHWAY | 10 | ROCKY RIVER RPO | B-4410A | PRE-STI (TRANSITION) | L, T | 2022 | 25000 |  |  | 2023 | 360000 |  |  | 385000
ANSON | SR 1634 (GRASSY ISLAND ROAD) | REPLACE BRIDGE 030007 OVER BROWN CREEK. NC FLAP DOT 1634(1). | HIGHWAY | 10 | ROCKY RIVER RPO | B-5817 | EXEMPT | [10 empty] | STATE MATCHING FUNDS FROM DIVISION 10 17BP FUNDS. COMPLETED.
ANSON | SR 1812 (DIGGS ROAD) | REPLACE BRIDGE 030039 OVER JONES CREEK. | HIGHWAY | 10 | ROCKY RIVER RPO | B-6048 | DIVISION 10 | BGOFF | 2023 | 190000 |  |  | 2024 | 1900000 |  |  | 2090000
ANSON | US 74 | NC 742 (GRAHAM STREET) TO ANSON HIGH SCHOOL ROAD. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 10 | ROCKY RIVER RPO | R-5871 | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10800000 |  |  | 25100000
ANSON | US 74 (ANDREW JACKSON HIGHWAY) | GRAHAM STREET TO SR 1749. CONSTRUCT MEDIAN. | HIGHWAY | 10 | ROCKY RIVER RPO | R-5798 | STATEWIDE MOBILITY | T | 2024 | 14800000 | 2024 | 4900000 | 2026 | 21300000 |  |  | 41000000
ANSON | WADESBORO | REPLACE BRIDGE 030316 ON BURNS STREET OVER LAMPLEY CREEK. | HIGHWAY | 10 | ROCKY RIVER RPO | B-5988 | DIVISION 10 | BGOFF, L | 2021 | 169000 |  |  | 2022 | 1211000 |  |  | 1380000 | PLANNING/DESIGN BY TOWN OF WADESBORO
ANSON | ANSON COUNTY | ADMINISTRATION | PUBLIC TRANSIT | 10 | ROCKY RIVER RPO | TK-6106 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 820000 | 820000 | FUNDS AUTHORIZED IN PROGRESS
ANSON | CSX SF LINE | CONSTRUCT SIDING EXTENSION IN POLKTON | RAIL | 10 | ROCKY RIVER RPO | P-5750 | [11 empty] | DP REPRESENTS FEDERAL INFRA GRANT FUNDS
ANSON | CSX SF LINE | CONSTRUCT SIDING EXTENSION IN POLKTON. | RAIL | 10 | ROCKY RIVER RPO | P-5750A | REGION E | DP, T | 2024 | 600000 |  |  | 2024 | 13037000 |  |  | 13637000
ANSON | CSX SF LINE | SR 1469 (FREEDOM ROAD) INTERSECTION. CONSTRUCT GRADE SEPARATION. | RAIL | 10 | ROCKY RIVER RPO | P-5750B | REGION E | T |  |  |  |  | 2026 | 16380000 |  |  | 16380000
ANSON | SR 1714 (STANBACK FERRY ICE PLANT ROAD) | CSX CROSSING 631750C NEAR WADESBORO. CONSTRUCT SAFETY IMPROVEMENTS. | RAIL | 10 | ROCKY RIVER RPO | RX-2010B | DIVISION 10 | RR |  |  |  |  | 2023 | 800000 |  |  | 800000
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | DIVISION 10 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | BIKE/PED | 10 | ROCKY RIVER RPO, CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | BO-2410 | DIVISION 10 | S, TA |  |  |  |  | 2024 | 4000000 |  |  | 4000000
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 10. | HIGHWAY | 10 | ROCKY RIVER RPO, CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | HS-2010 | DIVISION 10 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | DIVISION 10 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | HIGHWAY | 10 | ROCKY RIVER RPO, CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | R-5790 | DIVISION 10 | S, TA |  |  |  |  | 2020 | 3500000 |  |  | 3500000 | UNDER CONSTRUCTION. "S" FUNDS ARE STATE HIGHWAY FUNDS
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | DIVISION 10 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | 10 | ROCKY RIVER RPO, CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | W-5210 | [11 empty] | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 10. | HIGHWAY | 10 | ROCKY RIVER RPO, CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | W-5710 | [11 empty] | STATE MATCH FOR SEGMENTS Y & Z ARE SPOT SAFETY FUNDS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES.
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 10 | ROCKY RIVER RPO, CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | W-5710DIV | DIVISION 10 | HSIP | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 10 | ROCKY RIVER RPO, CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | W-5710REG | REGION E | HSIP | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 10 | ROCKY RIVER RPO, CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | W-5710SW | STATEWIDE MOBILITY | HSIP | 2020 | 160000 |  |  | 2020 | 960000 |  |  | 1120000
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 10. | HIGHWAY | 10 | ROCKY RIVER RPO, CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | W-5810 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 10. | RAIL | 10 | ROCKY RIVER RPO, CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | RC-2010 | DIVISION 10 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
ANSON, CABARRUS, MECKLENBURG, STANLY, UNION | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 10. | RAIL | 10 | ROCKY RIVER RPO, CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | RX-2010 | DIVISION 10 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
ANSON, ROBESON, RICHMOND, SCOTLAND, UNION | US 74 | EASTERN END OF MONROE BYPASS TO I-95 IN LUMBERTON. INSTALL BROADBAND AND ITS COMPONENTS INCLUDING CONNECTIONS TO SIGNAL SYSTEMS, DMS, AND CCTV. | HIGHWAY | 6, 8, 10 | LUMBER RIVER RPO, ROCKY RIVER RPO, CHARLOTTE REGIONAL TPO | HO-0002B | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2021 | 14216000 |  |  | 14216000 | LETTING TO BE COMBINED WITH R-5777D, I-5986C, HO-0002A, AND HO-0002C. UNDER CONSTRUCTION.
ASHE | ASHE COUNTY AIRPORT (GEV) | CONSTRUCT APRON EXPANSONS. | AVIATION | 11 | HIGH COUNTRY RPO | AV-5848 | DIVISION 11 | T |  |  |  |  | 2021 | 2700000 |  |  | 2700000 | Under construction
ASHE | NC 194 | BRIDGE 040008 ON NC 194 OVER NORTH FORK NEW RIVER | HIGHWAY | 11 | HIGH COUNTRY RPO | BR-0002 | REGION F | HFB |  |  |  |  | 2022 | 5500000 |  |  | 5500000 | RIGHT OF WAY IN PROGRESS.
ASHE | NC 88 | NC 88 TO NC 194. UPGRADE ROADWAY. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5832 | DIVISION 11 | T | 2023 | 12200000 | 2023 | 1500000 | 2025 | 45191000 |  |  | 58891000 | BUILD NC BOND FUNDING: $19M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE)
ASHE | NORTHWEST DRIVE, AEV LANE | NORTHWEST DRIVE FROM NC 88 TO BENFIELD DRIVE AND AEV LANE FROM NORTHWEST DRIVE TO AEV FACILITY. WIDEN ROADWAYS AND INSTALL SIGNAL AT NC 88 AND NORTHWEST DRIVE. | HIGHWAY | 11 | HIGH COUNTRY RPO | HA-0006 | EXEMPT | ADHSL | 2023 | 60000 |  |  | 2024 | 643000 | 2022 | 47000 | 750000 | ARC PROJECT NO. 20568, AWARD AMOUNT = $750,000
ASHE | US 221 | SR 1003 (IDLEWILD ROAD) TO NORTH OF SOUTH FORK NEW RIVER | HIGHWAY | 11 | HIGH COUNTRY RPO | R-2915B | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
ASHE | US 221 | NORTH OF SOUTH FORK NEW RIVER TO SOUTH OF NC 194 | HIGHWAY | 11 | HIGH COUNTRY RPO | R-2915C | DIVISION 11 | BGLT5 |  |  |  |  | 2017 | 19700000 |  |  | 19700000 | COMPLETE
ASHE | US 221 | SOUTH OF NC 194 TO US 221 BYPASS | HIGHWAY | 11 | HIGH COUNTRY RPO | R-2915D | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
ASHE | US 221 | US 221 BYPASS TO US 221 BUSINESS/NC 88 IN JEFFERSON | HIGHWAY | 11 | HIGH COUNTRY RPO | R-2915E | DIVISION 11 | T |  |  |  |  | 2020 | 41374000 |  |  | 41374000 | COMPLETE. BUILD NC BOND FUNDING: $21.633 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE)
ASHE | US 221 BUSINESS | NC 194 AND SR 1248 (BEAVER CREEK SCHOOL ROAD) INTERSECTION. CONSTRUCT SUPERSTREET INTERSECTION. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5833 | NOT FUNDED | T | NOT FUNDED | 1100000 | NOT FUNDED | 50000 | NOT FUNDED | 2800000 |  |  | 3950000
ASHE | ASHE COUNTY TRANSPORTATION | PURCHASE EXPANSION VEHICLE TO PROVIDE TRANSPORTATION SERVICES TO PERSONS OVER 65 YEARS OF AGE AND PERSONS WITH A DISABILITY. | PUBLIC TRANSIT | 11 | HIGH COUNTRY RPO | TA-6674 | DIVISION 11 | 5311, L, T
ASHE | ASHE COUNTY TRANSPORTATION | ADMINISTRATION | PUBLIC TRANSIT | 11 | HIGH COUNTRY RPO | TK-6108 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 784000 | 784000 | FUNDS AUTHORIZED IN PROGRESS
ASHE, WATAUGA | US 221 | US 421 IN WATAUGA COUNTY TO US 221 BUSINESS/NC 88 IN JEFFERSON. WIDEN TO FOUR LANES DIVIDED. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-2915
ASHE, WATAUGA | US 221 | US 421 IN WATAUGA COUNTY TO SR 1003 (IDLEWILD ROAD) IN ASHE COUNTY | HIGHWAY | 11 | HIGH COUNTRY RPO | R-2915A | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
AVERY | NC 184 | NC 105 TO SR 1342 (HICKORY NUT GAP ROAD) IN BANNER ELK. WIDEN TO MULTI-LANES. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5902 | NOT FUNDED | T | NOT FUNDED | 18200000 | NOT FUNDED | 7900000 | NOT FUNDED | 64798000 |  |  | 90898000
AVERY | SR 1306 (HICKS HOLLOW ROAD) | REPLACE BRIDGE 050125 OVER ELK RIVER. | HIGHWAY | 11 | HIGH COUNTRY RPO | B-5835 | DIVISION 11 | BGOFF | 2025 | 92000 |  |  | 2026 | 1450000 |  |  | 1542000
AVERY | SR 1511 (ROSEBORO ROAD) | INSTALL SHOULDER GUARDRAIL. | HIGHWAY | 11 | HIGH COUNTRY RPO | HS-2011C | DIVISION 11 | HSIP |  |  |  |  | 2021 | 7000 |  |  | 7000
AVERY | US 19E | NC 194 INTERSECTION. CONSTRUCT RIGHT TURN LANE FROM US 19E NORTHBOUND TO NC 194 EASTBOUND. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5911 | DIVISION 11 | BGLT5 | 2022 | 200000 |  |  | 2023 | 1200000 |  |  | 1400000
AVERY | US 19E-NC 194 | SR 1106 TO US 221. WIDEN TO MULTI-LANES. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-2520B | NOT FUNDED | T | NOT FUNDED | 4300000 |  |  | NOT FUNDED | 25600000 |  |  | 29900000
AVERY, MITCHELL | US 19E | MULTI-LANES EAST OF SPRUCE PINE TO SR 1106. WIDEN TO MULTI-LANES. | HIGHWAY | 11, 13 | HIGH COUNTRY RPO | R-2520A | DIVISION 11, 13 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 14700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 50801000 |  |  | 69501000
AVERY, MITCHELL | US 19E, NC 194 | MULTI-LANE SECTION EAST OF SPRUCE PINE TO US 221. WIDEN TO MULTI-LANES. | HIGHWAY | 11, 13 | HIGH COUNTRY RPO | R-2520
AVERY, WATAUGA | NC 105 | US 221 IN AVERY COUNTY TO SR 1136 (CLARKS CREEK ROAD) IN WATAUGA COUNTY. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-2566A | NOT FUNDED | T | NOT FUNDED | 1000000 |  |  | NOT FUNDED | 60350000 |  |  | 61350000
BEAUFORT | WARREN FIELD (OCW) | ACQUIRE LAND FOR AND CONSTRUCT RUNWAY 5-23 EXTENSION AND TAXIWAY. | AVIATION | 2 | MID-EAST RPO | AV-5743 | DIVISION 2 | T | 2028 | 1635000 |  |  | 2029 | 3648000 |  |  | 5283000
BEAUFORT | NC 32 | BRICK KILN ROAD. IMPROVE INTERSECTION. | HIGHWAY | 2 | MID-EAST RPO | R-5897 | NOT FUNDED | T | NOT FUNDED | 454000 | NOT FUNDED | 200000 | NOT FUNDED | 1400000 |  |  | 2054000
BEAUFORT | SR 1112 (MOUTH OF THE CREEK ROAD) | REPLACE BRIDGE 060009 OVER BLOUNTS CREEK. | HIGHWAY | 2 | MID-EAST RPO | B-5614 | DIVISION 2 | BGOFF | 2022 | 319000 | 2022 | 108000 | 2023 | 9800000 |  |  | 10227000 | RIGHT-OF-WAY IN PROGRESS.
BEAUFORT | SR 1127 (POSSUM TRACK ROAD) | REPLACE BRIDGE NO. 060072 OVER CHOCOWINITY CREEK ON SR 1127 (POSSUM TRACK ROAD). | HIGHWAY | 2 | MID-EAST RPO | BR-0110 | DIVISION 2 | DP, HFB | 2020 | 40000 |  |  | 2021 | 1200000 |  |  | 1240000 | HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. UNDER CONSTRUCTION.
BEAUFORT | SR 1136 (GRAY ROAD) | REPLACE BRIDGE 060069 OVER BRANCH OF CONCOWINITY CREEK. | HIGHWAY | 2 | MID-EAST RPO | BR-0223 | HIGHWAY FUND | [10 empty] | COMPLETE
BEAUFORT | SR 1306 (15TH STREET) | US 17 BUSINESS (CAROLINA AVENUE) TO BROWN STREET. WIDEN TO MULTI-LANES. | HIGHWAY | 2 | MID-EAST RPO | U-5860 | DIVISION 2 | T | 2026 | 8900000 | 2026 | 2800000 | 2028 | 11000000 |  |  | 22700000
BEAUFORT | SR 1422 (MARKET STREET EXTENSION) | REPLACE BRIDGE 060006 OVER BIG SWAMP. | HIGHWAY | 2 | MID-EAST RPO | BR-0225 | HIGHWAY FUND | [10 empty] | COMPLETE
BEAUFORT | SR 1611 (JONES BRIDGE ROAD) | REPLACE BRIDGE 060159 OVER PUNGO CREEK. | HIGHWAY | 2 | MID-EAST RPO | BR-0229 | HIGHWAY FUND | [10 empty] | COMPLETE
BEAUFORT | SR 1742 (POST ROAD) | REPLACE BRIDGE 060135 OVER ROWLAND CREEK. | HIGHWAY | 2 | MID-EAST RPO | BR-0228 | HIGHWAY FUND | [10 empty] | COMPLETE
BEAUFORT | SR 1932 (MARYS CHAPEL CHURCH ROAD) | REPLACE BRIDGE 060040 OVER DURHAM CREEK TRIBUTARY. | HIGHWAY | 2 | MID-EAST RPO | B-4433 | DIVISION 2 | [10 empty] | UNDER CONSTRUCTION
BEAUFORT | SR 1971 (DURHAM CREEK ROAD) | REPLACE BRIDGE 060014 OVER BRANCH OF DURHAM CREEK. | HIGHWAY | 2 | MID-EAST RPO | BR-0239 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 1500000 |  |  | 1500000 | PROJECT REPRESENTS HFB 2.R.95 PROJECT. UNDER CONSTRUCTION.
BEAUFORT | US 17 | SR 1130 (C.C. ROAD) TO SOUTH OF SR 1127 (POSSUM TRACK ROAD). | HIGHWAY | 2 | MID-EAST RPO | R-2513E | NOT FUNDED | T | NOT FUNDED | 4600000 | NOT FUNDED | 600000 | NOT FUNDED | 18300000 |  |  | 23500000
BEAUFORT | US 264 | CONSTRUCT A SUPERSTREET AT INTERSECTION OF US 264 AND SR 1410 (VOA ROAD). | HIGHWAY | 2 | MID-EAST RPO | HS-2002D | REGION B | HSIP | 2022 | 15000 |  |  | 2022 | 789000 |  |  | 804000 | UNDER CONSTRUCTION.
BEAUFORT | BEAUFORT COUNTY DEVELOPMENT CENTER, INC. | ADMINISTRATION | PUBLIC TRANSIT | 2 | MID-EAST RPO | TK-6110 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 564000 | 564000 | FUNDS AUTHORIZED IN PROGRESS
BEAUFORT, BERTIE, BRUNSWICK, CARTERET, CHOWAN, CRAVEN, CURRITUCK, DARE, DUPLIN, HYDE, NEW HANOVER, ONSLOW, PAMLICO, PERQUIMANS, TYRRELL, WASHINGTON, CAMDEN, GATES, GREENE, HERTFORD, JONES, LENOIR, MARTIN, NORTHAMPTON, PASQUOTANK, PENDER, PITT, SAMPSON | VARIOUS | REPLACEMENT VESSEL (SUPPORT FLEET) FOR TUGS AND BARGES | FERRY | 1, 2, 3 | JACKSONVILLE URBAN AREA MPO, ALBEMARLE RPO, CAPE FEAR RPO, WILMINGTON URBAN AREA MPO, EASTERN CAROLINA RPO, GRAND STRAND AREA TRANSPORTATION STUDY, GREENVILLE URBAN AREA MPO, MID-CAROLINA RPO, MID-EAST RPO, NEW BERN AREA MPO, PEANUT BELT RPO | F-5703 | DIVISION 1, 2, 3
BEAUFORT, BERTIE, BRUNSWICK, CARTERET, CHOWAN, CRAVEN, CURRITUCK, DARE, DUPLIN, HYDE, NEW HANOVER, ONSLOW, PAMLICO, PERQUIMANS, TYRRELL, WASHINGTON, CAMDEN, GATES, GREENE, HERTFORD, JONES, LENOIR, MARTIN, NORTHAMPTON, PASQUOTANK, PENDER, PITT, SAMPSON | VARIOUS | Z-DRIVE TOWING AND PUSHING TUG | FERRY | 1, 2, 3 | ALBEMARLE RPO, CAPE FEAR RPO, DOWN EAST RPO, WILMINGTON URBAN AREA MPO, EASTERN CAROLINA RPO, GRAND STRAND AREA TRANSPORTATION STUDY, GREENVILLE URBAN AREA MPO, JACKSONVILLE URBAN AREA MPO, MID-CAROLINA RPO, MID-EAST RPO, NEW BERN AREA MPO, PEANUT BELT RP | F-5703A | DIVISION 1, 2, 3 | T |  |  |  |  | 2019 | 3250000 |  |  | 3250000 | COMPLETE
BEAUFORT, BERTIE, BRUNSWICK, CARTERET, CHOWAN, CRAVEN, CURRITUCK, DARE, DUPLIN, HYDE, NEW HANOVER, ONSLOW, PAMLICO, PERQUIMANS, TYRRELL, WASHINGTON, CAMDEN, GATES, GREENE, HERTFORD, JONES, LENOIR, MARTIN, NORTHAMPTON, PASQUOTANK, PENDER, PITT, SAMPSON | VARIOUS | TWO SUPPORT/ANCHOR TUGS, ONE SUPPORT TUG, THREE BARGES | FERRY | 1, 2, 3 | ALBEMARLE RPO, CAPE FEAR RPO, DOWN EAST RPO, WILMINGTON URBAN AREA MPO, EASTERN CAROLINA RPO, GRAND STRAND AREA TRANSPORTATION STUDY, GREENVILLE URBAN AREA MPO, JACKSONVILLE URBAN AREA MPO, MID-CAROLINA RPO, MID-EAST RPO, NEW BERN AREA MPO, PEANUT BELT RP | F-5703B | DIVISION 1, 2, 3 | T |  |  |  |  | 2019 | 2100000 |  |  | 2100000 | COMPLETE
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | DIVISION 2 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | BIKE/PED | 2 | DOWN EAST RPO, EASTERN CAROLINA RPO, GREENVILLE URBAN AREA MPO, MID-EAST RPO, NEW BERN AREA MPO | BO-2402 | DIVISION 2 | S, TA |  |  |  |  | 2024 | 10000000 |  |  | 10000000
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 2. | HIGHWAY | 2 | DOWN EAST RPO, EASTERN CAROLINA RPO, GREENVILLE URBAN AREA MPO, MID-EAST RPO, NEW BERN AREA MPO | HS-2002 | DIVISION 2
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | DIVISION 2 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | HIGHWAY | 2 | DOWN EAST RPO, EASTERN CAROLINA RPO, GREENVILLE URBAN AREA MPO, MID-EAST RPO, NEW BERN AREA MPO | R-5782 | DIVISION 2 | S, TA |  |  |  |  | 2020 | 3500000 |  |  | 3500000 | UNDER CONSTRUCTION; "S" FUNDS REFLECT STATE HIGHWAY FUNDS
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | DIVISION 2 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | 2 | DOWN EAST RPO, EASTERN CAROLINA RPO, GREENVILLE URBAN AREA MPO, MID-EAST RPO | W-5202 | REGION B | [10 empty] | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 2. | HIGHWAY | 2 | DOWN EAST RPO, EASTERN CAROLINA RPO, GREENVILLE URBAN AREA MPO, MID-EAST RPO, NEW BERN AREA MPO | W-5702 | [11 empty] | IN PROGRESS
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 2 | DOWN EAST RPO, EASTERN CAROLINA RPO, GREENVILLE URBAN AREA MPO, MID-EAST RPO, NEW BERN AREA MPO | W-5702DIV | DIVISION 2 | HSIP | 2022 | 30000 |  |  | 2020 | 375000 |  |  | 405000
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 2 | DOWN EAST RPO, EASTERN CAROLINA RPO, GREENVILLE URBAN AREA MPO, MID-EAST RPO, NEW BERN AREA MPO | W-5702REG | REGION B | HSIP | 2020 | 131000 |  |  | 2020 | 375000 |  |  | 506000
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 2 | DOWN EAST RPO, EASTERN CAROLINA RPO, GREENVILLE URBAN AREA MPO, MID-EAST RPO, NEW BERN AREA MPO | W-5702SW | STATEWIDE MOBILITY | HSIP | 2022 | 40000 |  |  | 2020 | 500000 |  |  | 540000
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 2. | HIGHWAY | 2 | DOWN EAST RPO, EASTERN CAROLINA RPO, GREENVILLE URBAN AREA MPO, MID-EAST RPO, NEW BERN AREA MPO | W-5802 | [11 empty] | INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 2. | RAIL | 2 | DOWN EAST RPO, EASTERN CAROLINA RPO, GREENVILLE URBAN AREA MPO, MID-EAST RPO, NEW BERN AREA MPO | RC-2002 | DIVISION 2 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
BEAUFORT, CARTERET, CRAVEN, PITT, GREENE, JONES, LENOIR, PAMLICO | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 2. | RAIL | 2 | DOWN EAST RPO, EASTERN CAROLINA RPO, GREENVILLE URBAN AREA MPO, MID-EAST RPO, NEW BERN AREA MPO | RX-2002 | DIVISION 2 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
BEAUFORT, CARTERET, LENOIR, PITT, CRAVEN, GREENE, JONES, PAMLICO | VARIOUS | ECOSYSTEMS ENHANCEMENT PROGRAM FOR DIVISION 2 PROJECT MITIGATION. | HIGHWAY | 2 | DOWN EAST RPO, EASTERN CAROLINA RPO, MID-EAST RPO, GREENVILLE URBAN AREA MPO | EE-4902 | [11 empty] | COMPLETE
BEAUFORT, PASQUOTANK, PITT, WILSON, BERTIE, CHOWAN, EDGECOMBE, FRANKLIN, MARTIN, NASH, PERQUIMANS, WAKE | GREYHOUND LINES | INTERCITY BUS FROM RALEIGH TO NORFOLK, VA VIA ELIZABETH CITY ALONG US 64, US 301, US 264, AND US 17 WITH STOPS AT RALEIGH, ROCKY MOUNT, WILSON, GREENVILLE, WASHINGTON, WILLIAMSTON, EDENTON, AND ELIZABETH CITY | PUBLIC TRANSIT | 1, 2, 4, 5 |  | TI-6104 | PUBLIC TRANSIT | 5311, L | [6 empty] | 2020 | 9248000 | 9248000 | FUNDS AUTHORIZED IN PROGRESS
BERTIE | NC 45 | HERTFORD COUNTY LINE TO WASHINGTON COUNTY LINE. MODERNIZE ROADWAY. | HIGHWAY | 1 | PEANUT BELT RPO | R-5809
BERTIE | NC 45 | WASHINGTON COUNTY LINE TO US 17 AT MIDWAY. | HIGHWAY | 1 | PEANUT BELT RPO | R-5809A | DIVISION 1 | T | 2023 | 5000 | 2023 | 4420000 | 2023 | 17400000 |  |  | 21825000
BERTIE | NC 45 | US 17 AT MIDWAY TO SOUTHERN CITY LIMITS OF COLERAIN. | HIGHWAY | 1 | PEANUT BELT RPO | R-5809B | DIVISION 1 | T | 2024 | 3012000 | 2024 | 12944000 | 2026 | 33498000 |  |  | 49454000
BERTIE | NC 45 | SOUTHERN CITY LIMITS OF COLERAIN TO HERTFORD COUNTY LINE. | HIGHWAY | 1 | PEANUT BELT RPO | R-5809C | DIVISION 1 | [10 empty] | COMPLETED.
BERTIE, CURRITUCK, CAMDEN, CHOWAN, DARE, GATES, HERTFORD, HYDE, MARTIN, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 1 | ALBEMARLE RPO, PEANUT BELT RPO, MID-EAST RPO | W-5701DIV | DIVISION 1 | HSIP | 2022 | 30000 |  |  | 2020 | 375000 |  |  | 405000
BERTIE, CURRITUCK, CAMDEN, CHOWAN, DARE, GATES, HERTFORD, HYDE, MARTIN, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 1 | ALBEMARLE RPO, PEANUT BELT RPO, MID-EAST RPO | W-5701REG | REGION A | HSIP | 2022 | 30000 |  |  | 2020 | 375000 |  |  | 405000
BERTIE, CURRITUCK, CAMDEN, CHOWAN, DARE, GATES, HERTFORD, HYDE, MARTIN, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 1 | ALBEMARLE RPO, PEANUT BELT RPO, MID-EAST RPO | W-5701SW | STATEWIDE MOBILITY | HSIP | 2022 | 40000 |  |  | 2020 | 500000 |  |  | 540000
BERTIE, HALIFAX, HERTFORD, NORTHAMPTON | CHOANOKE PUBLIC TRANSPORTATION AUTHORITY | ADMINISTRATION | PUBLIC TRANSIT | 1, 4 | PEANUT BELT RPO | TK-6119 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 1972000 | 1972000 | FUNDS AUTHORIZED IN PROGRESS
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | DIVISION 1 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | BIKE/PED | 1 | ALBEMARLE RPO, PEANUT BELT RPO, MID-EAST RPO | BO-2401 | DIVISION 1 | S, TA |  |  |  |  | 2024 | 4000000 |  |  | 4000000
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 1. | HIGHWAY | 1 | ALBEMARLE RPO, PEANUT BELT RPO, MID-EAST RPO | HS-2001 | DIVISION 1 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | DIVISION 1 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | HIGHWAY | 1 | ALBEMARLE RPO, PEANUT BELT RPO, MID-EAST RPO | R-5781 | DIVISION 1 | S, TA |  |  |  |  | 2020 | 3500000 |  |  | 3500000 | UNDER CONSTRUCTION; "S" FUNDS REFLECT STATE HIGHWAY FUNDS
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | DIVISION 1 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | 1 | ALBEMARLE RPO, PEANUT BELT RPO, MID-EAST RPO | W-5201 | [11 empty] | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 1. | HIGHWAY | 1 | ALBEMARLE RPO, PEANUT BELT RPO, MID-EAST RPO | W-5701 | [11 empty] | IN PROGRESS
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 1. | HIGHWAY | 1 | ALBEMARLE RPO, PEANUT BELT RPO, MID-EAST RPO | W-5801 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 1 | ALBEMARLE RPO, PEANUT BELT RPO, MID-EAST RPO | W-5801DIV | DIVISION 1
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 1 | ALBEMARLE RPO, PEANUT BELT RPO, MID-EAST RPO | W-5801REG | REGION A
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 1 | ALBEMARLE RPO, PEANUT BELT RPO, MID-EAST RPO | W-5801SW | STATEWIDE MOBILITY
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 1. | RAIL | 1 | ALBEMARLE RPO, PEANUT BELT RPO, MID-EAST RPO | RC-2001 | DIVISION 1 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
BERTIE, MARTIN, CAMDEN, CHOWAN, CURRITUCK, DARE, GATES, HERTFORD, HYDE, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 1. | RAIL | 1 | ALBEMARLE RPO, PEANUT BELT RPO, MID-EAST RPO | RX-2001 | DIVISION 1 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
BLADEN | FIELD (EYF) CURTIS L BROWN JR | EXTEND RUNWAY TO 5500 FEET AND PARALLEL TAXIWAY. | AVIATION | 6 | MID-CAROLINA RPO | AV-5826 | DIVISION 6 | T |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5240000 |  |  | 5240000
BLADEN | NC 87 | REPLACE BRIDGE 080014 OVER HAMMOND CREEK. | HIGHWAY | 6 | MID-CAROLINA RPO | B-5945 | STATEWIDE MOBILITY | BFP | 2027 | 300000 |  |  | 2028 | 5999000 |  |  | 6299000
BLADEN | NC 87 | SR 1730 (ELWELL FERRY ROAD) IN BLADEN COUNTY TO NC 11 IN COLUMBUS COUNTY. | HIGHWAY | 6 | CAPE FEAR RPO, MID-CAROLINA RPO | R-2561B | NOT FUNDED | T | NOT FUNDED | 13437000 | NOT FUNDED | 1612000 | NOT FUNDED | 57000000 |  |  | 72049000
BLADEN | NC 87 | SMITHFIELD FOODS PROCESSING CENTER. IMPROVE ROADWAY. THIS IS AN ECONOMIC DEVELOPMENT PROJECT. | HIGHWAY | 6 | MID-CAROLINA RPO | R-5866 | REGION C | T |  |  |  |  | 2018 | 1042000 |  |  | 1042000 | COMPLETE
BLADEN | SR 1534 (OVER LYON ROAD) | REPLACE BRIDGE 080197 OVER KELLY CANAL. | HIGHWAY | 6 | MID-CAROLINA RPO | B-6004 | DIVISION 6 | [10 empty] | UNDER CONSTRUCTION
BLADEN | SR 1536 (JAMES PORTER ROAD) | REPLACE BRIDGE 080198 OVER KELLY CREEK. | HIGHWAY | 6 | MID-CAROLINA RPO | B-6008 | DIVISION 6 | [10 empty] | UNDER CONSTRUCTION
BLADEN | BLADEN COUNTY | ADMINISTRATION | PUBLIC TRANSIT | 6 | MID-CAROLINA RPO | TK-6111 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 484000 | 484000 | FUNDS AUTHORIZED IN PROGRESS
BLADEN, COLUMBUS | NC 87 | ELIZABETHTOWN BYPASS IN BLADEN COUNTY TO US 74/US 76 IN COLUMBUS COUNTY. WIDEN TO MULTI-LANES. | HIGHWAY | 6 | CAPE FEAR RPO, MID-CAROLINA RPO | R-2561
BLADEN, COLUMBUS | NC 87 | ELIZABETHTOWN BYPASS TO SR 1730 (ELWELL FERRY ROAD) IN BLADEN COUNTY. | HIGHWAY | 6 | MID-CAROLINA RPO | R-2561A | NOT FUNDED | T | NOT FUNDED | 13781000 | NOT FUNDED | 1654000 | NOT FUNDED | 96100000 |  |  | 111535000
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | DIVISION 6 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | BIKE/PED | 6 | MID-CAROLINA RPO, FAYETTEVILLE AREA MPO, CAPE FEAR RPO, LUMBER RIVER RPO | BO-2406 | DIVISION 6 | S, TA |  |  |  |  | 2024 | 10000000 |  |  | 10000000
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | ECOSYSTEM ENHANCEMENT PROGRAM FOR DIVISION 6 PROJECT MITIGATION. | HIGHWAY | 6 | MID-CAROLINA RPO, CAPE FEAR RPO, LUMBER RIVER RPO, FAYETTEVILLE AREA MPO | EE-4906 | [11 empty] | COMPLETE
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 6. | HIGHWAY | 6 | MID-CAROLINA RPO, FAYETTEVILLE AREA MPO, CAPE FEAR RPO, LUMBER RIVER RPO | HS-2006 | DIVISION 6 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | DIVISION 6 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | HIGHWAY | 6 | MID-CAROLINA RPO, FAYETTEVILLE AREA MPO, CAPE FEAR RPO, LUMBER RIVER RPO | R-5786 | DIVISION 6 | S, TA |  |  |  |  | 2020 | 3500000 |  |  | 3500000 | UNDER CONSTRUCTION; "S" FUNDS REFLECT STATE HIGHWAY FUNDS
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | DIVISION 6 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | 6 | MID-CAROLINA RPO, FAYETTEVILLE AREA MPO, CAPE FEAR RPO, LUMBER RIVER RPO | W-5206 | [11 empty] | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 6. | HIGHWAY | 6 | MID-CAROLINA RPO, FAYETTEVILLE AREA MPO, CAPE FEAR RPO, LUMBER RIVER RPO | W-5706 | [11 empty] | IN PROGRESS
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 6 | MID-CAROLINA RPO, FAYETTEVILLE AREA MPO, CAPE FEAR RPO, LUMBER RIVER RPO | W-5706DIV | DIVISION 6 | HSIP | 2022 | 30000 |  |  | 2020 | 375000 |  |  | 405000
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 6 | MID-CAROLINA RPO, FAYETTEVILLE AREA MPO, CAPE FEAR RPO, LUMBER RIVER RPO | W-5706REG | REGION C | HSIP | 2020 | 135000 |  |  | 2020 | 519000 |  |  | 654000
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 6 | MID-CAROLINA RPO, FAYETTEVILLE AREA MPO, CAPE FEAR RPO, LUMBER RIVER RPO | W-5706SW | STATEWIDE MOBILITY | HSIP | 2020 | 90000 |  |  | 2020 | 500000 |  |  | 590000
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 6. | HIGHWAY | 6 | MID-CAROLINA RPO, FAYETTEVILLE AREA MPO, CAPE FEAR RPO, LUMBER RIVER RPO | W-5806 | [11 empty] | INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 6. | RAIL | 6 | MID-CAROLINA RPO, FAYETTEVILLE AREA MPO, CAPE FEAR RPO, LUMBER RIVER RPO | RC-2006 | DIVISION 6 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
BLADEN, COLUMBUS, CUMBERLAND, HARNETT, ROBESON | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 6. | RAIL | 6 | MID-CAROLINA RPO, FAYETTEVILLE AREA MPO, CAPE FEAR RPO, LUMBER RIVER RPO | RX-2006 | DIVISION 6
BRUNSWICK | CAPE FEAR REGIONAL (SUT) | APPROACH CLEARING AT RUNWAY 5 AND RUNWAY 23. | AVIATION | 3 | CAPE FEAR RPO | AV-5739 | DIVISION 3 | [10 empty] | COMPLETE
BRUNSWICK | ODELL WILLIAMSON MUNICIPAL AIRPORT (60J) | RUNWAY PROTECTION ZONE 2 - RUNWAY 24 LAND ACQUISITION AND OBSTRUCTION REMOVAL. | AVIATION | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | AV-5742 | DIVISION 3 | T |  |  |  |  | 2022 | 600000 |  |  | 600000 | UNDER CONSTRUCTION
BRUNSWICK | BELVILLE ELEMENTARY MULTI USE PATH | MULTI USE PATH ALONG NC 133 CONNECTING NORTH AND SOUTH ENTRANCES OF HAWKESWATER DEVELOPMENT TO BELVILLE ELEMENTARY SCHOOL. | BIKE/PED | 3 | WILMINGTON URBAN AREA MPO | EB-6026 | DIVISION 3 | L, TADA |  |  |  |  | 2022 | 118000 | 2020 | 30000 | 148000
BRUNSWICK | NC 211 (NORTH HOWE STREET) | EAST OWEN STREET TO DOSHER HOSPITAL IN SOUTHPORT. CONSTRUCT SIDEWALK. | BIKE/PED | 3 | CAPE FEAR RPO | EB-5982 | DIVISION 3 | L, TA5200 | 2024 | 50000 |  |  | 2025 | 175000 | 2023 | 30000 | 255000
BRUNSWICK | RICE HOPE MULTI USE PATH | MULTI USE PATH ALONG NC 133 BETWEEN MORECAMBLE BOULEVARD AND RICE HOPE RUN IN BELVILLE. | BIKE/PED | 3 | WILMINGTON URBAN AREA MPO | EB-6025 | DIVISION 3 | BGDA, L |  |  |  |  | 2022 | 167000 | 2020 | 30000 | 197000
BRUNSWICK | SR 1116 (OCEAN BOULEVARD) | INSTALL BIKE LANES ALONG SR 1116 (OCEAN BOULEVARD) FROM JUST WEST OF SHELL DRIVE TO DUNESCAPE DRIVE. | BIKE/PED | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | BL-0046 | DIVISION 3 | BGDA, L |  |  |  |  | 2022 | 1613000 |  |  | 1613000
BRUNSWICK | SR 1144 (FIRST STREET) | CONSTRUCTION OF BIKE LANES ON BOTH SIDES OF FIRST STREET FROM EAST OF WEST FIRST STREET EXTENSION TO EAST OF GREENSBORO STREET IN OCEAN ISLE BEACH. | BIKE/PED | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | EB-6034 | DIVISION 3 | BGDA, L |  |  |  |  | 2021 | 788000 |  |  | 788000
BRUNSWICK | VARIOUS | GRAND STRAND AREA METROPOLITAN PLANNING ORGANIZATION TRANSPORTATION ALTERNATIVES PROGRAM. | BIKE/PED | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | BL-0021 | DIVISION 3 | TADA |  |  |  |  | 2022 | 1192000 |  |  | 1192000
BRUNSWICK | I-140 | US 17 TO NORTH OF US 74. PAVEMENT REHABILITATION. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | I-6036 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2023 | 5500000 |  |  | 5500000
BRUNSWICK | I-140/US 17 WILMINGTON BYPASS | US 74/US 76 EAST OF MALMO IN BRUNSWICK COUNTY TO SR 1430 (CEDAR HILL ROAD). | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | R-2633BA | PRE-STI (TRANSITION) | NHP |  |  |  |  | 2014 | 30750000 |  |  | 30750000 | COMPLETE. GARVEE BOND FUNDING $50 M FOR SEGMENT BA; PAYBACK FY 2014-2025.
BRUNSWICK | I-74 (CAROLINA BAYS PARKWAY EXTENSION) | FROM SC STATE LINE TO US 17 AT NC 130. CONSTRUCT FREEWAY ON NEW LOCATION. | HIGHWAY | 3 | CAPE FEAR RPO, GRAND STRAND AREA TRANSPORTATION STUDY | R-5876 | NOT FUNDED | O | NOT FUNDED | 128600000 | NOT FUNDED | 5300000 | NOT FUNDED | 232800000 |  |  | 366700000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY
BRUNSWICK | NC 130 | NC 130 AND SR 1120 (SABBATH HOME ROAD) / SR 1239 (OCEAN VIEW AVENUE) IN HOLDEN BEACH. REVISE TRAFFIC SIGNAL AND PAVEMENT MARKINGS. | HIGHWAY | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | HS-2003G | DIVISION 3 | HSIP |  |  |  |  | 2026 | 84000 |  |  | 84000
BRUNSWICK | NC 133 | US 17/US 74/US 76 TO SR 1554 (OLD RIVER ROAD). MODERNIZE ROADWAY. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5914 | DIVISION 3 | T |  |  |  |  | 2023 | 2428000 |  |  | 2428000 | RIGHT-OF-WAY IN PROGRESS.
BRUNSWICK | NC 211 | SR 1500 (MIDWAY ROAD) TO NC 87. WIDEN TO MULTI-LANES. | HIGHWAY | 3 | CAPE FEAR RPO | R-5021 | DIVISION 3 | BG5200 |  |  |  |  | 2022 | 249849000 |  |  | 249849000 | RIGHT-OF-WAY IN PROGRESS.
BRUNSWICK | NC 211 | SR 1112 (SUNSET HARBOR ROAD) TO NC 906 (MIDWAY ROAD). WIDEN ROADWAY. | HIGHWAY | 3 | CAPE FEAR RPO | R-5947 | NOT FUNDED | T | NOT FUNDED | 7300000 | NOT FUNDED | 4300000 | NOT FUNDED | 45700000 |  |  | 57300000
BRUNSWICK | SR 1300 (ASH-LITTLE RIVER ROAD NORTHWEST) | REPLACE BRIDGE 090126 OVER CAWCAW SWAMP. | HIGHWAY | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | B-5996 | DIVISION 3 | BGOFF | 2022 | 100000 |  |  | 2022 | 2000000 |  |  | 2100000 | RIGHT-OF-WAY IN PROGRESS.
BRUNSWICK | SR 1342 (MAKATOKA ROAD NORTHWEST) | REPLACE BRIDGE 090100 OVER MUDDY BRANCH. | HIGHWAY | 3 | CAPE FEAR RPO | B-4439 | DIVISION 3 | BGOFF | 2022 | 550000 |  |  | 2022 | 1086000 |  |  | 1636000 | UNDER CONSTRUCTION.
BRUNSWICK | SR 1515 (OLD MILL CREEK ROAD SE) | REPLACE BRIDGE 090040 OVER MILL CREEK. | HIGHWAY | 3 | CAPE FEAR RPO | B-5629 | DIVISION 3 | BGOFF | 2022 | 115000 |  |  | 2023 | 1500000 |  |  | 1615000 | RIGHT-OF-WAY IN PROGRESS.
BRUNSWICK | US 17 | US 17 AND SR 1130 (MOUNT PISGAH ROAD) / SR 1344 (SELLERS ROAD). INSTALL SIGNALIZED LEFTOVER. | HIGHWAY | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | HS-2003D | REGION B | HSIP |  |  |  |  | 2025 | 269000 |  |  | 269000
BRUNSWICK | US 17 | NC 904. CONVERT INTERSECTION TO SUPERSTREET. | HIGHWAY | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | R-5851 | NOT FUNDED | T | NOT FUNDED | 850000 | NOT FUNDED | 115000 | NOT FUNDED | 4950000 |  |  | 5915000
BRUNSWICK | US 17 | US 17 BUSINESS SOUTH OF SHALLOTTE AND US 17 BUSINESS NORTH OF SHALLOTTE. CONVERT INTERSECTIONS TO SUPERSTREETS. | HIGHWAY | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | R-5857 | STATEWIDE MOBILITY | T | 2023 | 763000 | 2023 | 174000 | 2025 | 13500000 |  |  | 14437000
BRUNSWICK | US 17 | NC 211. CONVERT INTERSECTION TO INTERCHANGE. | HIGHWAY | 3 | CAPE FEAR RPO, GRAND STRAND AREA TRANSPORTATION STUDY | U-5932 | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 38988000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1920000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 36102000 |  |  | 77010000
BRUNSWICK | US 17 (SHALLOTTE BYPASS) | SR 1357 (SMITH AVENUE). UPGRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | U-5862 | REGION B | T | 2028 | 5240000 | 2028 | 1840000 | 2030 | 22000000 |  |  | 29080000
BRUNSWICK | US 17 (SHALLOTTE BYPASS) | US 17 BUSINESS SOUTH (MAIN STREET). UPGRADE EXISTING AT GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | U-6104 | NOT FUNDED | NHP | NOT FUNDED | 4233000 | NOT FUNDED | 300000 | NOT FUNDED | 19200000 |  |  | 23733000
BRUNSWICK | US 17 BUSINESS (MAIN STREET) | WALL STREET/SHALLOTTE AVENUE. REALIGN INTERSECTION. | HIGHWAY | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | U-5788 | DIVISION 3 | T |  |  |  |  | 2021 | 1939000 |  |  | 1939000 | RIGHT-OF-WAY IN PROGRESS
BRUNSWICK | VARIOUS | GRAND STRAND AREA TRANSPORTATION STUDY METROPOLITAN PLANNING ORGANIZATION PLANNING (PL) SUPPLEMENT. | HIGHWAY | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | U-5910 | DIVISION 3 | BGDA, L | [6 empty] | 2023 | 290000 | 290000 | IN PROGRESS
BRUNSWICK | VARIOUS | GRAND STRAND AREA METROPOLITAN PLANNING ORGANIZATION STBGDA RESERVE ACCOUNT. | HIGHWAY | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | U-5990 | DIVISION 3 | BGDA |  |  |  |  | 2022 | 9608000 |  |  | 9608000
BRUNSWICK | BRUNSWICK TRANSIT SYSTEM, INC. | ADMINISTRATION | PUBLIC TRANSIT | 3 | CAPE FEAR RPO | TK-6112 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 712000 | 712000 | FUNDS AUTHORIZED IN PROGRESS
BRUNSWICK, NEW HANOVER | SOUTHPORT - FORT FISHER | CONSTRUCT MOORING FACILITIES. | FERRY | 3 | CAPE FEAR RPO, WILMINGTON URBAN AREA MPO | F-5707 | REGION B | T |  |  |  |  | 2025 | 5000000 |  |  | 5000000
BRUNSWICK, NEW HANOVER | SOUTHPORT-FORT FISHER | SOUTHPORT-FORT FISHER FERRY. CONSTRUCT RIVER CLASS FERRY. | FERRY | 3 | CAPE FEAR RPO, WILMINGTON URBAN AREA MPO | F-5705 | NOT FUNDED | T |  |  |  |  | NOT FUNDED | 14000000 |  |  | 14000000
BRUNSWICK, NEW HANOVER | I-140/US 17 (WILMINGTON BYPASS) | US 17 SOUTH OF NC 87 IN BRUNSWICK COUNTY TO I-40 IN NEW HANOVER COUNTY. FOUR LANE DIVIDED FREEWAY ON NEW LOCATION. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | R-2633 | [11 empty] | GARVEE BOND FUNDING $31.05 M FOR SEGMENT AA; PAYBACK FY 2010-2021 - GARVEE BOND FUNDING $50 M FOR SEGMENT BA; PAYBACK FY 2014-2025 - GARVEE BOND FUNDING $100 M FOR SEGMENT BB; PAYBACK FY 2013-2024
BRUNSWICK, NEW HANOVER | I-140/US 17 WILMINGTON BYPASS | NC 87 SOUTH OF BISHOP TO US 74/US 76 EAST OF MALMO IN BRUNSWICK COUNTY. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | R-2633AA | PRE-STI (TRANSITION) | NHP |  |  |  |  | 2010 | 6810000 |  |  | 6810000 | COMPLETE. GARVEE BOND FUNDING $31.05 M FOR SEGMENT AA; PAYBACK FY 2010-2021.
BRUNSWICK, NEW HANOVER | I-140/US 17 WILMINGTON BYPASS | NC 87 SOUTH OF BISHOP TO US 74/US 76 EAST OF MALMO IN BRUNSWICK COUNTY. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | R-2633AB | [11 empty] | COMPLETE
BRUNSWICK, NEW HANOVER | I-140/US 17 WILMINGTON BYPASS | US 74/US 76 EAST OF MALMO IN BRUNSWICK COUNTY TO WEST OF US 421 NORTH OF WILMINGTON. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | R-2633BC | [11 empty] | OPEN TO TRAFFIC
BRUNSWICK, NEW HANOVER | I-140/US 17 WILMINGTON BYPASS | IMPLEMENTATION OF INTELLIGENT TRANSPORTATION SYSTEMS (ITS). | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | R-2633D | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
BRUNSWICK, NEW HANOVER | US 17/US 74/US 76 | NC 133/SR 1472 (VILLAGE ROAD) INTERCHANGE TO THE US 421/NC 133 INTERCHANGE. ADD ADDITIONAL LANES ON NORTH AND SOUTHBOUND LANES AND WIDEN BRIDGE 090107 AND BRIDGE 090108. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | R-3601 | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
BRUNSWICK, NEW HANOVER, ONSLOW, PENDER, DUPLIN, SAMPSON | VARIOUS | ECOSYSTEMS ENHANCEMENT PROGRAM FOR DIVISION 3 PROJECT MITIGATION. | HIGHWAY | 3 | CAPE FEAR RPO, WILMINGTON URBAN AREA MPO, JACKSONVILLE URBAN AREA MPO, EASTERN CAROLINA RPO, MID-CAROLINA RPO | EE-4903 | [11 empty] | COMPLETE
BRUNSWICK, ONSLOW, NEW HANOVER | VARIOUS | DIVISION 3 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO, GRAND STRAND AREA TRANSPORTATION STUDY, WILMINGTON URBAN AREA MPO | W-5203SW | STATEWIDE MOBILITY
BUNCOMBE | ASHEVILLE REGIONAL AIRPORT | MODERNIZE AIRPORT TERMINAL BUILDING. | AVIATION | 13 | FRENCH BROAD RIVER MPO | AO-0001 | EXEMPT | FED, L, S |  |  |  |  | 2022 | 153808000 |  |  | 153808000 | "FED" FUNDS ARE FAA FUNDS; "S" FUNDS ARE A STATE APPROPRIATION FROM THE HIGHWAY FUND; "L" FUNDS PROVIDED BY ASHEVILLE REGIONAL AIRPORT
BUNCOMBE | ASHEVILLE REGIONAL AIRPORT (AVL) | AIRFIELD IMPROVEMENTS PROGRAM - RUNWAY CONSTRUCTION | AVIATION | 13 | FRENCH BROAD RIVER MPO | AV-5735 | REGION G | [10 empty] | UNDER CONSTRUCTION
BUNCOMBE | ASHEVILLE REGIONAL AIRPORT (AVL) | EXPAND TERMINAL APRON TO THE SOUTH. | AVIATION | 13 | FRENCH BROAD RIVER MPO | AV-5882 | STATEWIDE MOBILITY | O, T |  |  |  |  | 2019 | 7000000 |  |  | 7000000 | UNDER CONSTRUCTION
BUNCOMBE | ASHEVILLE | ON-STREET CROSSINGS AND CONNECTIONS FOR BICYCLISTS AND PEDESTRIANS IN ASHEVILLE'S EAST OF THE RIVERWAY. | BIKE/PED | 13 | FRENCH BROAD RIVER MPO | EB-5790 | DIVISION 13 | BGDA, L |  |  |  |  | 2023 | 1050000 |  |  | 1050000
BUNCOMBE | ASHEVILLE | LEXINGTON AVENUE, PATTON AVENUE TO SOUTHSIDE AVENUE. IMPROVE BICYCLE AND PEDESTRIAN INFRASTRUCTURE. | BIKE/PED | 13 | FRENCH BROAD RIVER MPO | EB-5830 | DIVISION 13 | BGDA, L | [6 empty] | 2022 | 675000 | 675000
BUNCOMBE | ASHEVILLE | COXE AVENUE, PATTON AVENUE TO SHORT COXE AVENUE. IMPROVE BICYCLE AND PEDESTRIAN INFRASTRUCTURE. | BIKE/PED | 13 | FRENCH BROAD RIVER MPO | EB-5831 | DIVISION 13 | BGANY, BGDA, L | 2024 | 300000 |  |  | 2025 | 11000000 | 2022 | 525000 | 11825000 | 6-13-2022: $7.552M IN STBG-DA FUNDS SWITCHED WITH $7.552M IN BG-ANY AS PART OF FUND SWAP.
BUNCOMBE | ASHEVILLE | JOHNSTON BOULEVARD, PATTON AVENUE TO IONA CIRCLE. CONSTRUCT SIDEWALKS. | BIKE/PED | 13 | FRENCH BROAD RIVER MPO | EB-5944 | DIVISION 13 | BGDA, L |  |  |  |  | 2023 | 2350000 |  |  | 2350000
BUNCOMBE | ASHEVILLE | NEW HAW CREEK ROAD, BEVERLY ROAD TO BELL ROAD. CONSTRUCT SIDEWALKS. | BIKE/PED | 13 | FRENCH BROAD RIVER MPO | EB-5947 | DIVISION 13 | BGANY, L |  |  |  |  | 2023 | 2375000 |  |  | 2375000 | $1.9M IN BGANY USED AS PART OF FUND SWAP
BUNCOMBE | ASHEVILLE | ONTEORA BOULEVARD, LINCOLN AVENUE TO RALEIGH ROAD. CONSTRUCT SIDEWALKS. | BIKE/PED | 13 | FRENCH BROAD RIVER MPO | EB-5948 | DIVISION 13 | BGDA, L |  |  |  |  | 2022 | 1140000 |  |  | 1140000
BUNCOMBE | BENT CREEK GREENWAY | CONSTRUCT MULTI-USE PATH FROM HOMINY CREEK RIVER PARK TO WESTERN NC FARMER'S MARKET | BIKE/PED | 13 | FRENCH BROAD RIVER MPO | EB-5823 | DIVISION 13 | [10 empty] | IN PROGRESS
BUNCOMBE | BLACK MOUNTAIN RIVERWALK GREENWAY | CONSTRUCT MULTI-USE PATH FROM EXISTING FLAT CREEK GREENWAY TRAILHEAD NORTH OF US 70 TO THE INTO THE OAKS TRAIL. | BIKE/PED | 13 | FRENCH BROAD RIVER MPO | EB-5547 | DIVISION 13 | [10 empty] | $3.234M IN BGANY USED AS PART OF MULTIPLE FUND SWAPS
BUNCOMBE | BLACK MOUNTAIN RIVERWALK GREENWAY | CONSTRUCT MULTI-USE PATH FROM BLACK MOUNTAIN AVENUE TO FLAT CREEK GREENWAY. | BIKE/PED | 13 | FRENCH BROAD RIVER MPO | EB-5547A | DIVISION 13 | BGANY, BGDA, L | 2023 | 94000 |  |  | 2024 | 960000 | 2022 | 117000 | 1171000
BUNCOMBE | BLACK MOUNTAIN RIVERWALK GREENWAY | CONSTRUCT MULTI-USE PATH FROM BLACK MOUNTAIN AVENUE TO THE INTO THE OAKS TRAIL. | BIKE/PED | 13 | FRENCH BROAD RIVER MPO | EB-5547B | DIVISION 13 | BGANY, L | 2022 | 150000 |  |  | 2023 | 2623000 | 2022 | 200000 | 2973000
BUNCOMBE | DEAVERVIEW ROAD | US 19/23/74A (PATTON AVENUE) TO WESTMORE DRIVE IN ASHEVILLE. CONSTRUCT SIDEWALK. | BIKE/PED | 13 | FRENCH BROAD RIVER MPO | EB-5965 | DIVISION 13 | L, TAANY | 2026 | 250000 |  |  | 2027 | 2245000 | 2024 | 710000 | 3205000
BUNCOMBE | HOMINY CREEK GREENWAY | CONSTRUCT MULTI-USE PATH FROM HOMINY VALLEY PARK AND ENKA HIGH SCHOOL TO EAST OF SAND HILL ROAD | BIKE/PED | 13 | FRENCH BROAD RIVER MPO | EB-5824 | DIVISION 13 | BGANY, BGDA, L |  |  |  |  | 2023 | 3845000 | 2021 | 1310000 | 5155000 | $4.4M IN BGANY USED AS PART OF FUND SWAP; $660K OF BGANY IN CON MOVED TO PE.
BUNCOMBE | MCDOWELL STREET CHOCTAW STREET | SOUTHSIDE AVENUE TO CHOCTAW STREET AT BILTMORE AVENUE. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | BIKE/PED | 13 | FRENCH BROAD RIVER MPO | EB-5919 | DIVISION 13 | L, TAANY | 2022 | 26000 |  |  | 2024 | 320000 | 2020 | 100000 | 446000
BUNCOMBE | NC 251 (RIVERSIDE DRIVE) MULTI-USE PATH | US 19/23/70 (EXIT 25) TO US 25. CONSTRUCT MULTI-USE PATH VIA BEAVERDAM CREEK. | BIKE/PED | 13 | FRENCH BROAD RIVER MPO | EB-5774 | DIVISION 13 | BGANY, BGDA, L | 2023 | 220000 |  |  | 2023 | 4780000 | 2020 | 2000000 | 7000000 | $2M IN BGANY USED AS PART OF FUND SWAP; PRELIMINARY ENGINEERING FUNDING IS FOR FORMER EB-5925 SECTION
BUNCOMBE | NC 251/ SR 1781 (BROADWAY STREET) | CONSTRUCT PEDESTRIAN IMPROVEMENTS FROM US 19/23 NORTHBOUND EXIT RAMP TO NORTH OF SR 1477 (RIVERSIDE DRIVE). | BIKE/PED | 13 | FRENCH BROAD RIVER MPO | BL-0005 | DIVISION 13 | BGDA, HF, HSIP, S(M) |  |  |  |  | 2022 | 776000 | 2021 | 4000 | 780000 | "S(M)" FUNDS REPRESENT NCDOT DIVISION 13 CONTINGENCY FUNDS. HF FUNDS REPRESENT EXTRA DIVISION 13 CONTINGENCY FUNDS TO COVER THE LOW BID.
BUNCOMBE | NORTH RAD GREENWAY | CONSTRUCT MULTI-USE PATH ALONG RIVERSIDE DRIVE FROM HILL STREET TO US 19/23/70 AT BROADWAY | BIKE/PED | 13 | FRENCH BROAD RIVER MPO | EB-5822 | DIVISION 13 | BGDA, L, TAANY | 2023 | 129000 |  |  | 2025 | 4000000 | 2021 | 300000 | 4429000
BUNCOMBE | REEMS CREEK GREENWAY | CONSTRUCT MULTI-USE PATH ALONG REEMS CREEK CORRIDOR FROM WESTERN EDGE OF TOWN OF WEAVERVILLE TO KARPEN SOCCER FIELDS | BIKE/PED | 13 | FRENCH BROAD RIVER MPO | EB-5821 | DIVISION 13 | [10 empty] | IN PROGRESS
BUNCOMBE | VARIOUS | CONSTRUCT PEDESTRIAN IMPROVEMENTS AT VARIOUS LOCATIONS WITHIN THE CITY OF ASHEVILLE (PRIMARILY WITHIN SCHOOL ZONES). | BIKE/PED | 13 | FRENCH BROAD RIVER MPO | BL-0006 | DIVISION 13 | BGDA, L |  |  |  |  | 2025 | 750000 | 2022 | 75000 | 825000
BUNCOMBE | 9TH STREET | REPLACE BRIDGE 100522 OVER TOMAHAWK BRANCH IN BLACK MOUNTAIN. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | HL-0013 | DIVISION 13 | BGANY, L | 2023 | 120000 |  |  | 2023 | 360000 | 2022 | 200000 | 680000 | 544K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP
BUNCOMBE | ASHEVILLE | US 19 (PATTON AVENUE) AND NC 63 (NEW LEICESTER HIGHWAY) . CONSTRUCTION INTERSECTION IMPROVEMENTS. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-5971
BUNCOMBE | ASHEVILLE | US 19 (PATTON AVENUE) AND NC 63 (NEW LEICESTER HIGHWAY). CONSTRUCT INITIAL INTERSECTION IMPROVEMENTS. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-5971A | REGION G | [10 empty] | SUPPLEMENT WITH SPOT MOBILITY FUNDS. UNDER CONSTRUCTION
BUNCOMBE | ASHEVILLE | US 19 (PATTON AVENUE) AND NC 63 (NEW LEICESTER HIGHWAY). CONSTRUCT DRAINAGE IMPROVEMENTS. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-5971AA | REGION G | T | 2021 | 100000 |  |  | 2022 | 550000 |  |  | 650000 | WORK TO BE PERFORMED BY STATE FORCES
BUNCOMBE | ASHEVILLE | US 19 (PATTON AVENUE) AND NC 63 (NEW LEICESTER HIGHWAY). CONSTRUCT FINAL INTERSECTION IMPROVEMENTS. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-5971B | NOT FUNDED | T | NOT FUNDED | 35590000 | NOT FUNDED | 300000 | NOT FUNDED | 6500000 |  |  | 42390000
BUNCOMBE | ASHEVILLE | NC 63 (NEW LEICESTER HIGHWAY), US 19/23 (PATTON AVENUE) TO NEWFOUND ROAD. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-5972 | NOT FUNDED | T | NOT FUNDED | 66000000 | NOT FUNDED | 6700000 | NOT FUNDED | 31899000 |  |  | 104599000
BUNCOMBE | ASHEVILLE EAST OF THE RIVERWAY MULTI-MODAL NETWORK | CONSTRUCT INTERCONNECTED NETWORK OF PEDESTRIAN, BICYCLE, ROADWAY, AND STREETSCAPE IMPROVEMENTS. PROJECT INCLUDES: CLINGMAN FOREST AND TOWN BRANCH GREENWAYS, FRENCH BROAD RIVER WEST GREENWAY, WILMA DIKEMAN RIVERWAY AND FIVE POINTS ROUNDABOUT, LIVINGSTON S | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-5019 | [11 empty] | SEGMENT A - $3.42M IN BGANY USED AS PART OF FUND SWAP, $8K USED FOR PRELIMINARY ENGINEERING
BUNCOMBE | CITYWIDE | ASHEVILLE SIGNAL SYSTEM. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-4715 | [11 empty] | A PORTION OF THE SIGNALS ARE NOT ELIGIBLE FOR FEDERAL FUNDING DUE THE ROAD'S FUNCTIONAL CLASSIFICATION. THE RESULTING FUNDING SPLIT IS 74% FEDERAL AND 26% STATE
BUNCOMBE | CITYWIDE | SIGNAL IMPROVEMENTS | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-4715B | DIVISION 13 | [10 empty] | UNDER CONSTRUCTION
BUNCOMBE | I-240 | US 70 (CHARLOTTE STREET) INTERSECTIONS. CONSTRUCT PEDESTRIAN IMPROVEMENTS AND A RIGHT TURN LANE ON THE I-240 EASTBOUND OFF-RAMP. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | HL-0012 | EXEMPT | BGDA, S(M) |  |  |  |  | 2022 | 1680000 |  |  | 1680000 | "S(M)" FUNDS REPRESENT SPOT MOBILITY AND HIGH IMPACT/LOW COST FUNDS; STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE STATEWIDE MOBILITY PROJECT. PE AND ROW FUNDED UNDER SM-5713E (HIGHWAY FUNDS).
BUNCOMBE | I-240 | MILEMARKER 4 TO MILEMARKER 9. PAVEMENT REHABILITATION. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-5901 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2025 | 20906000 |  |  | 20906000
BUNCOMBE | I-26 | CONSTRUCT NEW INTERCHANGE NEAR AND ACCESS ROAD NEAR MILEMARKER 35, CONNECTING TO FREDERICK LAW OLMSTEAD WAY EAST. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | HE-0001 | DIVISION 13 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY.
BUNCOMBE | I-26 | NC 191 (BREVARD ROAD). UPGRADE INTERCHANGE. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-5504 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION AS DESIGN-BUILD PROJECT
BUNCOMBE | I-26 (US 19/US 23) | SR 1781 (BROADWAY STREET) TO US 25/70 | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | A-0010AA | REGION G | T | 2028 | 42700000 | 2028 | 1000000 | 2031 | 279800000 |  |  | 323500000
BUNCOMBE | I-26 (US 19/US 23) | US 25/70 TO SR 2207 (N BUNCOMBE SCHOOL ROAD) | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | A-0010AB | NOT FUNDED | T | NOT FUNDED | 5600000 |  |  | NOT FUNDED | 72000000 |  |  | 77600000
BUNCOMBE | I-26 (US 19/US 23) | SR 2207 (N BUNCOMBE SCHOOL ROAD) TO SOUTH OF SR 2148 (STOCKTON ROAD) | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | A-0010AC | NOT FUNDED | T | NOT FUNDED | 700000 |  |  | NOT FUNDED | 27000000 |  |  | 27700000
BUNCOMBE | I-26, I-40 | I-26/I-40 AND I-40/US 19/23 (SMOKEY PARK HIGHWAY) INTERCHANGES. CONSTRUCT THE FOLLOWING IMPROVEMENTS: WIDEN I-40 EASTBOUND TO I-26 EASTBOUND RAMP, WIDEN I-26 WESTBOUND BETWEEN I-40 RAMPS, CONSTRUCT NEW I-40 WESTBOUND TO US 19/23 (SMOKEY PARK HIGHWAY) NO | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-2513AB | REGION G | NHP | 2023 | 3400000 |  |  | 2024 | 20200000 |  |  | 23600000 | TO BE LET WITH I-2513AA
BUNCOMBE | I-26/I-240 | I-26 CONNECTOR, I-40 TO US 19/US 23. CONSTRUCT MULTI-LANE FREEWAY, PART ON NEW LOCATION. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-2513
BUNCOMBE | I-26/I-240 | NORTH OF I-40 TO SR 3548 (HAYWOOD ROAD). WIDEN TO SIX LANE FREEWAY. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-2513AC | REGION G | T | 2023 | 38815000 | 2023 | 3000000 | 2024 | 179005000 |  |  | 220820000 | BUILD NC BOND FUNDING: $10.5M FOR RIGHT-OF-WAY, PAYBACK FY 2023-2036 (FY 2022 / YR 4 SALE); $45.3M FOR CONSTRUCTION, PAYBACK 2024-2038 (FY 2024 / YR 6 SALE).
BUNCOMBE | I-26/I-240 | I-26/I-40/I-240 FINAL INTERCHANGE IMPROVEMENTS | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-2513C | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4075000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 17400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 185001000 |  |  | 206476000
BUNCOMBE | I-40 | EAST OF SR 1224 (MONTE VISTA ROAD) TO PAVEMENT JOINT WEST OF SR 3412 (SAND HILL ROAD). RECONSTRUCT PAVEMENT. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-2513AA | STATEWIDE MOBILITY | NHPIM | 2023 | 1900000 | 2023 | 100000 | 2024 | 29700000 |  |  | 31700000 | TO BE LET WITH I-2513AB
BUNCOMBE | I-40 | I-40/SR 1228 (LIBERTY ROAD). CONVERT GRADE SEPARATION TO AN INTERCHANGE AND CONSTRUCT TWO LANE ROADWAY NORTH OF I-40 TO SR 1224 AND FOUR LANE ROADWAY SOUTH OF I-40 TO US 19/US 23/NC 151 WITH PARTS ON NEW LOCATION. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-4759 | STATEWIDE MOBILITY | BGANY, BGDA | 2019 | 15582000 | 2019 | 700000 | 2025 | 35200000 |  |  | 51482000 | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING - $1.3M FOR RIGHT-OF-WAY, PAYBACK FY 2019-2033
BUNCOMBE | I-40 | MILE MARKER 45 TO MILE MARKER 50. PAVEMENT REHABILITATION. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-5108 | PRE-STI (TRANSITION) | NHP |  |  |  |  | 2009 | 512000 |  |  | 512000 | COMPLETE - GARVEE BOND FUNDING $4.67 MILLION; CONSTRUCTION - PAYBACK FY 2009-2020
BUNCOMBE | I-40 | HAYWOOD COUNTY LINE TO MILE MARKER 43 IN BUNCOMBE COUNTY. PAVEMENT REHABILITATION. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-5109 | PRE-STI (TRANSITION) | NHP |  |  |  |  | 2009 | 669000 |  |  | 669000 | COMPLETE - GARVEE BOND FUNDING $6.1 MILLION; CONSTRUCTION - PAYBACK FY 2009-2020
BUNCOMBE | I-40 | US 25A (SWEETEN CREEK ROAD). CONSTRUCT INTERCHANGE IMPROVEMENTS. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-5886 | DIVISION 13 | [10 empty] | COMPLETE
BUNCOMBE | I-40 | MILE MARKER 37 TO MILE MARKER 44. REHABILIATE PAVEMENT AND BRIDGES. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-5888
BUNCOMBE | I-40 | MILE MARKER 37 TO MILE MARKER 44. REHABILITATE PAVEMENT AND BRIDGES. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-5888A | STATEWIDE MOBILITY | [10 empty] | COMPLETE
BUNCOMBE | I-40 | MILE MARKER 37 TO MILE MARKER 44. REHABILITATE BRIDGES. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-5888B | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2025 | 4110000 |  |  | 4110000
BUNCOMBE | I-40 | MILE MARKER 45.25 TO MILE MARKER 50. REHABILTATE PAVEMENT AND PRESERVE BRIDGES. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-5889
BUNCOMBE | I-40 | MILE MARKER 46 TO MILE MARKER 50. PRESERVE BRIDGES. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-5889A | STATEWIDE MOBILITY | [10 empty] | COMPLETED
BUNCOMBE | I-40 | MILE MARKER 45.25 TO MILE MARKER 50. REHABILITATE PAVEMENT AND PRESERVE BRIDGES 100352, 100356, 100344, 100347, 100339, AND 100334. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-5889B | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2022 | 20409000 |  |  | 20409000
BUNCOMBE | I-40 | MILEMARKER 55 TO MILEMARKER 67.5. PAVEMENT REHABILITATION. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-5890 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2019 | 23160000 |  |  | 23160000 | UNDER CONSTRUCTION. GARVEE BOND FUNDING: $18M FOR CONSTRUCTION, PAYBACK FY 2019-2033.
BUNCOMBE | I-40 | I-240 / US 74 ALTERNATE INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-6018 | NOT FUNDED | NHP | NOT FUNDED | 4000000 | NOT FUNDED | 700000 | NOT FUNDED | 117200000 |  |  | 121900000
BUNCOMBE | I-40 | SR 2838 (PORTERS COVE ROAD) INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-6021 | NOT FUNDED | NHP |  |  | NOT FUNDED | 200000 | NOT FUNDED | 1700000 |  |  | 1900000
BUNCOMBE | I-40 | SR 1200 (WIGGINS ROAD) TO SR 1224 (MONTE VISTA ROAD). ADD ADDITIONAL LANES. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-6054C | NOT FUNDED | NHP | NOT FUNDED | 13900000 | NOT FUNDED | 4700000 | NOT FUNDED | 200199000 |  |  | 218799000
BUNCOMBE | I-40 | MILEMARKER 50 TO MILEMARKER 55. PAVEMENT REHABILITATION. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-6063 | STATEWIDE MOBILITY | NHPIM, S(M) |  |  |  |  | 2020 | 30222000 |  |  | 30222000 | GARVEE BOND FUNDING - $5M FOR CONSTRUCTION, PAYBACK FY 2020-2034
BUNCOMBE | I-40, I-26 | SR 3548 (HAYWOOD ROAD) TO US 19/23 AT SR 1781 (BROADWAY) | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-2513B | STATEWIDE MOBILITY | NHP, S(M) | 2024 | 174526000 | 2024 | 23200000 | 2024 | 686575000 |  |  | 884301000 | GARVEE BOND FUNDING: $75M FOR RIGHT-OF-WAY, PAYBACK FY 2025-2039; $75M FOR CONSTRUCTION, PAYBACK FY 2025-2039; $150M FOR CONSTRUCTION, PAYBACK FY 2027-2041. TO BE LET WITH I-2513D.
BUNCOMBE | MONTREAT (TEXAS ROAD) | REPLACE BRIDGE 100528 OVER FLAT CREEK. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | B-5196 | DIVISION 13 | [10 empty] | MUNICIPAL BRIDGE
BUNCOMBE | NC 112 (SARDIS ROAD/ SANDHILL ROAD) | NC 191 (BREVARD ROAD) TO US 19/23 (SMOKEY PARK HIGHWAY). WIDEN ROADWAY. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-6047 | DIVISION 13 | T | 2025 | 60800000 | 2025 | 6800000 | 2028 | 69000000 |  |  | 136600000
BUNCOMBE | NC 191 (BREVARD ROAD - OLD HAYWOOD ROAD) | SR 3498 (LEDBETTER ROAD) TO NORTH OF BLUE RIDGE PARKWAY. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-3403B | NOT FUNDED | T | NOT FUNDED | 23800000 | NOT FUNDED | 3900000 | NOT FUNDED | 48873000 |  |  | 76573000
BUNCOMBE | NC 191 (BREVARD ROAD - OLD HAYWOOD ROAD) | NORTH OF BLUE RIDGE PARKWAY TO NC 112 (SARDIS ROAD) | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-3403C | [11 empty] | COMPLETE
BUNCOMBE | NC 63 (LEICESTER HIGHWAY) | SR 1615 (GILBERT ROAD) TO WEST OF SR 1004 (NEWFOUND ROAD) IN ASHEVILLE. WIDEN TO MULTI-LANES, SOME RELOCATION. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-3301 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION - DESIGN BUILD PROJECT
BUNCOMBE | NC 81 (SWANNANOA RIVER ROAD) | SR 3214 (BILTMORE AVENUE) TO US 74A (SOUTH TUNNEL ROAD). WIDEN EXISTING ROADWAY. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-5832 | DIVISION 13 | T | 2028 | 24400000 | 2028 | 1700000 | 2030 | 21901000 |  |  | 48001000 | COORDINATE WITH U-6046.
BUNCOMBE | NC 81 (SWANNANOA RIVER ROAD) | US 70 (TUNNEL ROAD) TO US 74 (SOUTH TUNNEL ROAD). UPGRADE ROADWAY. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-6046 | DIVISION 13 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 16300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 24700000 |  |  | 43100000 | COORDINATE WITH U-5832.
BUNCOMBE | NEW LEICESTER HIGHWAY | NEW LEICESTER HIGHWAY, CITY LIMITS TO PATTON AVENUE IN ASHEVILLE. CONSTRUCT SIDEWALK. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-5190 | PRE-STI (TRANSITION) | BGANY, BGDA, L | 2020 | 241000 |  |  | 2022 | 3322000 |  |  | 3563000 | $2.199M IN BGANY USED AS PART OF FUND SWAP; PROJECT ADMINISTERED BY CITY OF ASHEVILLE
BUNCOMBE | NEW ROUTE - ENKA HERITAGE ROAD | US 19/23 (SMOKEY PARK HIGHWAY) TO WALKOFF WAY. CONSTRUCT ACCESS ROAD ON NEW LOCATION. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-6251A | EXEMPT | ADHSL, L |  |  |  |  | 2022 | 2750000 |  |  | 2750000
BUNCOMBE | NEW ROUTE- ENKA HERITAGE ROAD | CONSTRUCT ACCESS ROAD FOR HAAKON INDUSTRIES IN ENKA COMMERCE PARK. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-6251 | EXEMPT | [10 empty] | ARC PROJECT #19852, AWARD AMOUNT = $3,300,000; LOCAL FUNDS PROVIDED BY BUNCOMBE COUNTY. STATE FUNDS ARE SPOT MOBILITY FUNDS.
BUNCOMBE | PATTON AVENUE AND COLLEGE STREET. | SIGNAL IMPROVEMENTS | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-4715AB | [11 empty] | COMPLETE
BUNCOMBE | RIVERWAY MULTI-MODAL NETWORK | CONSTRUCT TOWN BRANCH GREENWAY. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-5019A | DIVISION 13 | BGANY, L |  |  |  |  | 2023 | 4267000 |  |  | 4267000
BUNCOMBE | RIVERWAY MULTI-MODAL NETWORK | FRENCH BROAD RIVER WEST GREENWAY, FRENCH BROAD RIVER PARK TO HAYWOOD ROAD. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-5019B | DIVISION 13 | [10 empty] | UNDER CONSTRUCTION
BUNCOMBE | RIVERWAY MULTI-MODAL NETWORK | WILMA DYKEMAN RIVERWAY - RADTIP AND FIVE POINTS ROUNDABOUT. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-5019C | DIVISION 13 | [10 empty] | UNDER CONSTRUCTION
BUNCOMBE | RIVERWAY MULTI-MODAL NETWORK | LIVINGSTON STREET COMPLETE STREETS IMPROVEMENTS. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-5019D | DIVISION 13 | L |  |  |  |  | 2023 | 1500000 |  |  | 1500000
BUNCOMBE | RIVERWAY MULTI-MODAL NETWORK | CRAVEN STREET BRIDGE IMPROVEMENTS OVER THE FRENCH BROAD RIVER | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-5019E | DIVISION 13 | BGANY, L |  |  |  |  | 2024 | 5250000 |  |  | 5250000
BUNCOMBE | SR 1002 (OLD LEICESTER HWY) | REPLACE BRIDGE 100649 OVER FRENCH BROAD RIVER AND SOUTHERN RAILROAD. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | B-5953 | DIVISION 13 | HFB | 2023 | 1000000 |  |  | 2024 | 20000000 |  |  | 21000000
BUNCOMBE | SR 1296 (BROOKS BRANCH ROAD) | REPLACE BRIDGE 100536 OVER NEWFOUND CREEK. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | B-6018 | DIVISION 13 | BGOFF | 2021 | 55000 |  |  | 2021 | 872000 |  |  | 927000 | RIGHT-OF-WAY AND CONSTRUCTION TO BE COMBINED WITH B-6015. UNDER CONSTRUCTION.
BUNCOMBE | SR 1332 | SR 1332 (NORTH LOUISIANA AVENUE) AT SR 1338 (EMMA ROAD). INSTALL PEDESTRIAN SIGNAL PHASING, HIGH VISIBILITY CROSSWALKS, SIDEWALK AND CURB RAMPS. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | W-5813C | DIVISION 13 | HSIP | 2022 | 2000 |  |  | 2023 | 95000 |  |  | 97000
BUNCOMBE | SR 1332 (NORTH LOUISIANA AVENUE) | US 19/23 (PATTON AVENUE) TO SR 1338 (EMMA ROAD). MODERNIZE ROADWAY. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-6162 | DIVISION 13 | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 13200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6000000 |  |  | 20000000
BUNCOMBE | SR 1477 (RIVERSIDE DRIVE) | SR 1517 (HILL STREET) TO SR 1781 (BROADWAY STREET) | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-2513D | DIVISION 13 | BGANY | 2024 | 15300000 | 2024 | 3100000 | 2024 | 13100000 |  |  | 31500000 | TO BE LET WITH I-2513B.
BUNCOMBE | SR 1620 (FLETCHER MARTIN ROAD) | REPLACE BRIDGE 100007 OVER FRENCH BROAD RIVER AND SOUTHERN RAILROAD. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | B-5992 | DIVISION 13 | BGOFF | 2022 | 67000 | 2022 | 543000 | 2024 | 7501000 |  |  | 8111000
BUNCOMBE | SR 2002 (RICEVILLE ROAD) | US 70 (TUNNEL ROAD) TO SR 2285 (CLEAR VISTA LANE). UPGRADE ROADWAY. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-5837 | DIVISION 13 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9100000 |  |  | 25700000
BUNCOMBE | SR 2002 (RICEVILLE ROAD) | US 70 TO SR 2419 (BULL CREEK ROAD) NEAR HAW CREEK. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | W-5213G | DIVISION 13 | HSIP |  |  |  |  | 2023 | 1225000 |  |  | 1225000
BUNCOMBE | SR 2027 (MARTINS CREEK ROAD) | REPLACE BRIDGE 100142 OVER MARTIN CREEK. | HIGHWAY | 13 | LAND-OF-SKY RPO | B-6016 | DIVISION 13 | BGOFF | 2022 | 50000 |  |  | 2022 | 700000 |  |  | 750000 | DESIGN-BUILD; COMBINED LETTING WITH B-6011, B-6013, & B-6014
BUNCOMBE | SR 2500 (BLUE RIDGE ROAD) | CONVERT I-40/SR 2500 (BLUE RIDGE ROAD) GRADE SEPARATION TO INTERCHANGE. WIDEN SR 2500 (BLUE RIDGE ROAD) TO THREE LANES FROM US 70 TO SOUTH OF I-40 AND UPGRADE ROADWAY SOUTH OF I-40 TO SR 2713. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-4409 | DIVISION 13 | NHP, T | 2023 | 6300000 | 2023 | 900000 | 2025 | 26990000 |  |  | 34190000 | BUILD NC BOND FUNDING: $8M FOR CONSTRUCTION, PAYBACK FY 2026-2040 (FY 2026 / YR 8 SALE)
BUNCOMBE | SR 2806 | SR 2806 (GARREN CREEK ROAD) FROM SR 2815 TO SR 2786, NEAR FAIRVIEW. INSTALL SHOULDER GUARDRAIL. | HIGHWAY | 13 | LAND-OF-SKY RPO | W-5813I | DIVISION 13 | HSIP |  |  |  |  | 2022 | 460000 |  |  | 460000 | COMPLETE
BUNCOMBE | SR 3116 (MILLS GAP ROAD) | US 25 (HENDERSONVILLE ROAD) TO SR 3157 (WESTON ROAD). UPGRADE EXISTING ROADWAY. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-5834 | DIVISION 13 | T | 2019 | 12333000 |  |  | 2024 | 14925000 |  |  | 27258000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $6M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE).
BUNCOMBE | SR 3116 (MILLS GAP ROAD) | SR 3136 (CANE CREEK ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-6163 | DIVISION 13 | S, T | 2024 | 100000 | 2024 | 300000 | 2024 | 2400000 |  |  | 2800000 | STATE FUNDS ARE HIGH IMPACT/LOW COST FUNDS
BUNCOMBE | SR 3214 (BILTMORE AVENUE) | WHITE FAWN DRIVE INTERSECTION. INSTALL A TRAFFIC SIGNAL AND CONSTRUCT PEDESTRIAN IMPROVEMENTS. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | HL-0014 | DIVISION 13 | BGANY, BGDA, L | 2023 | 25000 |  |  | 2023 | 340000 | 2022 | 75000 | 440000 | 320K STBG-ANYAREA PROVIDED AS PART OF FUND SWAP
BUNCOMBE | SR 3556 (AMBOYROAD/ MEADOW ROAD) | I-240 TO NC 81/SR 3214 (BILTMORE AVENUE). WIDEN TO MULTI-LANES WITH NEW BRIDGE OVER THE FRENCH BROAD RIVER. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-4739 | DIVISION 13 | BGANY | 2025 | 18500000 | 2025 | 7400000 | 2028 | 38900000 |  |  | 64800000
BUNCOMBE | US 19/23 (SMOKEY PARK HIGHWAY) | ENKA HERITAGE ROAD INTERSECTION. CONSTRUCT FINAL INTERSECTION IMPROVEMENTS. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-6251B | EXEMPT | ADHSL, L, S | 2022 | 900000 |  |  | 2022 | 635000 |  |  | 1535000
BUNCOMBE | US 19/23 BUSINESS (HAYWOOD ROAD) | UPGRADE ROADWAY (INCLUDING RESURFACING AND PEDESTRIAN IMPROVEMENTS) FROM US 19/23/74 (PATTON AVENUE) TO RIDGELAWN ROAD. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | HL-0003 | REGION G | BGANY, BGDA, S(M) |  |  |  |  | 2023 | 7692000 | 2022 | 30000 | 7722000 | $2.9M STBG-ANY AREA PROVIDED AS PART OF FUND SWAP; "S(M)" FUNDS REPRESENT NCDOT DIVISION 13 HMIP FUNDS; STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT.
BUNCOMBE | US 19/23/25/70 | REHABILITATE DECK ON BRIDGE 100353 OVER SR 1882. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | B-4444 | STATEWIDE MOBILITY | BFP |  |  |  |  | 2026 | 1000000 |  |  | 1000000
BUNCOMBE | US 19/US 23/US 25/ US 70 | REPLACE BRIDGE 100370, AND BRIDGE 100373 OVER REEMS CREEK. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | B-4442 | STATEWIDE MOBILITY | NHPB | 2022 | 400000 | 2022 | 0 | 2022 | 22400000 |  |  | 22800000 | COORDINATE WITH A-0010 A
BUNCOMBE | US 19/US 23/US 25/ US 70 | REPLACE BRIDGE 100345, AND BRIDGE 100346 OVER SR 1839. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | B-4443 | STATEWIDE MOBILITY | BFP | 2025 | 720000 |  |  | 2026 | 7199000 |  |  | 7919000 | COORDINATE WITH A-0010 A
BUNCOMBE | US 19-23-74 ALT | US 19-23-74 ALT (PATTON AVENUE) AT US 19-23 BUS (HAYWOOD ROAD)/SR 1319 (JOHNSTON ROAD). INSTALL PEDESTRIAN SIGNAL PHASING, HIGH VISIBILITY CROSSWALKS AND CURB RAMPS. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | W-5813E | REGION G | HSIP |  |  |  |  | 2023 | 115000 |  |  | 115000
BUNCOMBE | US 19-23-74 ALT | US 19-23-74 ALT (SMOKEY PARK HIGHWAY) AT OLD HAYWOOD ROAD. INSTALL PEDESTRIAN SIGNAL PHASING, HIGH VISIBILITY CROSSWALKS, AND CURB RAMPS. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | W-5813F | REGION G | HSIP |  |  |  |  | 2023 | 70000 |  |  | 70000
BUNCOMBE | US 25 | US 25 (MCDOWELL STREET) AT DOCTOR'S DRIVE/ASHEVILLE HIGH SCHOOL ENTRANCE. INSTALL PEDESTRIAN SIGNALS, HIGH VISIBILITY CROSSWALKS, AND CURB RAMPS. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | W-5813A | REGION G | HSIP |  |  |  |  | 2022 | 64000 |  |  | 64000
BUNCOMBE | US 25 | ALL SOULS CRESCENT AND US 25 ALT (LODGE STREET) INTERSECTIONS. INSTALL CURB RAMPS, SIDEWALK, AND SIGNAL UPGRADES. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | W-5813D | REGION G | HSIP |  |  |  |  | 2023 | 96000 |  |  | 96000
BUNCOMBE | US 25 (HENDERSONVILLE ROAD) | SIGNAL IMPROVEMENTS | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-4715AA | [11 empty] | COMPLETE
BUNCOMBE | US 25A (SWEETEN CREEK ROAD) | US 25 (HENDERSONVILLE ROAD) TO ROBERTS ROAD IN ASHEVILLE. WIDEN TO MULTI-LANES. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-2801
BUNCOMBE | US 25A (SWEETEN CREEK ROAD) | US 25 (HENDERSONVILLE ROAD) TO SR 3081 (ROCK HILL ROAD) | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-2801A | REGION G | T | 2028 | 112100000 | 2028 | 6720000 | 2031 | 76500000 |  |  | 195320000
BUNCOMBE | US 25A (SWEETEN CREEK ROAD) | SR 3081 (ROCK HILL ROAD) TO SR 3079 (ROBERTS ROAD) | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-2801B | [11 empty] | COMPLETE
BUNCOMBE | US 70; US 74 ALT | (1) US 70 (TUNNEL ROAD) AT OLD CHUNNS COVE ROAD, (2) US 74 ALT (S. TUNNEL ROAD) AT MAIN MALL ENTRANCE (EAST LEG), (3) US 74 ALT (S. TUNNEL ROAD) AT LOWER MALL ENTRANCE. INSTALL CURB RAMPS, SIDEWALK, AND SIGNAL UPGRADES. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | W-5813G | REGION G | HSIP |  |  |  |  | 2022 | 135000 |  |  | 135000
BUNCOMBE | VARIOUS | DIVISION 13 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS IN THE DIVISION CATEGORY. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | W-5213DIV | DIVISION 13 | HSIP | 2020 | 50000 |  |  | 2020 | 700000 |  |  | 750000
BUNCOMBE | WALK OFF WAY | CONSTRUCT WALK OFF WAY EXTENSION FOR HAAKON INDUSTRIES IN ENKA COMMERCE PARK. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-6230 | DIVISION 13 | T |  |  |  |  | 2021 | 1300000 |  |  | 1300000 | ECONOMIC DEVELOPMENT PROJECT.
BUNCOMBE | WEAVERVILLE | US 19 BUSINESS (WEAVERVILLE HIGHWAY) AND SR 1740 (NEW STOCK ROAD). CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-5973 | NOT FUNDED | T |  |  |  |  | NOT FUNDED | 200000 |  |  | 200000
BUNCOMBE | ASHEVILLE REDEFINES TRANSIT | 5310 TRADITIONAL PROJECTS | PUBLIC TRANSIT | 13 | FRENCH BROAD RIVER MPO | TQ-6186 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2020 | 693000 | 693000
BUNCOMBE | BUNCOMBE MOUNTAIN MOBILITY - | REPLACEMENT VANS | PUBLIC TRANSIT | 13 | FRENCH BROAD RIVER MPO | TA-6701 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 544000 | 544000
BUNCOMBE | CITY OF ASHEVILLE | ART BUSES AND OTHER ROUTINE CAPITAL ITEMS | PUBLIC TRANSIT | 13 | FRENCH BROAD RIVER MPO | TA-6626 | PUBLIC TRANSIT | 5339, L | [6 empty] | 2020 | 1439000 | 1439000
BUNCOMBE | CITY OF ASHEVILLE | ASHEVILLE RIDES TRANSIT LO-NO TRANSIT VEHICLE PURCHASE | PUBLIC TRANSIT | 13 | FRENCH BROAD RIVER MPO | TA-6703 | PUBLIC TRANSIT | 5339, L | [6 empty] | 2020 | 3365000 | 3365000
BUNCOMBE | CITY OF ASHEVILLE | BUSES AND BUS FACILITIES - BUS STOP IMPROVEMENT PROGRAM | PUBLIC TRANSIT | 13 | FRENCH BROAD RIVER MPO | TG-0011 | PUBLIC TRANSIT | 5339, L | [6 empty] | 2021 | 1250000 | 1250000
BUNCOMBE | CITY OF ASHEVILLE | TRANSIT PREVENTATIVE MAINTENANCE | PUBLIC TRANSIT | 13 | FRENCH BROAD RIVER MPO | TG-6183B | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 1000000 | 1000000 | FUNDS AUTHORIZED IN PROGRESS
BUNCOMBE | CITY OF ASHEVILLE | JARC OPERATIONS | PUBLIC TRANSIT | 13 | FRENCH BROAD RIVER MPO | TM-5138 | PUBLIC TRANSIT | 3037, L | [6 empty] | 2021 | 734000 | 734000
BUNCOMBE | CITY OF ASHEVILLE | TRANSIT OPERATIONS | PUBLIC TRANSIT | 13 | FRENCH BROAD RIVER MPO | TO-4075 | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 18194000 | 18194000
BUNCOMBE | CITY OF ASHEVILLE | PLANNING ASSISTANCE | PUBLIC TRANSIT | 13 | FRENCH BROAD RIVER MPO | TP-5113 | PUBLIC TRANSIT | 5303, L, S | [6 empty] | 2020 | 180000 | 180000 | FUNDS AUTHORIZED IN PROGRESS
BUNCOMBE | CITY OF ASHEVILLE | PLANNING FOR MOUNTAIN MOBILITY | PUBLIC TRANSIT | 13 | FRENCH BROAD RIVER MPO | TP-5153 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 604000 | 604000
BUNCOMBE | CITY OF ASHEVILLE | 5310 OTHER PROJECTS | PUBLIC TRANSIT | 13 | FRENCH BROAD RIVER MPO | TQ-6187 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2020 | 688000 | 688000
BUNCOMBE | CITY OF ASHEVILLE | ASHEVILLE RIDES TRANSIT. 5310 ADMINISTRATIVE OVERSIGHT. | PUBLIC TRANSIT | 13 | FRENCH BROAD RIVER MPO | TQ-7010 | PUBLIC TRANSIT | 5310 | [6 empty] | 2021 | 67000 | 67000
BUNCOMBE | CITY OF ASHEVILLE | SAFETY & SECURITY - MIN. 1% SET ASIDE | PUBLIC TRANSIT | 13 | FRENCH BROAD RIVER MPO | TS-5102 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2021 | 36000 | 36000 | FUNDS AUTHORIZED IN PROGRESS
BUNCOMBE | MOUNTAIN MOBILITY - BUNCOMBE | MOUNTAIN MOBILITY BUNCOMBE - BUNCOMBE COUNTY TRANSIT ROUTINE CAPITAL COST OF CONTRACTING. | PUBLIC TRANSIT | 13 | FRENCH BROAD RIVER MPO | TG-6786 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2021 | 1927000 | 1927000
BUNCOMBE | MOUNTAIN MOBILITY - BUNCOMBE | ADMINISTRATION | PUBLIC TRANSIT | 13 |  | TK-6148 | PUBLIC TRANSIT | 5309, 5311, L, S | [6 empty] | 2020 | 1816000 | 1816000 | FUNDS AUTHORIZED IN PROGRESS
BUNCOMBE | MOUNTAIN MOBILITY - BUNCOMBE | BUNCOMBE COUNTY TRANSIT OPERATING ASSISTANCE. | PUBLIC TRANSIT | 13 | FRENCH BROAD RIVER MPO | TO-6154 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2251000 | 2251000
BUNCOMBE, BURKE, MADISON, MCDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | DIVISION 13 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | BIKE/PED | 13 | HIGH COUNTRY RPO, FOOTHILLS RPO, FRENCH BROAD RIVER MPO, GREATER HICKORY MPO, LAND-OF-SKY RPO | BO-2413 | DIVISION 13 | S, TA |  |  |  |  | 2024 | 4000000 |  |  | 4000000
BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 13. | HIGHWAY | 13 | HIGH COUNTRY RPO, FOOTHILLS RPO, FRENCH BROAD RIVER MPO, GREATER HICKORY MPO, LAND-OF-SKY RPO | HS-2013 | DIVISION 13 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
BUNCOMBE, BURKE, MADISON, MCDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | DIVISION 13 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | HIGHWAY | 13 | HIGH COUNTRY RPO, FOOTHILLS RPO, FRENCH BROAD RIVER MPO, GREATER HICKORY MPO, LAND-OF-SKY RPO | R-5793 | DIVISION 13 | S, TA |  |  |  |  | 2020 | 3500000 |  |  | 3500000 | UNDER CONSTRUCTION. "S" FUNDS ARE STATE HIGHWAY FUNDS
BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | DIVISION 13 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | 13 | HIGH COUNTRY RPO, FOOTHILLS RPO, FRENCH BROAD RIVER MPO, GREATER HICKORY MPO, LAND-OF-SKY RPO | W-5213 | [11 empty] | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS
BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 13. | HIGHWAY | 13 | HIGH COUNTRY RPO, FOOTHILLS RPO, FRENCH BROAD RIVER MPO, GREATER HICKORY MPO, LAND-OF-SKY RPO | W-5713 | [11 empty] | COMPLETE
BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 13 | HIGH COUNTRY RPO, FOOTHILLS RPO, FRENCH BROAD RIVER MPO, GREATER HICKORY MPO, LAND-OF-SKY RPO | W-5713DIV | DIVISION 13 | HSIP | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000
BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 13 | HIGH COUNTRY RPO, FOOTHILLS RPO, FRENCH BROAD RIVER MPO, GREATER HICKORY MPO, LAND-OF-SKY RPO | W-5713REG | REGION G | HSIP | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000
BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 13 | HIGH COUNTRY RPO, FOOTHILLS RPO, FRENCH BROAD RIVER MPO, GREATER HICKORY MPO, LAND-OF-SKY RPO | W-5713SW | STATEWIDE MOBILITY | HSIP | 2020 | 160000 |  |  | 2020 | 960000 |  |  | 1120000
BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 13. | HIGHWAY | 13 | HIGH COUNTRY RPO, FOOTHILLS RPO, FRENCH BROAD RIVER MPO, GREATER HICKORY MPO, LAND-OF-SKY RPO | W-5813 | [11 empty] | INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 13. | RAIL | 13 | HIGH COUNTRY RPO, FOOTHILLS RPO, FRENCH BROAD RIVER MPO, GREATER HICKORY MPO, LAND-OF-SKY RPO | RC-2013 | DIVISION 13 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
BUNCOMBE, BURKE, MADISON, McDOWELL, MITCHELL, RUTHERFORD, YANCEY | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 13. | RAIL | 13 | HIGH COUNTRY RPO, FOOTHILLS RPO, FRENCH BROAD RIVER MPO, GREATER HICKORY MPO, LAND-OF-SKY RPO | RX-2013 | DIVISION 13 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
BUNCOMBE, HAYWOOD | I-40 | US 74 (SMOKY MOUNTAIN EXPRESSWAY) TO SR 1224 (MONTE VISTA ROAD). ADD ADDITIONAL LANES. | HIGHWAY | 13, 14 | FRENCH BROAD RIVER MPO | I-6054
BUNCOMBE, HAYWOOD | CITY OF ASHEVILLE | CITY OF ASHEVILLE ADMINISTRATIVE OVERSIGHT OF JARC PROJECTS IN THE ASHEVILLE UAZ | PUBLIC TRANSIT | 13, 14 | FRENCH BROAD RIVER MPO | TM-5163 | PUBLIC TRANSIT | L | [6 empty] | 2020 | 85000 | 85000
BUNCOMBE, HENDERSON | I-26 | NC 280 (EXIT 40) TO I-40 AT ASHEVILLE. ADD ADDITIONAL LANES. | HIGHWAY | 13, 14 | FRENCH BROAD RIVER MPO | I-4700 | STATEWIDE MOBILITY | NHP |  |  |  |  | 2019 | 62468000 |  |  | 62468000 | UNDER CONSTRUCTION. SEGMENTS A AND B DELETED; GARVEE BOND FUNDING - $52M FOR CONSTRUCTION, PAYBACK FY 2019-2033
BUNCOMBE, HENDERSON | NC 191 (BREVARD ROAD - OLD HAYWOOD ROAD) | NC 280 (BOYLSTON HIGHWAY) TO SR 3498 (LEDBETTER ROAD). | HIGHWAY | 13, 14 | FRENCH BROAD RIVER MPO | U-3403A | NOT FUNDED | T | NOT FUNDED | 9000000 |  |  | NOT FUNDED | 17700000 |  |  | 26700000
BUNCOMBE, HENDERSON | NC 191 (BREVARD ROAD) | NC 280 TO NC 112 (SARDIS ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 13, 14 | FRENCH BROAD RIVER MPO | U-3403
BUNCOMBE, HENDERSON, HAYWOOD | VARIOUS | STBG-DA IN THE FRENCH BROAD RIVER METROPOLITAN PLANNING ORGANIZATION. | HIGHWAY | 13, 14 | FRENCH BROAD RIVER MPO | U-5100 | DIVISION 13, 14 | BGDA, L |  |  |  |  | 2020 | 62720000 |  |  | 62720000
BUNCOMBE, HENDERSON, HAYWOOD, MADISON | VARIOUS | FRENCH BROAD RIVER MPO TRANSPORTATION ALTERNATIVES (TA) PROGRAM. | BIKE/PED | 13, 14 | FRENCH BROAD RIVER MPO | U-5535 | DIVISION 13, 14 | L, TADA |  |  |  |  | 2020 | 12257000 |  |  | 12257000
BUNCOMBE, HENDERSON, HAYWOOD, MADISON | VARIOUS | FRENCH BROAD RIVER METROPOLITAN PLANNING ORGANIZATION PLANNING (PL) SUPPLEMENT. | HIGHWAY | 13, 14 | FRENCH BROAD RIVER MPO | U-5616 | DIVISION 13, 14 | BGDA, L | [6 empty] | 2020 | 3620000 | 3620000
BUNCOMBE, MADISON | I-26 (US 19/US 23) | SR 1781 (BROADWAY STREET) IN ASHEVILLE TO TENNESSEE STATE LINE AT SAMS GAP. MULTI-LANE FREEWAY, PART ON NEW LOCATION. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO, LAND-OF-SKY RPO | A-0010 | [11 empty] | COORDINATE WITH B-4442, B-4443, B-4444.
BUNCOMBE, MADISON | I-26 (US 19/US 23) | SOUTH OF SR 2148 IN BUNCOMBE COUNTY TO NORTH OF NC 213 | HIGHWAY | 13 | LAND-OF-SKY RPO, FRENCH BROAD RIVER MPO | A-0010BA | [11 empty] | COMPLETE
BUNCOMBE, MADISON | US 25/70 | NORTH OF SR 1584 (TILLERY BRANCH ROAD) TO SR 1727 (MONTICELLO ROAD). UPGRADE ROADWAY TO SUPERSTREET. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO, LAND-OF-SKY RPO | U-6173 | NOT FUNDED | BGANY | NOT FUNDED | 300000 | NOT FUNDED | 600000 | NOT FUNDED | 33249000 |  |  | 34149000
BURKE | COLLEGE STREET MULTIMODAL CONNECTOR | NORTH GREEN STREET TO US 70 IN MORGANTON. CONSTRUCT MULTI-USE PATH. | BIKE/PED | 13 | GREATER HICKORY MPO | EB-5978 | DIVISION 13 | L, TAANY | 2022 | 100000 |  |  | 2024 | 2900000 |  |  | 3000000
BURKE | FONTA FLORA TRAIL | FONTA FLORA STATE TRAIL, INTERSECTION OF LAUREL RIDGE COURT AND NORTH POWERHOUSE ROAD TO THE PROPOSED HARRIS WHISNANT TRAILHEAD AT THE INTERSECTION OF HARRY WHISNANT ROAD AND COBB ROAD. CONSTRUCT BICYCLE AND PEDESTRIAN FACILITY. | BIKE/PED | 13 | GREATER HICKORY MPO | EB-5827 | DIVISION 13 | BGANY, L | 2023 | 626000 | [6 empty] | 626000 | $410K IN STBG-DA FUNDS SWITCHED WITH $410K IN BG-ANY AS PART OF FUND SWAP 5-19-22.
BURKE | HICKORY | RIVERWALK. CONSTRUCT MULTI-USE PATH FROM OLD LENOIR ROAD AT CITY OWNED PROPERTY TO END OF PROPOSED ROSALES BRIDGE. | BIKE/PED | 13 | GREATER HICKORY MPO | EB-5939 | DIVISION 13 | BGDA, L |  |  |  |  | 2023 | 6500000 |  |  | 6500000
BURKE | MAIN AVENUE EAST | 2ND STREET SE TO US 70 IN HILDEBRAN. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | BIKE/PED | 13 | GREATER HICKORY MPO | BL-0001 | DIVISION 13 | BGANY, BGDA, L | 2023 | 100000 |  |  | 2023 | 340000 | 2022 | 80000 | 520000 | $272K IN STBG-DA FUNDS SWITCHED WITH $272K IN BG-ANY AS PART OF FUND SWAP 5-19-22.
BURKE | MORGANTON | MORGANTON DOWNTOWN GREENWAY CONNECTOR. | BIKE/PED | 13 | GREATER HICKORY MPO | EB-5807 | DIVISION 13 | BGANY, BGDA, L |  |  |  |  | 2021 | 1619000 |  |  | 1619000 | RIGHT-OF-WAY IN PROGRESS
BURKE | I-40 | REPLACE BRIDGES 110114 AND 110120 OVER SILVER CREEK. | HIGHWAY | 13 | GREATER HICKORY MPO | BR-0130 | STATEWIDE MOBILITY | BFP |  |  |  |  | 2026 | 11800000 |  |  | 11800000
BURKE | I-40 | SR 1734 (CAROLINA STREET SE)/SR 1826 - EXIT 111. REVISE INTERCHANGE. | HIGHWAY | 13 | GREATER HICKORY MPO | I-5008 | REGION G | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 31600000 |  |  | 37400000 | PROJECT TO BE LET WITH I-5875.
BURKE | I-40 | US 64 (BURKEMONT ROAD). IMPROVE INTERCHANGE. | HIGHWAY | 13 | GREATER HICKORY MPO | I-5009 | REGION G | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 16400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 26200000 |  |  | 48700000
BURKE | I-40 | SR 1142 (JAMESTOWN ROAD) - EXIT 100. UPGRADE INTERCHANGE. | HIGHWAY | 13 | GREATER HICKORY MPO | I-5874 | REGION G | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 31300000 |  |  | 33200000
BURKE | I-40 | SR 1712 (DREXEL ROAD). UPGRADE INTERCHANGE. | HIGHWAY | 13 | GREATER HICKORY MPO | I-5875 | REGION G | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 27200000 |  |  | 29300000 | PROJECT TO BE LET WITH I-5008
BURKE | I-40 | SR 1761 (OLD HIGHWAY NC 10) - EXIT 116. UPGRADE INTERCHANGE AND REMOVE TWO-WAY TRAFFIC. | HIGHWAY | 13 | GREATER HICKORY MPO | I-5971 | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 21500000 |  |  | 23000000
BURKE | I-40 | SR 1744 (MINERAL SPRINGS MOUNTAIN ROAD)/SR 1744 (ELDRED STREET SE) - EXIT 112. CONSTRUCT INTERCHANGE IMPROVEMENTS. | HIGHWAY | 13 | GREATER HICKORY MPO | I-5975 | NOT FUNDED | NHP | NOT FUNDED | 2660000 | NOT FUNDED | 100000 | NOT FUNDED | 5200000 |  |  | 7960000
BURKE | I-40 | EXIT 118 - SR 1761 (OLD NC 10). CONTRUCT INTERCHANGE IMPROVEMENTS. | HIGHWAY | 13 | GREATER HICKORY MPO | I-5990 | DIVISION 13 | NHP | 2023 | 2500000 | 2023 | 1100000 | 2024 | 9600000 |  |  | 13200000
BURKE | I-40 | SR 1147 (CAUSBY ROAD). REDESIGN INTERCHANGE AND REMOVE TWO-WAY ON RAMP. | HIGHWAY | 13 | GREATER HICKORY MPO | I-6058 | NOT FUNDED | NHP | NOT FUNDED | 300000 | NOT FUNDED | 1100000 | NOT FUNDED | 4300000 |  |  | 5700000
BURKE | MORGANTON | SOUTH STERLING STREET TO WEST PARKER ROAD. CONSTRUCT CONNECTOR ROAD. | HIGHWAY | 13 | GREATER HICKORY MPO | U-6057 | EXEMPT | [10 empty] | UNDER CONSTRUCTION. ARC PROJECT NO. 18703
BURKE | NC 126 | SR 1250 (WATERMILL ROAD) TO SR 1254 (FISH HATCHERY ROAD). MODERNIZE ROADWAY. | HIGHWAY | 13 | GREATER HICKORY MPO | U-6164 | NOT FUNDED | BGLT5 | NOT FUNDED | 3400000 | NOT FUNDED | 700000 | NOT FUNDED | 27201000 |  |  | 31301000
BURKE | NC 181 | US 64 TO SR 1405 (BROWN MOUNTAIN BEACH ROAD). UPGRADE GUARDRAIL. | HIGHWAY | 13 | GREATER HICKORY MPO | HS-2013C | REGION G | HSIP |  |  |  |  | 2021 | 195000 |  |  | 195000 | COMPLETE
BURKE | NC 181 | SR 1414 (ST MARY'S CHURCH ROAD) TO MORGANTON ETJ. WIDEN EXISTING ROADWAY. | HIGHWAY | 13 | GREATER HICKORY MPO | U-5836 | REGION G | T | 2027 | 3000000 |  |  | 2029 | 7800000 |  |  | 10800000
BURKE | NC 181 | SR 1440 TO SR 1419. WIDEN TO 3-LANES. | HIGHWAY | 13 | GREATER HICKORY MPO | U-5978 | NOT FUNDED | T | NOT FUNDED | 8500000 | NOT FUNDED | 1510000 | NOT FUNDED | 12900000 |  |  | 22910000
BURKE | NEW ROUTE | CONSTRUCT ACCESS ROAD INTO BURKE COUNTY INDUSTRIAL PARK. | HIGHWAY | 13 | GREATER HICKORY MPO | HA-0001 | EXEMPT | ADHSL |  |  |  |  | 2023 | 1700000 | 2021 | 200000 | 1900000 | ARC PROJECT NO. 19857, AWARD AMOUNT = $1,900,000
BURKE | SR 1001 (CONNELLY SPRINGS ROAD) | REPLACE BRIDGE 110010 OVER CATAWBA RIVER. | HIGHWAY | 13 | GREATER HICKORY MPO | R-3430B | HIGHWAY FUND | HFB | 2022 | 500000 | 2022 | 65000 | 2024 | 17499000 |  |  | 18064000
BURKE | SR 1001 (MALCOLM BOULEVARD) | US 70 TO CATAWBA RIVER. | HIGHWAY | 13 | GREATER HICKORY MPO | R-3430A | NOT FUNDED | T | NOT FUNDED | 10000000 | NOT FUNDED | 1600000 | NOT FUNDED | 20000000 |  |  | 31600000
BURKE | SR 1430 (HARLAND ROAD) | REPLACE BRIDGE 110145 OVER BRISTOL CREEK. | HIGHWAY | 13 | GREATER HICKORY MPO | B-6011 | DIVISION 13 | BGOFF | 2022 | 65000 |  |  | 2022 | 725000 |  |  | 790000 | DESIGN-BUILD, COMBINED LETTING WITH B-6013, B-6014, & B-6016
BURKE | SR 1687 (GOAT FARM ROAD) | IMPROVE EXISTING SR 1687 (GOAT FARM ROAD) ACCESS ROAD INTO THE PROPOSED INDUSTRIAL PARK. | HIGHWAY | 13 | GREATER HICKORY MPO | R-5967 | EXEMPT | ADHSL, L |  |  |  |  | 2023 | 2857000 |  |  | 2857000 | ARC PROJECT # 19768; AWARD AMOUNT = $1,500,000; LOCAL FUNDING PROVIDED BY CITY OF HICKORY
BURKE | SR 1913 (SUGAR LOAF ROAD) | REPLACE BRIDGE 110237 OVER ROCK CREEK. | HIGHWAY | 13 | GREATER HICKORY MPO | B-6015 | DIVISION 13 | BGOFF | 2021 | 100000 |  |  | 2021 | 819000 |  |  | 919000 | RIGHT-OF-WAY AND CONSTRUCTION TO BE COMBINED WITH B-6018. UNDER CONSTRUCTION.
BURKE | US 321 | BRIDGES #366 AND #367 AT THE CATAWBA COUNTY LINE. INSTALL GUARDRAIL. | HIGHWAY | 13 | GREATER HICKORY MPO | HS-2013A | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2021 | 92000 |  |  | 92000 | COMPLETE
BURKE | US 64 (BURKEMONT AVENUE) | US 70 (W. FLEMING DRIVE) INTERSECTION. IMPROVE INTERSECTION. | HIGHWAY | 13 | GREATER HICKORY MPO | U-6123 | NOT FUNDED | NHP | NOT FUNDED | 2300000 | NOT FUNDED | 500000 | NOT FUNDED | 9100000 |  |  | 11900000
BURKE | US 64/70 | REPLACE BRIDGE 110099 OVER SOUTHERN RAILROAD. | HIGHWAY | 13 | GREATER HICKORY MPO | B-5869 | REGION G | BFP, BGDA | 2021 | 3200000 | 2021 | 270000 | 2023 | 13400000 |  |  | 16870000 | $2.56M IN BFP FUNDS SWITCHED WITH $2.56M IN STBG-DA AS PART OF FUND SWAP 5-19-22.
BURKE | US 64/NC 18 | NC 181 TO CALDWELL COUNTY LINE. UPGRADE GUARDRAIL. | HIGHWAY | 13 | GREATER HICKORY MPO | HS-2013E | REGION G | HSIP |  |  |  |  | 2021 | 385000 |  |  | 385000 | COMPLETE
BURKE, MITCHELL, RUTHERFORD | US 321, US 70, US 19E, US 221A | UPGRADE GUARDRAIL. | HIGHWAY | 13 | GREATER HICKORY MPO, HIGH COUNTRY RPO, FOOTHILLS RPO | HS-2013F | REGION G | HSIP |  |  |  |  | 2021 | 348000 |  |  | 348000 | COMPLETE
CABARRUS | CONCORD REGIONAL AIRPORT (JQF) | SOUTH DEVELOPMENT AREA APRON EXPANSION - PHASE II: APRON EXPANSION (DESIGN & CONSTRUCTION) | AVIATION | 10 | CABARRUS-ROWAN MPO | AV-5731 | REGION E | O, T |  |  |  |  | 2025 | 7917000 |  |  | 7917000
CABARRUS | CONCORD REGIONAL AIRPORT (JQF) | EXTEND RUNWAY SAFETY AREA. | AVIATION | 10 | CABARRUS-ROWAN MPO | AV-5889 | NOT FUNDED | T |  |  |  |  | NOT FUNDED | 300000 |  |  | 300000 | PROJECT SWAPPED WITH AV-5892 PER AGREEMENT BETWEEN NCDOT AND MPO.
CABARRUS | CONCORD REGIONAL AIRPORT (JQF) | REHABILITATE APRON AND TAXIWAY PAVEMENT. | AVIATION | 10 | CABARRUS-ROWAN MPO | AV-5890 | REGION E | T |  |  |  |  | 2020 | 300000 |  |  | 300000
CABARRUS | CONCORD REGIONAL AIRPORT (JQF) | CONSTRUCT NORTH APRON EXPANSION. | AVIATION | 10 | CABARRUS-ROWAN MPO | AV-5892 | REGION E | O, T |  |  |  |  | 2023 | 2170000 |  |  | 2170000 | OTHER FUNDING PROVIDED BY CONCORD REGIONAL AIRPORT. PROJECT SWAPPED WITH AV-5889 PER AGREEMENT BETWEEN NCDOT AND MPO.
CABARRUS | BRUTON SMITH BLVD/ CONCORD MILLS BLVD/ PORTION OF | US 29 TO WEDDINGTON ROAD. CONSTRUCT SIDEWALK ON BOTH SIDES OF THE ROAD, INCLUDING A PORTION OF WEDDINGTON ROAD. | BIKE/PED | 10 | CABARRUS-ROWAN MPO | EB-5732 | DIVISION 10 | L, TAANY | 2023 | 100000 |  |  | 2024 | 6000000 |  |  | 6100000
CABARRUS | CLARKE CREEK GREENWAY | STRADER STREET TO COX MILL ROAD. CONSTRUCT GREENWAY. | BIKE/PED | 10 | CABARRUS-ROWAN MPO | BL-0060 | EXEMPT | CMAQ, L |  |  |  |  | 2025 | 1937000 |  |  | 1937000
CABARRUS | CONCORD | DOWNTOWN PEDESTRIAN SIGNAL UPGRADES. | BIKE/PED | 10 | CABARRUS-ROWAN MPO | EB-5902 | DIVISION 10 | L, TADA |  |  |  |  | 2020 | 312000 |  |  | 312000
CABARRUS | CONCORD | UNION STREET. CONSTRUCT SIDEWALK EXTENSION. | BIKE/PED | 10 | CABARRUS-ROWAN MPO | EB-5903 | DIVISION 10 | CMAQ, L, TADA |  |  |  |  | 2020 | 866000 |  |  | 866000
CABARRUS | KANNAPOLIS | LITTLE TEXAS ROAD, LANE STREET TO DALE EARNHARDT BOULEVARD. CONSTRUCT SIDEWALK AND CURB AND GUTTER. | BIKE/PED | 10 | CABARRUS-ROWAN MPO | EB-5844 | DIVISION 10 | CMAQ, L, TAANY | 2023 | 400000 |  |  | 2024 | 1764000 |  |  | 2164000
CABARRUS | NORTH WASHINGTON STREET | PARK DRIVE TO NC 73 (EAST FRANKLIN STREET). CONSTRUCT SIDEWALK, CURB AND GUTTER AND WIDEN TO 12 FOOT SHARED TRAVEL LANES WITH BIKE SHARROWS. | BIKE/PED | 10 | CABARRUS-ROWAN MPO | BL-0043 | EXEMPT | CMAQ, L |  |  |  |  | 2023 | 524000 | 2022 | 115000 | 639000
CABARRUS | DALE EARNHARDT BOULEVARD | HUDSON STREET TO SOUTH CANNON BOULEVARD | HIGHWAY | 10 | CABARRUS-ROWAN MPO | C-4916A | EXEMPT | [10 empty] | COMPLETE
CABARRUS | FISHER STREET | FUNDS TRANSFERRED TO C-4918B | HIGHWAY | 10 | CABARRUS-ROWAN MPO | C-4916B | EXEMPT
CABARRUS | GEORGE LILES PARKWAY | NC 49 TO SOUTH OF I-85. WIDEN TO FOUR LANES DIVIDED, SOME NEW LOCATION. | HIGHWAY | 10 | CABARRUS-ROWAN MPO | R-2246
CABARRUS | GEORGE LILES PARKWAY | NC 49 TO SR 1304 (ROBERTA ROAD) | HIGHWAY | 10 | CABARRUS-ROWAN MPO | R-2246A | DIVISION 10 | T | 2028 | 4100000 | 2028 | 2900000 | 2030 | 24100000 |  |  | 31100000
CABARRUS | GEORGE LILES PARKWAY | SR 1304 (ROBERTA ROAD) TO SR 1431 (WEDDINGTON ROAD) | HIGHWAY | 10 | CABARRUS-ROWAN MPO | R-2246B | [11 empty] | COMPLETE
CABARRUS | GEORGE LILES PARKWAY | SR 1431 (WEDDINGTON ROAD) TO SOUTH OF I-85 | HIGHWAY | 10 | CABARRUS-ROWAN MPO | R-2246C | [11 empty] | COMPLETE
CABARRUS | I-85 | ITS FOR I-3802 A | HIGHWAY | 10 | CABARRUS-ROWAN MPO | I-3802AA | PRE-STI (TRANSITION) | CMAQ |  |  |  |  | 2023 | 1630000 |  |  | 1630000
CABARRUS | I-85 | SOUTH OF SR 2894 (CONCORD MILLS - BRUTON SMITH BOULEVARD) TO NC 73 IN CABARRUS COUNTY. WIDEN TO 8-LANES. | HIGHWAY | 10 | CABARRUS-ROWAN MPO | I-3803B | PRE-STI (TRANSITION) | NHP |  |  |  |  | 2010 | 22592000 |  |  | 22592000 | COMPLETE. GARVEE BOND FUNDING - SEGMENT B: $103M FOR CONSTRUCTION, PAYBACK FY 2010-2021
CABARRUS | I-85 | ITS FOR I-3803 B | HIGHWAY | 10 | CABARRUS-ROWAN MPO | I-3803BA | PRE-STI (TRANSITION)
CABARRUS | KANNAPOLIS | IRISH BUFFALO CREEK GREENWAY IN KANNAPOLIS. CONSTRUCT GREENWAY. | HIGHWAY | 10 | CABARRUS-ROWAN MPO | C-5161 | EXEMPT | [10 empty] | UNDER CONSTRUCTION
CABARRUS | NC 24/27 | SR 1120 (BETHEL SCHOOL RD) INTERSECTION. INSTALL A REDUCED CONFLICT INTERSECTION (RCI) WEITH UNSIGNALIZED BULBOUTS. | HIGHWAY | 10 | CABARRUS-ROWAN MPO | HS-2010D | REGION E | HSIP | 2022 | 301000 |  |  | 2023 | 392000 |  |  | 693000
CABARRUS | NC 24/27 | NC 24/27 AND SR 1100 (PINE BLUFF ROAD/ REED MINE ROAD) NEAR LOCUST. INSTALL A REDUCED CONFLICT INTERSECTION. | HIGHWAY | 10 | CABARRUS-ROWAN MPO | HS-2010F | REGION E | HSIP | 2024 | 5000 |  |  | 2025 | 747000 |  |  | 752000
CABARRUS | NC 24/NC 27 | REPLACE BRIDGE 22 OVER ROCKY RIVER. | HIGHWAY | 10 | CABARRUS-ROWAN MPO | B-5810 | REGION E | HFB |  |  |  |  | 2023 | 6200000 |  |  | 6200000
CABARRUS | NC 3 | PROPOSED WEST SIDE BYPASS (U-2009) TO SR 1691 (LOOP ROAD) IN KANNAPOLIS. WIDEN TO A FOUR-LANE DIVIDED FACILITY. | HIGHWAY | 10 | CABARRUS-ROWAN MPO | U-3440 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
CABARRUS | NC 3 (DALE EARNHARDT BOULEVARD) | INTERSECTION OF NC 3 (DALE EARNHARDT BOULEVARD) AND US 29/601 (CANNON BOULEVARD). CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 10 | CABARRUS-ROWAN MPO | U-5761 | REGION E | T |  |  |  |  | 2024 | 8100000 |  |  | 8100000 | RIGHT-OF-WAY IN PROGRESS.
CABARRUS | NC 73 (DAVIDSON HIGHWAY) | EAST OF SR 1394 (POPLAR TENT ROAD) TO US 29. | HIGHWAY | 10 | CABARRUS-ROWAN MPO | R-5706B | REGION E | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 70000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 175102000 |  |  | 252402000
CABARRUS | OAKWOOD AVENUE | WINDSOR DRIVE TO ROGERS LAKE ROAD | HIGHWAY | 10 | CABARRUS-ROWAN MPO | C-4916C | EXEMPT | [10 empty] | UNDER CONSTRUCTION
CABARRUS | SR 1132 (MIAMI CHURCH ROAD) | REPLACE BRIDGE 120137 OVER DUTCH BUFFALO CREEK. | HIGHWAY | 10 | CABARRUS-ROWAN MPO | B-5375 | DIVISION 10 | BGOFF |  |  |  |  | 2022 | 1370000 |  |  | 1370000 | RIGHT-OF-WAY IN PROGRESS
CABARRUS | SR 1394 (POPLAR TENT ROAD) | SR 1449 (HARRIS ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS AND WIDEN SR 1394 (POPLAR TENT ROAD) FROM SR 2880 (MOSS DRIVE) TO FULLERTON PLACE DRIVE. | HIGHWAY | 10 | CABARRUS-ROWAN MPO | HL-0001 | DIVISION 10 | BGANY, BGDA, L | 2023 | 5520000 |  |  | 2025 | 7850000 | 2022 | 1710000 | 15080000 | $5M IN STBG-DA FUNDS SWITCHED WITH $5M IN STBG ANYAREA FUNDS AS PART OF FUND SWAP ON 5/31/2022.
CABARRUS | SR 1394 (POPLAR TENT ROAD) | SR 1445 (DERITA ROAD) TO US 29/601 BYPASS. WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CABARRUS-ROWAN MPO | U-3415
CABARRUS | SR 1394 (POPLAR TENT ROAD) | EAST OF I-85 TO GEORGE LILES PARKWAY | HIGHWAY | 10 | CABARRUS-ROWAN MPO | U-3415A | DIVISION 10 | T | 2024 | 12900000 | 2024 | 900000 | 2027 | 27712000 |  |  | 41512000
CABARRUS | SR 1394 (POPLAR TENT ROAD) | GEORGE LILES PARKWAY TO US 29/601 | HIGHWAY | 10 | CABARRUS-ROWAN MPO | U-3415B | NOT FUNDED | T | NOT FUNDED | 9900000 | NOT FUNDED | 13200000 | NOT FUNDED | 32900000 |  |  | 56000000
CABARRUS | SR 1445 (DERITA ROAD) | SR 2894 (CONCORD MILLS BOULEVARD) TO SR 1394 (POPLAR TENT ROAD) IN CONCORD. WIDEN TO 4-LANES DIVIDED. | HIGHWAY | 10 | CABARRUS-ROWAN MPO | U-4910 | [11 empty] | SEGMENTS A AND B LET TOGETHER
CABARRUS | SR 1445 (DERITA ROAD) | SR 2894 (CONCORD MILLS BOULEVARD) TO AVIATION BOULEVARD. WIDEN TO 4-LANES DIVIDED. | HIGHWAY | 10 | CABARRUS-ROWAN MPO | U-4910A | DIVISION 10 | [10 empty] | UNDER CONSTRUCTION
CABARRUS | SR 1445 (DERITA ROAD) | AVIATION BOULEVARD TO SR 1394 (POPLAR TENT ROAD). WIDEN TO 4-LANES DIVIDED. | HIGHWAY | 10 | CABARRUS-ROWAN MPO | U-4910B | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
CABARRUS | SR 1706 (EAST 1ST STREET) | REPLACE BRIDGE 120109 OVER US 29 (NORTH CANNON BOULEVARD). | HIGHWAY | 10 | CABARRUS-ROWAN MPO | B-5372 | DIVISION 10 | HFB | 2024 | 481000 |  |  | 2025 | 4500000 |  |  | 4981000
CABARRUS | SR 2894 (CONCORD MILLS BOULEVARD) | INTERSECTION OF SR 2894 (CONCORD MILLS BOULEVARD) AND ENTRANCE #1 - KINGS GRANT PAVILION. CONSTRUCT 2-LANE GRADE SEPARATED DIRECTIONAL LEFT FLYOVER. | HIGHWAY | 10 | CABARRUS-ROWAN MPO | U-5806 | DIVISION 10 | T |  |  |  |  | 2021 | 10380000 | 2021 | 2010000 | 12390000 | UNDER CONSTRUCTION. $1.5M PROVIDED BY CITY OF CONCORD; BUILD NC BOND FUNDING: $1.557 M FOR PE, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE); $8.068 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE)
CABARRUS | US 29 | REPLACE BRIDGE 120014 AND 120019 OVER ROCKY RIVER AND ACCESS ROAD. | HIGHWAY | 10 | CABARRUS-ROWAN MPO | B-5123 | REGION E | [10 empty] | COMPLETE
CABARRUS | US 29 | REALIGN UNION CEMETERY ROAD TO INTERSECT US 29 AT ROCK HILL CHURCH ROAD AND CONSTRUCT IMPROVEMENTS ALONG US 29 FROM 0.6 MILE WEST OF ROCK HILL CHURCH ROAD TO JUST EAST OF ROCK HILL CHURCH ROAD. | HIGHWAY | 10 | CABARRUS-ROWAN MPO | U-5956 | REGION E | T | 2022 | 3400000 | 2022 | 2100000 | 2025 | 11800000 |  |  | 17300000
CABARRUS | US 29 US 601 | REPLACE BRIDGE 120057 AND BRIDGE 120059 OVER IRISH BUFFALO CREEK. | HIGHWAY | 10 | CABARRUS-ROWAN MPO | B-5808 | REGION E | BFP, NHPB | 2021 | 255000 | 2021 | 425000 | 2023 | 5100000 |  |  | 5780000 | RIGHT-OF-WAY IN PROGRESS
CABARRUS | US 29/US 601 | REPLACE BRIDGE 120066 AND BRIDGE 120069 OVER SOUTHERN RAILROAD. | HIGHWAY | 10 | CABARRUS-ROWAN MPO | B-5136 | REGION E | T |  |  |  |  | 2021 | 2790000 |  |  | 2790000 | COMPLETE; BUILD NC BOND FUNDING: $2.167 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE).
CABARRUS | VARIOUS | CONSTRUCT SIDEWALKS AT SELECTED LOCATIONS IN KANNAPOLIS. | HIGHWAY | 10 | CABARRUS-ROWAN MPO | C-4916 | EXEMPT | [10 empty] | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF KANNAPOLIS
CABARRUS | VARIOUS | EXTEND LEFT TURN LANE AT NC 73 AND SR 1430, CONSTRUCT RIGHT AND LEFT TURN AT ACCESS ROAD ON NC 73. CONSTRUCT ROUNDABOUT AT SR 1620 AND SR 1621 (BARR ROAD). CONSTRUCT 200 FEET SB ON-RAMP RIGHT TURN LANE AT I-85 AND EXTEND STORAGE TO NB OFF RAMP | HIGHWAY | 10 | CABARRUS-ROWAN MPO | U-6098 | DIVISION 10 | T |  |  |  |  | 2019 | 850000 |  |  | 850000 | ECONOMIC DEVELOPMENT PROJECT - UNDER CONSTRUCTION
CABARRUS | VARIOUS | DIVISION 10 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS IN REGIONAL CATEGORY. | HIGHWAY | 10 | CABARRUS-ROWAN MPO | W-5210REG | REGION E
CABARRUS | CABARRUS COUNTY | CAPITAL FOR CABARRUS COUNTY THROUGH THE CITY OF CONCORD | PUBLIC TRANSIT | 10 | CABARRUS-ROWAN MPO | TG-6789 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2256000 | 2256000
CABARRUS | CONCORD | PURCHASE NEW 35 FOOT HYBRID ELECTRIC HEAVY DUTY LOW FLOOR BUS | PUBLIC TRANSIT | 10 | CABARRUS-ROWAN MPO | TL-0021 | DIVISION 10 | BGDACV, L |  |  |  |  | 2023 | 725000 |  |  | 725000
CABARRUS | RIDER TRANSIT / CONCORD | 5310 PROGRAM PROJECTS - CAPITAL | PUBLIC TRANSIT | 10 | CABARRUS-ROWAN MPO | TA-5128A | PUBLIC TRANSIT | 5310, L | [6 empty] | 2020 | 2500000 | 2500000 | FUNDS AUTHORIZED IN PROGRESS
CABARRUS | RIDER TRANSIT / CONCORD | 5310 PROGRAM PROJECTS - OPERATING | PUBLIC TRANSIT | 10 | CABARRUS-ROWAN MPO | TA-5128B | PUBLIC TRANSIT | 5310, L | [6 empty] | 2020 | 1350000 | 1350000 | FUNDS AUTHORIZED IN PROGRESS
CABARRUS | RIDER TRANSIT / CONCORD | ADMINISTRATION OF 5310 PROGRAM | PUBLIC TRANSIT | 10 | CABARRUS-ROWAN MPO | TA-5128C | PUBLIC TRANSIT | 5310 | [6 empty] | 2020 | 200000 | 200000 | FUNDS AUTHORIZED IN PROGRESS
CABARRUS | RIDER TRANSIT / CONCORD | 5339 BUS AND BUS FACILITIES - EXPANSION VEHICLES | PUBLIC TRANSIT | 10 | CABARRUS-ROWAN MPO | TA-5130B | PUBLIC TRANSIT | 5339, L | [6 empty] | 2020 | 2000000 | 2000000 | FUNDS AUTHORIZED IN PROGRESS
CABARRUS | RIDER TRANSIT / CONCORD | OPERATING ASSISTANCE | PUBLIC TRANSIT | 10 | CABARRUS-ROWAN MPO | TO-5138 | PUBLIC TRANSIT | 5307, L, SMAP | [6 empty] | 2020 | 10852000 | 10852000 | FUNDS AUTHORIZED IN PROGRESS
CABARRUS | RIDER TRANSIT / CONCORD | PLANNING ASSISTANCE - CABARRUS-ROWAN | PUBLIC TRANSIT | 10 | CABARRUS-ROWAN MPO | TP-5118 | PUBLIC TRANSIT | 5303, L, S | [6 empty] | 2020 | 304000 | 304000 | FUNDS AUTHORIZED IN PROGRESS
CABARRUS | RIDER TRANSIT / CONCORD | SAFETY & SECURITY - MIN. 1% SET ASIDE | PUBLIC TRANSIT | 10 | CABARRUS-ROWAN MPO | TS-5116 | PUBLIC TRANSIT | 5307 | [6 empty] | 2020 | 100000 | 100000 | FUNDS AUTHORIZED IN PROGRESS
CABARRUS | RIDER TRANSIT/ CONCORD | RIDER TRANSIT STIP AMENDMENT FOR PURCHASE OF REPLACEMENT BUSES. ADD A TOTAL PROJECT COST OF $8,500,000 TO TA-5173 FOR PURCHASE OF REPLACEMENT BUSES WITH EIGHT BUSES BEING PURCHASED IN FY 21 AND TWO BUSES BEING PURCHASED IN FY 22 | PUBLIC TRANSIT | 10 | CABARRUS-ROWAN MPO | TA-5173 | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2021 | 8500000 | 8500000
CABARRUS | KANNAPOLIS | CONSTRUCT TRACK IMPROVEMENTS, SECOND PLATFORM, PEDESTRIAN UNDERPASS, SITEWORK, RETAINING WALL, SIGNALING EQUIPMENT | RAIL | 10 | CABARRUS-ROWAN MPO | P-5725 | REGION E | T |  |  |  |  | 2023 | 10100000 |  |  | 10100000 | RIGHT-OF-WAY IN PROGRESS
CABARRUS | NORFOLK SOUTHERN MAINLINE | GRADE SEPARATION AT ROGERS LAKE ROAD CROSSING (724408Y) IN KANNAPOLIS. | RAIL | 10 | CABARRUS-ROWAN MPO | Y-4810K | STATEWIDE MOBILITY | O, T |  |  |  |  | 2023 | 12449000 |  |  | 12449000 | RIGHT-OF-WAY IN PROGRESS. OTHER FUNDING PROVIDED BY NORFOLK SOUTHERN
CABARRUS, MECKLENBURG | NC 73 (DAVIDSON HIGHWAY) | EAST OF SR 2693 (DAVIDSON-CONCORD ROAD) TO US 29. WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CABARRUS-ROWAN MPO, CHARLOTTE REGIONAL TPO | R-5706 | [11 empty] | COORDINATE WITH R-2632AB.
CABARRUS, MECKLENBURG | POPLAR TENT ROAD | DERITA ROAD TO NC 73. WIDEN TO FOUR-LANES. | HIGHWAY | 10 | CABARRUS-ROWAN MPO, CHARLOTTE REGIONAL TPO | U-6029 | NOT FUNDED | T | NOT FUNDED | 43403000 | NOT FUNDED | 1085000 | NOT FUNDED | 80200000 |  |  | 124688000
CABARRUS, MECKLENBURG | PIEDMONT CORRIDOR | PIEDMONT CORRIDOR, RESTORE DOUBLE TRACK, HAYDOCK TO JUNKER. | RAIL | 10 | CABARRUS-ROWAN MPO, CHARLOTTE REGIONAL TPO | P-5208 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
CABARRUS, ROWAN | VARIOUS | CABARRUS ROWAN MPO TRANSPORTATION ALTERNATIVES (TAP) PROGRAM. | BIKE/PED | 9, 10 | CABARRUS-ROWAN MPO | U-5545 | DIVISION 9, 10 | L, TADA |  |  |  |  | 2022 | 10099000 |  |  | 10099000
CABARRUS, ROWAN | I-85 | NC 73 IN CABARRUS COUNTY (EXIT 55) TO US 29 / US 601 CONNECTOR (EXIT 68) IN ROWAN COUNTY. WIDEN TO EIGHT LANES. | HIGHWAY | 9, 10 | CABARRUS-ROWAN MPO | I-3802 | [11 empty] | SEGMENT B INCLUDES B-5365 AND I-3610
CABARRUS, ROWAN | I-85 | NC 73 IN CABARRUS COUNTY (EXIT 55) TO SR 2180 (LANE STREET) IN CABARRUS COUNTY. | HIGHWAY | 9, 10 | CABARRUS-ROWAN MPO | I-3802A | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
CABARRUS, ROWAN | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CABARRUS-ROWAN MPO. | HIGHWAY | 9, 10 | CABARRUS-ROWAN MPO | C-5603 | EXEMPT | CMAQ, L | 2020 | 309000 |  |  | 2020 | 1848000 | 2020 | 927000 | 3084000 | IN PROGRESS
CABARRUS, ROWAN | VARIOUS | STBG-DA IN THE CABARRUS-ROWAN METROPOLITAN PLANNING ORGANIZATION (MPO) AREA. | HIGHWAY | 9, 10 | CABARRUS-ROWAN MPO | U-5614 | DIVISION 9, 10 | BGDA, L |  |  |  |  | 2020 | 63521000 |  |  | 63521000 | $6M STBG-ANY AREA PROVIDED AS PART OF FUND SWAP
CABARRUS, ROWAN | CONCORD KANNAPOLIS AREA TRANSIT | TO SUPPORT THE PURCHASE OF ROUTINE CAPITAL: BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, VEHICLES ETC USING SECTION 5339 FUNDS AT A FEDERAL SHARE OF $200,000 AND LOCAL SHARE OF $50,000. | PUBLIC TRANSIT | 9, 10 |  | TA-5130A | PUBLIC TRANSIT | 5339, L | [6 empty] | 2020 | 1000000 | 1000000
CABARRUS, ROWAN | CONCORD KANNAPOLIS AREA TRANSIT | EXPANSION BUS | PUBLIC TRANSIT | 9, 10 | CABARRUS-ROWAN MPO | TL-0005 | DIVISION 9, 10 | BGDA, L |  |  |  |  | 2022 | 725000 |  |  | 725000
CABARRUS, ROWAN | RIDER TRANSIT / CONCORD | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC | PUBLIC TRANSIT | 9, 10 | CABARRUS-ROWAN MPO | TG-5103A | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2500000 | 2500000 | FUNDS AUTHORIZED IN PROGRESS
CABARRUS, ROWAN | RIDER TRANSIT / CONCORD | ROUTINE CAPITAL - ADA SERVICES | PUBLIC TRANSIT | 9, 10 | CABARRUS-ROWAN MPO | TG-5103B | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 1563000 | 1563000 | FUNDS AUTHORIZED IN PROGRESS
CABARRUS, ROWAN | RIDER TRANSIT / CONCORD | PREVENTIVE MAINTENANCE | PUBLIC TRANSIT | 9, 10 | CABARRUS-ROWAN MPO | TG-5103C | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 6750000 | 6750000 | FUNDS AUTHORIZED IN PROGRESS
CALDWELL | HUDSON US 321A (MAIN STREET)/ | CONSTRUCT PEDESTRIAN CROSSING IMPROVEMENTS FROM SR 1952 (CEDAR VALLEY ROAD) TO SR 1156 (LEGION ROAD). | BIKE/PED | 11 | GREATER HICKORY MPO | BL-0002 | DIVISION 11 | BGANY, BGDA, L | 2023 | 24000 |  |  | 2023 | 440000 | 2022 | 80000 | 544000 | $352K IN STBG-DA FUNDS SWITCHED WITH $352K IN BG-ANY AS PART OF FUND SWAP 5-19-22.
CALDWELL | LENIOR GREENWAY | HARPER AVENUE TO MORGANTON BOULEVARD. EXTEND MULTI-USE PATH. | BIKE/PED | 11 | GREATER HICKORY MPO | BL-0065 | DIVISION 11 | BGDA, L | 2024 | 281000 |  |  | 2025 | 1581000 | 2023 | 306000 | 2168000
CALDWELL | LENOIR | HOSPITAL AVENUE, HARPER AVENUE TO US 321 (BLOWING ROCK BOULEVARD). CONSTRUCT SIDEWALK. | BIKE/PED | 11 | GREATER HICKORY MPO | EB-5806 | DIVISION 11 | BGANY, BGDACV, L, TADA | 2021 | 120000 |  |  | 2022 | 1000000 |  |  | 1120000 | $414K IN STBG-DA FUNDS SWITCHED WITH $414K IN BG-ANY AS PART OF FUND SWAP 5-19-22.
CALDWELL | SR 1328 (BROWN MOUNTAIN BEACH ROAD) | WIDEN ROADWAY TO 20 FEET IN FIVE LOCATIONS ALONG WILSON CREEK. | HIGHWAY | 11 | GREATER HICKORY MPO | HF-0003 | EXEMPT | FLAP, S(M) |  |  |  |  | 2024 | 1575000 | 2022 | 175000 | 1750000 | FLAP PROJECT ID: NC 39. AWARD AMOUNT = $1,400,000. STATE MATCH ARE HIGHWAY FUNDS.
CALDWELL | SR 1328 (BROWN MOUNTAIN BEACH ROAD) | WIDEN ROADWAY TO 20 FEET IN FIVE LOCATIONS ALONG WILSON CREEK. | HIGHWAY | 11 | GREATER HICKORY MPO | HO-0006 | EXEMPT | FLAP, S(M) |  |  |  |  | 2022 | 1575000 | 2021 | 175000 | 1750000 | FLAP PROJECT ID: NC 39. AWARD AMOUNT = $1,400,000. STATE MATCH ARE HIGHWAY FUNDS.
CALDWELL | GRANITE FALLS | INTERSECTION OF US 321 AND SR 1109 (PINEWOODS ROAD EXTENSION). CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 11 | GREATER HICKORY MPO | R-5775 | EXEMPT | BGANY, BGDA, S(M) |  |  |  |  | 2022 | 1050000 |  |  | 1050000 | RIGHT OF WAY IN PROGRESS. PROJECT IS IN EXEMPT CATEGORY BECAUSE STBG-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT - STATE MATCH IS SPOT SAFETY (SS-4911 AL); $487KM IN BGANY USED AS PART OF FUND SWAP.
CALDWELL | SR 1001 (CONNELLY SPRINGS ROAD) | CATAWBA RIVER TO SR 1933 (SOUTH-WEST BOULEVARD) | HIGHWAY | 11 | GREATER HICKORY MPO | R-3430C | DIVISION 11 | T | 2026 | 27500000 | 2026 | 4000000 | 2029 | 47001000 |  |  | 78501000
CALDWELL | SR 1002 (DUDLEY SHOALS ROAD) | SR 1002 (DUDLEY SHOALS ROAD) AND SR 1751 (GRACE CHAPEL ROAD/CAMPGROUND ROAD)/SR 1752 (PEACH ORCHARD ROAD). CONSTRUCT ROUNDABOUT. | HIGHWAY | 11 | GREATER HICKORY MPO | U-6035 | DIVISION 11 | T | 2019 | 200000 |  |  | 2023 | 925000 |  |  | 1125000 | RIGHT-OF-WAY IN PROGRESS
CALDWELL | SR 1109 (PINEWOOD ROAD) | US 321 TO SR 1931 (BERT HUFFMAN ROAD). UPGRADE ROADWAY. | HIGHWAY | 11 | GREATER HICKORY MPO | U-6036 | DIVISION 11 | T | 2019 | 1500000 | 2019 | 400000 | 2023 | 8800000 |  |  | 10700000 | RIGHT-OF-WAY IN PROGRESS
CALDWELL | SR 1130 (CAJAH MOUNTAIN ROAD) | SR 1001 (CONNELLY SPRINGS ROAD) TO US 321A. MODERNIZE ROADWAY. | HIGHWAY | 11 | GREATER HICKORY MPO | U-6157 | DIVISION 11 | BGANY, T | 2023 | 15900000 | 2023 | 9100000 | 2025 | 24236000 |  |  | 49236000 | BUILD NC BOND FUNDING: $1.5M FOR CONSTRUCTION, PAYBACK FY 2026-2040 (FY 2026 / YR 8 SALE).
CALDWELL | SR 1328 (BROWN MOUNTAIN BEACH ROAD) | MILEPOST 5.3 TO MILEPOST 7.5. INSTALL GUARDRAIL AT VARIOUS LOCATIONS. | HIGHWAY | 11 | GREATER HICKORY MPO | HF-0001 | EXEMPT | FLAP, S(M) |  |  |  |  | 2022 | 235000 | 2022 | 5000 | 240000 | FLAP PROJECT ID: NC 38. AWARD AMOUNT = $240,000. STATE MATCH ARE HIGHWAY FUNDS.
CALDWELL | US 321 | REPLACE BRIDGE 130367 OVER CATAWBA RIVER. | HIGHWAY | 11 | GREATER HICKORY MPO | B-4450 | [11 empty] | TO BE CONSTRUCTED WITH U-4700
CALDWELL | US 321 | INTERIM STRUCTURE IMPROVEMENTS ON US 321 SOUTHBOUND BRIDGE OVER LAKE HICKORY. | HIGHWAY | 11 | GREATER HICKORY MPO | U-4700AA | STATEWIDE MOBILITY | NHP |  |  |  |  | 2022 | 2000000 |  |  | 2000000
CALDWELL | US 321 | US 321A TO SR 1108 (MISSION ROAD) | HIGHWAY | 11 | GREATER HICKORY MPO | U-4700B | NOT FUNDED | NHP | NOT FUNDED | 35000000 | NOT FUNDED | 4000000 | NOT FUNDED | 57500000 |  |  | 96500000
CALDWELL | US 321 | SR 1108 (MISSION ROAD) TO SR 1933 (SOUTHWEST BOULEVARD). | HIGHWAY | 11 | GREATER HICKORY MPO | U-4700C | NOT FUNDED | NHP | NOT FUNDED | 5000000 | NOT FUNDED | 2000000 | NOT FUNDED | 12000000 |  |  | 19000000
CALDWELL | US 321 | SR 1160 (MOUNT HERMAN ROAD). UPGRADE INTERSECTION TO SUPERSTREET DESIGN - WITHIN THE LIMITS OF U-4700 C. | HIGHWAY | 11 | GREATER HICKORY MPO | U-4700CA | REGION F | NHP | 2020 | 420000 |  |  | 2023 | 4100000 |  |  | 4520000 | DESIGN BY DIVISION
CALDWELL | US 321 | SR 1809/1952 (PINE MOUNTAIN ROAD). UPGRADE INTERSECTION TO SUPERSTREET DESIGN - WITHIN THE LIMITS OF U-4700 C. | HIGHWAY | 11 | GREATER HICKORY MPO | U-4700CB | STATEWIDE MOBILITY | NHP | 2020 | 400000 | 2020 | 100000 | 2023 | 9200000 |  |  | 9700000
CALDWELL | US 321 | SR 1108 (MISSION ROAD). UPGRADE INTERSECTION TO SUPERSTREET DESIGN - WITHIN THE LIMITS OF U-4700 C. | HIGHWAY | 11 | GREATER HICKORY MPO | U-4700CC | STATEWIDE MOBILITY | NHP | 2020 | 450000 | 2020 | 100000 | 2023 | 5900000 |  |  | 6450000
CALDWELL | US 321 | SR 1002 (DUDLEY SHOALS ROAD) GRADE SEPARATION. CONSTRUCT RAMP ONTO US 321 SOUTHBOUND. | HIGHWAY | 11 | GREATER HICKORY MPO | U-6161 | DIVISION 11 | NHP | 2026 | 800000 | 2026 | 200000 | 2028 | 4000000 |  |  | 5000000 | COORDINATE WITH U-4700A
CALDWELL | US 321 ALT | SR 1109 (PINEWOOD ROAD) TO SR 1106 (DUKE STREET). UPGRADE ROADWAY. | HIGHWAY | 11 | GREATER HICKORY MPO | U-6034 | DIVISION 11 | T | 2024 | 9000000 | 2024 | 3000000 | 2026 | 14400000 |  |  | 26400000
CALDWELL | US 64/ NC 18 | SR 1142 (CALLICO ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 11 | GREATER HICKORY MPO | U-6033 | DIVISION 11 | T | 2019 | 400000 |  |  | 2023 | 2247000 |  |  | 2647000 | RIGHT-OF-WAY IN PROGRESS.
CALDWELL | US 64/NC 90/NC 18 (WILKESBORO BLVD) | INTERSECTION OF US 64/NC 90/NC 18 (WILKESBORO BOULEVARD) AND US 64/NC 90 (TAYLORSVILLE ROAD). CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 11 | GREATER HICKORY MPO | R-5745 | DIVISION 11 | T |  |  |  |  | 2019 | 1695000 |  |  | 1695000 | COMPLETE; BUILD NC BOND FUNDING: $1.313M FOR CONSTRUCTION, PAYBACK FY 2019-2033 (FY 2019 / YR 1 SALE)
CALDWELL | SR 1159 (PLEASANT HILL ROAD) | CWCY CROSSING 729801L IN HUDSON. CONSTRUCT SAFETY IMPROVEMENTS. | RAIL | 11 | GREATER HICKORY MPO | RX-2011A | DIVISION 11 | RR |  |  |  |  | 2023 | 800000 |  |  | 800000
CALDWELL, BURKE | SR 1001 (MALCOLM BLVD/ CONNELLY SPRINGS ROAD) | US 70 TO SR 1933 (SOUTH-WEST BOULEVARD) IN LENOIR. MODERNIZE ROADWAY TO INCLUDE BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | 11, 13 | GREATER HICKORY MPO | R-3430
CALDWELL, CATAWBA, BURKE | US 321 | NORTH OF US 70 IN HICKORY TO SR 1933 (SOUTHWEST BOULEVARD). WIDEN TO SIX LANES. | HIGHWAY | 11, 12, 13 | GREATER HICKORY MPO | U-4700 | [11 empty] | INCLUDES B-4450.
CALDWELL, CATAWBA, LINCOLN, MECKLENBURG, WATAUGA | COACH AMERICA | INTERCITY BUS - BOONE TO CHARLOTTE | PUBLIC TRANSIT | 10, 11, 12 |  | TI-6101 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 2384000 | 2384000 | FUNDS AUTHORIZED IN PROGRESS
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | DIVISION 11 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | BIKE/PED | 11 | HIGH COUNTRY RPO, NORTHWEST PIEDMONT RPO, GREATER HICKORY MPO | BO-2411 | DIVISION 11 | S, TA |  |  |  |  | 2024 | 4000000 |  |  | 4000000
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 11. | HIGHWAY | 11 | HIGH COUNTRY RPO, NORTHWEST PIEDMONT RPO, GREATER HICKORY MPO | HS-2011 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | INSTALL LONG-LIFE PAVEMENT MARKINGS. | HIGHWAY | 11 | HIGH COUNTRY RPO, NORTHWEST PIEDMONT RPO, GREATER HICKORY MPO | HS-2011A | DIVISION 11 | HSIP |  |  |  |  | 2021 | 6100000 |  |  | 6100000
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | INSTALL LONG-LIFE PAVEMENT MARKINGS. | HIGHWAY | 11 | HIGH COUNTRY RPO, NORTHWEST PIEDMONT RPO, GREATER HICKORY MPO | HS-2011D | DIVISION 11 | HSIP |  |  |  |  | 2021 | 1185000 |  |  | 1185000
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | DIVISION 11 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | HIGHWAY | 11 | HIGH COUNTRY RPO, NORTHWEST PIEDMONT RPO, GREATER HICKORY MPO | R-5791 | DIVISION 11 | S, TA |  |  |  |  | 2020 | 3500000 |  |  | 3500000 | UNDER CONSTRUCTION. "S" FUNDS ARE STATE HIGHWAY FUNDS
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | DIVISION 11 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | 11 | HIGH COUNTRY RPO, NORTHWEST PIEDMONT RPO, GREATER HICKORY MPO | W-5211 | [11 empty] | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 11. | HIGHWAY | 11 | HIGH COUNTRY RPO, NORTHWEST PIEDMONT RPO, GREATER HICKORY MPO | W-5711
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 11 | HIGH COUNTRY RPO, NORTHWEST PIEDMONT RPO, GREATER HICKORY MPO | W-5711DIV | DIVISION 11 | HSIP | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000 | IN PROGRESS
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 11 | HIGH COUNTRY RPO, NORTHWEST PIEDMONT RPO, GREATER HICKORY MPO | W-5711REG | REGION F | HSIP | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000 | IN PROGRESS
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 11 | HIGH COUNTRY RPO, NORTHWEST PIEDMONT RPO, GREATER HICKORY MPO | W-5711SW | STATEWIDE MOBILITY | HSIP | 2020 | 160000 |  |  | 2020 | 960000 |  |  | 1120000 | IN PROGRESS
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 11. | HIGHWAY | 11 | HIGH COUNTRY RPO, NORTHWEST PIEDMONT RPO, GREATER HICKORY MPO | W-5811 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 11. | RAIL | 11 | HIGH COUNTRY RPO, NORTHWEST PIEDMONT RPO, GREATER HICKORY MPO | RC-2011 | DIVISION 11 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
CALDWELL, SURRY, WATAUGA, WILKES, ALLEGHANY, ASHE, AVERY, YADKIN | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 11. | RAIL | 11 | HIGH COUNTRY RPO, NORTHWEST PIEDMONT RPO, GREATER HICKORY MPO | RX-2011 | DIVISION 11 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
CAMDEN | NC 343 | US 158 IN CAMDEN TO SR 1119 (SOUTH TROTMAN ROAD) IN SHILOH. MODERNIZE ROADWAY AND REPLACE BRIDGES 140017 AND 140018 IN CAMDEN COUNTY. | HIGHWAY | 1 | ALBEMARLE RPO | R-5807 | DIVISION 1 | T | 2024 | 508000 | 2024 | 9232000 | 2026 | 19700000 |  |  | 29440000
CAMDEN | SR 1224 (OLD SWAMP ROAD) | 0.15 SOUTH OF SR 1225 (LILLY ROAD) TO 0.25 MILES NORTH OF SR 1225 (LILLY ROAD). | HIGHWAY | 1 | ALBEMARLE RPO | R-5717A | DIVISION 1 | [10 empty] | UNDER CONSTRUCTION.
CAMDEN | US 17 (FUTURE I-87) | PASQUOTANK COUNTY LINE TO VIRGINIA STATE LINE. PAVEMENT REHABILITATION. | HIGHWAY | 1 | ALBEMARLE RPO | I-6026 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2025 | 6100000 |  |  | 6100000
CAMDEN, CHOWAN, CURRITUCK, PASQUOTANK, PERQUIMANS | ALBEMARLE REGIONAL HEALTH SERVICE | ADMINISTRATION | PUBLIC TRANSIT | 1 | ALBEMARLE RPO | TK-6104 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 1656000 | 1656000 | FUNDS AUTHORIZED IN PROGRESS
CAMDEN, CURRITUCK | SR 1227/SR 1208 (SOUTH MILLS ROAD) SR 1224/SR 1223 | NC 343 IN CAMDEN COUNTY TO NC 168 IN CURRITUCK COUNTY. WIDEN AND INTERSECTION IMPROVEMENTS. | HIGHWAY | 1 | ALBEMARLE RPO | R-5717 | DIVISION 1 | T |  |  |  |  | 2024 | 17900000 |  |  | 17900000 | RIGHT-OF-WAY IN PROGRESS.
CARTERET | MICHAEL J. SMITH FIELD (MRH) | FULL PARALLEL TAXIWAY 8-26. | AVIATION | 2 | DOWN EAST RPO | AV-5746 | DIVISION 2 | [10 empty] | COMPLETE
CARTERET | NC 24 | NC 24 BETWEEN SR 1259 (TAYLOR NOTION ROAD) AND US 70. INSTALL PAVEMENT MARKINGS AND RUMBLE STRIPES ON TWO-WAY LEFT TURN LANE. | HIGHWAY | 2 | DOWN EAST RPO | HS-2002B | REGION B | HSIP |  |  |  |  | 2021 | 640000 |  |  | 640000 | UNDER CONSTRUCTION.
CARTERET | NC 24 | NC 58. INTERSECTION IMPROVEMENTS. | HIGHWAY | 2 | DOWN EAST RPO | R-5858 | STATEWIDE MOBILITY | T |  |  |  |  | 2025 | 6000000 |  |  | 6000000 | RIGHT OF WAY IN PROGRESS
CARTERET | NC 58 | REHABILITATE BRIDGE 150006 OVER BOGUE SOUND. | HIGHWAY | 2 | DOWN EAST RPO | B-5939 | REGION B | [10 empty] | UNDER CONSTRUCTION
CARTERET | NC 58 | NC 58 JUST WEST OF CEDAR LANE. INSTALL CROSSWALKS, CONCRETE MONOLITHIC PEDESTRIAN REFUGE ISLAND, SIDEWALKS, AND RECTANGULAR RAPID-FLASHING BEACONS. | HIGHWAY | 2 | DOWN EAST RPO | HS-2002I | DIVISION 2 | HSIP | 2024 | 5000 |  |  | 2025 | 77000 |  |  | 82000
CARTERET | NC 58 | NC 58 (E. FORT MACON ROAD) AT BROOKS STREET. INSTALL RECTANGULAR RAPID FLASH BEACON AT CROSSWALK. | HIGHWAY | 2 | DOWN EAST RPO | W-5802B | REGION B | HSIP |  |  |  |  | 2021 | 30000 |  |  | 30000 | UNDER CONSTRUCTION
CARTERET | NC 58 | NC 58 (E. FORT MACON ROAD) AT E. BOGUE SOUND DRIVE. INSTALL RECTANGULAR RAPID FLASH BEACON AT CROSSWALK. | HIGHWAY | 2 | DOWN EAST RPO | W-5802C | REGION B | HSIP |  |  |  |  | 2021 | 30000 |  |  | 30000 | UNDER CONSTRUCTION
CARTERET | NC 58 (EMERALD DRIVE) | LOON STREET. INSTALL ROUNDABOUT. | HIGHWAY | 2 | DOWN EAST RPO | R-5884 | NOT FUNDED | T | NOT FUNDED | 300000 | NOT FUNDED | 300000 | NOT FUNDED | 1400000 |  |  | 2000000
CARTERET | NC 58 (EMERALD DRIVE) | SR 1000 (COAST GUARD ROAD). INSTALL ROUNDABOUT. | HIGHWAY | 2 | DOWN EAST RPO | R-5886 | NOT FUNDED | T | NOT FUNDED | 300000 | NOT FUNDED | 1600000 | NOT FUNDED | 1700000 |  |  | 3600000
CARTERET | NC 58 (EMERALD DRIVE) | MANGROVE DRIVE. UPGRADE INTERSECTION. | HIGHWAY | 2 | DOWN EAST RPO | R-5944 | DIVISION 2 | T | 2027 | 337000 | 2027 | 100000 | 2029 | 2650000 |  |  | 3087000
CARTERET | NC 58 (SALTER PATH ROAD) | NC 58 (SALTER PATH ROAD) AT THE OCEAN CLUB ENTRANCE JUST WEST OF TRADEWINDS DRIVE. INSTALL CROSSWALK WITH RAPID FLASHING BEACONS. | HIGHWAY | 2 | DOWN EAST RPO | HS-2002G | DIVISION 2 | HSIP |  |  |  |  | 2022 | 25000 |  |  | 25000 | UNDER CONSTRUCTION.
CARTERET | NC 58 (WEST FORT MACON ROAD) | NC 58 (WEST FORT MACON ROAD) AT ATLANTIC STATION SHOPPING CENTER / ATLANTIC BEACH TOWN PARK. INSTALL PEDESTRIAN HEADS FOR EXISTING SIGNAL AND WHEEL CHAIR RAMP REVISIONS. | HIGHWAY | 2 | DOWN EAST RPO | HS-2002H | REGION B | HSIP |  |  |  |  | 2022 | 9000 |  |  | 9000
CARTERET | NC 58 (WEST FORT MACON) | ATLANTIC BEACH CAUSEWAY. ADD RIGHT TURN LANE. | HIGHWAY | 2 | DOWN EAST RPO | R-5816 | REGION B | T | 2020 | 600000 |  |  | 2023 | 1500000 |  |  | 2100000 | RIGHT-OF-WAY IN PROGRESS.
CARTERET | SR 1175 (BRIDGES STREET) | SR 1243 (BARBOUR ROAD). REALIGN INTERSECTIONS. | HIGHWAY | 2 | DOWN EAST RPO | R-5941 | DIVISION 2 | T | 2027 | 7400000 | 2027 | 1100000 | 2029 | 2000000 |  |  | 10500000
CARTERET | SR 1176 (BRIDGES STREET EXTENSION) | SR 1738 (BRIDGES STREET) TO SR 1147 (MCCABE ROAD). WIDEN EXISTING ROADWAY AND CONSTRUCT PART ON NEW LOCATION. | HIGHWAY | 2 | DOWN EAST RPO | R-5727 | DIVISION 2 | T | 2027 | 12700000 | 2027 | 1300000 | 2029 | 62699000 |  |  | 76699000
CARTERET | SR 1182 (ATLANTIC BEACH CAUSEWAY) | REHABILITATE BRIDGE 150068 OVER BOGUE SOUND. | HIGHWAY | 2 | DOWN EAST RPO | B-5938 | DIVISION 2 | T |  |  |  |  | 2019 | 6195000 |  |  | 6195000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $4,817,543 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE)
CARTERET | SR 1335 (ISLAND ROAD) | REPLACE LIFT SPAN ON BRIDGE 150073 AND BRIDGE 150096 OVER THE STRAITS AT HARKERS ISLAND. | HIGHWAY | 2 | DOWN EAST RPO | B-4863 | DIVISION 2 | DP, T |  |  |  |  | 2022 | 73735000 |  |  | 73735000 | UNDER CONSTRUCTION; BUILD NC BOND FUNDING: $16,500,000 FOR CON PAYBACK 2022 – 2036 (FY 2022 / YR 4 SALE). DP FUNDS REPRESENT FEDERAL AID DEMONSTRATION FUNDS.
CARTERET | SR 1493 | SR 1493 (LIVE OAK STREET) AT CAMPEN ROAD. REVISE TRAFFIC SIGNAL, INSTALL PEDESTRIAN CROSSING WITH SIGNAL HEADS, AND UPGRADE SIDEWALK. | HIGHWAY | 2 | DOWN EAST RPO | W-5802A | DIVISION 2 | HSIP |  |  |  |  | 2021 | 38000 |  |  | 38000 | UNDER CONSTRUCTION
CARTERET | US 70 | REPLACE BRIDGE 150033 OVER NORTH RIVER AND REPAIRS TO EXISTING STRUCTURE TO SERVE AS DETOUR. | HIGHWAY | 2 | DOWN EAST RPO | B-4722 | REGION B
CARTERET | US 70 | REQUIRED REPAIRS NECESSARY FOR EXISTING STRUCTURE TO SERVE AS THE DETOUR ROUTE FOR B-4722B. | HIGHWAY | 2 | DOWN EAST RPO | B-4722A | [11 empty] | COMPLETE
CARTERET | US 70 | REPLACEMENT OF BRIDGE NO. 33 OVER NORTH RIVER. | HIGHWAY | 2 | DOWN EAST RPO | B-4722B | REGION B | [10 empty] | COMPLETE
CARTERET | US 70 (ARENDELL STREET) | 4TH STREET TO SR 1175 (RADIO ISLAND ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 2 | DOWN EAST RPO | U-5876 | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 85200000 |  |  | 103000000
CARTERET | US 70 (CEDAR STREET) | US 70 (LIVE OAK STREET). CONSTRUCT ROUNDABOUT. | HIGHWAY | 2 | DOWN EAST RPO | R-5962 | NOT FUNDED | T | NOT FUNDED | 3300000 | NOT FUNDED | 370000 | NOT FUNDED | 1700000 |  |  | 5370000
CARTERET | US 70 (LIVE OAK STREET) | NC 101 TO SR 1429 (OLGA ROAD). ACCESS MANAGEMENT. | HIGHWAY | 2 | DOWN EAST RPO | R-5945 | DIVISION 2 | NHP | 2027 | 31800000 | 2027 | 600000 | 2029 | 23600000 |  |  | 56000000
CARTERET | US 70 (LIVE OAK STREET) | SR 1310 (LENNOXVILLE ROAD). UPGRADE INTERSECTION. | HIGHWAY | 2 | DOWN EAST RPO | R-5946 | DIVISION 2 | NHP | 2027 | 4900000 | 2027 | 700000 | 2029 | 2200000 |  |  | 7800000
CARTERET | US 70 (LIVE OAK STREET) | NC 101. CONSTRUCT ONE LANE ROUNDABOUT. | HIGHWAY | 2 | DOWN EAST RPO | U-6058 | REGION B | L, T | 2023 | 859000 | 2023 | 193000 | 2025 | 3550000 |  |  | 4602000 | LOCAL FUNDS CONTRIBUTION BY TOWN OF BEAUFORT.
CARTERET | US 70/NC 12 | SR 1429 (OLGA ROAD) TO SR 1350 (WHITEHURST ROAD). UPGRADE ROADWAY. | HIGHWAY | 2 | DOWN EAST RPO | R-4746 | NOT FUNDED | T | NOT FUNDED | 30900000 | NOT FUNDED | 9100000 | NOT FUNDED | 71199000 |  |  | 111199000
CARTERET | CARTERET COUNTY | PURCHASE EXPANSION VEHICLE. | PUBLIC TRANSIT | 2 | DOWN EAST RPO | TA-6717 | DIVISION 2 | 5311, L, T |  |  |  |  | 2020 | 70000 |  |  | 70000
CARTERET | CARTERET COUNTY | PURCHASE EXPANSION VEHICLE. | PUBLIC TRANSIT | 2 | DOWN EAST RPO | TA-6718 | DIVISION 2 | 5311, L, T |  |  |  |  | 2020 | 70000 |  |  | 70000
CARTERET | CARTERET COUNTY | ADMINISTRATION | PUBLIC TRANSIT | 2 | DOWN EAST RPO | TK-6115 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 300000 | 300000 | FUNDS AUTHORIZED IN PROGRESS
CARTERET | NS/NCRR EC LINE | CONSTRUCT GRADE SEPARATION AT US 70 EASTBOUND AND WESTBOUND. CLOSE EXISTING AT-GRADE CROSSING NEAR NEWPORT. | RAIL | 2 | DOWN EAST RPO | P-5742 | NOT FUNDED | O, T | NOT FUNDED | 2000000 |  |  | NOT FUNDED | 13000000 |  |  | 15000000 | OTHER FUNDS PROVIDED BY NS.
CARTERET, HYDE | NC 12 | CEDAR ISLAND - OCRACOKE FERRY. REPLACE M/V SILVER LAKE SOUND CLASS FERRY | FERRY | 1, 2 | ALBEMARLE RPO, DOWN EAST RPO | F-5704 | DIVISION 1, 2 | T |  |  |  |  | 2025 | 25600000 |  |  | 25600000
CASWELL | NC 86 | US 158 TO VIRGINIA STATE LINE. CONSTRUCT PASSING LANES AND SHOULDER IMPROVEMENTS AT VARIOUS LOCATIONS, AND CONSTRUCT TURN LANES FROM SR 1300 (PARK SPRINGS ROAD) TO SOLID WASTE CONVENIENCE CENTER. | HIGHWAY | 7 | PIEDMONT TRIAD RPO | R-5822 | REGION D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 183000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 14200000 |  |  | 14683000 | SCOPE INCLUDES SPOT ID H170625
CASWELL | SR 1710 (GRIERS CHURCH ROAD) | REPLACE BRIDGE 160007 OVER HYCO CREEK. | HIGHWAY | 7 | PIEDMONT TRIAD RPO | B-5725 | DIVISION 7 | BGOFF | 2024 | 290000 |  |  | 2026 | 2900000 |  |  | 3190000
CASWELL | US 158 / NC 86 | SR 1572 (COUNTY HOME ROAD) TO SR 1734 (RP FUQUAY ROAD). CONSTRUCT PASSING LANES. | HIGHWAY | 7 | PIEDMONT TRIAD RPO | R-5926 | DIVISION 7 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 269000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 83000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3649000 |  |  | 4001000
CASWELL | CASWELL COUNTY | ADMINISTRATION | PUBLIC TRANSIT | 7 | PIEDMONT TRIAD RPO | TK-6116 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 448000 | 448000 | FUNDS AUTHORIZED IN PROGRESS
CATAWBA | HICKORY REGIONAL AIRPORT (HKY) | 600 FEET EXTENSION OF RUNWAY 6 - PHASE I AND II. | AVIATION | 12 | GREATER HICKORY MPO | AV-5741 | DIVISION 12 | O, T |  |  |  |  | 2024 | 3844000 |  |  | 3844000
CATAWBA | HICKORY REGIONAL AIRPORT (HKY) | LAND ACQUISITION AND OBSTRUCTION REMOVAL. | AVIATION | 12 | GREATER HICKORY MPO | AV-5752 | DIVISION 12 | T | 2026 | 600000 | [6 empty] | 600000
CATAWBA | 9TH STREET NW CONNECTOR | CITY WALK TO OLD LENOIR ROAD IN HICKORY. CONSTRUCT MULTI-USE TRAIL ALONG 9TH STREET NW. | BIKE/PED | 12 | GREATER HICKORY MPO | EB-5977 | DIVISION 12 | BGDA, BGDACV, L | 2021 | 108000 |  |  | 2023 | 1460000 |  |  | 1568000
CATAWBA | AVIATION WALK CONNECTOR | CLEMENT BOULEVARD TO 17TH STREET NW. EXTEND MULTI-USE PATH. | BIKE/PED | 12 | GREATER HICKORY MPO | BL-0067 | DIVISION 12 | BGDA, L | 2024 | 313000 |  |  | 2025 | 1500000 | 2023 | 187000 | 2000000
CATAWBA | CLAREMONT | CENTENNIAL BOULEVARD, NORTH OXFORD STREET TO NORTH LOOKOUT STREET. CONSTRUCT SIDEWALK. | BIKE/PED | 12 | GREATER HICKORY MPO | EB-5828 | DIVISION 12 | BGANY, BGDA, L | 2022 | 31000 |  |  | 2023 | 541000 |  |  | 572000 | $433K IN STBG-DA FUNDS SWITCHED WITH $433K IN BG-ANY AS PART OF FUND SWAP 5-19-22.
CATAWBA | CLAREMONT | CONSTRUCT SIDEWALK ALONG CENTENNIAL BOULEVARD FROM NORTH LOOKOUT STREET TO MAIN STREET - (PHASE II). | BIKE/PED | 12 | GREATER HICKORY MPO | EB-5935 | DIVISION 12 | BGANY, L |  |  |  |  | 2022 | 600000 |  |  | 600000 | $480K IN STBG-DA FUNDS SWITCHED WITH $480K IN BG-ANY AS PART OF FUND SWAP 5-19-22.
CATAWBA | HICKORY | BOOK WALK. CONSTRUCT MULTI-USE PATH FROM CITY WALK TO RIDGEVIEW LIBRARY. | BIKE/PED | 12 | GREATER HICKORY MPO | EB-5937 | DIVISION 12 | BGANY, BGDA, L, TADA | 2021 | 225000 |  |  | 2022 | 1931000 |  |  | 2156000
CATAWBA | HICKORY | BOOK WALK SOUTH. CONSTRUCT MULTI-USE PATH FROM RIDGEVIEW LIBRARY TO WALMART. | BIKE/PED | 12 | GREATER HICKORY MPO | EB-5938 | DIVISION 12 | BGANY, L, TADA | 2021 | 105000 |  |  | 2022 | 3145000 |  |  | 3250000
CATAWBA | HICKORY - 9TH STREET NW & 11TH STREET NW MULTI-USE | CONSTRUCT MULTI-USE TRAIL FROM OLD LENOIR ROAD MULTI-USE TO HICKORY REGIONAL AIRPORT ALONG CLEMENT BOULEVARD, 13TH AVENUE DRIVE NW, AND 19TH STREET LANE NW (INCLUDES CONSTRUCTION OF BIKE/PED BRIDGE OVER US 321), AND CONSTRUCT MULTI-USE TRAIL FROM 9TH STRE | BIKE/PED | 12 | GREATER HICKORY MPO | EB-6038 | EXEMPT | DP, L | 2020 | 662000 |  |  | 2021 | 19216000 | 2020 | 2052000 | 21930000 | DP REPRESENTS FEDERAL INFRA GRANT FUNDS; ADMINISTERED BY CITY OF HICKORY; DESIGN-BUILD PROJECT.
CATAWBA | ISLAND FORD ROAD | DON'S GRILL TO LIVING WORD CHURCH. CONSTRUCT SIDEWALKS. | BIKE/PED | 12 | GREATER HICKORY MPO | BL-0068 | DIVISION 12 | BGDA, L | 2025 | 500000 |  |  | 2027 | 850000 | 2023 | 405000 | 1755000
CATAWBA | MAIN AVENUE NW/NE | 7TH AVENUE NE TO 9TH STREET NW. CONSTRUCT GREENWAY WITH PARK NODES AND PEDESTRIAN BRIDGE OVER NC 127. | BIKE/PED | 12 | GREATER HICKORY MPO | EB-5750 | DIVISION 12 | BGANY, L, TAANY |  |  |  |  | 2020 | 14100000 |  |  | 14100000
CATAWBA | OLD LENOIR ROAD MULTI-USE PATH | 9TH STREET NW TO HICKORY WATER PLANT. CONSTRUCT MULTI-USE PATH. | BIKE/PED | 12 | GREATER HICKORY MPO | EB-5911 | DIVISION 12 | L, TAANY | 2021 | 1205000 |  |  | 2023 | 8123000 |  |  | 9328000 | $3.6M IN STBG-DA FUNDS PREVIOUSLY ALLOCATED TO THIS PROJECT, TO BE REASSIGNED TO U-2307B AS PART OF FUNDING SWAP.
CATAWBA | SPRINGS ROAD NE | SANDY RIDGE ROAD TO MCDONALD PARKWAY. CONSTRUCT SIDEWALK. | BIKE/PED | 12 | GREATER HICKORY MPO | BL-0066 | DIVISION 12 | BGDA, L, TADA | 2024 | 313000 |  |  | 2025 | 2250000 | 2023 | 437000 | 3000000
CATAWBA | 17TH STREET NW | CONSTRUCT ROADWAY EXTENSION FROM 9TH AVENUE NW TO SR 1371 (CLEMENT BOULEVARD NW). | HIGHWAY | 12 | GREATER HICKORY MPO | HL-0004 | DIVISION 12 | BGANY, BGDA, L | 2023 | 720000 |  |  | 2024 | 4800000 | 2021 | 480000 | 6000000 | $3.84M IN STBG-DA FUNDS SWITCHED WITH $3.84M IN BG-ANY AS PART OF FUND SWAP 5-19-22.
CATAWBA | 2ND AVENUE SE | CONSTRUCT ROADWAY EXTENSION FROM LENOIR-RHYNE BOULEVARD TO 3RD AVENUE SE. INCLUDE INTERSECTION AND PEDESTRIAN IMPROVEMENTS. | HIGHWAY | 12 | GREATER HICKORY MPO | HL-0017 | DIVISION 12 | BGANY, BGDA, L | 2022 | 500000 |  |  | 2023 | 1700000 | 2021 | 300000 | 2500000 | $1.491 M STBG-ANY AREA PROVIDED AS PART OF FUND SWAP, ROW: $269K IN STBG-DA FUNDS SWITCHED WITH $269K IN BG-ANY AS PART OF FUND SWAP 5-19-22.
CATAWBA | CLAREMONT | CONSTRUCT SIDEWALKS AT VARIOUS LOCATIONS IN CLAREMONT. | HIGHWAY | 12 | GREATER HICKORY MPO | C-5195 | EXEMPT | [10 empty] | UNDER CONSTRUCTION
CATAWBA | CLAREMOUNT | PRESERVATION OF BUNKER HILL COVERED BRIDGE. | HIGHWAY | 12 | GREATER HICKORY MPO | B-5542 | DIVISION 12 | O |  |  |  |  | 2022 | 296000 |  |  | 296000 | OTHER FUNDS NATIONAL HISTORIC BRIDGE PROGRAM FUNDS.
CATAWBA | CONOVER | CONSTRUCT 1ST STREET/US 70 BIKE AND PEDESTRIAN IMPROVEMENTS. | HIGHWAY | 12 | GREATER HICKORY MPO | C-5624 | DIVISION 12 | BGANY, L |  |  |  |  | 2024 | 2654000 |  |  | 2654000 | $2.123M IN BGANY USED AS PART OF FUND SWAP.
CATAWBA | HICKORY | 16TH STREET (SANDY RIDGE ROAD) AT 21ST AVENUE NE IN HICKORY. CONSTRUCT ROUNDABOUT. | HIGHWAY | 12 | GREATER HICKORY MPO | C-5196 | DIVISION 12 | BGANY, CMAQ, L | 2023 | 2856000 |  |  | 2025 | 4988000 | 2022 | 500000 | 8344000 | $2.39M IN BGANY USED AS PART OF FUND SWAP.
CATAWBA | HICKORY | EAST SIDE THOROUGHFARE (MCDONALD PARKWAY), US 70-321 TO NC 127. MULTI-LANES, PART ON NEW LOCATION. | HIGHWAY | 12 | GREATER HICKORY MPO | U-2307 | [11 empty] | STBG-DA FUNDS (W/ STATE MATCH) AS A RESULT OF FUNDING SWAP WITH EB-5911.
CATAWBA | HICKORY | US 70-321 TO NORTH OF I-40. | HIGHWAY | 12 | GREATER HICKORY MPO | U-2307AA | [11 empty] | COMPLETE
CATAWBA | HICKORY | NORTH OF I-40 TO SR 1453 (SPRINGS ROAD) | HIGHWAY | 12 | GREATER HICKORY MPO | U-2307AB | [11 empty] | COMPLETE
CATAWBA | HICKORY | NORTH OF I-40 TO NORTH OF SR 1692 (TATE BOULEVARD) | HIGHWAY | 12 | GREATER HICKORY MPO | U-2307AD | [11 empty] | COMPLETE
CATAWBA | HICKORY | NORTH OF SR 1692 (TATE BOULEVARD) TO SR 1453 (SPRINGS ROAD) | HIGHWAY | 12 | GREATER HICKORY MPO | U-2307AE | [11 empty] | COMPLETE
CATAWBA | HICKORY | SR 1453 (SPRINGS ROAD) TO NC 127 | HIGHWAY | 12 | GREATER HICKORY MPO | U-2307B | DIVISION 12 | BGANY, BGDA, S(M), T | 2025 | 22600000 | 2025 | 9800000 | 2028 | 42000000 |  |  | 74400000
CATAWBA | HICKORY | HICKORY EAST SIDE THOROUGHFARE TO 15TH AVE SE | HIGHWAY | 12 | GREATER HICKORY MPO | U-2307C | [11 empty] | COMPLETE
CATAWBA | I-40 | REPLACE BRIDGE 170177 AND 170178 OVER LYLE CREEK. | HIGHWAY | 12 | GREATER HICKORY MPO | B-6041 | STATEWIDE MOBILITY | BFP | 2025 | 860000 |  |  | 2026 | 8599000 |  |  | 9459000
CATAWBA | I-40 | SR 1007 (LENOIR RHYNE BOULEVARD) INTERCHANGE. CONSTRUCT INTERCHANGE IMPROVEMENTS. | HIGHWAY | 12 | GREATER HICKORY MPO | I-5716 | STATEWIDE MOBILITY | NHP |  |  |  |  | 2025 | 8500000 |  |  | 8500000 | RIGHT-OF-WAY IN PROGRESS
CATAWBA | I-40 | US 321 TO NC 16. WIDEN TO SIX LANES. | HIGHWAY | 12 | GREATER HICKORY MPO | I-5991
CATAWBA | I-40 | US 321 TO SR 1476 (FAIRGROVE CHURCH ROAD). WIDEN TO SIX LANES. | HIGHWAY | 12 | GREATER HICKORY MPO | I-5991A | STATEWIDE MOBILITY | NHP |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 69300000 |  |  | 69900000
CATAWBA | I-40 | SR 1476 (FAIRGROVE CHURCH ROAD) TO NC 16. WIDEN TO SIX LANES. | HIGHWAY | 12 | GREATER HICKORY MPO | I-5991B | NOT FUNDED | NHP | NOT FUNDED | 4600000 | NOT FUNDED | 1200000 | NOT FUNDED | 85000000 |  |  | 90800000
CATAWBA | NC 127 | WIDEN NC 127 TO MULTI-LANES, SR 1132 TO SR 1008. UPGRADE AND EXTEND SR 1213 (CURRENTLY NC 127), PROPOSED US 321-NC 127 INTERCHANGE TO NORTH OF SR 1182. | HIGHWAY | 12 | GREATER HICKORY MPO | U-2530
CATAWBA | NC 127 | SR 1132 (HUFFMAN FARM ROAD) TO SR 1008 (ZION CHURCH ROAD). | HIGHWAY | 12 | GREATER HICKORY MPO | U-2530A | DIVISION 12 | T | 2025 | 23900000 | 2025 | 3800000 | 2027 | 25501000 |  |  | 53201000
CATAWBA | NC 127 | NORTH OF US 321-NC 127 INTERCHANGE TO NORTH OF SR 1182 | HIGHWAY | 12 | GREATER HICKORY MPO | U-2530B | [11 empty] | COMPLETE
CATAWBA | NC 127 | 1ST AVENUE SE TO 2ND AVENUE SE. ADD TURN LANES. | HIGHWAY | 12 | GREATER HICKORY MPO | U-5777 | REGION F | T | 2019 | 2150000 |  |  | 2025 | 3951000 |  |  | 6101000 | RIGHT-OF-WAY IN PROGRESS
CATAWBA | NC 127 (2ND STREET NORTHEAST, NORTH CENTER STREET) | 8TH AVENUE NORTHEAST TO SR 1327 (30TH AVENUE NORTHWEST). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 12 | GREATER HICKORY MPO | U-6135 | NOT FUNDED | T | NOT FUNDED | 19700000 | NOT FUNDED | 6100000 | NOT FUNDED | 23299000 |  |  | 49099000
CATAWBA | NC 16 | SR 1895 TO SR 1800 SOUTHEAST OF NEWTON. WIDEN TO FOUR LANES. | HIGHWAY | 12 | GREATER HICKORY MPO | R-3100
CATAWBA | NC 16 | SR 1895 (TOWER ROAD) TO SR 1814 (CALDWELL ROAD) | HIGHWAY | 12 | GREATER HICKORY MPO | R-3100A | DIVISION 12 | T |  |  |  |  | 2021 | 42510000 |  |  | 42510000 | UNDER CONSTRUCTION; BUILD NC BOND FUNDING: $33.028 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE).
CATAWBA | NC 16 | SR 1814 (CALDWELL ROAD) TO SR 1801 (CLAREMONT ROAD) | HIGHWAY | 12 | GREATER HICKORY MPO | R-3100B | DIVISION 12 | [10 empty] | UNDER CONSTRUCTION WITH SEGMENT A
CATAWBA | NC 16 | SR 1801 (CLAREMONT ROAD) TO SR 1800 (CALEB SETZER ROAD) | HIGHWAY | 12 | GREATER HICKORY MPO | R-3100C | [11 empty] | COMPLETE
CATAWBA | SR 1005 (STARTOWN ROAD) | US 70 TO NC 10. WIDEN TO MULTI-LANES. | HIGHWAY | 12 | GREATER HICKORY MPO | R-5113 | DIVISION 12 | T | 2028 | 38600000 | 2028 | 9700000 | 2031 | 42600000 |  |  | 90900000
CATAWBA | SR 1124 (33RD STREET SW) | SR 1124 (33RD STREET SW) AND (34TH STREET NW). REALIGN INTERSECTION. | HIGHWAY | 12 | GREATER HICKORY MPO | U-6042 | DIVISION 12 | T | 2027 | 1400000 | 2027 | 200000 | 2029 | 3300000 |  |  | 4900000
CATAWBA | SR 1453 (16TH STREET NE, 12TH AVE NE, SPRINGS ROAD | 9TH AVENUE NE TO SR 1504 (CHARLOTTE STREET). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 12 | GREATER HICKORY MPO | U-6176 | DIVISION 12 | BGANY, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 26200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 20500000 |  |  | 49600000
CATAWBA | SR 1709 (ROCK BARN ROAD) | REPLACE BRIDGE 170173 OVER I-40. | HIGHWAY | 12 | GREATER HICKORY MPO | B-5847 | DIVISION 12 | BFP | 2023 | 200000 |  |  | 2024 | 4500000 |  |  | 4700000
CATAWBA | SR 1844 (SLANTING BRIDGE ROAD) | UPGRADE GUARDRAIL AND END UNITS AT BRIDGE 23 | HIGHWAY | 12 | GREATER HICKORY MPO | HS-2012B | DIVISION 12 | HSIP |  |  |  |  | 2021 | 372000 |  |  | 372000 | COMPLETE
CATAWBA | SR 1849 (MOUNT PLEASANT ROAD) | INSTALL GUARDRAIL ON BRIDGE 163 ON SR 1849 OVER MOUNTAIN CREEK PORTION OF LAKE NORMAN | HIGHWAY | 12 | GREATER HICKORY MPO | HS-2012A | DIVISION 12 | HSIP |  |  |  |  | 2021 | 85000 |  |  | 85000 | COMPLETE
CATAWBA | TRIVIUM PARKWAY, NEW ROUTE | EXTEND TRIVIUM PARKWAY AND CONSTRUCT NEW ROADWAY IN TRIVIUM CORPORATE CENTER. | HIGHWAY | 12 | GREATER HICKORY MPO | U-6238 | DIVISION 12 | T |  |  |  |  | 2022 | 1316000 |  |  | 1316000 | ECONOMIC DEVELOPMENT PROJECT
CATAWBA | US 70 | SR 1358 (4TH STREET DRIVE SW) INTERSECTION IN HICKORY. CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 12 | GREATER HICKORY MPO | HL-0002 | EXEMPT | BGANY, BGDA, L | 2022 | 100000 |  |  | 2022 | 400000 |  |  | 500000 | $320K IN STBG-DA FUNDS SWITCHED WITH $320K IN BG-ANY AS PART OF FUND SWAP 5-19-22.
CATAWBA | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HICKORY MPO AND UNIFOUR RPO. | HIGHWAY | 12 | GREATER HICKORY MPO | C-5608 | EXEMPT | CMAQ, L | 2020 | 51000 |  |  | 2020 | 303000 | 2020 | 153000 | 507000 | IN PROGRESS
CATAWBA | REGIONAL TRANSIT AUTHORITY WESTERN PIEDMONT | REPLACEMENT BUSES | PUBLIC TRANSIT | 12 | GREATER HICKORY MPO | TA-6708 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2021 | 2477000 | 2477000 | FUNDING ADDED TO FY 21 AT THE REQUEST OF THE MPO (FUNDING UNCHANGED IN FY 20 ALREADY FLEXED FROM CMAQ TO FUZ)
CATAWBA | REGIONAL TRANSIT AUTHORITY WESTERN PIEDMONT | REPLACEMENT BUSES LIGHT TRANSIT VEHICLE | PUBLIC TRANSIT | 12 | GREATER HICKORY MPO | TA-6709 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2535000 | 2535000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23
CATAWBA | REGIONAL TRANSPORTATION WESTERN PIEDMONT | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | PUBLIC TRANSIT | 12 | GREATER HICKORY MPO | TA-6707 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2520000 | 2520000
CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | MOBILITY MANAGER | PUBLIC TRANSIT | 12 | GREATER HICKORY MPO | TG-6798 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 970000 | 970000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23
CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | PREVENTIVE MAINTANENCE | PUBLIC TRANSIT | 12 | GREATER HICKORY MPO | TG-6799 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 3894000 | 3894000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23
CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, COMPUTER HARDWARE AND SOFTWARE, AVL SOFTWARE, ETC. | PUBLIC TRANSIT | 12 | GREATER HICKORY MPO | TG-6800 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 1559000 | 1559000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23
CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | OPERATING ASSISTANCE - ADA PARATRANSIT | PUBLIC TRANSIT | 12 | GREATER HICKORY MPO | TG-6801 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2117000 | 2117000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23
CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | PROGRAM ADMINISTRATION | PUBLIC TRANSIT | 12 | GREATER HICKORY MPO | TL-1000 | PUBLIC TRANSIT | 5310 | [6 empty] | 2020 | 232000 | 232000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23
CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | OPERATING ASSISTANCE | PUBLIC TRANSIT | 12 | GREATER HICKORY MPO | TO-6162 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 19730000 | 19730000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23
CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | CAPITAL PURCHASE OF SERVICE | PUBLIC TRANSIT | 12 | GREATER HICKORY MPO | TQ-9039 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2020 | 1281000 | 1281000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23
CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | MOBILITY MANAGER | PUBLIC TRANSIT | 12 | GREATER HICKORY MPO | TQ-9040 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2020 | 312000 | 312000 | MODIFYING FUNDING IN FY 20, FY 21, FY 22, FY 23
CATAWBA | WESTERN PIEDMONT REGIONAL TRANSIT AUTHORITY | SAFETY AND SECURITY | PUBLIC TRANSIT | 12 | GREATER HICKORY MPO | TS-7002 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 342000 | 342000 | MODIFY FUNDING IN FY 20, FY 21, FY 22, AND FY 23
CATAWBA | WESTERN PIEDMONT REGIONAL TRANSPORTATION | OPERATING ASSISTANCE-ADA PARATRANSIT | PUBLIC TRANSIT | 12 | GREATER HICKORY MPO | TG-6802 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2020 | 300000 | 300000
CATAWBA, ALEXANDER, BURKE, CALDWELL | VARIOUS | GREATER HICKORY METROPOLITAN PLANNING ORGANIZATION (MPO) PLANNING (PL) SUPPLEMENT. | HIGHWAY | 11, 12, 13 | GREATER HICKORY MPO | U-5924 | DIVISION 11, 12, 13 | BGDA, L | [6 empty] | 2020 | 1750000 | 1750000
CATAWBA, BURKE, CALDWELL | HICKORY | UPGRADE CURRENT PEDESTRIAN SIGNALS AND INSTALL NEW PEDESTRIAN SIGNALS. | BIKE/PED | 11, 12, 13 | GREATER HICKORY MPO | EB-5808 | DIVISION 11, 12, 13 | BGANY, L |  |  |  |  | 2023 | 402000 |  |  | 402000 | $322K IN STBG-DA FUNDS SWITCHED WITH $322K IN BG-ANY AS PART OF FUND SWAP 5-19-22.
CATAWBA, BURKE, CALDWELL, ALEXANDER | VARIOUS | GREATER HICKORY MPO TRANSPORTATION ALTERNATIVES (TAP) PROGRAM. | BIKE/PED | 11, 12, 13 | GREATER HICKORY MPO | U-5546 | DIVISION 11, 12, 13 | L, TADA |  |  |  |  | 2020 | 6200000 |  |  | 6200000
CATAWBA, BURKE, CALDWELL, ALEXANDER | VARIOUS | STBG-DA IN THE GREATER HICKORY METROPOLITAN PLANNING ORGANIZATION (MPO) AREA. | HIGHWAY | 11, 12, 13 | GREATER HICKORY MPO | U-5615 | DIVISION 11, 12, 13 | BGDA, L |  |  |  |  | 2020 | 36948000 |  |  | 36948000
CATAWBA, CALDWELL, BURKE | US 321 | NORTH OF US 70 IN HICKORY TO US 321A | HIGHWAY | 11, 12, 13 | GREATER HICKORY MPO | U-4700A | STATEWIDE MOBILITY | L, NHP, S(M) | 2021 | 88015000 |  |  | 2025 | 156999000 |  |  | 245014000 | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING: $45M FOR RIGHT-OF-WAY, PAYBACK FY 2021-2035
CATAWBA, IREDELL, LINCOLN | NC 150 | RELOCATED NC 16 (STIP PROJECT R-2206) TO US 21. WIDEN TO MULTI-LANES. | HIGHWAY | 12 | GREATER HICKORY MPO, CHARLOTTE REGIONAL TPO, GASTON-CLEVELAND-LINCOLN MPO | R-2307 | [11 empty] | SEGMENT B INCORPORATES WORK PREVIOUSLY UNDER I-5717.
CATAWBA, LINCOLN | NC 150 | RELOCATED NC 16 (STIP PROJECT R-2206) TO EAST OF SR 1840 (GREENWOOD ROAD). WIDEN TO 4-LANES WITH A BYPASS OF THE TERRELL HISTORIC DISTRICT. | HIGHWAY | 12 | GREATER HICKORY MPO, GASTON-CLEVELAND-LINCOLN MPO | R-2307A | REGION F | BGANY, T | 2027 | 82300000 | 2027 | 17800000 | 2030 | 115901000 |  |  | 216001000
CHATHAM | SILER CITY MUNICIPAL AIRPORT (SCR) | ACQUIRE NAVIGATION EASEMENTS IN RUNWAY 4 AND RUNWAY 22 APPROACHES, AND REMOVE OBSTRUCTIONS IN EASEMENTS. | AVIATION | 8 | TRIANGLE AREA RPO | AV-5736 | DIVISION 8 | T | 2023 | 365000 | [6 empty] | 365000
CHATHAM | SILER CITY MUNICIPAL AIRPORT (SCR) | EXTEND RUNWAY 22 AND PARALLEL TAXIWAY BY 500 FT, INCLUDING RELOCATION OF AIRPORT ROAD | AVIATION | 8 | TRIANGLE AREA RPO | AV-5816 | DIVISION 8 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2758000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5000000 |  |  | 7758000
CHATHAM | CHATHAM BUSINESS DR | SOUTH OF US 64 BUSINESS (EAST STREET) TO 900 FEET SOUTH OF US 64 BUSINESS (EAST STREET) IN PITTSBORO. CONSTRUCT SIDEWALK SEGMENT TO CONNECT EXISTING SIDEWALK | BIKE/PED | 8 | TRIANGLE AREA RPO | BL-0035 | EXEMPT | CMAQ, L | 2022 | 10000 |  |  | 2022 | 160000 | 2022 | 40000 | 210000
CHATHAM | SR 1107 (WEST 3RD STREET) | NORTH GARDEN AVENUE TO SR 1108 (NORTH CHATHAM AVENUE) IN SILER CITY. CONSTRUCT SIDEWALK. | BIKE/PED | 8 | TRIANGLE AREA RPO | EB-6006 | DIVISION 8 | L, TA5200 | 2024 | 45000 |  |  | 2026 | 676000 | 2022 | 113000 | 834000
CHATHAM | SR 2103 (EAST RALEIGH STREET) | SOUTH 7TH AVENUE TO US 64 (EAST 11TH STREET) IN SILER CITY. CONSTRUCT SIDEWALK ON SOUTH SIDE. | BIKE/PED | 8 | TRIANGLE AREA RPO | EB-5734 | DIVISION 8 | L, TA5200 |  |  |  |  | 2023 | 744000 |  |  | 744000
CHATHAM | SR 2106 (EAST CARDINAL STREET); SOUTH 10TH AVENUE | SR 2016 (EAST CARDINAL STREET) FROM SR 2223 (MATTHEWS STREET) TO SOUTH 10TH AVENUE, AND SOUTH 10TH AVENUE FROM EAST CARDINAL STREET TO SR 2103 (EAST RALEIGH STREET) IN SILER CITY. CONSTRUCT SIDEWALK. | BIKE/PED | 8 | TRIANGLE AREA RPO | EB-6007 | NOT FUNDED | L, TA5200 | NOT FUNDED | 45000 |  |  | NOT FUNDED | 730000 | NOT FUNDED | 127000 | 902000
CHATHAM | VARIOUS | NORTH SIDE OF GOVERNORS DRIVE TO EXISTING SIDEWALK ON MOUNT CARMEL CHURCH DRIVE. CONSTRUCT SIDEWALK. INTERSECTION OF MORNING DRIVE AND VILLAGE PARK DRIVE, AND INTERSECTION OF US 15 / US 501 AND OLD LYSTRA ROAD. INSTALL PEDESTRIAN SIGNALS AND CROSSWALKS. | BIKE/PED | 8 | DURHAM-CHAPEL HILL-CARRBORO MPO | BL-0070 | DIVISION 8 | BGDA, L, S |  |  |  |  | 2023 | 175000 |  |  | 175000 | "S" FUNDING REFLECTS HIGH IMPACT / LOW COST (HILC) FUNDS.
CHATHAM | NC 751 | SR 1731 (O'KELLY CHAPEL ROAD). UPGRADE AND REALIGN INTERSECTION. | HIGHWAY | 8 | DURHAM-CHAPEL HILL-CARRBORO MPO | R-5825 | DIVISION 8 | T |  |  |  |  | 2023 | 1026000 |  |  | 1026000
CHATHAM | NC 87 | NC 902 IN PITTSBORO TO US 64 BYPASS. WIDEN TO 12-FT LANES AND 4-FT PAVED SHOULDERS. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5961 | NOT FUNDED | T | NOT FUNDED | 2500000 | NOT FUNDED | 2200000 | NOT FUNDED | 13200000 |  |  | 17900000
CHATHAM | NEW ROUTE | US 64 BYPASS IN PITTSBORO TO US 15 / US 501. CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5930 | DIVISION 8 | O, T | 2023 | 1692000 | 2023 | 360000 | 2024 | 28901000 |  |  | 30953000 | "O" FUNDING REFLECTS LOCAL PARTICIPATION
CHATHAM | NEW ROUTE | US 15 / US 501 / NC 87 TO US 64 BUSINESS. CONSTRUCT 2-LANE ROADWAY ON NEW LOCATION. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5963 | DIVISION 8 | T | 2024 | 2399000 | 2024 | 360000 | 2027 | 53600000 |  |  | 56359000
CHATHAM | PITTSBORO ELEMENTARY SCHOOL ROAD | FARRELL STREET TO MCCLEHANAN STREET. DESIGN AND CONSTRUCT 0.6 MILE GAP BETWEEN FARRELL STREET AND MCCLENAHAN STREET. | HIGHWAY | 8 | TRIANGLE AREA RPO | BL-0062 | EXEMPT | CMAQ, L | 2024 | 5000 |  |  | 2024 | 141000 | 2023 | 59000 | 205000
CHATHAM | SR 1916 (CORINTH ROAD) | REPLACE BRIDGE 180010 OVER SHADDOX CREEK. | HIGHWAY | 8 | TRIANGLE AREA RPO | B-4461 | HIGHWAY FUND | [10 empty] | COMPLETE
CHATHAM | US 15 / US 501 | SOUTH OF US 64 BUSINESS TO POWELL PLACE LANE IN PITTSBORO. WIDEN TO MULTILANES, MILL AND RESURFACE, AND CONSTRUCT ROADWAY AND STREETSCAPE IMPROVEMENTS AT TRAFFIC CIRCLE. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5724
CHATHAM | US 15 / US 501 | US 15 / US 501, SOUTH OF US 64 BUSINESS TO NORTH OF US 64 BUSINESS. CONSTRUCT ROADWAY AND STREETSCAPE IMPROVEMENTS AT TRAFFIC CIRCLE. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5724A | DIVISION 8 | T |  |  |  |  | 2021 | 4000000 | 2021 | 450000 | 4450000
CHATHAM | US 15 / US 501 | US 15 / US 501, NORTH OF US 64 BUSINESS TO POWELL PLACE LANE. MILL AND RESURFACE FROM NORTH OF US 64 BUSINESS TO LAUNIS STREET AND WIDEN FROM LAUNIS STREET TO POWELL PLACE LANE. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5724B | DIVISION 8 | T | 2023 | 3900000 | 2023 | 1300000 | 2025 | 10200000 | 2022 | 425000 | 15825000
CHATHAM | US 421 | NC 902 INTERSECTION. CONVERT EXISTING SIGNALIZED INTERSECTION TO A SUPERSTREET. | HIGHWAY | 8 | TRIANGLE AREA RPO | W-5808B | STATEWIDE MOBILITY | HSIP | 2022 | 100000 |  |  | 2023 | 736000 |  |  | 836000
CHATHAM | US 64 (EAST 11TH STREET) | NORTH GLENN AVENUE TO EAST OF US 421 IN SILER CITY. UPGRADE ROADWAY TO INCLUDE MEDIAN FOR ACCESS CONTROL, SIDEWALKS, CROSSWALKS, BICYCLE LANES AND / OR MULTIUSE SIDEPATH. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5737 | REGION E | T | 2023 | 5000000 | 2023 | 2800000 | 2026 | 20501000 |  |  | 28301000
CHATHAM | VARIOUS | TRIANGLE INNOVATION POINT MEGASITE. ROADWAY IMPROVEMENTS. | HIGHWAY | 8 | TRIANGLE AREA RPO | HE-0006 | DIVISION 8 | [10 empty] | ECONOMIC DEVELOPMENT PROJECT; PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY
CHATHAM | CHATHAM TRANSIT NETWORK | ADMINISTRATION | PUBLIC TRANSIT | 8 | TRIANGLE AREA RPO | TK-6117 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 944000 | 944000 | FUNDS AUTHORIZED IN PROGRESS
CHATHAM | VARIOUS | CHATHAM TRANSIT NETWORK. PURCHASE 3 NEW RAMP-EQIPPED MINIVANS. | PUBLIC TRANSIT | 8 | TRIANGLE AREA RPO, DURHAM-CHAPEL HILL-CARRBORO MPO | TA-6719 | DIVISION 8 | L, T | [6 empty] | 2021 | 141000 | 141000
CHATHAM | SR 1916 (CORINTH ROAD) | CSX CROSSING 630723C NEAR HAYWOOD. INSTALL ACTIVE WARNING DEVICES. | RAIL | 8 | TRIANGLE AREA RPO | RX-2008A | DIVISION 8 | RR |  |  |  |  | 2023 | 800000 |  |  | 800000
CHATHAM, HOKE, LEE, RANDOLPH, SCOTLAND | VARIOUS | VARIOUS SECONDARY ROUTES IN CHATHAM, LEE, HOKE, RANDOLPH AND SCOTLAND COUNTIES. INSTALL LONG LIFE PAVEMENT MARKINGS. | HIGHWAY | 8 | LUMBER RIVER RPO, TRIANGLE AREA RPO, PIEDMONT TRIAD RPO, HIGH POINT URBAN AREA MPO, FAYETTEVILLE AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | HS-2008C | REGION E | HSIP |  |  |  |  | 2022 | 1580000 |  |  | 1580000
CHATHAM, HOKE, LEE, RICHMOND, MONTGOMERY, MOORE, RANDOLPH, SCOTLAND | VARIOUS | ECOSYSTEM ENHANCEMENT PROGRAM FOR DIVISION 8 PROJECT MITIGATION. | HIGHWAY | 8 | LUMBER RIVER RPO, TRIANGLE AREA RPO, PIEDMONT TRIAD RPO, DURHAM-CHAPEL HILL-CARRBORO MPO, HIGH POINT URBAN AREA MPO | EE-4908 | [11 empty] | COMPLETE
CHATHAM, LEE | SR 1007 (PLANK ROAD) | REPLACE BRIDGE 180169 OVER DEEP RIVER. | HIGHWAY | 8 | TRIANGLE AREA RPO | HB-0034 | DIVISION 8 | BGOFF | 2025 | 325000 | 2025 | 325000 | 2026 | 6500000 |  |  | 7150000
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | DIVISION 8 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | BIKE/PED | 8 | LUMBER RIVER RPO, TRIANGLE AREA RPO, PIEDMONT TRIAD RPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | BO-2408 | DIVISION 8 | S, TA |  |  |  |  | 2024 | 10000000 |  |  | 10000000
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 8. | HIGHWAY | 8 | LUMBER RIVER RPO, TRIANGLE AREA RPO, PIEDMONT TRIAD RPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | HS-2008 | DIVISION 8
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | DIVISION 8 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | HIGHWAY | 8 | LUMBER RIVER RPO, TRIANGLE AREA RPO, PIEDMONT TRIAD RPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | R-5788 | DIVISION 8 | S, TA |  |  |  |  | 2020 | 3600000 |  |  | 3600000 | IN PROGRESS; "S" FUNDS REFLECT STATE HIGHWAY FUNDS
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | DIVISION 8 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | 8 | LUMBER RIVER RPO, TRIANGLE AREA RPO, PIEDMONT TRIAD RPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | W-5208 | [11 empty] | UNDER CONSTRUCTION
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 8. | HIGHWAY | 8 | LUMBER RIVER RPO, TRIANGLE AREA RPO, PIEDMONT TRIAD RPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | W-5708 | [11 empty] | IN PROGRESS
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 8 | LUMBER RIVER RPO, TRIANGLE AREA RPO, PIEDMONT TRIAD RPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | W-5708DIV | DIVISION 8 | HSIP | 2020 | 90000 |  |  | 2020 | 540000 |  |  | 630000
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 8 | LUMBER RIVER RPO, TRIANGLE AREA RPO, PIEDMONT TRIAD RPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | W-5708REG | REGION E | HSIP | 2020 | 90000 |  |  | 2020 | 540000 |  |  | 630000
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 8 | LUMBER RIVER RPO, TRIANGLE AREA RPO, PIEDMONT TRIAD RPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | W-5708SW | STATEWIDE MOBILITY | HSIP | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 8. | HIGHWAY | 8 | LUMBER RIVER RPO, TRIANGLE AREA RPO, PIEDMONT TRIAD RPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | W-5808 | [11 empty] | INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 8. | RAIL | 8 | LUMBER RIVER RPO, TRIANGLE AREA RPO, PIEDMONT TRIAD RPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | RC-2008 | DIVISION 8 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
CHATHAM, MONTGOMERY, MOORE, RANDOLPH, HOKE, LEE, RICHMOND, SCOTLAND | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 8. | RAIL | 8 | LUMBER RIVER RPO, TRIANGLE AREA RPO, PIEDMONT TRIAD RPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | RX-2008 | DIVISION 8
CHATHAM, ORANGE | US 15 / US 501 | US 64 BYPASS TO SR 1919 (SMITH LEVEL ROAD). CONVERT REMAINING NON-SYNCHRONIZED SECTIONS OF FACILITY TO SYNCHRONIZED STREET. | HIGHWAY | 7, 8 | TRIANGLE AREA RPO, DURHAM-CHAPEL HILL-CARRBORO MPO | U-6192 | DIVISION 7, 8 | T | 2027 | 9300000 | 2027 | 30000000 | 2030 | 78400000 |  |  | 117700000
CHATHAM, ORANGE | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE TRIANGLE AREA RPO. | HIGHWAY | 7, 8 | TRIANGLE AREA RPO | C-5618 | EXEMPT | CMAQ, L | 2020 | 45000 |  |  | 2020 | 255000 | 2020 | 135000 | 435000
CHATHAM, WAKE | US 64 | NC 751. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 5, 8 | TRIANGLE AREA RPO, CAPITAL AREA MPO | R-5887 | REGION C, E | NHP | 2027 | 3300000 | 2027 | 1500000 | 2029 | 31000000 |  |  | 35800000
CHEROKEE | SR 1326 | REPLACE BRIDGE 159 OVER HANGING DOG CREEK. | HIGHWAY | 14 | SOUTHWESTERN RPO | B-4069 | DIVISION 14 | BGOFF | 2024 | 295000 |  |  | 2024 | 1800000 |  |  | 2095000
CHEROKEE | SR 1548 (OLD HIGHWAY 64) | REPLACE BRIDGE 223 OVER HIWASSEE RIVER. | HIGHWAY | 14 | SOUTHWESTERN RPO | B-5925 | DIVISION 14 | BFP | 2023 | 260000 |  |  | 2024 | 2600000 |  |  | 2860000
CHEROKEE | US 19/129 | GEORGIA STATE LINE TO US 64. WIDEN ROADWAY. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5861 | DIVISION 14 | T | 2022 | 11400000 | 2022 | 1100000 | 2024 | 43400000 |  |  | 55900000
CHEROKEE | US 19/US 74/ US 129 | US 64 TO SR 1689 (CASINO PARKWAY). MODERNIZE ROADWAY. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5908 | DIVISION 14 | BGLT5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 21400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 20401000 |  |  | 42901000
CHEROKEE | US 19/US 74/ US 64/US 129 | END OF 4-LANE DIVIDED SECTION TO US 19 BUSINESS (HIWASSEE STREET). IMPROVE ROADWAY. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5735 | DIVISION 14 | T | 2020 | 4815000 |  |  | 2020 | 12825000 | 2020 | 2700000 | 20340000 | UNDER CONSTRUCTION; BUILD NC BOND FUNDING: $2.07 M FOR PE, $3.74 M FOR ROW, $4.505 M FOR CON - PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $19,307 FOR PE- PAYBACK 2021-2035 (YR 2&3 SALE); $5.452 M FOR CON, PAYBACK FY 2021-2035 (YR 2&3 SALE)
CHEROKEE | US 19/US 74/US 64/US 129 | END OF 4-LANE DIVIDED SECTION TO US 19 BUSINESS (HIWASSEE STREET). IMPROVE ROADWAY. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5735A | DIVISION 14 | [10 empty] | CLEARING ONLY.
CHEROKEE | CHEROKEE COUNTY | ADMINISTRATION | PUBLIC TRANSIT | 14 | SOUTHWESTERN RPO | TK-6118 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 712000 | 712000 | FUNDS AUTHORIZED IN PROGRESS
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | DIVISION 14 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | BIKE/PED | 14 | SOUTHWESTERN RPO, FRENCH BROAD RIVER MPO, FOOTHILLS RPO, LAND-OF-SKY RPO | BO-2414 | DIVISION 14 | S, TA |  |  |  |  | 2024 | 4000000 |  |  | 4000000
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 14. | HIGHWAY | 14 | SOUTHWESTERN RPO, FRENCH BROAD RIVER MPO, FOOTHILLS RPO, LAND-OF-SKY RPO | HS-2014 | [11 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | DIVISION 14 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | HIGHWAY | 14 | SOUTHWESTERN RPO, FRENCH BROAD RIVER MPO, FOOTHILLS RPO, LAND-OF-SKY RPO | R-5794 | DIVISION 14 | S, TA |  |  |  |  | 2020 | 3500000 |  |  | 3500000 | UNDER CONSTRUCTION. "S" FUNDS ARE STATE HIGHWAY FUNDS
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | DIVISION 14 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | 14 | SOUTHWESTERN RPO, LAND-OF-SKY RPO, FRENCH BROAD RIVER MPO, FOOTHILLS RPO | W-5214 | [11 empty] | IN PROGRESS - DIVISION PURCHASE ORDER CONTRACT (DPOC)
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 14. | HIGHWAY | 14 | SOUTHWESTERN RPO, FRENCH BROAD RIVER MPO, FOOTHILLS RPO, LAND-OF-SKY RPO | W-5714 | [11 empty] | IN PROGRESS
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 14 | SOUTHWESTERN RPO, FRENCH BROAD RIVER MPO, FOOTHILLS RPO, LAND-OF-SKY RPO | W-5714DIV | DIVISION 14 | HSIP | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 14 | SOUTHWESTERN RPO, FRENCH BROAD RIVER MPO, FOOTHILLS RPO, LAND-OF-SKY RPO | W-5714REG | REGION G | HSIP | 2020 | 120000 |  |  | 2020 | 720000 |  |  | 840000
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 14 | SOUTHWESTERN RPO, FRENCH BROAD RIVER MPO, FOOTHILLS RPO, LAND-OF-SKY RPO | W-5714SW | STATEWIDE MOBILITY | HSIP | 2020 | 160000 |  |  | 2020 | 960000 |  |  | 1120000
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 14. | HIGHWAY | 14 | SOUTHWESTERN RPO, FRENCH BROAD RIVER MPO, FOOTHILLS RPO, LAND-OF-SKY RPO | W-5814 | [11 empty] | INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 14. | RAIL | 14 | SOUTHWESTERN RPO, FRENCH BROAD RIVER MPO, FOOTHILLS RPO, LAND-OF-SKY RPO | RC-2014 | DIVISION 14 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
CHEROKEE, CLAY, GRAHAM, HAYWOOD, HENDERSON, JACKSON, MACON, POLK, SWAIN, TRANSYLVANIA | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 14. | RAIL | 14 | SOUTHWESTERN RPO, FRENCH BROAD RIVER MPO, FOOTHILLS RPO, LAND-OF-SKY RPO | RX-2014 | DIVISION 14 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
CHEROKEE, GRAHAM, JACKSON, SWAIN | EASTERN BAND OF CHEROKE INDIANS | ADMINISTRATION | PUBLIC TRANSIT | 14 |  | TK-6127 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 464000 | 464000 | FUNDS AUTHORIZED IN PROGRESS
CHEROKEE, MACON | US 74 | SR 1393 (WAKEFIELD ROAD) TO SR 1310 (WAYAH ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5920 | NOT FUNDED | BGLT5 | NOT FUNDED | 20000000 | NOT FUNDED | 1000000 | NOT FUNDED | 71998000 |  |  | 92998000
CHOWAN | NC 32 | REPLACE BRIDGE 200024 OVER WARWICK CREEK, BRIDGE 200020 OVER DILLARD CREEK, AND BRIDGE 200021 OVER SAND RUN. | HIGHWAY | 1 | ALBEMARLE RPO | B-5507 | HIGHWAY FUND | [10 empty] | UNDER CONSTRUCTION
CHOWAN | US 17 (FUTURE I-87) | BERTIE COUNTY LINE TO PERQUIMANS COUNTY LINE. PAVEMENT REHABILITATION. | HIGHWAY | 1 | ALBEMARLE RPO | I-6027 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2028 | 8250000 |  |  | 8250000
CLAY | NC 175 | GEORGIA STATE LINE TO US 64. UPGRADE ROADWAY. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5742 | DIVISION 14 | T | 2020 | 540000 |  |  | 2020 | 28077000 | 2020 | 2505000 | 31122000 | UNDER CON - INCL PRJ W-5119. BUILD NC BOND: $1.925M FOR PE, $419,979 FOR ROW, $8.008 M FOR CON - PAYBACK 2020-2034 (FY 2019/YR1 SALE); $8,839 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $13.270M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE).
CLAY | NC 175 | GEORGIA STATE LINE TO US 64. UPGRADE ROADWAY. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5742A | DIVISION 14 | [10 empty] | CLEARING ONLY.
CLAY | NC 69 | GEORGIA STATE LINE TO US 64 (HAYESVILLE BYPASS). UPGRADE EXISTING TWO-LANES | HIGHWAY | 14 | SOUTHWESTERN RPO | A-0011A | [11 empty] | COMPLETE
CLAY | NC 69 | GEORGIA STATE LINE TO US 64 (HAYESVILLE BYPASS). WIDEN TO FOUR-LANES | HIGHWAY | 14 | SOUTHWESTERN RPO | A-0011C | EXEMPT | ADHS |  |  |  |  | 2020 | 52600000 |  |  | 52600000 | UNDER CONSTRUCTION
CLAY | SR 1140 (MYERS CHAPEL ROAD) | REPLACE BRIDGE #63 OVER BLAIR CREEK AND BRIDGE #88 OVER HYATT MILL CREEK. | HIGHWAY | 14 | SOUTHWESTERN RPO | HF-0005 | EXEMPT | FLAP, S(M) |  |  |  |  | 2024 | 1200000 | 2021 | 300000 | 1500000 | FLAP PROJECT ID: NC 53; AWARD AMOUNT = $1,200,000. STATE FUNDS ARE HIGHWAY FUNDS. DIVISION 14 IS RESPONSIBLE FOR ANY RIGHT-OF-WAY AND UTILITY RELOCATION COSTS.
CLAY | US 64 | NC 69 IN HAYESVILLE TO EAST OF THE HIWASSEE RIVER | HIGHWAY | 14 | SOUTHWESTERN RPO | A-0011BA | [11 empty] | COMPLETE
CLAY | US 64 | EAST OF THE HIWASSEE RIVER TO EAST OF NC 175 | HIGHWAY | 14 | SOUTHWESTERN RPO | A-0011BB | [11 empty] | COMPLETE
CLAY | US 64 | EAST OF THE HIWASSEE RIVER TO EAST OF NC 175. WIDEN TO FOUR-LANES. | HIGHWAY | 14 | SOUTHWESTERN RPO | A-0011D | NOT FUNDED | ADHS | NOT FUNDED | 20845000 | NOT FUNDED | 378000 | NOT FUNDED | 52800000 |  |  | 74023000
CLAY | US 64 | NC 175 TO SR 1349 (OLD HWY 64 EAST). WIDEN TO MULTI-LANE. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5922 | NOT FUNDED | BGLT5 | NOT FUNDED | 3700000 | NOT FUNDED | 2700000 | NOT FUNDED | 39700000 |  |  | 46100000
CLAY | US 64 BUSINESS | US 64 TO SR 1307 (MAIN STREET). UPGRADE ROADWAY. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5863 | DIVISION 14 | T | 2022 | 4200000 |  |  | 2023 | 6100000 |  |  | 10300000
CLAY | US 64/NC 69 | NC 69, GEORGIA STATE LINE TO US 64. WIDEN TO FOUR LANES DIVIDED. US 64, NC 69 TO EAST OF NC 175. WIDEN TO MULTI-LANES. | HIGHWAY | 14 | SOUTHWESTERN RPO | A-0011 | [11 empty] | APD FUNDS ARE 100% FEDERAL
CLAY | CLAY COUNTY | ADMINISTRATION | PUBLIC TRANSIT | 14 | SOUTHWESTERN RPO | TK-6120 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 704000 | 704000 | FUNDS AUTHORIZED IN PROGRESS
CLAY, CHEROKEE | US 64 | US 64 BUSINESS WEST OF HAYESVILLE TO EAST OF NC 141. WIDEN TO FOUR-LANES DIVIDED. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5847 | NOT FUNDED | T | NOT FUNDED | 32000000 | NOT FUNDED | 6000000 | NOT FUNDED | 95901000 |  |  | 133901000 | WORK FOR B-5911 INCLUDED.
CLEVELAND | SHELBY RAIL TRAIL | SOUTH DEKALB STREET TO WEST GROVER STREET IN SHELBY. CONSTRUCT MULTIUSE PATH. | BIKE/PED | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-6037A | DIVISION 12 | L, TAANY |  |  |  |  | 2024 | 5200000 |  |  | 5200000
CLEVELAND | NEW ROUTE | CONSTRUCT IMPROVEMENTS TO SR 1313 (WASHBURN SWITCH ROAD) AND A NEW 3-LANE ROAD OFF SR 1313 (WASHBURN SWITCH ROAD) FOR ACCESS TO NEW INDUSTRIAL SITES. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-5849 | DIVISION 12 | [10 empty] | UNDER CONSTRUCTION
CLEVELAND | SR 2226 (LAVENDAR ROAD) | REPLACE BRIDGE 220072 OVER BUFFALO CREEK. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | B-5848 | DIVISION 12 | BGOFF | 2022 | 200000 |  |  | 2023 | 3700000 |  |  | 3900000
CLEVELAND | US 74 | REPLACE BRIDGES 220048 AND 220049 OVER SANDY RUN. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | BR-0012 | HIGHWAY FUND | HFB | 2022 | 42000 |  |  | 2024 | 10300000 |  |  | 10342000 | TO BE LET WITH R-4045
CLEVELAND | US 74 | SR 1168 (LATTIMORE ROAD) INTERSECTION. UPGRADE AT-GRADE INTERSECTION TO INTERCHANGE AND UPGRADE US 74 TO FULL CONTROL OF ACCESS FROM WEST OF US 74 BUSINESS (ELLENBORO ROAD) TO EAST OF BRIDGES 48 AND 49 OVER SANDY RUN. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-4045 | REGION F | DP, T | 2023 | 3000000 | 2023 | 1900000 | 2023 | 25000000 |  |  | 29900000 | DP REPRESENTS FEDERAL INFRA GRANT FUNDS. TOTAL AWARD AMOUNT = $23,240,000. PROJECT TO BE LET WITH BR-0012. DESIGN-BUILD PROJECT.
CLEVELAND | US 74 | US 74 BUSINESS TO NC 226. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-5713 | REGION F | T |  |  |  |  | 2024 | 1950000 |  |  | 1950000
CLEVELAND | US 74 (DIXON BOULEVARD) | NC 150 (DEKALB STREET) INTERSECTION. CONSTRUCT INTERCHANGE. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-2567 | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 21200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 25200000 |  |  | 48100000 | TO BE LET WITH U-5929
CLEVELAND | US 74 (DIXON BOULEVARD) | INTERSECTION OF US 74 (DIXON BOULEVARD) AND NC 226 (EARL ROAD). CONSTRUCT IMPROVEMENTS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5929 | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6500000 |  |  | 15700000 | TO BE LET WITH U-2567
CLEVELAND | US 74 (SHELBY BYPASS) | FOUR LANE DIVIDED FREEWAY ON NEW LOCATION. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-2707
CLEVELAND | US 74 BUSINESS (MARION STREET) | INTERSECTION OF US 74 BUSINESS (MARION STREET) AND NC 150 (CHERRYVILLE ROAD). REALIGN INTERSECTION. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5775 | REGION F | L, T |  |  |  |  | 2022 | 4000000 |  |  | 4000000 | RIGHT-OF-WAY IN PROGRESS. $300,000 FROM CITY OF SHELBY
CLEVELAND | US 74 SHELBY BYPASS | WEST OF SR 1162 (PEACHTREE ROAD) TO EAST OF SR 1315 (PLATO LEE ROAD). RIGHT-OF-WAY ONLY. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-2707A | [11 empty] | COMPLETE
CLEVELAND | US 74 SHELBY BYPASS | WEST OF SR 1162 (PEACHTREE ROAD) TO EAST OF SR 1318 (KIMBRELL ROAD). GRADING, STRUCTURES, PAVING | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-2707AA | [11 empty] | COMPLETE
CLEVELAND | US 74 SHELBY BYPASS | EAST OF SR 1318 (KIMBRELL ROAD) TO EAST OF SR 1315 (PLATO LEE ROAD). GRADING AND STRUCTURES | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-2707AB | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
CLEVELAND | US 74 SHELBY BYPASS | EAST OF SR 1315 (PLATO LEE ROAD) TO EAST OF NC 226. GRADING AND STRUCTURES | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-2707B | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
CLEVELAND | US 74 SHELBY BYPASS | EAST OF NC 226 TO EAST OF NC 150. GRADING, STRUCTURES, AND PAVING. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-2707C | REGION F | T |  |  |  |  | 2020 | 43050000 | 2021 | 75000 | 43125000 | BUILD NC BOND FUNDING: $56,071 FOR PE, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE); $11.336M FOR CON, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $22.109M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE).
CLEVELAND | US 74 SHELBY BYPASS | EAST OF NC 150 TO EXISTING US 74 WEST OF SR 2238 (LONG BRANCH ROAD). GRADING, STRUCTURE, PAVING. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-2707D | REGION F | T | 2019 | 10040000 |  |  | 2024 | 85905000 |  |  | 95945000 | RIGHT-OF-WAY IN PROGRESS. R-2707D: BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); $45.3M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE)
CLEVELAND | US 74 SHELBY BYPASS | US 74 WEST OF SR 2238 TO WEST OF SR 1001 (STONEY POINT ROAD). GRADING, STRUCTURES, PAVING. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-2707E | REGION F | T | 2019 | 14290000 |  |  | 2024 | 34300000 |  |  | 48590000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE)
CLEVELAND | US 74 SHELBY BYPASS | EAST OF SR 1318 (KIMBRELL ROAD) TO EAST OF NC 226. PAVING | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-2707F | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
CLEVELAND | TRANSPORTATION ADMIN. OF CLEVELAND COUNTY | ADMINISTRATION | PUBLIC TRANSIT | 12 | GASTON-CLEVELAND-LINCOLN MPO | TK-6166 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 1196000 | 1196000 | FUNDS AUTHORIZED IN PROGRESS
CLEVELAND, GASTON | I-85 | SOUTH CAROLINA STATE LINE TO US 74 | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | I-5985A | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 150300000 |  |  | 157000000
CLEVELAND, POLK, GASTON, HENDERSON, RUTHERFORD, MECKLENBURG, BUNCOMBE | US 74 | I-40 IN ASHEVILLE TO I-77 AT I-485 (SOUTH) IN CHARLOTTE. INSTALL BROADBAND. | HIGHWAY | 10, 12, 13, 14 | GASTON-CLEVELAND-LINCOLN MPO, FOOTHILLS RPO, FRENCH BROAD RIVER MPO, CHARLOTTE REGIONAL TPO | HO-0002A | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2021 | 18435000 |  |  | 18435000 | LETTING TO BE COMBINED WITH R-5777D, I-5986C, HO-0002B, AND HO-0002C.
COLUMBUS | COLUMBUS COUNTY AIRPORT (CPC) | APRON EXPANSION. | AVIATION | 6 | CAPE FEAR RPO | AV-5748 | DIVISION 6 | T |  |  |  |  | 2023 | 1808000 |  |  | 1808000
COLUMBUS | NC 11 | NC 11 AT SR 1740 (OLD LAKE ROAD). CONSTRUCT ROUNDABOUT. | HIGHWAY | 6 | CAPE FEAR RPO | W-5806A | REGION C | HSIP | 2024 | 85000 |  |  | 2025 | 1342000 |  |  | 1427000
COLUMBUS | NC 211 | NC 211 FROM THE BRUNSWICK COUNTY LINE TO NC 214. INSTALL RUMBLE STRIPES. | HIGHWAY | 6 | CAPE FEAR RPO | HS-2006F | DIVISION 6 | HSIP |  |  |  |  | 2023 | 574000 |  |  | 574000
COLUMBUS | NC 87 | NC 11 TO US 74/US 76 IN COLUMBUS COUNTY. | HIGHWAY | 6 | CAPE FEAR RPO | R-2561C | DIVISION 6 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 26512000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4488000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 85800000 |  |  | 116800000
COLUMBUS | NC 87 | NC 87 AT NC 11. CONSTRUCT INTERCHANGE. | HIGHWAY | 6 | CAPE FEAR RPO | R-2561CA | REGION C | BGLT5, T | 2020 | 3304000 | 2020 | 3000000 | 2023 | 29700000 |  |  | 36004000 | RIGHT-OF-WAY IN PROGRESS.
COLUMBUS | ROAD) SR 1800 (BLACKSMITH | REPLACE BRIDGE 230250 OVER RICEFIELD BRANCH. | HIGHWAY | 6 | CAPE FEAR RPO | HB-0009 | DIVISION 6 | BGOFF | 2024 | 140000 |  |  | 2025 | 1400000 |  |  | 1540000
COLUMBUS | SR 1159 (OLD TRAM ROAD) | REPLACE BRIDGE 230313 OVER BOOGY BRANCH. | HIGHWAY | 6 | CAPE FEAR RPO | B-6006 | DIVISION 6 | [10 empty] | COMPLETE
COLUMBUS | SR 1904 (RED BUG ROAD) | REPLACE BRIDGE NUMBER 230211 OVER JOCKEY BRANCH. | HIGHWAY | 6 | CAPE FEAR RPO | B-6039 | DIVISION 6 | [10 empty] | COMPLETE
COLUMBUS | US 701 | NC 410 (JOE BROWN HIGHWAY). IMPROVE INTERSECTION. | HIGHWAY | 6 | CAPE FEAR RPO | R-5013 | DIVISION 6 | T |  |  |  |  | 2019 | 1235000 |  |  | 1235000 | COMPLETE
COLUMBUS | US 701 BYPASS | SR 1166 (PLEASANT PLAINS CHURCH ROAD) TO SR 1437 (VIRGIL AVENUE). | HIGHWAY | 6 | CAPE FEAR RPO | R-5020A | REGION C | T |  |  |  |  | 2026 | 39201000 |  |  | 39201000
COLUMBUS | US 701 BYPASS | SR 1437 (VIRGIL AVENUE) TO US 74/US 76. | HIGHWAY | 6 | CAPE FEAR RPO | R-5020B | DIVISION 6 | T |  |  |  |  | 2022 | 32487000 |  |  | 32487000
COLUMBUS | US 701 BYPASS | SR 1305 (COMPLEX STREET). UPGRADE INTERSECTION. | HIGHWAY | 6 | CAPE FEAR RPO | R-5952 | DIVISION 6 | T | 2025 | 2100000 | 2025 | 1300000 | 2027 | 17500000 |  |  | 20900000
COLUMBUS | US 701 BYPASS (MADISON STREET- POWELL BOULEVARD) | SOUTH OF SR 1166 (PLEASANT PLAINS ROAD) TO NORTH OF US 74/US 76 BYPASS IN WHITEVILLE. WIDEN TO MULTI-LANE FACILITY. | HIGHWAY | 6 | CAPE FEAR RPO | R-5020 | [11 empty] | RIGHT-OF-WAY IN PROGRESS
COLUMBUS | US 74 | SR 1506 (BOARDMAN ROAD). UPGRADE AT-GRADE INTERSECTION TO AN INTERCHANGE. | HIGHWAY | 6 | CAPE FEAR RPO | R-5797 | REGION C | T |  |  |  |  | 2021 | 18620000 |  |  | 18620000 | RIGHT OF WAY IN PROGRESS
COLUMBUS | US 74 (FUTURE I-74) | US 74 (FUTURE I-74) FROM EAST OF NC 214 TO WEST OF SR 1824 (WATER TANK ROAD). PAVEMENT REHABILITATION. | HIGHWAY | 6 | CAPE FEAR RPO | HI-0015 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2024 | 7700000 |  |  | 7700000
COLUMBUS | US 74 (FUTURE I-74) | US 74 (FUTURE I-74) FROM WEST OF US 701 BUSINESS TO WEST OF NC 214. PAVEMENT REHABILITATION. | HIGHWAY | 6 | CAPE FEAR RPO | HI-0018 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2025 | 18200000 |  |  | 18200000
COLUMBUS | US 74 (FUTURE I-74) | US 74 (FUTURE I-74) FROM WEST OF SR 1585 (UNION VALLEY ROAD) TO WEST OF US 701 BUSINESS. PAVEMENT REHABILITATION. | HIGHWAY | 6 | CAPE FEAR RPO | HI-0019 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2027 | 5400000 |  |  | 5400000
COLUMBUS | US 74 (FUTURE I-74) | US 74 (FUTURE I-74) FROM THE ROBESON COUNTY LINE TO WEST OF SR 1585 (UNION VALLEY ROAD). PAVEMENT REHABILITATION. | HIGHWAY | 6 | CAPE FEAR RPO | HI-0020 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2027 | 15000000 |  |  | 15000000
COLUMBUS | US 74 / 76 | ADVANCED CONSTRUCTION OF TEMPORARY REDUCED CONFLICT INTERSECTIONS AT SR 1735 (CHAUNCEY TOWN ROAD) AND SR 1740 (OLD LAKE ROAD). | HIGHWAY | 6 | CAPE FEAR RPO | R-5819A | REGION C | T |  |  |  |  | 2021 | 2300000 |  |  | 2300000
COLUMBUS | US 74/US 76 | SR 1001 (HALLSBORO ROAD). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 6 | CAPE FEAR RPO | R-5749 | DIVISION 6 | [10 empty] | COMPLETE
COLUMBUS | US 74/US 76 | SR 1740 (OLD LAKE ROAD). CONVERT AT-GRADE INTERSECTION TO OVERPASS. | HIGHWAY | 6 | CAPE FEAR RPO | R-5819 | REGION C | T | 2021 | 346000 | 2021 | 129000 | 2022 | 11664000 |  |  | 12139000 | COMBINE WITH R-5820. RIGHT-OF-WAY IN PROGRESS.
COLUMBUS | US 74/US 76 | SR 1735 (CHAUNCEY TOWN ROAD). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 6 | CAPE FEAR RPO | R-5820 | REGION C | T | 2021 | 931000 | 2021 | 1297000 | 2022 | 39049000 |  |  | 41277000 | COMBINE WITH R-5819. RIGHT-OF-WAY IN PROGRESS.
COLUMBUS | COLUMBUS COUNTY | ADMINISTRATION | PUBLIC TRANSIT | 6 | CAPE FEAR RPO | TK-6121 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 688000 | 688000 | FUNDS AUTHORIZED IN PROGRESS
COLUMBUS, ROBESON | US 74 | NC 41 NEAR LUMBERTON TO US 76 NEAR CHADBOURN. UPGRADE US 74 TO INTERSTATE STANDARDS. | HIGHWAY | 6 | CAPE FEAR RPO, LUMBER RIVER RPO | I-6011 | NOT FUNDED | T | NOT FUNDED | 179000 | NOT FUNDED | 1469000 | NOT FUNDED | 169100000 |  |  | 170748000
COLUMBUS, ROBESON, ANSON, SCOTLAND, RICHMOND, BRUNSWICK, UNION | US 74 | EASTERN END OF MONROE BYPASS TO I-140 IN WILMINGTON. VULNERABILITY ASSESSMENTS, INSTALLATION OF FLOOD GAUGES, AND FLOOD MONITORING. | HIGHWAY | 3, 6, 8, 10 | LUMBER RIVER RPO, CAPE FEAR RPO, ROCKY RIVER RPO, CHARLOTTE REGIONAL TPO, WILMINGTON URBAN AREA MPO | HO-0002D | STATEWIDE MOBILITY | DP, T | [6 empty] | 2022 | 2200000 | 2200000
COLUMBUS, ROBESON, BRUNSWICK | US 74 | I-95 IN LUMBERTON TO I-140 IN WILMINGTON. INSTALL BROADBAND. | HIGHWAY | 3, 6 | CAPE FEAR RPO, LUMBER RIVER RPO, WILMINGTON URBAN AREA MPO | HO-0002C | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2021 | 10456000 |  |  | 10456000 | LETTING TO BE COMBINED WITH R-5777D, I-5986C, HO-0002A, AND HO-0002B. UNDER CONSTRUCTION.
COLUMBUS, ROBESON, CLEVELAND, ANSON, GASTON, POLK, SCOTLAND, HENDERSON, RICHMOND, RUTHERFORD, MECKLENBURG, BRUNSWICK, BUNCOMBE, UNION | US 74 | I-40 IN ASHEVILLE TO I-140 IN WILMINGTON. IMPLEMENT BROADBAND, ITS, AND RESILIENCY IMPROVEMENTS. | HIGHWAY | 3, 6, 8, 10, 12, 13, 14 | LUMBER RIVER RPO, CAPE FEAR RPO, GASTON-CLEVELAND-LINCOLN MPO, FOOTHILLS RPO, FRENCH BROAD RIVER MPO, ROCKY RIVER RPO, CHARLOTTE REGIONAL TPO, WILMINGTON URBAN AREA MPO | HO-0002 | [11 empty] | DP REPRESENTS FEDERAL INFRA GRANT FUNDS
CRAVEN | COASTAL CAROLINA REGIONAL AIRPORT (EWN) | DESIGN AND CONSTRUCTION OF TAXIWAYS, TAXI LANES, AND APRON AREAS. | AVIATION | 2 | NEW BERN AREA MPO | AV-5808 | [11 empty] | COMPLETE
CRAVEN | COASTAL CAROLINA REGIONAL AIRPORT (EWN) | RUNWAY EXTENSION. | AVIATION | 2 | NEW BERN AREA MPO | AV-5891 | NOT FUNDED | T |  |  |  |  | NOT FUNDED | 300000 |  |  | 300000
CRAVEN | NC 43 CONNECTOR | NC 43/NC 55 TO US 17 IN NEW BERN. CONSTRUCT ROUTE ON NEW LOCATION WITH INTERCHANGE AT US 70. | HIGHWAY | 2 | NEW BERN AREA MPO | R-4463
CRAVEN | NC 43 CONNECTOR | US 17 BUSINESS TO SOUTH OF US17/US 70. | HIGHWAY | 2 | NEW BERN AREA MPO | R-4463A | REGION B | T | 2020 | 240000 |  |  | 2025 | 24500000 | 2020 | 1725000 | 26465000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,335,267 FOR PE, $191,706.08 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE)
CRAVEN | NC 43 CONNECTOR | SOUTH OF US17/US 70 TO US 70. | HIGHWAY | 2 | NEW BERN AREA MPO | R-4463AA | [11 empty] | COMPLETE
CRAVEN | NC 43 CONNECTOR | US 70 TO NC 43/NC 55. | HIGHWAY | 2 | NEW BERN AREA MPO | R-4463B | [11 empty] | COMPLETE - ECONOMIC DEVELOPMENT PROJECT
CRAVEN | NC 55 (FIRST STREET/ COUNTRY CLUB ROAD) | NC 55 (NEUSE BOULEVARD) TO PEMBROKE AVENUE. REDUCE LANES AND INCLUDE BICYCLE AND PEDESTRIAN ACCOMODATIONS. | HIGHWAY | 2 | NEW BERN AREA MPO | U-5992 | DIVISION 2 | T |  |  |  |  | 2019 | 990000 |  |  | 990000 | LOCAL FUNDING IS PROVIDED BY CITY OF NEW BERN. UNDER CONSTRUCTION.
CRAVEN | NC 55 (NEUSE BOULEVARD) | US 17 BUSINESS (MLK BOULEVARD). CONSTRUCT ROUNDABOUT. | HIGHWAY | 2 | NEW BERN AREA MPO | U-5993 | REGION B | T | 2026 | 400000 |  |  | 2028 | 3450000 |  |  | 3850000
CRAVEN | ROAD) SR 1470 (MAPLE CYPRESS | BRIDGE 138 AND BRIDGE 139 OVER THE NEUSE RIVER ON SR 1470. | HIGHWAY | 2 | DOWN EAST RPO | B-4484 | DIVISION 2 | T |  |  |  |  | 2021 | 15927000 |  |  | 15927000 | RIGHT OF WAY IN PROGRESS.
CRAVEN | SR 1001 / SR 1256 (MAIN STREET) | SR 1001 / SR 1256 (MAIN STREET) AT SR 1005 (SUNSET BOULEVARD). INSTALL ALL WAY STOP, REVISE OVERHEAD FLASHER, AND INSTALL CHANNELIZATION. | HIGHWAY | 2 | DOWN EAST RPO | HS-2002F | DIVISION 2 | HSIP | 2022 | 15000 |  |  | 2023 | 58000 |  |  | 73000 | RIGHT-OF-WAY IN PROGRESS.
CRAVEN | SR 1763 (MILLER BOULEVARD) | SR 1756 (LAKE ROAD) TO OUTER BANKS DRIVE. WIDEN TO MULTI-LANES. | HIGHWAY | 2 | DOWN EAST RPO | U-3431 | DIVISION 2 | T | 2026 | 18759000 | 2026 | 4864000 | 2028 | 36400000 |  |  | 60023000
CRAVEN | US 17 | NC 43 TO SR 1438 (SPRUILL TOWN ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 2 | DOWN EAST RPO | R-2513
CRAVEN | US 17 | NORTH OF NC 43 TO SR 1438 (SPRUILL TOWN ROAD). | HIGHWAY | 2 | DOWN EAST RPO | R-2513A | DIVISION 2 | T | 2026 | 3000000 | 2026 | 2400000 | 2028 | 15200000 |  |  | 20600000 | TO BE LET WITH R-3403B.
CRAVEN | US 17 | SR 1438 (SPRUILL TOWN ROAD) TO SR 1637 (MILL POND ROAD). | HIGHWAY | 2 | DOWN EAST RPO | R-2513B | NOT FUNDED | T | NOT FUNDED | 5800000 | NOT FUNDED | 800000 | NOT FUNDED | 16300000 |  |  | 22900000
CRAVEN | US 17 | SR 1637 (MILL POND ROAD) TO SR 1646 (MILE ROAD). | HIGHWAY | 2 | DOWN EAST RPO | R-2513C | NOT FUNDED | T | NOT FUNDED | 2300000 | NOT FUNDED | 600000 | NOT FUNDED | 11300000 |  |  | 14200000
CRAVEN | US 17 | SR 1646 (MILE ROAD) IN CRAVEN COUNTY TO SR 1130 (C.C. ROAD) IN BEAUFORT COUNTY. | HIGHWAY | 2 | DOWN EAST RPO | R-2513D | NOT FUNDED | T | NOT FUNDED | 4600000 | NOT FUNDED | 600000 | NOT FUNDED | 21000000 |  |  | 26200000
CRAVEN | US 17 | MILLS STREET IN BRIDGETON TO NC 43. WIDEN TO MULTI-LANES. | HIGHWAY | 2 | DOWN EAST RPO, NEW BERN AREA MPO | R-3403 | REGION B
CRAVEN | US 17 | MILLS STREET IN BRIDGETON TO NORTH "C" STREET. | HIGHWAY | 2 | DOWN EAST RPO | R-3403AA | [11 empty] | COMPLETE
CRAVEN | US 17 | NORTH "C" STREET TO NORTH OF SR 1433 (ANTIOCH ROAD). | HIGHWAY | 2 | DOWN EAST RPO | R-3403AB | [11 empty] | COMPLETE
CRAVEN | US 17 | SR 1433 (ANTIOCH ROAD) TO NORTH OF NC 43. | HIGHWAY | 2 | DOWN EAST RPO, NEW BERN AREA MPO | R-3403B | REGION B | T | 2027 | 6000000 | 2027 | 4500000 | 2029 | 71800000 |  |  | 82300000 | TO BE LET WITH R-2513A.
CRAVEN | US 17 ALTERNATE (MARTIN LUTHER KING JR. BOULEVARD) | US 70 TO SR 1278 (TRENT ROAD). UGRADE TO SUPERSTREET. | HIGHWAY | 2 | NEW BERN AREA MPO | U-6198 | NOT FUNDED | T | NOT FUNDED | 18000000 | NOT FUNDED | 3100000 | NOT FUNDED | 24700000 |  |  | 45800000
CRAVEN | US 17 NEW BERN BYPASS | US 17 SOUTH OF NEW BERN TO US 70. | HIGHWAY | 2 | NEW BERN AREA MPO | R-2301A | PRE-STI (TRANSITION) | NHP |  |  |  |  | 2009 | 3713000 |  |  | 3713000 | COMPLETE. GARVEE BOND FUNDING $33.9 MILLION; PAYBACK FY 2009-2020.
CRAVEN | US 17 NEW BERN BYPASS | US 70 TO US 17 NORTH OF NEW BERN. | HIGHWAY | 2 | DOWN EAST RPO, NEW BERN AREA MPO | R-2301B | NOT FUNDED | T | NOT FUNDED | 15800000 |  |  | NOT FUNDED | 146000000 |  |  | 161800000
CRAVEN | US 70 | SLOCUMB ROAD AT CHERRY POINT MILITARY BASE. CONSTRUCT INTERCHANGE. | HIGHWAY | 2 | DOWN EAST RPO | R-5516 | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
CRAVEN | US 70 | SR 1124 (GRANTHAM ROAD) TO THE PROPOSED US 70 HAVELOCK BYPASS. UPGRADE ROADWAY TO FREEWAY. | HIGHWAY | 2 | NEW BERN AREA MPO | R-5777
CRAVEN | US 70 | TABERNA WAY. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 2 | NEW BERN AREA MPO | R-5777A | STATEWIDE MOBILITY | T | 2020 | 47438000 | 2020 | 300000 | 2020 | 46759000 |  |  | 94497000 | DESIGN BUILD PROJECT. LETTING TO BE COMBINED WITH R-5777B AND U-5713. UNDER CONSTRUCTION.
CRAVEN | US 70 | WEST THURMAN ROAD/EAST THURMAN ROAD. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 2 | NEW BERN AREA MPO | R-5777B | REGION B | T | 2020 | 47447000 | 2020 | 300000 | 2020 | 46759000 | 2020 | 105000 | 94611000 | DESIGN BUILD PROJECT. LETTING TO BE COMBINED WITH R-5777A AND U-5713. UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $84,124 FOR PE, $6,534.01 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE).
CRAVEN | US 70 | EAST OF THURMAN ROAD TO HAVELOCK BYPASS. UPGRADE ROADWAY TO FREEWAY AND CONSTRUCT SERVICE ROADS. | HIGHWAY | 2 | NEW BERN AREA MPO | R-5777C | STATEWIDE MOBILITY | T | 2023 | 29129000 | 2023 | 13344000 | 2023 | 225800000 |  |  | 268273000
CRAVEN | US 70 | SR 1124 (GRANTHAM ROAD) TO NEUSE RIVER BRIDGE. UPGRADE ROADWAY TO FREEWAY. | HIGHWAY | 2 | NEW BERN AREA MPO | U-5713 | STATEWIDE MOBILITY | T | 2020 | 94876000 | 2020 | 1000000 | 2020 | 140278000 |  |  | 236154000 | DESIGN BUILD PROJECT. LETTING TO BE COMBINED WITH R-5777A AND R-5777B. UNDER CONSTRUCTION.
CRAVEN | US 70 | SR 1309 (GLENBURNIE ROAD). IMPROVE INTERCHANGE. | HIGHWAY | 2 | NEW BERN AREA MPO | U-6102 | NOT FUNDED | T | NOT FUNDED | 2700000 | NOT FUNDED | 500000 | NOT FUNDED | 21200000 |  |  | 24400000
CRAVEN | US 70 (HAVELOCK BYPASS) | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | HIGHWAY | 2 | DOWN EAST RPO, NEW BERN AREA MPO | R-1015 | [11 empty] | UNDER CONSTRUCTION. GARVEE BOND FUNDING: $3.8 M; PAYBACK FY 2019 - 2033 FOR ROW, $2.2 M; PAYBACK FY 2019 - 2033 FOR UTILITIES, AND $100 M; PAYBACK FY 2019 - 2033 FOR CONSTRUCTION,
CRAVEN | US 70 (HAVELOCK BYPASS) | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | HIGHWAY | 2 | NEW BERN AREA MPO | R-1015DIV | DIVISION 2 | NHP, S(M) | 2019 | 2603000 | 2019 | 1517000 | 2019 | 114172000 |  |  | 118292000 | UNDER CONSTRUCTION. GARVEE BOND FUNDING: $3.8 M; PAYBACK FY 2019 - 2033 FOR ROW, $2.2 M; PAYBACK FY 2019 - 2033 FOR UTILITIES, AND $100 M; PAYBACK FY 2019 - 2033 FOR CONSTRUCTION,
CRAVEN | US 70 (HAVELOCK BYPASS) | NORTH OF PINE GROVE TO NORTH OF CARTERET COUNTY LINE. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | HIGHWAY | 2 | NEW BERN AREA MPO | R-1015REG | REGION B | NHP, S(M) | 2019 | 2603000 | 2019 | 1517000 | 2019 | 105707000 |  |  | 109827000 | UNDER CONSTRUCTION. GARVEE BOND FUNDING: $3.8 M; PAYBACK FY 2019 - 2033 FOR ROW, $2.2 M; PAYBACK FY 2019 - 2033 FOR UTILITIES, AND $100 M; PAYBACK FY 2019 - 2033 FOR CONSTRUCTION,
CRAVEN | CARTS | TG-5026 LEASE OF TABLETS | PUBLIC TRANSIT | 2 | NEW BERN AREA MPO | TG-5026 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2022 | 0
CRAVEN | CARTS | TG-5122 SHORT RANGE PLANNING | PUBLIC TRANSIT | 2 | NEW BERN AREA MPO | TG-5122 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2023 | 0
CRAVEN | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | TA-5165 RURAL VEHICLE REPLACEMENT. | PUBLIC TRANSIT | 2 | NEW BERN AREA MPO | TA-5165 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 310000 | 310000 | FUNDS AUTHORIZED IN PROGRESS
CRAVEN | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | ADMINISTRATION | PUBLIC TRANSIT | 2 | DOWN EAST RPO | TK-6122 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 1356000 | 1356000 | FUNDS AUTHORIZED IN PROGRESS
CRAVEN | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | OPERATING ASSISTANCE | PUBLIC TRANSIT | 2 | NEW BERN AREA MPO | TO-5024 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2100000 | 2100000
CRAVEN | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | OPERATING ASSISTANCE | PUBLIC TRANSIT | 2 | NEW BERN AREA MPO | TO-5204 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 480000 | 480000 | FUNDS AUTHORIZED IN PROGRESS
CRAVEN | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | OPERATING ASSISTANCE | PUBLIC TRANSIT | 2 | DOWN EAST RPO | TO-6102 | PUBLIC TRANSIT | 5311, L | [6 empty] | 2020 | 344000 | 344000 | FUNDS AUTHORIZED IN PROGRESS
CRAVEN | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | SHORT RANGE PLANNING | PUBLIC TRANSIT | 2 | NEW BERN AREA MPO | TP-5122 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 30000 | 30000 | FUNDS AUTHORIZED IN PROGRESS
CRAVEN | CRAVEN AREA RURAL TRANSPORTATION SYSTEM | LEASE OF TABLETS | PUBLIC TRANSIT | 2 | NEW BERN AREA MPO | TT-5206 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 36000 | 36000 | FUNDS AUTHORIZED IN PROGRESS
CRAVEN | TRANSPORTATION SYSTEM CRAVEN AREA RURAL | MOBILITY MANAGEMENT | PUBLIC TRANSIT | 2 | NEW BERN AREA MPO | TC-5100 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 90000 | 90000 | FUNDS AUTHORIZED IN PROGRESS
CRAVEN | TRANSPORTATION SYSTEM CRAVEN AREA RURAL | PREVENTIVE MAINTENANCE | PUBLIC TRANSIT | 2 | NEW BERN AREA MPO | TG-5256 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 170000 | 170000 | FUNDS AUTHORIZED IN PROGRESS
CRAVEN | TRANSPORTATION SYSTEM CRAVEN AREA RURAL | ADA/PARATRANSIT | PUBLIC TRANSIT | 2 | NEW BERN AREA MPO | TG-5257 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 274000 | 274000 | FUNDS AUTHORIZED IN PROGRESS
CRAVEN, JOHNSTON, WAYNE, LENOIR, CARTERET, WAKE | US 70 | INSTALL BROADBAND FIBER ALONG US 70 FROM I-40 TO PORT OF MOREHEAD CITY. | HIGHWAY | 2, 4, 5 | DOWN EAST RPO, EASTERN CAROLINA RPO, NEW BERN AREA MPO, UPPER COASTAL PLAIN RPO, GOLDSBORO URBAN AREA MPO, CAPITAL AREA MPO | R-5777D | STATEWIDE MOBILITY | DP, T |  |  |  |  | 2021 | 26000000 |  |  | 26000000 | LETTING TO BE COMBINED WITH I-5986C, HO-0002A, HO-0002B, AND HO-0002C. DP FUNDS REPRESENT FEDERAL INFRA GRANT FUNDS.
CRAVEN, JONES | US 17 (NEW BERN BYPASS) | US 17 SOUTH OF NEW BERN TO US 17 NORTH OF NEW BERN. FOUR LANE DIVIDED FREEWAY ON NEW LOCATION. | HIGHWAY | 2 | NEW BERN AREA MPO, DOWN EAST RPO | R-2301 | [11 empty] | SECTION A COMPLETE, GARVEE BOND FUNDING $33.9 MILLION; PAYBACK FY 2009-2020
CRAVEN, JONES | US 70 (FUTURE I-42) | DOVER IN JONES COUNTY TO NEUSE RIVER BRIDGE IN NEW BERN. PAVEMENT REHABILITATION. | HIGHWAY | 2 | DOWN EAST RPO, NEW BERN AREA MPO | I-6002 | STATEWIDE MOBILITY | [10 empty] | COMPLETE
CUMBERLAND | FAYETTEVILLE REGIONAL AIRPORT (FAY) | REPLACE PERIMETER FENCING AND ROAD. | AVIATION | 6 | FAYETTEVILLE AREA MPO | AV-5734 | REGION C | O, T |  |  |  |  | 2023 | 3440000 |  |  | 3440000
CUMBERLAND | BIG CROSS CREEK GREENWAY | LITTLE CROSS CREEK TO SMITH LAKE IN FORT BRAGG. CONSTRUCT MULTI-USE TRAIL. | BIKE/PED | 6 | FAYETTEVILLE AREA MPO | EB-5541 | DIVISION 6 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY USING STBGDA FUNDS
CUMBERLAND | FAYETTEVILLE | CAPE FEAR RIVER GREENWAY, CLARK PARK SOUTH TO THE CAPE FEAR BOTANICAL GARDENS. CONSTRUCT SECOND PHASE OF AN OFF-ROAD MULTI-USE TRAIL. | BIKE/PED | 6 | FAYETTEVILLE AREA MPO | EB-4539 | PRE-STI (TRANSITION)
CUMBERLAND | FAYETTEVILLE | I-95 BUSINESS/US 301 TO THE SOUTH SIDE OF CSX RAIL LINE. | BIKE/PED | 6 | FAYETTEVILLE AREA MPO | EB-4539A | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
CUMBERLAND | FAYETTEVILLE | EXISTING TRAIL AT CLARK PARK TO NORTH SIDE OF CSX RAIL LINE. | BIKE/PED | 6 | FAYETTEVILLE AREA MPO | EB-4539BB | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
CUMBERLAND | FAYETTEVILLE | NORTH OF CSX RAIL LINE TO SOUTH OF CSX RAIL LINE. | BIKE/PED | 6 | FAYETTEVILLE AREA MPO | EB-4539BC | PRE-STI (TRANSITION) | L, TAANY |  |  |  |  | 2020 | 951000 |  |  | 951000 | UNDER CONSTRUCTION
CUMBERLAND | FAYETTEVILLE | CROSS CREEK PARKS CONNECTOR TRAIL, NC 24 (BRAGG BOULEVARD) TO RAY AVENUE IN FAYETTEVILLE. CONSTRUCT GREENWAY. | BIKE/PED | 6 | FAYETTEVILLE AREA MPO | EB-5907 | DIVISION 6 | L, TAANY | 2024 | 10000 |  |  | 2026 | 842000 | 2023 | 84000 | 936000
CUMBERLAND | LITTLE CROSS CREEK GREENWAY EXTENSION | FILTER PLANT DRIVE TO ROWAN STREET BRIDGE IN FAYETTEVILLE. CONSTRUCT MULTI-USE PATH. | BIKE/PED | 6 | FAYETTEVILLE AREA MPO | EB-5540 | DIVISION 6 | L, TAANY |  |  |  |  | 2023 | 480000 |  |  | 480000
CUMBERLAND | NC 59 (HOPE MILLS ROAD) | CONSTRUCT SIDEWALK FROM FAYETTEVILLE CITY LIMITS TO SUMAC CIRCLE. | BIKE/PED | 6 | FAYETTEVILLE AREA MPO | EB-6032 | DIVISION 6 | L, TADA |  |  |  |  | 2022 | 375000 |  |  | 375000 | UNDER CONSTRUCTION
CUMBERLAND | SPRING LAKE | CONSTRUCT GREENWAY TRAIL NEAR THE LITTLE RIVER IN THE TOWN OF SPRING LAKE. | BIKE/PED | 6 | FAYETTEVILLE AREA MPO | EB-6041 | DIVISION 6 | L, TADA |  |  |  |  | 2020 | 545000 |  |  | 545000
CUMBERLAND | SR 2251 (OWEN DRIVE) | US 301 TO SR 1007 (ALL AMERICAN EXPRESSWAY). CONSTRUCT SIDEWALK ON EAST SIDE. | BIKE/PED | 6 | FAYETTEVILLE AREA MPO | EB-5800 | DIVISION 6 | [10 empty] | COMPLETE
CUMBERLAND | US 401 (RAMSEY STREET) | CONSTRUCT SIDEWALK FROM SUMMERCHASE DRIVE TO SR 1611 (ANDREWS ROAD). | BIKE/PED | 6 | FAYETTEVILLE AREA MPO | EB-6031 | DIVISION 6 | L, TADA |  |  |  |  | 2021 | 85000 |  |  | 85000
CUMBERLAND | US 401 BYPASS (SKIBO ROAD) | CONSTRUCT SIDEWALK FROM RICHWOOD COURT TO NC 24 (BRAGG BOULEVARD). | BIKE/PED | 6 | FAYETTEVILLE AREA MPO | EB-6030 | DIVISION 6 | L, TADA | 2022 | 75000 |  |  | 2023 | 450000 | 2022 | 75000 | 600000
CUMBERLAND | FAYETTEVILLE | FAYETTEVILLE COMPUTERIZED TRAFFIC SIGNAL SYSTEM. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-5742 | REGION C | T |  |  |  |  | 2019 | 735000 |  |  | 735000 | COMPLETE. BUILD NC BOND FUNDING: $574,684 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE).
CUMBERLAND | FISHER ROAD | SR 1104 (STRICKLAND BRIDGE ROAD) TO NC 162 (BINGHAM DRIVE). WIDEN TO MULTI-LANES. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-6073 | DIVISION 6 | BGDA, S(M) | 2026 | 17600000 | 2026 | 2138000 | 2028 | 22300000 |  |  | 42038000
CUMBERLAND | I-295 | SOUTH OF SR 1118 (PARKTON ROAD) TO SOUTH OF SR 1003 (CAMDEN ROAD). | HIGHWAY | 6 | FAYETTEVILLE AREA MPO, LUMBER RIVER RPO | U-2519AB | REGION C | [10 empty] | DESIGN BUILD PROJECT. WORK BEING ACCOMPLISHED UNDER U-2519AA.
CUMBERLAND | I-295 | SOUTH OF SR 1003 (CAMDEN ROAD) TO SOUTH OF SR 1104 (STRICKLAND BRIDGE ROAD). | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-2519BA | REGION C | NHP |  |  |  |  | 2022 | 118747000 |  |  | 118747000 | UNDER CONSTRUCTION
CUMBERLAND | I-295 | SOUTH OF SR 1104 (STRICKLAND BRIDGE ROAD) TO SOUTH OF US 401. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-2519BB | REGION C | NHP |  |  |  |  | 2022 | 55880000 |  |  | 55880000 | UNDER CONSTRUCTION
CUMBERLAND | I-295 | SOUTH OF US 401 TO SOUTH OF SR 1400 (CLIFFDALE ROAD). | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-2519CA | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION - DESIGN BUILD PROJECT
CUMBERLAND | I-295 | SOUTH OF SR 1400 (CLIFFDALE ROAD) TO EAST OF SR 1415 (YADKIN ROAD). | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-2519CB | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
CUMBERLAND | I-295 | EAST OF SR 1415 (YADKIN ROAD) TO WEST OF NC24/NC 87 (BRAGG BOULEVARD). | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-2519DA | [11 empty] | COMPLETE
CUMBERLAND | I-295 (FAYETTEVILLE OUTER LOOP) | WEST OF NC 24/NC 87 (BRAGG BOULEVARD) TO I-95. FREEWAY ON NEW LOCATION WITH STRUCTURE OVER THE CAPE FEAR RIVER. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | X-0002
CUMBERLAND | I-295 FAYETTEVILLE OUTER LOOP | WEST OF NC 24/NC 87 (BRAGG BOULEVARD) TO NC 210 (MURCHISON ROAD). - GRADING AND STRUCTURES | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | X-0002B | [11 empty] | COMPLETE
CUMBERLAND | I-295 FAYETTEVILLE OUTER LOOP | WEST OF NC 24/NC 87 (BRAGG BOULEVARD) TO NC 210 (MURCHISON ROAD). PAVING | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | X-0002BB | [11 empty] | COMPLETE
CUMBERLAND | I-295 FAYETTEVILLE OUTER LOOP | NC 210 (MURCHISON ROAD) TO 1.1 MILES EAST OF NC 210. GRADING AND STRUCTURES | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | X-0002BC | [11 empty] | COMPLETE
CUMBERLAND | I-295 FAYETTEVILLE OUTER LOOP | 1.1 MILES EAST OF NC 210 (MURCHISON ROAD) TO EAST OF SR 1600 (MCARTHUR ROAD). GRADING AND STRUCTURES | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | X-0002CA | [11 empty] | COMPLETE
CUMBERLAND | I-295 FAYETTEVILLE OUTER LOOP | EAST OF SR 1600 (MCARTHUR ROAD) TO US 401. - GRADING AND STRUCTURES | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | X-0002CB | [11 empty] | COMPLETE
CUMBERLAND | I-295 FAYETTEVILLE OUTER LOOP | EAST OF SR 1007 (ALL AMERICAN FREEWAY) TO EAST OF US 401 (RAMSEY STREET). PAVING | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | X-0002CC | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
CUMBERLAND | I-295 FAYETTEVILLE OUTER LOOP | WEST OF US 401 TO EAST OF SR 1714 (RIVER ROAD). | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | X-0002DA | [11 empty] | COMPLETE
CUMBERLAND | I-295 FAYETTEVILLE OUTER LOOP | EAST OF SR 1714 (RIVER ROAD) TO WEST OF US 301. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | X-0002DB | [11 empty] | COMPLETE
CUMBERLAND | I-295 FAYETTEVILLE OUTER LOOP | CONNECTOR FROM US 301 TO US 13. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | X-0002DC | [11 empty] | COMPLETE
CUMBERLAND | I-295 FAYETTEVILLE OUTER LOOP | WEST OF US 301 TO EAST OF I-95. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | X-0002DD | [11 empty] | COMPLETE
CUMBERLAND | I-295 FAYETTEVILLE OUTER LOOP | SR 1714 (RIVER ROAD) TO WEST OF US 301. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | X-0002DF | [11 empty] | COMPLETE
CUMBERLAND | I-295 FAYETTEVILLE OUTER LOOP | EAST OF NORFOLK SOUTHERN RAILWAY TO SR 1714 (RIVER ROAD). | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | X-0002E | [11 empty] | COMPLETE
CUMBERLAND | I-295 FAYETTEVILLE OUTER LOOP | ITS FOR FAYETTEVILLE OUTER LOOP. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | X-0002F | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
CUMBERLAND | I-95 | I-95 FROM THE ROBESON COUNTY LINE TO NC 53/210. PAVEMENT REHABILITATION. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | HI-0021 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2026 | 8000000 |  |  | 8000000
CUMBERLAND | I-95 | I-95 FROM NC 53 TO I-95 BUSINESS / US 301. PAVEMENT REHABILITATION. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | HI-0022 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2026 | 5800000 |  |  | 5800000
CUMBERLAND | I-95 BUSINESS/US 301 | NC 87 SOUTH TO NC 59. SAFETY IMPROVEMENTS. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | W-5519 | REGION C | [10 empty] | COMPLETE
CUMBERLAND | NC 210 (MURCHISON ROAD) | I-295 TO SOUTH OF US 401 BYPASS. ADD ADDITIONAL LANES. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-4900 | EXEMPT | BGDA, S(M) | 2023 | 10600000 | 2023 | 15000000 | 2025 | 23300000 |  |  | 48900000 | PROJECT IS IN EXEMPT CATEGORY BECAUSE STP-DA FUNDS ARE BEING USED ON REGIONAL CATEGORY PROJECT
CUMBERLAND | NC 210 (MURCHISON ROAD) | LANGDON STREET TO US 401 BYPASS. MODERNIZE ROADWAY. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-5015 | NOT FUNDED | T | NOT FUNDED | 14900000 | NOT FUNDED | 2200000 | NOT FUNDED | 8300000 |  |  | 25400000
CUMBERLAND | NC 24 | REPLACE BRIDGE 250144 OVER SOUTH RIVER. | HIGHWAY | 6 | MID-CAROLINA RPO | B-5708 | STATEWIDE MOBILITY | T | 2026 | 204000 | 2026 | 56000 | 2027 | 4080000 |  |  | 4340000
CUMBERLAND | NC 24 | WEST OF SR 1006 (MAXWELL ROAD/CLINTON ROAD) IN CUMBERLAND COUNTY TO SR 1853 (JOHN NUNNERY ROAD). | HIGHWAY | 6 | MID-CAROLINA RPO, FAYETTEVILLE AREA MPO | R-2303A | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
CUMBERLAND | NC 24 (BRAGG BOULEVARD) | US 401 (SKIBO ROAD) TO GLENVILLE AVENUE. MEDIAN AND GUARDRAIL REPLACEMENT, ADD PEDESTRIAN SIGNALS, RESURFACE PAVEMENT. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-6229 | DIVISION 6 | HSIP, T |  |  | 2022 | 10131000 | 2023 | 7200000 |  |  | 17331000
CUMBERLAND | NC 24 (NORTH BRAGG BOULEVARD) | SR 1451 (MANCHESTER ROAD). CONSTRUCT INTERCHANGE. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-5930 | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 22400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 67500000 |  |  | 97400000
CUMBERLAND | NC 24 / NC 87 | SR 1451 (MANCHESTER ROAD) TO NC 210 (LILLINGTON HIGHWAY). IMPROVE EXISTING MULTI-LANE FACILITY BY ADDING ACCESS MANAGEMENT AND OTHER IMPROVEMENTS. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-5802 | DIVISION 6 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 33200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 25100000 |  |  | 63100000
CUMBERLAND | NC 24/NC 210 | REPLACE BRIDGE 250116 OVER CSX RAILROAD, NORFOLK SOUTHERN RAILROAD, AND HILLSBORO STREET. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | B-4490 | STATEWIDE MOBILITY | [10 empty] | COMPLETE
CUMBERLAND | NC 53 (CEDAR CREEK ROAD) | NC 53 (CEDAR CREEK ROAD) FROM JUST NORTH OF PLYMOUTH STREET TO JUST SOUTH OF TROY DRIVE. INSTALL MEDIAN WITH SOUTHBOUND U-TURN AND BULB-OUT, SIDEWALK, AND RECTANGULAR RAPID FLASHING BEACON PEDESTRIAN CROSSING WITH REFUGE IN FAYETTEVILLE. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | HS-2006C | DIVISION 6 | HSIP | 2023 | 37000 |  |  | 2024 | 1142000 |  |  | 1179000
CUMBERLAND | NC 59 | REPLACE BRIDGE 250022 OVER I-95 BUSINESS/US 301. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | B-4491 | REGION C | NHPB |  |  |  |  | 2018 | 3533000 |  |  | 3533000 | COMPLETE
CUMBERLAND | NC 59 (NORTH MAIN STREET) | REPLACE EXISTING SIDEWALK AND CONSTRUCT NEW SIDEWALK ALONG NC 59 (NORTH MAIN STREET) IN HOPE MILLS. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | HL-0036 | DIVISION 6 | L, TADA |  |  |  |  | 2022 | 449000 | 2021 | 50000 | 499000
CUMBERLAND | NC 59 (SOUTH MAIN STREET) | SR 1243 (SHIPMAN ROAD) TO SR 1118 (PARKTON ROAD). WIDEN TO THREE LANES. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-6001 | REGION C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1028000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10699000 |  |  | 12427000
CUMBERLAND | SR 1003 (CAMDEN ROAD) | NC 59 (HOPE MILLS ROAD) TO SR 1007 (OWEN DRIVE) IN FAYETTEVILLE. WIDEN ROADWAY TO MULTI-LANES, PART ON NEW LOCATION. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-2810
CUMBERLAND | SR 1003 (CAMDEN ROAD) | NC 59 (HOPE MILLS ROAD) TO NC 162 (HOPE MILLS BYPASS). | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-2810A | [11 empty] | COMPLETE
CUMBERLAND | SR 1003 (CAMDEN ROAD) | NC 162 (HOPE MILLS BYPASS TO EAST OF CSX RAILROAD. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-2810B | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
CUMBERLAND | SR 1003 (CAMDEN ROAD) | EAST OF CSX RAILROAD TO SR 1007 (OWEN DRIVE). | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-2810C | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
CUMBERLAND | SR 1003 (CAMDEN ROAD) | PROPOSED FAYETTEVILLE OUTER LOOP (U-2519) TO NC 59 (HOPE MILLS ROAD) IN FAYETTEVILLE. WIDEN TO MULTI-LANES. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-3422 | DIVISION 6 | BGANY, T | 2021 | 9975000 | 2021 | 2825000 | 2024 | 36980000 |  |  | 49780000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $15,000,000 FOR CONSTRUCTION PAYBACK 2024 - 2038 (FY 2024 / YR 6 SALE)
CUMBERLAND | SR 1006 (PERSON STREET) | SR 1006 (PERSON STREET) FROM US 301 / I-95 BUSINESS (EASTERN BOULEVARD) TO JUST EAST OF WATER STREET. CONVERT SECTION FROM FOUR LANES TO THREE LANES WITH INTERSECTION IMPROVEMENTS AT BROAD STREET AND EASTERN BOULEVARD IN FAYETTEVILLE. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | HS-2006B | DIVISION 6 | HSIP |  |  |  |  | 2022 | 651000 |  |  | 651000 | UNDER CONSTRUCTION.
CUMBERLAND | SR 1007 (ALL AMERICAN FREEWAY) | SR 1151 (OWEN DRIVE) TO NORTH OF SR 1437 (SANTA FE DRIVE). ADD ADDITIONAL LANES. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-4414 | REGION C | NHP | 2028 | 1548000 | 2028 | 919000 | 2030 | 67100000 |  |  | 69567000
CUMBERLAND | SR 1102 (GILLIS HILL ROAD) | FROM NORTH OF SR 1112 (STONEY POINT ROAD) TO US 401 (RAEFORD ROAD). WIDEN TO MULTI-LANES AND REPLACE BRIDGE 250075 OVER LITTLE ROCKFISH CREEK. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-5798A | DIVISION 6 | T | 2020 | 3863000 | 2020 | 475000 | 2022 | 26036000 |  |  | 30374000 | UNDER CONSTRUCTION.
CUMBERLAND | SR 1104 (STRICKLAND BRIDGE ROAD) | US 401 TO FISHER ROAD. WIDEN ROADWAY. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-6210 | NOT FUNDED | T | NOT FUNDED | 15000000 | NOT FUNDED | 7900000 | NOT FUNDED | 22800000 |  |  | 45700000
CUMBERLAND | SR 1112 (ROCKFISH ROAD) | STRICKLAND BRIDGE ROAD TO GOLFVIEW ROAD. WIDEN TO MULTI-LANES. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-6072
CUMBERLAND | SR 1112 (ROCKFISH ROAD) | SR 1102 (GILLIS HILL ROAD) TO CAMDEN ROAD. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-6072A | NOT FUNDED | T | NOT FUNDED | 13600000 | NOT FUNDED | 4960000 | NOT FUNDED | 24500000 |  |  | 43060000
CUMBERLAND | SR 1112 (ROCKFISH ROAD) | CAMDEN ROAD TO GOLFVIEW ROAD. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-6072B | NOT FUNDED | T | NOT FUNDED | 10400000 | NOT FUNDED | 1100000 | NOT FUNDED | 4300000 |  |  | 15800000
CUMBERLAND | SR 1112 (ROCKFISH ROAD) SR 1115 (GOLFVIEW ROAD) | SR 1112 (ROCKFISH ROAD) FROM SR 1115 (GOLFVIEW ROAD) TO NC 59 (MAIN STREET) AND SR 1115 (GOLFVIEW ROAD) FROM SR 1112 (ROCKFISH ROAD) TO NC 59 (MAIN STREET). WIDEN TO MULTI-LANES. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-4709 | DIVISION 6 | T | 2022 | 9556000 | 2022 | 1575000 | 2023 | 13700000 |  |  | 24831000 | RIGHT-OF-WAY IN PROGRESS.
CUMBERLAND | SR 1219 (IRELAND DRIVE) | SR 1141 (CUMBERLAND ROAD) TO US 401 (RAEFORD ROAD). WIDEN ROADWAY. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-6213 | NOT FUNDED | T | NOT FUNDED | 16600000 | NOT FUNDED | 19750000 | NOT FUNDED | 22500000 |  |  | 58850000
CUMBERLAND | SR 1400 (CLIFFDALE ROAD) | MCPHERSON CHURCH ROAD TO SR 1404 (MORGANTON ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-4404 | DIVISION 6 | T | 2028 | 4392000 | 2028 | 1020000 | 2030 | 10400000 |  |  | 15812000
CUMBERLAND | SR 1400 (CLIFFDALE ROAD) | SR 1411 (BUNCE ROAD) TO MCPHERSON CHURCH ROAD. ACCESS MANAGEMENT. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-6209 | DIVISION 6 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 32300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 17300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 36400000 |  |  | 86000000
CUMBERLAND | SR 1415 (YADKIN ROAD) | SR 1415 (YADKIN ROAD) AT US 401 (SKIBO ROAD), AT SR 1437 (SANTE FE DRIVE), AND AT SOUTHWICK DRIVE. ADD SIGNALIZED PEDESTRIAN CROSSINGS TO ALL THREE INTERSECTIONS AND UPGRADE SIGNAL AT SOUTHWICK DRIVE. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | HS-2006A | DIVISION 6 | HSIP |  |  |  |  | 2023 | 213000 |  |  | 213000
CUMBERLAND | SR 1437 (SHAW RD) | NC 24/87 (BRAGG BLVD) TO NC 210 (MURCHISON ROAD). INTERCONNECT AND WIDEN TO MULTI-LANES. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-5101A | DIVISION 6 | T | 2026 | 22090000 | 2026 | 9167000 | 2028 | 36600000 |  |  | 67857000 | BUILD NC BOND FUNDING: $15,000,000 FOR RIGHT OF WAY AND $5,000,000 FOR UTILITIES PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE).
CUMBERLAND | SR 1437 (SHAW ROAD) SR 1614 (SHAW MILL ROAD) SR 16 | NC 24/87 (BRAGG BLVD) TO US 401 (RAMSEY STREET). WIDEN ROADWAY AND CONSTRUCT PART ON NEW LOCATION. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-5101 | DIVISION 6
CUMBERLAND | SR 1614 (SHAW MILL RD)-SR 1615 (ROSEHILL RD-STACEY | NC 210 (MURCHISON ROAD) TO US 401 (RAMSEY STREET). INTERCONNECT AND WIDEN TO MULTI-LANES. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-5101B | NOT FUNDED | T | NOT FUNDED | 38500000 | NOT FUNDED | 21445000 | NOT FUNDED | 36300000 |  |  | 96245000
CUMBERLAND | SR 1615 (ROSEHILL ROAD) | SR 1615 (ROSEHILL ROAD) AT TAMARACK DRIVE AND SR 1615 (ROSEHILL ROAD) AT LANDAU ROAD. CONSTRUCT MINI-ROUNDABOUTS. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | W-5806C | DIVISION 6 | HSIP | 2021 | 75000 |  |  | 2023 | 772000 |  |  | 847000 | RIGHT-OF-WAY IN PROGRESS.
CUMBERLAND | SR 1716 (JACKIE LEE ROAD) | REPLACE BRIDGE 250091 OVER WADE CANAL. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | HB-0010 | DIVISION 6 | BGOFF | 2024 | 120000 |  |  | 2025 | 1200000 |  |  | 1320000
CUMBERLAND | SR 1835 (ROCK HILL ROAD) | SR 1835 (ROCK HILL ROAD) AT SR 1838 (DUNN ROAD) IN EASTOVER. REALIGN SR 1838 (DUNN ROAD) TO FORM A T-INTERSECTION WITH SR 1835 (ROCK HILL ROAD) AND REMOVE SLIP LANES. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | HS-2006G | DIVISION 6 | HSIP |  |  |  |  | 2023 | 336000 |  |  | 336000
CUMBERLAND | SR 2030 (HOLLOW BRIDGE ROAD) | REPLACE BRIDGE 250044 OVER SANDY CREEK AND BRIDGE 250043 OVER SANDY CREEK OVERFLOW. | HIGHWAY | 6 | MID-CAROLINA RPO | B-6009 | DIVISION 6 | [10 empty] | COMPLETE
CUMBERLAND | SR 2217 (CLARK WEST ROAD) | EXTEND SR 2217(CLEARWATER ROAD) TO ACCESS PROPOSED CAMPBELL SOUP COMPANY DEVELOPMENT. ECONOMIC DEVELOPMENT PROJECT. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-6097 | DIVISION 6 | T |  |  |  |  | 2019 | 1457000 |  |  | 1457000 | ECONOMIC DEVELOPMENT PROJECT - UNDER CONSTRUCTION
CUMBERLAND | US 401 | US 401 BYPASS TO NORTH OF SLOCUMB ROAD. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-4403C | DIVISION 6 | T | 2026 | 27001000 | 2026 | 26328000 | 2029 | 34700000 |  |  | 88029000 | BUILD NC BOND FUNDING: $17,000,000 FOR RIGHT OF WAY AND $16,000,000 FOR UTILITIES PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE).
CUMBERLAND | US 401 (RAEFORD ROAD) | SR 3569 (OLD RAEFORD ROAD) TO EAST OF SR 3828 (ROBESON STREET) IN FAYETTEVILLE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-4405 | DIVISION 6 | [10 empty] | RIGHT OF WAY IN PROGRESS
CUMBERLAND | US 401 (RAEFORD ROAD) | OLD RAEFORD ROAD TO EAST OF BUNCE ROAD | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-4405A | DIVISION 6 | BGANY |  |  |  |  | 2022 | 41125000 |  |  | 41125000
CUMBERLAND | US 401 (RAEFORD ROAD) | EAST OF BUNCE ROAD TO EAST OF GLENSFORD DRIVE | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-4405B | DIVISION 6 | BGANY |  |  |  |  | 2023 | 23099000 |  |  | 23099000
CUMBERLAND | US 401 (RAEFORD ROAD) | EAST OF GLENSFORD DRIVE TO EAST OF ROBESON STREET. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-4405C | DIVISION 6 | BGANY |  |  |  |  | 2024 | 41400000 |  |  | 41400000
CUMBERLAND | US 401 (RAMSEY STREET) | US 401 BUSINESS (MARTIN LUTHER KING, JR. FREEWAY) TO NORTH OF SLOCUMB ROAD. WIDEN TO MULTI-LANES. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-4403
CUMBERLAND | US 401 (ROBESON STREET) | US 401 (RAEFORD ROAD) TO WALTER STREET. ACCESS MANAGEMENT. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-6152 | NOT FUNDED | NHP | NOT FUNDED | 17500000 | NOT FUNDED | 19700000 | NOT FUNDED | 19900000 |  |  | 57100000
CUMBERLAND | US 401 BUSINESS | NC 24/210 (GROVE STREET) TO US 401 BUSINESS (MARTIN LUTHER KING, JR. FREEWAY). | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-4403A | NOT FUNDED | T | NOT FUNDED | 3121000 |  |  | NOT FUNDED | 7400000 |  |  | 10521000
CUMBERLAND | US 401 BUSINESS | US 401 BUSINESS (MARTIN LUTHER KING, JR. FREEWAY) TO US 401 BYPASS. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-4403B | REGION C | NHP | 2027 | 10124000 | 2027 | 12020000 | 2029 | 33001000 |  |  | 55145000
CUMBERLAND | US 401 BUSINESS (SKIBO ROAD) | SR 1400 (CLIFFDALE ROAD). IMPROVE INTERSECTION | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-6133 | REGION C | T | 2028 | 7900000 | 2028 | 1100000 | 2030 | 6900000 |  |  | 15900000
CUMBERLAND | VARIOUS | DIVISION 6 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | W-5206DIV | DIVISION 6
CUMBERLAND | VARIOUS | DIVISION 6 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | W-5206SW | STATEWIDE MOBILITY
CUMBERLAND | CUMBERLAND COUNTY | ADMINISTRATION | PUBLIC TRANSIT | 6 | MID-CAROLINA RPO | TK-6123 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 320000 | 320000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | REPLACEMENT - LIGHT TRANSIT VEHICLE | PUBLIC TRANSIT | 6 | FAYETTEVILLE AREA MPO | TA-4743A | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2021 | 225000 | 225000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | REPLACEMENT - PARATRANSIT VAN | PUBLIC TRANSIT | 6 | FAYETTEVILLE AREA MPO | TA-4743B | PUBLIC TRANSIT | 5307, 5339, L, S | [6 empty] | 2021 | 1850000 | 1850000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | REPLACEMENT BUS | PUBLIC TRANSIT | 6 | FAYETTEVILLE AREA MPO | TA-4948A | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 2750000 | 2750000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | ELDERLY AND DISABLED PROJECTS (NON-TRADITIONAL) | PUBLIC TRANSIT | 6 | FAYETTEVILLE AREA MPO | TA-5139 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2020 | 500000 | 500000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | EXPANSION BUS. | PUBLIC TRANSIT | 6 | FAYETTEVILLE AREA MPO | TA-6685 | DIVISION 6 | FEDT, L, T |  |  |  |  | 2026 | 490000 |  |  | 490000
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | OPERATING ASSISTANCE | PUBLIC TRANSIT | 6 | FAYETTEVILLE AREA MPO | TO-5132 | PUBLIC TRANSIT | SMAP | [6 empty] | 2020 | 2136000 | 2136000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | OPERATING ASSISTANCE (LESS THAN 75 BUSES) MAP 21 | PUBLIC TRANSIT | 6 | FAYETTEVILLE AREA MPO | TO-5144 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 1600000 | 1600000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | PLANNING ASSISTANCE - 5303 | PUBLIC TRANSIT | 6 | FAYETTEVILLE AREA MPO | TP-5103 | PUBLIC TRANSIT | 5303, L, S | [6 empty] | 2020 | 264000 | 264000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | PLANNING ASSISTANCE - 5307 | PUBLIC TRANSIT | 6 | FAYETTEVILLE AREA MPO | TP-5103B | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 1800000 | 1800000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | ELDERLY AND DISABLED PROJECTS (TRADITIONAL) | PUBLIC TRANSIT | 6 | FAYETTEVILLE AREA MPO | TQ-6514 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2020 | 624000 | 624000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | SAFETY & SECURITY - MIN. 1% SET ASIDE | PUBLIC TRANSIT | 6 | FAYETTEVILLE AREA MPO | TS-5109 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 120000 | 120000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | TECHNOLOGY - REPLACEMENT UPGRADES | PUBLIC TRANSIT | 6 | FAYETTEVILLE AREA MPO | TT-5204 | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2022 | 50000 | 50000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | SYSTEM TRANSIT FAYETTEVILLE AREA | PREVENTIVE MAINTENANCE | PUBLIC TRANSIT | 6 | FAYETTEVILLE AREA MPO | TG-5224A | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 6000000 | 6000000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | SYSTEM TRANSIT FAYETTEVILLE AREA | ROUTINE CAPITAL | PUBLIC TRANSIT | 6 | FAYETTEVILLE AREA MPO | TG-5224C | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 840000 | 840000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | SYSTEM TRANSIT FAYETTEVILLE AREA | ROUTINE CAPITAL - SUPPORT VEHICLE | PUBLIC TRANSIT | 6 | FAYETTEVILLE AREA MPO | TG-5224D | PUBLIC TRANSIT | 5307, L | [6 empty] | 2022 | 100000 | 100000
CUMBERLAND | SYSTEM TRANSIT FAYETTEVILLE AREA | ROUTINE CAPITAL - ADA SERVICES | PUBLIC TRANSIT | 6 | FAYETTEVILLE AREA MPO | TG-5224E | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 363000 | 363000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND | SR 1714 (CHURCH STREET) | INSTALLATION OF ACTIVE WARNING DEVICES AT CSX CROSSING 629869Y IN WADE. | RAIL | 6 | MID-CAROLINA RPO | RX-2006A | DIVISION 6 | RR |  |  |  |  | 2023 | 800000 |  |  | 800000
CUMBERLAND, HARNETT | I-95 | I-95 BUSINESS/US 301 (EXIT 56) TO SR 1001 (LONG BRANCH ROAD - EXIT 71). WIDEN TO EIGHT LANES. | HIGHWAY | 6 | MID-CAROLINA RPO, FAYETTEVILLE AREA MPO | I-5986A | STATEWIDE MOBILITY | T | 2019 | 30400000 |  |  | 2019 | 375400000 |  |  | 405800000 | DESIGN BUILD PROJECT. LETTING TO BE COMBINED WITH I-5877. DP FUNDS REPRESENT FEDERAL INFRA GRANT FUNDS. UNDER CONSTRUCTION.
CUMBERLAND, HARNETT, HOKE, ROBESON | VARIOUS | FAYETTEVILLE URBAN AREA MPO TRANSPORTATION ALTERNATIVES PROGRAM. | BIKE/PED | 6, 8 | FAYETTEVILLE AREA MPO | U-5528 | DIVISION 6, 8 | TADA |  |  |  |  | 2020 | 16689000 |  |  | 16689000 | IN PROGRESS
CUMBERLAND, HARNETT, HOKE, ROBESON | VARIOUS | FAYETTEVILLE URBAN AREA METROPOLITAN PLANNING ORGANIZATION STBGDA RESERVE ACCOUNT. | HIGHWAY | 6, 8 | FAYETTEVILLE AREA MPO | HL-0026 | DIVISION 6, 8 | BGDA |  |  |  |  | 2022 | 57636000 |  |  | 57636000
CUMBERLAND, HARNETT, HOKE, ROBESON | VARIOUS | FAYETTEVILLE URBAN AREA PLANNING (PL) SUPPLEMENT. | HIGHWAY | 6, 8 | FAYETTEVILLE AREA MPO | U-5207 | DIVISION 6, 8 | BGDA, L | [6 empty] | 2020 | 2950000 | 2950000 | IN PROGRESS
CUMBERLAND, HARNETT, JOHNSTON | I-95 | I-95 BUSINESS/US 301 (EXIT 56) TO I-40 (EXIT 81). WIDEN TO EIGHT LANES. | HIGHWAY | 4, 6 | MID-CAROLINA RPO, FAYETTEVILLE AREA MPO, UPPER COASTAL PLAIN RPO | I-5986
CUMBERLAND, HOKE | SR 1102 (GILLIS HILL ROAD) | US 401 (RAEFORD ROAD) TO SR 1418 (LINDSAY ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 6, 8 | FAYETTEVILLE AREA MPO | U-5798 | DIVISION 6, 8 | [10 empty] | COORDINATE WITH U-5707, U-5753, U-5857, AND U-5858
CUMBERLAND, HOKE | SR 1102 (GILLIS HILL ROAD) | FROM SR 1418 (LINDSAY ROAD) TO NORTH OF SR 1112 (STONEY POINT ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 6, 8 | FAYETTEVILLE AREA MPO | U-5798B | DIVISION 6, 8 | T | 2023 | 2437000 | 2023 | 715000 | 2025 | 11600000 |  |  | 14752000
CUMBERLAND, MOORE, ANSON, HOKE, RICHMOND, UNION | COACH AMERICA | INTERCITY BUS - CHARLOTTE TO WILMINGTON | PUBLIC TRANSIT | 6, 8, 10 |  | TI-6102 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 2584000 | 2584000 | FUNDS AUTHORIZED IN PROGRESS
CUMBERLAND, ROBESON | I-295 | ITS FOR FAYETTEVILLE OUTER LOOP. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO, LUMBER RIVER RPO | U-2519F | STATEWIDE MOBILITY | NHP |  |  |  |  | 2025 | 3448000 |  |  | 3448000
CUMBERLAND, ROBESON | I-295 (FAYETTEVILLE OUTER LOOP) | I-95 SOUTH OF FAYETTEVILLE TO WEST OF NC 24/87 (BRAGG BOULEVARD). FREEWAY ON NEW LOCATION. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO, LUMBER RIVER RPO | U-2519 | [11 empty] | SEGMENT AA: GARVEE BOND FUNDING $111 M; PAYBACK FY 2018 - 2032 FOR CONSTRUCTION;
CURRITUCK | NEW ROUTE | MID-CURRITUCK BRIDGE, COINJOCK TO COROLLA. NEW STRUCTURE OVER CURRITUCK SOUND AND UPGRADE APPROACHES. | HIGHWAY | 1 | ALBEMARLE RPO | R-2576 | DIVISION 1 | BGLT5, BOND R, S(M) | 2024 | 16496000 | 2024 | 17412000 | 2024 | 434004000 |  |  | 467912000 | DESIGN BUILD PROJECT - NORTH CAROLINA TURNPIKE AUTHORITY PROJECT - GARVEE BOND FUNDING CON $130M PAYBACK FY 2024-2038.
CURRITUCK | US 158 | REHABILITATE BRIDGE 260016 OVER CURRITUCK SOUND. | HIGHWAY | 1 | ALBEMARLE RPO | B-5937 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
CURRITUCK | US 158 | CONSTRUCT A ROUNDABOUT AT US 158 AND SR 1147 (INDIANTOWN ROAD). | HIGHWAY | 1 | ALBEMARLE RPO | HS-2001A | REGION A | HSIP | 2022 | 20000 |  |  | 2023 | 450000 |  |  | 470000
CURRITUCK, CAMDEN | US 158 (SHORTCUT ROAD) | EAST OF NC 34 (SHAWBORO ROAD) AT BELCROSS IN CAMDEN COUNTY TO US 158/NC 168 (CARATOKE HIGHWAY) IN CURRITUCK COUNTY. WIDEN TO MULTI-LANES. | HIGHWAY | 1 | ALBEMARLE RPO | R-2574 | REGION A | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 24152000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5176000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 76200000 |  |  | 105528000
CURRITUCK, DARE, BERTIE, CAMDEN, CHOWAN, GATES, HERTFORD, HYDE, MARTIN, NORTHAMPTON, PASQUOTANK, PERQUIMANS, TYRRELL, WASHINGTON | VARIOUS | ECOSYSTEMS ENHANCEMENT PROGRAM FOR DIVISION 1 PROJECT MITIGATION. | HIGHWAY | 1 | ALBEMARLE RPO, PEANUT BELT RPO, MID-EAST RPO | EE-4901 | [11 empty] | COMPLETE
DARE | US 158 | CYPRESS KNEE LANE TO JEJAC STREET IN KITTY HAWK. CONSTRUCT SIDEWALK ON WEST SIDE. | BIKE/PED | 1 | ALBEMARLE RPO | EB-5848 | DIVISION 1 | L, TALT5 |  |  |  |  | 2025 | 1280000 |  |  | 1280000
DARE | NC 12 | HATTERAS PARKING LOT IMPROVEMENTS AND CONNECTIVITY MEASURES, HATTERAS LOADING FACILITY | FERRY | 1 | ALBEMARLE RPO | F-5702A | DIVISION 1 | [10 empty] | COMPLETE - WORK ACCOMPLISHED UNDER F-5702B.
DARE | NC 12 | REPLACE BRIDGE 270011 (HERBERT C. BONNER BRIDGE) OVER OREGON INLET AND NC 12 IMPROVEMENTS. | HIGHWAY | 1 | ALBEMARLE RPO | B-2500 | PRE-STI (TRANSITION)
DARE | NC 12 | PHASE II, SHORT-TERM IMPROVEMENTS AT PEA ISLAND. | HIGHWAY | 1 | ALBEMARLE RPO | B-2500AB | PRE-STI (TRANSITION) | [10 empty] | COMPLETED
DARE | NC 12 | PHASE II, LONG-TERM IMPROVEMENTS AT RODANTHE. | HIGHWAY | 1 | ALBEMARLE RPO | B-2500B | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
DARE | NC 12 | REPLACE BRIDGE 270008 OVER CANAL OF PAMLICO SOUND IN HATTERAS | HIGHWAY | 1 | ALBEMARLE RPO | B-5610 | REGION A | NHPB | 2021 | 70000 | 2021 | 440000 | 2023 | 1404000 |  |  | 1914000 | RIGHT-OF-WAY IN PROGRESS.
DARE | SR 1208 (WEST KITTY HAWK ROAD) | SR 1210 (BOB PERRY ROAD) TO IVY LANE. UPGRADE FACILITY AND REPLACE BRIDGE 270040. | HIGHWAY | 1 | ALBEMARLE RPO | R-5738 | DIVISION 1 | T |  |  |  |  | 2019 | 4646000 |  |  | 4646000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,561,232 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE)
DARE | SR 1217 (COLLINGTON ROAD) | DEAD END TO US 158 (CROATON HIGHWAY) IN KILL DEVIL HILLS. OPERATIONAL-SAFETY IMPROVEMENTS. | HIGHWAY | 1 | ALBEMARLE RPO | R-5014 | DIVISION 1 | BG5200 |  |  |  |  | 2022 | 22948000 |  |  | 22948000 | RIGHT-OF-WAY IN PROGRESS
DARE | US 158 | US 64-NC 12 TO EASTERN END OF CURRITUCK SOUND BRIDGE. ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 1 | ALBEMARLE RPO | R-3419 | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 20236000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9608000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 137000000 |  |  | 166844000
DARE | US 158 | NC 12. IMPROVE INTERSECTION. | HIGHWAY | 1 | ALBEMARLE RPO | R-4457 | NOT FUNDED | NHP | NOT FUNDED | 1100000 | NOT FUNDED | 400000 | NOT FUNDED | 5800000 |  |  | 7300000
DARE | US 64 | PRESERVATION OF BRIDGE 270009 ON US 64 IN MANNS HARBOR. | HIGHWAY | 1 | ALBEMARLE RPO | HB-0017 | REGION A | BFP |  |  |  |  | 2022 | 45000000 |  |  | 45000000
DARE | US 64 | EAST OF SR 1153 (OLD FERRY LANDING ROAD) TO US 264. WIDEN TO MULTI-LANES. | HIGHWAY | 1 | ALBEMARLE RPO | R-2544 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY
DARE | US 64 | EAST OF SR 1153 (OLD FERRY LANDING ROAD) TO WEST OF SR 1102 (EAST LAKE ROAD). | HIGHWAY | 1 | ALBEMARLE RPO | R-2544A | NOT FUNDED | T | NOT FUNDED | 1175000 | NOT FUNDED | 315000 | NOT FUNDED | 14700000 |  |  | 16190000
DARE | US 64 | WEST OF SR 1102 (EAST LAKE ROAD) TO EAST OF DARE COUNTY LANDFILL. | HIGHWAY | 1 | ALBEMARLE RPO | R-2544B | NOT FUNDED | T | NOT FUNDED | 1350000 | NOT FUNDED | 1401000 | NOT FUNDED | 23300000 |  |  | 26051000
DARE | US 64 | EAST OF DARE COUNTY LANDFILL TO US 264. | HIGHWAY | 1 | ALBEMARLE RPO | R-2544C | NOT FUNDED | T | NOT FUNDED | 300000 | NOT FUNDED | 1860000 | NOT FUNDED | 46200000 |  |  | 48360000
DARE | VARIOUS | DEPLOYMENT OF AUTOMATED SHUTTLE AT WRIGHT BROTHERS NATIONAL MEMORIAL. | HIGHWAY | 1 | ALBEMARLE RPO | R-5753A | EXEMPT | FLTP | [6 empty] | 2021 | 95000 | 95000
DARE | DARE COUNTY | ADMINISTRATION | PUBLIC TRANSIT | 1 | ALBEMARLE RPO | TK-6124 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 512000 | 512000 | FUNDS AUTHORIZED IN PROGRESS
DARE, CARTERET, HYDE | NC 12/US 70 | OUTER BANKS SCENIC BYWAY WAYSIDES AND INTERPRETIVE SIGNS. | HIGHWAY | 1, 2 | ALBEMARLE RPO, DOWN EAST RPO | S-5502 | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
DARE, HALIFAX | NC 12 | HATTERAS AND OCRACOKE DOCK IMPROVEMENTS | FERRY | 1, 4 | ALBEMARLE RPO | F-5702E | DIVISION 1, 4 | [10 empty] | UNDER CONSTRUCTION - WORK ACCOMPLISHED UNDER F-5702B.
DARE, HYDE | HATTERAS - SOUTH DOCK | CONSTRUCT PASSENGER FERRY. | FERRY | 1 | ALBEMARLE RPO | F-5706 | NOT FUNDED | T |  |  |  |  | NOT FUNDED | 6500000 |  |  | 6500000
DARE, HYDE | NC 12 | CONSTRUCT RIVER CLASS FERRY. | FERRY | 1 | ALBEMARLE RPO | F-5700 | DIVISION 1 | [10 empty] | COMPLETE
DARE, HYDE | NC 12 | HATTERAS FERRY DOCK IN DARE COUNTY TO OCRACOKE FERRY DOCKS IN HYDE COUNTY. CONSTRUCT TWO PASSENGER FERRIES TO BE USED ALONG NEW ROUTE. IMPLEMENT TRANSIT SYSTEM TO AID PASSENGERS ON OCRACOKE ISLAND. | FERRY | 1 | ALBEMARLE RPO | F-5702 | DIVISION 1 | [10 empty] | OTHER FUNDS ARE FROM STATE APPROPRIATION7355
DARE, HYDE | NC 12 | CONSTRUCT TWO PASSENGER FERRIES | FERRY | 1 | ALBEMARLE RPO | F-5702C | DIVISION 1 | [10 empty] | UNDER CONSTRUCTION
DARE, TYRRELL | US 64 | REPLACE BRIDGE NUMBER 7 OVER THE ALLIGATOR RIVER. | HIGHWAY | 1 | ALBEMARLE RPO | HB-0001 | NOT FUNDED | NHPB | NOT FUNDED | 436000 | NOT FUNDED | 129000 | NOT FUNDED | 262000000 |  |  | 262565000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY
DARE, TYRRELL | US 64 | WEST OF ALLIGATOR RIVER TO EAST OF SR 1153 (OLD FERRY LANDING ROAD). | HIGHWAY | 1 | ALBEMARLE RPO | R-2545B | NOT FUNDED | T | NOT FUNDED | 3175000 | NOT FUNDED | 1156000 | NOT FUNDED | 503100000 |  |  | 507431000
DAVIDSON | DAVIDSON COUNTY AIRPORT (EXX) | INSTALL RUNWAY 6 MEDIUM INTENSITY APPROACH LIGHTING SYSTEM WITH RUNWAY ALIGNMENT INDICATOR LIGHTS ACROSS I-85, INCLUDING INTERCHANGE LIGHTING. | AVIATION | 9 | HIGH POINT URBAN AREA MPO | AV-5749 | DIVISION 9 | T |  |  |  |  | 2019 | 4529000 |  |  | 4529000 | COMPLETE
DAVIDSON | DAVIDSON COUNTY AIRPORT (EXX) | UPGRADE AND STRENGTHEN RUNWAY TO ACCOMMODATE LARGER PRIVATE AIRCRAFT. | AVIATION | 9 | HIGH POINT URBAN AREA MPO | AV-5831 | DIVISION 9 | T |  |  |  |  | 2022 | 12816000 |  |  | 12816000 | UNDER CONSTRUCTION. TO BE LET WITH AV-5900
DAVIDSON | DAVIDSON COUNTY AIRPORT (EXX) | UPGRADE TAXIWAY AND APRON. | AVIATION | 9 | HIGH POINT URBAN AREA MPO | AV-5900 | DIVISION 9 | T |  |  |  |  | 2022 | 8600000 |  |  | 8600000 | TO BE LET WITH AV-5831
DAVIDSON | I-285 / US 52 / NC 8 | I-85 TO FORSYTH COUNTY LINE. PAVEMENT REHABILITATION. | HIGHWAY | 9 | HIGH POINT URBAN AREA MPO, WINSTON-SALEM URBAN AREA MPO | HI-0005 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2025 | 30147000 |  |  | 30147000
DAVIDSON | I-85 | NORTH OF NC 150 TO US 29-70-52/BUSINESS 85 IN DAVIDSON COUNTY | HIGHWAY | 9 | HIGH POINT URBAN AREA MPO | I-2304AD | PRE-STI (TRANSITION) | NHP | 2009 | 984000 | [6 empty] | 984000 | COMPLETE. GARVEE BOND FUNDING: $14.3 MILLION FOR RIGHT-OF-WAY, SECTIONS AC & AD, PAYBACK FY 2009-2021
DAVIDSON | I-85 | NORTH CAROLINA RAILROAD MP 327.4 - CURVE REALIGNMENT | HIGHWAY | 9 | HIGH POINT URBAN AREA MPO | I-2304AE | [11 empty] | COMPLETE
DAVIDSON | I-85 | SR 2205 (OLD US 64) TO 0.4 MILES NORTH OF US 64. PAVEMENT REHABILITATION. | HIGHWAY | 9 | HIGH POINT URBAN AREA MPO | I-5740 | STATEWIDE MOBILITY | [10 empty] | COMPLETE
DAVIDSON | I-85 | REHABILITATE BRIDGE 280181 AND BRIDGE 280182. | HIGHWAY | 9 | HIGH POINT URBAN AREA MPO | I-5740A | STATEWIDE MOBILITY | [10 empty] | COMPLETE
DAVIDSON | I-85 | I-285 / US 29 / US 52 / US 70 TO NORTH OF US 64. PAVEMENT REHABILITATION. | HIGHWAY | 9 | HIGH POINT URBAN AREA MPO | I-5950 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2022 | 14739000 |  |  | 14739000
DAVIDSON | NC 109 | NC 109 IN DENTON TO I-85 IN THOMASVILLE. WIDEN TO MULTILANES. | HIGHWAY | 9 | HIGH POINT URBAN AREA MPO | R-4734 | DIVISION 9 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1336000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 132096000 |  |  | 133932000
DAVIDSON | NC 109 | DENTON NORTHERN MUNICIPAL BOUNDARY TO SR 2067 (LAMBETH ROAD), AND SR 1798 (OLD GREENSBORO ROAD) / SR 1756 (WEST LEXINGTON AVENUE EXTENSION) TO SR 1711 (GUMTREE ROAD). INSTALL RUMBLE STRIPS AND LONG-LIFE PAVEMENT MARKINGS. | HIGHWAY | 9 | HIGH POINT URBAN AREA MPO | W-5809A | REGION D | HSIP |  |  |  |  | 2022 | 1100000 |  |  | 1100000 | UNDER CONSTRUCTION
DAVIDSON | NC 47 | REPLACE BRIDGE 280017 OVER SWEARING CREEK. | HIGHWAY | 9 | HIGH POINT URBAN AREA MPO | B-5780 | HIGHWAY FUND | [10 empty] | COMPLETE
DAVIDSON | NC 8 | REPLACE BRIDGE 280027 OVER US 29 / US 64 / US 70 / I-85 BUSINESS IN LEXINGTON. | HIGHWAY | 9 | HIGH POINT URBAN AREA MPO | B-3159 | REGION D | [10 empty] | COMPLETE
DAVIDSON | NC 8 (WINSTON ROAD) | 9TH STREET TO SR 1408 (BIESECKER ROAD) IN LEXINGTON. WIDEN TO MULTILANES. | HIGHWAY | 9 | HIGH POINT URBAN AREA MPO | U-5757 | REGION D | T | 2019 | 17575000 |  |  | 2024 | 8800000 |  |  | 26375000 | RIGHT-OF-WAY IN PROGRESS
DAVIDSON | SR 1508 (HICKORY TREE ROAD) | US 52 / NC 8 / FUTURE I-285 TO NC 150. WIDEN TO MULTILANES. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-5786 | DIVISION 9 | T | 2026 | 5000000 | 2026 | 5100000 | 2028 | 22000000 |  |  | 32100000
DAVIDSON | US 29 / US 70 | US 29 / US 70, VICINITY OF FLEET DARR ROAD WEST OF SR 2123 (LEXINGTON AVENUE) CONNECTOR. INSTALL DIRECTIONAL LEFTOVERS. | HIGHWAY | 9 | HIGH POINT URBAN AREA MPO | HS-2009C | REGION D | HSIP |  |  |  |  | 2026 | 500000 |  |  | 500000
DAVIDSON | US 29 / US 70 / BUSINESS 85 | REPLACE BRIDGE 280164 AND BRIDGE 280168 OVER NORFOLK SOUTHERN RAILROAD. | HIGHWAY | 9 | HIGH POINT URBAN AREA MPO | B-5783 | REGION D | BFP |  |  |  |  | 2023 | 5777000 |  |  | 5777000
DAVIDSON | US 29 / US 70 / BUSINESS 85 | SR 1798 (OLD GREENSBORO ROAD). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 9 | HIGH POINT URBAN AREA MPO | R-5737 | DIVISION 9 | T |  |  |  |  | 2022 | 29777000 |  |  | 29777000 | UNDER CONSTRUCTION; INCLUDES PARTICIPATION BY DAVIDSON COUNTY COMMUNITY COLLEGE
DAVIDSON | US 29 NB / US 64 EB / US 70 EB / BUSINESS 85 NB | REPLACE BRIDGE 280118 OVER SR 3346 (NORTH MAIN STREET) IN LEXINGTON. | HIGHWAY | 9 | HIGH POINT URBAN AREA MPO | B-5779 | REGION D | BFP | 2024 | 203000 | 2024 | 798000 | 2025 | 4061000 |  |  | 5062000
DAVIDSON | US 64 | SR 2112 (DECKER ROAD) TO RAIL CROSSING 836515Y. EXTEND LEFT TURN LANE AND CONSTRUCT RIGHT TURN LANE AT PROPOSED NEW ACCESS ROAD ACROSS FROM SR 2112, AND WIDEN CROSSING 836515Y. | HIGHWAY | 9 | HIGH POINT URBAN AREA MPO | HE-0008 | DIVISION 9 | T |  |  |  |  | 2023 | 800000 | 2022 | 200000 | 1000000 | ECONOMIC DEVELOPMENT PROJECT
DAVIDSON | US 64 | US 64 FROM SR 2782 (BOWERS ROAD TO EAST OF SR 2012 / SR 2227 (HEATH CHURCH ROAD / NEW BOWERS ROAD). CONSTRUCT 4 REDUCED CONFLICT INTERSECTIONS AND LEFT-OVER WITH U-TURN BULB EAST OF SR 2012 / SR 2227. | HIGHWAY | 9 | HIGH POINT URBAN AREA MPO | HS-2009B | REGION D | HSIP | 2023 | 30000 | 2023 | 20000 | 2023 | 1500000 |  |  | 1550000
DAVIDSON | US 64 | US 64, I-85 BUSINESS IN LEXINGTON TO EAST OF I-85. | HIGHWAY | 9 | HIGH POINT URBAN AREA MPO | R-2220A | [11 empty] | COMPLETE
DAVIDSON | US 64 | I-85 EAST OF LEXINGTON TO NC 109 | HIGHWAY | 9 | HIGH POINT URBAN AREA MPO | R-2220B | NOT FUNDED | T | NOT FUNDED | 30992000 | NOT FUNDED | 5635000 | NOT FUNDED | 40572000 |  |  | 77199000
DAVIDSON | VARIOUS | TRANSIT OPERATIONS SUPPORT FOR CITY OF LEXINGTON CIRCULATOR ROUTE AND THOMASVILLE / LEXINGTON CONNECTOR ROUTE. | HIGHWAY | 9 | HIGH POINT URBAN AREA MPO | C-5559 | EXEMPT | [10 empty] | IMPLEMENTATION BY DAVIDSON COUNTY - IN PROGRESS
DAVIDSON | DAVIDSON COUNTY | PREVENTIVE MAINTENANCE | PUBLIC TRANSIT | 9 | WINSTON-SALEM URBAN AREA MPO | TG-6808B | PUBLIC TRANSIT | 5307, L |  |  |  |  | 2020 | 408360000 |  |  | 408360000
DAVIDSON | DAVIDSON COUNTY | ROUTINE CAPITAL - PASSENGER SHELTERS, PASSENGER AMENITIESA, SHOP EQUIPMENT, SPARE PARTS, CAPITAL COST OF CONTRACTING, ETC. | PUBLIC TRANSIT | 9 | WINSTON-SALEM URBAN AREA MPO | TG-6809 | PUBLIC TRANSIT | 5307, L |  |  |  |  | 2020 | 204180000 |  |  | 204180000
DAVIDSON | DAVIDSON COUNTY | ADMINISTRATION | PUBLIC TRANSIT | 9 | PIEDMONT TRIAD RPO | TK-6125 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 836000 | 836000 | FUNDS AUTHORIZED IN PROGRESS
DAVIDSON | DAVIDSON COUNTY | OPERATING FUNIDING FOR DAVIDSON COUNTY TRANSPORATION FOR SERVICE IN THE HIGH POINT URBAN AREA - THROUGH NCDOT | PUBLIC TRANSIT | 9 | HIGH POINT URBAN AREA MPO | TO-5215 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 360000 | 360000 | FUNDS AUTHORIZED IN PROGRESS
DAVIDSON | DAVIDSON COUNTY | OPERATING ASSISTANCE | PUBLIC TRANSIT | 9 | WINSTON-SALEM URBAN AREA MPO | TO-6165 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 326688000 | 326688000
DAVIDSON | DAVIDSON COUNTY TRANSPORTATION SYSTEM | INSTALLING COVERED BUS SHELTERS WITH ADA ACCESS TO MAJOR STOPS SUCH AS WALMART AND BIG LOTS. INSTALL SIMME SEATS AT THE REMAINDER OF BUS STOPS. SIMME SEATS PROVIDE TWO SEATS ATTACHED TO THE BUS STOP SIGN POLE. | PUBLIC TRANSIT | 9 | WINSTON-SALEM URBAN AREA MPO | TL-0014 | DIVISION 9 | BGDA, L | [6 empty] | 2021 | 140000 | 140000
DAVIDSON | NCRR | LEXINGTON TRAIN STATION, CONSTRUCT TRACK IMPROVEMENTS AND MULTIMODAL PASSENGER RAIL AND BUS STATION IN THE LEXINGTON DEPOT DISTRICT. | RAIL | 9 | HIGH POINT URBAN AREA MPO | P-5732 | EXEMPT | DP, L | 2022 | 1160000 | 2022 | 500000 | 2022 | 10941000 |  |  | 12601000 | "DP" FUNDING REFLECTS FEDERAL RAILROAD ADMINISTRATION BUILD GRANT
DAVIDSON | NCRR / NORFOLK SOUTHERN MAIN LINE | SR 2165 (TURNER STREET) IN THOMASVILLE. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722327S. | RAIL | 9 | HIGH POINT URBAN AREA MPO | P-5751 | DIVISION 9 | O, T | 2028 | 5000000 |  |  | 2031 | 22001000 |  |  | 27001000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION
DAVIDSON | NORFOLK SOUTHERN | KIMBERLY CLARK IN LEXINGTON. CONSTRUCT LEAD. | RAIL | 9 | HIGH POINT URBAN AREA MPO | P-5722 | REGION D | O, T |  |  |  |  | 2024 | 2038000 |  |  | 2038000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION
DAVIDSON | NORFOLK SOUTHERN | CROSSING 722306Y (EAST 7TH AVENUE) IN LEXINGTON. CONSTRUCT GRADE SEPARATION IN VICINITY OF 5TH STREET AND CLOSE CROSSING 722306Y. | RAIL | 9 | HIGH POINT URBAN AREA MPO | P-5731 | DIVISION 9 | DP, O, T | 2022 | 5625000 |  |  | 2022 | 19795000 |  |  | 25420000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION; "DP" FUNDING REFLECTS FEDERAL RAILROAD ADMINISTRATION BUILD GRANT
DAVIDSON, ALAMANCE, CABARRUS, DURHAM, GUILFORD, MECKLENBURG, ORANGE, ROWAN, WAKE | PIEDMONT CORRIDOR | ACQUIRE AND REFURBISH 8 RAIL CARS. | RAIL | 5, 7, 9, 10 | CAPITAL AREA MPO, HIGH POINT URBAN AREA MPO, BURLINGTON-GRAHAM MPO, CABARRUS-ROWAN MPO, CHARLOTTE REGIONAL TPO, DURHAM-CHAPEL HILL-CARRBORO MPO, GREENSBORO URBAN AREA MPO | P-5719C | REGION C, D, E | DP, T |  |  |  |  | 2023 | 212528000 |  |  | 212528000
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | DIVISION 9 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | BIKE/PED | 9 | NORTHWEST PIEDMONT RPO, WINSTON-SALEM URBAN AREA MPO, HIGH POINT URBAN AREA MPO, CABARRUS-ROWAN MPO | BO-2409 | DIVISION 9 | S, TA |  |  |  |  | 2024 | 10000000 |  |  | 10000000
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 9. | HIGHWAY | 9 | NORTHWEST PIEDMONT RPO, WINSTON-SALEM URBAN AREA MPO, HIGH POINT URBAN AREA MPO, CABARRUS-ROWAN MPO | HS-2009 | DIVISION 9
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | VARIOUS SECONDARY ROUTES. INSTALL LONG-LIFE PAVEMENT MARKINGS. | HIGHWAY | 9 | CABARRUS-ROWAN MPO, HIGH POINT URBAN AREA MPO, NORTHWEST PIEDMONT RPO, WINSTON-SALEM URBAN AREA MPO | HS-2009A | DIVISION 9 | HSIP |  |  |  |  | 2021 | 1900000 |  |  | 1900000
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | DIVISION 9 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | HIGHWAY | 9 | NORTHWEST PIEDMONT RPO, WINSTON-SALEM URBAN AREA MPO, HIGH POINT URBAN AREA MPO, CABARRUS-ROWAN MPO | R-5789 | DIVISION 9 | S, TA |  |  |  |  | 2020 | 3600000 |  |  | 3600000 | IN PROGRESS; "S" FUNDS REFLECT STATE HIGHWAY FUNDS
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | DIVISION 9 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | 9 | NORTHWEST PIEDMONT RPO, WINSTON-SALEM URBAN AREA MPO, HIGH POINT URBAN AREA MPO, CABARRUS-ROWAN MPO | W-5209 | [11 empty] | COMPELTE
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 9. | HIGHWAY | 9 | NORTHWEST PIEDMONT RPO, WINSTON-SALEM URBAN AREA MPO, HIGH POINT URBAN AREA MPO, CABARRUS-ROWAN MPO | W-5709 | [11 empty] | IN PROGRESS; $1.3M NHP FUNDING APPLIED TO W-5709E
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 9 | NORTHWEST PIEDMONT RPO, WINSTON-SALEM URBAN AREA MPO, HIGH POINT URBAN AREA MPO, CABARRUS-ROWAN MPO | W-5709DIV | DIVISION 9 | HSIP | 2020 | 90000 |  |  | 2020 | 555000 |  |  | 645000
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 9 | NORTHWEST PIEDMONT RPO, WINSTON-SALEM URBAN AREA MPO, HIGH POINT URBAN AREA MPO, CABARRUS-ROWAN MPO | W-5709REG | REGION D | HSIP | 2020 | 90000 |  |  | 2020 | 555000 |  |  | 645000
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 9 | NORTHWEST PIEDMONT RPO, WINSTON-SALEM URBAN AREA MPO, HIGH POINT URBAN AREA MPO, CABARRUS-ROWAN MPO | W-5709SW | STATEWIDE MOBILITY | HSIP | 2020 | 120000 |  |  | 2020 | 740000 |  |  | 860000
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 9. | HIGHWAY | 9 | NORTHWEST PIEDMONT RPO, WINSTON-SALEM URBAN AREA MPO, HIGH POINT URBAN AREA MPO, CABARRUS-ROWAN MPO | W-5809
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 9. | RAIL | 9 | NORTHWEST PIEDMONT RPO, WINSTON-SALEM URBAN AREA MPO, HIGH POINT URBAN AREA MPO, CABARRUS-ROWAN MPO | RC-2009 | DIVISION 9 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
DAVIDSON, DAVIE, FORSYTH, ROWAN, STOKES | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 9. | RAIL | 9 | NORTHWEST PIEDMONT RPO, WINSTON-SALEM URBAN AREA MPO, HIGH POINT URBAN AREA MPO, CABARRUS-ROWAN MPO | RX-2009 | DIVISION 9
DAVIDSON, GUILFORD, FORSYTH | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE HIGH POINT MPO. | HIGHWAY | 7, 9 | HIGH POINT URBAN AREA MPO | C-5609 | EXEMPT | CMAQ, L | 2020 | 243000 |  |  | 2020 | 1455000 | 2020 | 729000 | 2427000 | IN PROGRESS
DAVIDSON, GUILFORD, RANDOLPH | HIGH POINT TRANSIT SYSTEM / HI-TRAN | SAFETY & SECURITY - MIN. 1% SET ASIDE | PUBLIC TRANSIT | 7, 8, 9 | HIGH POINT URBAN AREA MPO | TS-5113 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 64000 | 64000 | FUNDS AUTHORIZED IN PROGRESS
DAVIDSON, RANDOLPH | US 64 | US 64, EAST OF I-85 BUSINESS IN LEXINGTON TO ASHEBORO BYPASS. WIDEN TO MULTILANES. | HIGHWAY | 8, 9 | HIGH POINT URBAN AREA MPO, PIEDMONT TRIAD RPO | R-2220
DAVIDSON, ROWAN | I-85 | NORTH OF SR 2120 (LONG FERRY ROAD) IN ROWAN COUNTY TO US 29 / US 52 / US 70 / BUSINESS 85 IN DAVIDSON COUNTY. ADDITIONAL LANES AND YADKIN RIVER BRIDGE RECONSTRUCTION. (PROJECT INCLUDES B-3833). | HIGHWAY | 9 | HIGH POINT URBAN AREA MPO, CABARRUS-ROWAN MPO | I-2304 | PRE-STI (TRANSITION) | [10 empty] | INCLUDES B-3833; GARVEE BOND FUNDING: $14.3 MILLION FOR RIGHT-OF-WAY, SECTIONS AC & AD, PAYBACK FY 2009-2021; $111.7 MILLION FOR CONSTRUCTION, SECTIONS AC, PAYBACK FY 2010-2021; TIGER AWARD / INTERSTATE MAINTENANCE DISCRETIONARY FUNDING $11.7 MILLION
DAVIDSON, ROWAN | I-85 | NORTH OF SR 2120 (LONG FERRY ROAD) IN ROWAN COUNTY TO NORTH OF NC 150 IN DAVIDSON COUNTY, INCLUDING YADKIN RIVER BRIDGE | HIGHWAY | 9 | CABARRUS-ROWAN MPO, HIGH POINT URBAN AREA MPO | I-2304AC | EXEMPT | NHP | 2009 | 1066000 |  |  | 2010 | 8220000 |  |  | 9286000 | COMPLETE. GARVEE BOND FUNDING: $14.3 MILLION FOR RIGHT-OF-WAY, SECTIONS AC & AD, PAYBACK FY 2009-2021; $111.7 MILLION FOR CONSTRUCTION, SECTIONS AC, PAYBACK FY 2010-2021; TIGER AWARD / INTERSTATE MAINTENANCE DISCRETIONARY FUNDING $11.7 MILLION
DAVIDSON, ROWAN | I-85 | IMPLEMENTATION OF INTELLIGENT TRANSPORTATION SYSTEM (ITS) | HIGHWAY | 9 | CABARRUS-ROWAN MPO, HIGH POINT URBAN AREA MPO | I-2304AF | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
DAVIE | BLUE HERON TRAIL | TWINS WAY (NEAR INTERSECTION WITH US-158) WEST TO PEDESTRIAN TUNNEL UNDER I-40 IN BERMUDA RUN. CONSTRUCT SECTION OF MULTIUSE PATH. | BIKE/PED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-5958 | DIVISION 9 | BGANY, BGDA, L |  |  |  |  | 2022 | 3693000 |  |  | 3693000 | UNDER CONSTRUCTION
DAVIE | I-40 | 0.5 MILES WEST OF US 601 TO 1.2 MILES EAST OF SR 1410 (FARMINGTON ROAD). PAVEMENT REHABILITATION. | HIGHWAY | 9 | NORTHWEST PIEDMONT RPO | I-5765 | STATEWIDE MOBILITY | [10 empty] | COMPLETE
DAVIE | I-40 | IREDELL COUNTY LINE TO 0.5 MILE WEST OF US 601. PAVEMENT REHABILITATION. | HIGHWAY | 9 | NORTHWEST PIEDMONT RPO | I-5823 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
DAVIE | I-40 | SR 1436 (PINEBROOK SCHOOL ROAD) TO WEST OF NC 801. PAVEMENT REHABILITATION. | HIGHWAY | 9 | NORTHWEST PIEDMONT RPO, WINSTON-SALEM URBAN AREA MPO | I-6003 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2021 | 7677000 |  |  | 7677000 | UNDER CONSTRUCTION
DAVIE | NEW ROUTE | SR 1630 (BALTIMORE ROAD) TO I-40. CONSTRUCT 2-LANE EXTENSION OF BALTIMORE ROAD AND INTERCHANGE AT I-40. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-6187 | DIVISION 9 | BGANY, T | 2024 | 3400000 | 2024 | 300000 | 2025 | 30035000 |  |  | 33735000 | BUILD NC BONDS: $5 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE)
DAVIE | SR 1410 (FARMINGTON ROAD) | I-40 EASTBOUND RAMP AND US 158 INTERSECTION. CONSTRUCT ROUNDABOUTS. | HIGHWAY | 9 | NORTHWEST PIEDMONT RPO | R-5854 | DIVISION 9 | T | 2023 | 100000 | 2023 | 300000 | 2025 | 1900000 |  |  | 2300000
DAVIE | US 601 | SOUTH SALISBURY STREET IN MOCKSVILLE. INTERSECTION IMPROVEMENTS. | HIGHWAY | 9 | NORTHWEST PIEDMONT RPO | R-5728 | REGION D | [10 empty] | UNDER CONSTRUCTION
DAVIE | US 601 | SR 1345 (BLAISE CHURCH ROAD) TO SR 1408 (CANA ROAD). WIDEN TO MULTILANES. | HIGHWAY | 9 | NORTHWEST PIEDMONT RPO | R-5736 | DIVISION 9 | T | 2026 | 5000000 | 2026 | 800000 | 2028 | 17001000 |  |  | 22801000
DAVIE | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE NORTHWEST PIEDMONT RPO. | HIGHWAY | 9 | NORTHWEST PIEDMONT RPO | C-5614 | EXEMPT | CMAQ, L | 2020 | 12000 |  |  | 2020 | 57000 | 2020 | 36000 | 105000
DAVIE | WILKESBORO STREET | YADKINVILLE ROAD IN MOCKSVILLE. CONSTRUCT ROUNDABOUT. | HIGHWAY | 9 | NORTHWEST PIEDMONT RPO | U-6002 | DIVISION 9 | T |  |  |  |  | 2022 | 1800000 |  |  | 1800000 | RIGHT-OF-WAY IN PROGRESS
DAVIE, FORSYTH | I-40 | WEST OF NC 801 IN DAVIE COUNTY TO SR 1101 (HARPER ROAD) IN FORSYTH COUNTY. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | I-0911A | REGION D | T |  |  |  |  | 2021 | 35894000 |  |  | 35894000 | COMPLETE; DESIGN-BUILD PROJECT; BUILD NC BONDS: $27.889 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
DAVIE, FORSYTH | I-40 | 0.3 MILE WEST OF NC 801 IN DAVIE COUNTY TO SR 1101 (HARPER ROAD) IN FORSYTH COUNTY. PAVEMENT REHABILITATION. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | I-5794 | STATEWIDE MOBILITY | [10 empty] | COMPLETE
DAVIE, STOKES, SURRY, YADKIN | YADKIN VALLEY ECONOMIC DEVELOPMENT DISTRICT | ADMINISTRATION | PUBLIC TRANSIT | 9, 11 | NORTHWEST PIEDMONT RPO | TK-6174 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 1704000 | 1704000 | FUNDS AUTHORIZED IN PROGRESS
DUPLIN | DUPLIN COUNTY AIRPORT (DPL) | WIDEN RUNWAY AND STRENGTHEN PAVEMENT TO ACCOMMODATE LARGER AIRCRAFT. | AVIATION | 3 | EASTERN CAROLINA RPO | AV-5842 | DIVISION 3 | [10 empty] | COMPLETE
DUPLIN | I-40 | I-40 FROM THE SAMPSON COUNTY LINE (MILE MARKER 360) TO THE PENDER COUNTY LINE (MILE MARKER 388). PAVEMENT REHABILITATION. | HIGHWAY | 3 | EASTERN CAROLINA RPO | HI-0012 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2028 | 31100000 |  |  | 31100000
DUPLIN | NC 11 | BRIDGE 36 OVER MAXWELL CREEK ON NC 11. | HIGHWAY | 3 | EASTERN CAROLINA RPO | B-5639 | HIGHWAY FUND | HFB | 2020 | 56000 |  |  | 2021 | 3422000 |  |  | 3478000 | RIGHT OF WAY IN PROGRESS.
DUPLIN | NC 11/NC 111 | BRIDGE 300082 OVER BURNT COAT CREEK ON NC 11/NC 111. | HIGHWAY | 3 | EASTERN CAROLINA RPO | B-5534 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 2675000 |  |  | 2675000 | RIGHT OF WAY IN PROGRESS.
DUPLIN | NC 24 BUSINESS (ROUTLEDGE ROAD) | NC 24 BUSINESS (ROUTLEDGE ROAD) AND NC 24 / NC 903 (SOUTH KENANSVILLE BYPASS). REVISE TRAFFIC SIGNAL AND PAVEMENT MARKINGS. | HIGHWAY | 3 | EASTERN CAROLINA RPO | HS-2003N | REGION B | HSIP |  |  |  |  | 2025 | 252000 |  |  | 252000
DUPLIN | NC 403 | NC 403 AT SR 1306 (BEAUTANCUS ROAD). INSTALL ALL WAY STOP, STOP AHEAD WARNING SIGNS, BRIGHTSIDES, STOP BARS, CONCRETE ISLAND, AND REFRESH PAVEMENT MARKINGS. REMOVE ACTUATED CURVE WARNING FLASHER. | HIGHWAY | 3 | EASTERN CAROLINA RPO | HS-2003I | REGION B | HSIP |  |  |  |  | 2024 | 154000 |  |  | 154000
DUPLIN | SR 1004 (RONES CHAPEL ROAD) | REPLACE BRIDGE 300325 OVER NE CAPE FEAR RIVER. | HIGHWAY | 3 | EASTERN CAROLINA RPO | BR-0224 | DIVISION 3 | [10 empty] | UNDER CONSTRUCTION. PROJECT REPRESENTS HFB 3.R.76 PROJECT.
DUPLIN | SR 1135 (PROVIDENCE CHURCH ROAD) | REPLACE BRIDGE 300052 OVER ROCKFISH CREEK. | HIGHWAY | 3 | EASTERN CAROLINA RPO | B-5647 | DIVISION 3 | BGOFF | 2023 | 150000 |  |  | 2024 | 1500000 |  |  | 1650000
DUPLIN | SR 1162 (BAY ROAD) | REPLACE BRIDGE 300045 OVER ISLAND CREEK. | HIGHWAY | 3 | EASTERN CAROLINA RPO | BR-0243 | HIGHWAY FUND | HFB |  |  |  |  | 2022 | 1700000 |  |  | 1700000 | PROJECT REPRESENTS HFB 3.R.83 PROJECT.
DUPLIN | SR 1535 (LIDDELL ROAD) | SR 1535 (LIDDELL ROAD) AND SR 1534 (DRUMMERSVILLE ROAD). INSTALL ALL WAY STOP. | HIGHWAY | 3 | EASTERN CAROLINA RPO | HS-2003C | DIVISION 3 | HSIP |  |  |  |  | 2024 | 31000 |  |  | 31000
DUPLIN | SR 1828 (CYPRESS CREEK ROAD) | REPLACE BRIDGE 300187 OVER BLACK SWAMP. | HIGHWAY | 3 | EASTERN CAROLINA RPO | B-5632 | DIVISION 3 | BGOFF | 2023 | 190000 |  |  | 2023 | 1900000 |  |  | 2090000
DUPLIN | SR 1946 (NORTHEAST ROAD) | REPLACE BRIDGE 300201 OVER ISLAND CREEK. | HIGHWAY | 3 | EASTERN CAROLINA RPO | B-5641 | DIVISION 3 | BGOFF |  |  |  |  | 2022 | 1669000 |  |  | 1669000
DUPLIN | US 117 (NORWOOD STREET) | US 117 (NORWOOD STREET) AND SR 1173 (SOUTHERLAND STREET) IN WALLACE. REVISE TRAFFIC SIGNAL. | HIGHWAY | 3 | EASTERN CAROLINA RPO | HS-2003M | REGION B | HSIP |  |  |  |  | 2025 | 44000 |  |  | 44000
DUPLIN | US 117 (SYCAMORE STREET) | US 117 (SYCAMORE STREET) AND SR 1102 (CHARITY ROAD) IN ROSE HILL. REVISE TRAFFIC SIGNAL AND PAVEMENT MARKINGS. | HIGHWAY | 3 | EASTERN CAROLINA RPO | HS-2003E | REGION B | HSIP |  |  |  |  | 2025 | 97000 |  |  | 97000
DUPLIN | US 117 NBL | REPLACE BRIDGE 300016 OVER CSX RAILROAD. BRIDGE PRESERVATION OF BRIDGE 300017 OVER CSX. | HIGHWAY | 3 | EASTERN CAROLINA RPO | B-5981 | STATEWIDE MOBILITY | BGLT5 | 2022 | 443000 |  |  | 2023 | 7100000 |  |  | 7543000 | RIGHT-OF-WAY IN PROGRESS.
DUPLIN | DUPLIN COUNTY | ADMINISTRATION | PUBLIC TRANSIT | 3 | EASTERN CAROLINA RPO | TK-6177 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 836000 | 836000 | FUNDS AUTHORIZED IN PROGRESS
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | DIVISION 3 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | BIKE/PED | 3 | CAPE FEAR RPO, EASTERN CAROLINA RPO, JACKSONVILLE URBAN AREA MPO, MID-CAROLINA RPO, WILMINGTON URBAN AREA MPO, GRAND STRAND AREA TRANSPORTATION STUDY | BO-2403 | DIVISION 3 | S, TA |  |  |  |  | 2024 | 10000000 |  |  | 10000000
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 3. | HIGHWAY | 3 | CAPE FEAR RPO, EASTERN CAROLINA RPO, JACKSONVILLE URBAN AREA MPO, MID-CAROLINA RPO, WILMINGTON URBAN AREA MPO, GRAND STRAND AREA TRANSPORTATION STUDY | HS-2003 | DIVISION 3
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | DIVISION 3 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | HIGHWAY | 3 | CAPE FEAR RPO, EASTERN CAROLINA RPO, JACKSONVILLE URBAN AREA MPO, MID-CAROLINA RPO, WILMINGTON URBAN AREA MPO, GRAND STRAND AREA TRANSPORTATION STUDY | R-5783 | DIVISION 3 | S, TA |  |  |  |  | 2020 | 3500000 |  |  | 3500000 | UNDER CONSTRUCTION; "S" FUNDS REFLECT STATE HIGHWAY FUNDS
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 3. | HIGHWAY | 3 | CAPE FEAR RPO, EASTERN CAROLINA RPO, JACKSONVILLE URBAN AREA MPO, MID-CAROLINA RPO, WILMINGTON URBAN AREA MPO, GRAND STRAND AREA TRANSPORTATION STUDY | W-5703 | [11 empty] | IN PROGRESS
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 3 | CAPE FEAR RPO, EASTERN CAROLINA RPO, JACKSONVILLE URBAN AREA MPO, MID-CAROLINA RPO, WILMINGTON URBAN AREA MPO, GRAND STRAND AREA TRANSPORTATION STUDY | W-5703DIV | DIVISION 3 | HSIP | 2022 | 30000 |  |  | 2020 | 375000 |  |  | 405000
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 3 | CAPE FEAR RPO, EASTERN CAROLINA RPO, JACKSONVILLE URBAN AREA MPO, MID-CAROLINA RPO, WILMINGTON URBAN AREA MPO, GRAND STRAND AREA TRANSPORTATION STUDY | W-5703REG | REGION B | HSIP | 2022 | 30000 |  |  | 2020 | 375000 |  |  | 405000
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 3 | CAPE FEAR RPO, EASTERN CAROLINA RPO, JACKSONVILLE URBAN AREA MPO, MID-CAROLINA RPO, WILMINGTON URBAN AREA MPO, GRAND STRAND AREA TRANSPORTATION STUDY | W-5703SW | STATEWIDE MOBILITY | HSIP | 2022 | 40000 |  |  | 2020 | 500000 |  |  | 540000
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 3. | HIGHWAY | 3 | CAPE FEAR RPO, EASTERN CAROLINA RPO, JACKSONVILLE URBAN AREA MPO, MID-CAROLINA RPO, WILMINGTON URBAN AREA MPO, GRAND STRAND AREA TRANSPORTATION STUDY | W-5803 | [11 empty] | INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 3. | RAIL | 3 | CAPE FEAR RPO, EASTERN CAROLINA RPO, JACKSONVILLE URBAN AREA MPO, MID-CAROLINA RPO, WILMINGTON URBAN AREA MPO, GRAND STRAND AREA TRANSPORTATION STUDY | RC-2003 | DIVISION 3 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
DUPLIN, ONSLOW, PENDER, SAMPSON, BRUNSWICK, NEW HANOVER | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 3. | RAIL | 3 | CAPE FEAR RPO, EASTERN CAROLINA RPO, JACKSONVILLE URBAN AREA MPO, MID-CAROLINA RPO, WILMINGTON URBAN AREA MPO, GRAND STRAND AREA TRANSPORTATION STUDY | RX-2003 | DIVISION 3 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
DUPLIN, PENDER | I-40 | DUPLIN COUNTY LINE (MILE MARKER 360) TO WEST OF US 117 (MILE MARKER 390). PAVEMENT AND BRIDGE REHABILITATION. | HIGHWAY | 3 | EASTERN CAROLINA RPO, CAPE FEAR RPO | I-5940 | STATEWIDE MOBILITY | BGIM |  |  |  |  | 2019 | 28826000 |  |  | 28826000 | GARVEE BOND FUNDING $24.0 M; PAYBACK FY 2019-2033. UNDER CONSTRUCTION.
DUPLIN, SAMPSON | US 117 (FUTURE 1-795) | I-40 TO SR 1006 (WEST TRADE ROAD). | HIGHWAY | 3 | EASTERN CAROLINA RPO, MID-CAROLINA RPO | U-3125A | NOT FUNDED | NHP | NOT FUNDED | 7183000 | NOT FUNDED | 2238000 | NOT FUNDED | 103500000 |  |  | 112921000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY.
DUPLIN, SAMPSON | VARIOUS | INSTALL PAVEMENT MARKINGS ALONG VARIOUS ROUTES. | HIGHWAY | 3 | EASTERN CAROLINA RPO, MID-CAROLINA RPO | HS-2003B | DIVISION 3 | HSIP |  |  |  |  | 2021 | 3432000 |  |  | 3432000 | UNDER CONSTRUCTION.
DURHAM | BIVINS STREET; CLEVELAND STREET; CORPORATION STREE | ENGLEWOOD AVENUE; GEORGIA AVENUE TO WATTS STREET; KNOX STREET, WATTS STREET TO ACADIA STREET; BIVINS STREET, SR 1127 (CHAPEL HILL ROAD) TO ARNETTE AVENUE; IREDELL STREET, US 70 BUSINESS (MAIN STREET) TO WEST CLUB BOULEVARD; MARYLAND AVENUE, WEST CLUB | BIKE/PED | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | BL-0031 | DIVISION 5 | L, STBG |  |  |  |  | 2023 | 340000 | 2022 | 60000 | 400000
DURHAM | BRYANT BRIDGE NORTH / GOOSE CREEK WEST TRAIL | NC 55 TO TO DREW-GRANBY PARK IN DURHAM. CONSTRUCT SHARED-USE PATH AND CONNECTING SIDEWALKS. | BIKE/PED | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5720 | DIVISION 5 | L, TAANY | 2022 | 14000 |  |  | 2023 | 4432000 |  |  | 4446000 | SCOPE AND COST OF EB-5833 PROJECT IS COMBINED WITH EB-5720
DURHAM | DURHAM BELTLINE TRAIL | PETTIGREW STREET TO AVONDALE DRIVE IN DURHAM. CONSTRUCT MULTI-USE TRAIL ON FORMER RAIL CORRIDOR. | BIKE/PED | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5904 | DIVISION 5 | BGDA, DP, L, TAANY, TADA |  |  |  |  | 2023 | 16341000 |  |  | 16341000 | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM; "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT
DURHAM | LASALLE STREET | KANGAROO DRIVE TO SPRUNT AVENUE IN DURHAM. CONSTRUCT SIDEWALKS ON BOTH SIDES FROM KANGAROO DRIVE TO US 70 BUSINESS (HILLSBOROUGH ROAD) AND ON ONE SIDE FROM HILLSBOROUGH ROAD TO SPRUNT AVENUE. | BIKE/PED | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5703 | DIVISION 5 | L, TAANY | 2022 | 150000 |  |  | 2022 | 1440000 |  |  | 1590000 | RIGHT-OF-WAY IN PROGRESS
DURHAM | NC 157 / SR 1322 (GUESS ROAD) | HILLCREST DRIVE TO SR 1407 (WEST CARVER STREET) IN DURHAM. CONSTRUCT SIDEWALKS ON BOTH SIDES. | BIKE/PED | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5834 | DIVISION 5 | BGDACV, L, TAANY | 2025 | 204000 |  |  | 2026 | 1293000 | 2023 | 108000 | 1605000
DURHAM | NC 54 | NC 55 TO RESEARCH TRIANGLE PARK WESTERN LIMIT IN DURHAM. CONSTRUCT SECTIONS OF SIDEWALK ON SOUTH SIDE. | BIKE/PED | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5708 | DIVISION 5 | L, SRTS, TAANY | 2021 | 177000 |  |  | 2022 | 491000 |  |  | 668000 | RIGHT-OF-WAY IN PROGRESS
DURHAM | NC 55 (ALSTON AVENUE) | SR 1171 (RIDDLE ROAD) TO CECIL STREET IN DURHAM. CONSTRUCT SIDEWALK ON EAST SIDE TO FILL IN MISSING GAPS. | BIKE/PED | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5835 | DIVISION 5 | L, TAANY | 2027 | 50000 |  |  | 2028 | 1196000 | 2025 | 105000 | 1351000
DURHAM | NC 751 / SR 1183 / SR 2220 / NON-SYSTEM (UNIVERSIT | SR 1116 (GARRETT ROAD) TO SR 1158 (CORNWALLIS ROAD) IN DURHAM. ADD BICYCLE LANES AND PEDESTRIAN IMPROVEMENTS. | BIKE/PED | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5514 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION BY CITY OF DURHAM
DURHAM | RAYNOR STREET | NORTH MIAMI BOULEVARD TO NORTH HARDEE STREET IN DURHAM. CONSTRUCT SIDEWALK ON ONE SIDE OF STREET. | BIKE/PED | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5704 | DIVISION 5 | L, TAANY | 2021 | 169000 |  |  | 2022 | 510000 |  |  | 679000 | RIGHT-OF-WAY IN PROGRESS
DURHAM | SR 1127 (CHAPEL HILL STREET); WEST CLUB BOULEVARD | WEST CLUB BOULEVARD, WASHINGTON ST TO SR 1322 (BROAD ST); BLACKWELL STREET / CORCORAN STREET / FOSTER STREET, ATT TRAILHEAD TO WASHINGTON STREET; SR 1127 (CHAPEL HILL STREET), RAMSEUR STREET TO SWIFT AVENUE IN DURHAM. CONSTRUCT BUFFERED BICYCLE LANES. | BIKE/PED | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | BL-0028 | DIVISION 5 | CMAQ, L, STBG |  |  |  |  | 2023 | 911000 | 2022 | 154000 | 1065000
DURHAM | SR 1158 (CORNWALLIS ROAD) | SR 2295 (SOUTH ROXBORO STREET) TO SR 1127 (CHAPEL HILL ROAD) IN DURHAM. BICYCLE AND PEDESTRIAN FEATURES. | BIKE/PED | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-4724 | PRE-STI (TRANSITION) | BGANY, BGDA, L | 2022 | 2233000 |  |  | 2024 | 4978000 |  |  | 7211000
DURHAM | THIRD FORK CREEK TRAIL | SOUTHERN BOUNDARIES PARK TO AMERICAN TOBACCO TRAIL IN DURHAM. CONSTRUCT SHARED USE PATH AND SIDEWALKS, AND INSTALL BEACON AT SR 1158 (CORNWALLIS ROAD) CROSSING. | BIKE/PED | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5837 | DIVISION 5 | L, TAANY | 2022 | 17000 |  |  | 2023 | 3215000 |  |  | 3232000
DURHAM | US 15 BUSINESS / US 501 BUSINESS (DURHAM-CHAPEL HI | SR 2295 (SOUTH ROXBORO ROAD), SR 1158 (CORNWALLIS ROAD) TO SUMMIT STREET; SOUTH ROXBORO STREET, SHADY CREEK DRIVE TO MARTIN LUTHER KING JR. PARKWAY; SR 1322 (BROAD STREET), US 70 BUSINESS (MAIN STREET) TO GUESS ROAD; US 15 BUSINESS / US 501 BUSINESS (DURH | BIKE/PED | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | BL-0030 | DIVISION 5 | BGDA, BGDACV, L |  |  |  |  | 2022 | 162000 | 2022 | 36000 | 198000
DURHAM | US 501 BYPASS (NORTH DUKE STREET) | MURRAY AVENUE TO US 501 BUSINESS (NORTH ROXBORO ROAD) IN DURHAM. CONSTRUCT SIDEWALK ON EAST SIDE TO FILL IN EXISTING GAPS. | BIKE/PED | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5715 | DIVISION 5 | L, TAANY | 2021 | 296000 |  |  | 2022 | 2680000 |  |  | 2976000 | RIGHT-OF-WAY IN PROGRESS BY CITY OF DURHAM
DURHAM | (HORTON ROAD) SR 1443 | NC 157 (GUESS ROAD) TO US 501 (ROXBORO ROAD) IN DURHAM. CONSTRUCT MULTI-USE PATH AND COMPLETE SIDEWALK GAPS. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | BL-0063 | EXEMPT | CMAQ, L | 2023 | 571000 |  |  | 2024 | 275000 | 2023 | 359000 | 1205000
DURHAM | I-40 | ORANGE COUNTY LINE TO NC 147 (DURHAM FREEWAY / TRIANGLE EXPRESSWAY) IN DURHAM | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-3306B | [11 empty] | COMPLETE
DURHAM | I-40 | NC 55 (ALSTON AVENUE) TO NC 147 (DURHAM FREEWAY / TRIANGLE EXPRESSWAY) IN DURHAM. CONSTRUCT WESTBOUND AUXILIARY LANE. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-5707 | STATEWIDE MOBILITY | NHP | 2024 | 900000 | 2024 | 205000 | 2026 | 8200000 |  |  | 9305000
DURHAM | I-40 | US 15 / US 501 TO EAST OF NC 147. PAVEMENT REHABILITATION. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-5993 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2025 | 36500000 |  |  | 36500000 | TO BE LET WITH I-5994
DURHAM | I-40 | US 15 / US 501 TO EAST OF NC 147. BRIDGE REHABILITATION - MULTIPLE STRUCTURES. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-5994 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2025 | 12167000 |  |  | 12167000 | TO BE LET WITH I-5993
DURHAM | I-40, NC 54 | EAST OF LITTLE CREEK TO EAST OF I-40. UPGRADE ROADWAY CORRIDOR AND CONSTRUCT INTERCHANGE IMPROVEMENTS AT I-40. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5774F | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 91472000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 638000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 81302000 |  |  | 173412000
DURHAM | I-85 |  | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-5729 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
DURHAM | I-85 | ORANGE COUNTY LINE TO US 15 / US 501 IN DURHAM. PAVEMENT REHABILITATION | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-5941 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2024 | 10600000 |  |  | 10600000
DURHAM | I-85 / US 15 | EAST OF SR 1827 (MIDLAND TERRACE) TO SR 1632 (RED MILL ROAD) IN DURHAM. ADD LANES. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-6010 | NOT FUNDED | NHP | NOT FUNDED | 10417000 | NOT FUNDED | 1774000 | NOT FUNDED | 55301000 |  |  | 67492000
DURHAM | I-885 | I-40 TO NC 147 IN DURHAM. ADD LANES AND REHABILITATE PAVEMENT. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5934 | STATEWIDE MOBILITY | NHP |  |  | 2028 | 300000 | 2029 | 142301000 |  |  | 142601000
DURHAM | NC 147 (DURHAM FREEWAY) | SR 1127 (WEST CHAPEL HILL STREET) TO BRIGGS AVENUE IN DURHAM. CONSTRUCT AUXILIARY LANES AND OPERATIONAL IMPROVEMENTS. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5937 | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7750000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 64301000 |  |  | 81351000
DURHAM | NC 54 | NC 55 IN DURHAM. INSTALL CONCRETE PEDESTRIAN REFUGE ISLANDS IN ALL QUADRANTS. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | HS-2005C | REGION C | HSIP |  |  |  |  | 2023 | 75000 |  |  | 75000
DURHAM | NC 54 | EAST OF SR1110 (BARBEE CHAPEL ROAD) TO EAST OF LITTLE CREEK. UPGRADE ROADWAY CORRIDOR. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5774C | REGION C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 934000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 267000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10399000 |  |  | 11600000
DURHAM | NC 54 | FALCONBBRIDGE ROAD. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5774D | [11 empty] | SCOPE INCLUDED IN U-5774F
DURHAM | NC 54 | SR 1110 (FARRINGTON ROAD). CONVERT AT-GRADE INTERSECTION TO GRADE SEPARATION. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5774E | [11 empty] | SCOPE INCLUDED IN U-5774F
DURHAM | NC 54 | EAST OF I-40 TO EAST OF NC 751. UPGRADE ROADWAY CORRIDOR. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5774G | NOT FUNDED | T | NOT FUNDED | 1800000 | NOT FUNDED | 800000 | NOT FUNDED | 16900000 |  |  | 19500000
DURHAM | NC 54 | EAST OF NC 751 TO EAST OF SR 1118 (FAYETTEVILLE ROAD). UPGRADE ROADWAY CORRIDOR. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5774H | NOT FUNDED | T | NOT FUNDED | 5900000 | NOT FUNDED | 726000 | NOT FUNDED | 18000000 |  |  | 24626000
DURHAM | NC 54 | EAST OF SR 1118 (FAYETTEVILLE ROAD) TO EAST OF SR 1106 (BARBEE ROAD). UPGRADE ROADWAY CORRIDOR. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5774I | NOT FUNDED | T | NOT FUNDED | 2500000 | NOT FUNDED | 617000 | NOT FUNDED | 12300000 |  |  | 15417000
DURHAM | NC 54 | EAST OF SR 1106 (BARBEE ROAD) TO NC 55. UPGRADE ROADWAY CORRIDOR. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5774J | NOT FUNDED | T | NOT FUNDED | 3200000 | NOT FUNDED | 420000 | NOT FUNDED | 17100000 |  |  | 20720000
DURHAM | NC 55 | MERIDIAN PARKWAY TO I-40 INTERCHANGE IN DURHAM. ADD THIRD SOUTHBOUND LANE AND UPGRADE RAMP TERMINALS. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-6118 | NOT FUNDED | T | NOT FUNDED | 300000 | NOT FUNDED | 200000 | NOT FUNDED | 4799000 |  |  | 5299000
DURHAM | NC 55 (ALSTON AVENUE) | NC 147 (DURHAM FREEWAY) TO US 70 BUSINESS / NC 98 (HOLLOWAY STREET) IN DURHAM. WIDEN TO FOUR-LANE DIVIDED FACILITY FROM NC 147 TO MAIN STREET AND REPLACE NORFOLK SOUTHERN RAILROAD BRIDGES. MODERNIZE FROM MAIN STREET TO US 70 BUSINESS / NC 98 (HOLLOWAY ST | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-3308 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
DURHAM | NC 751 (HOPE VALLEY ROAD) | SR 1183 (UNIVERSITY DRIVE) INTERSECTION IN DURHAM. CONSTRUCT ROUNDABOUT. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5745 | REGION C | T | 2019 | 435000 |  |  | 2019 | 1313000 | 2019 | 624000 | 2372000 | UNDER CONSTRUCTION; BUILD NC BONDS: $457,000 FOR PE, $338,000 FOR RIGHT OF WAY, AND $1.02 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE)
DURHAM | NC 98 (HOLLOWAY STREET) | SR 1938 (JUNCTION ROAD) TO SR 1919 (LYNN ROAD) IN DURHAM. CONSTRUCT SAFETY IMPROVEMENTS AND WIDEN TO ADD MEDIAN, BICYCLE LANES, SIDEWALKS, TRANSIT STOP IMPROVEMENTS, AND TRAFFIC SIGNALS WHERE NEEDED. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-6120 | DIVISION 5 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9999000 |  |  | 18199000
DURHAM | NEW ROUTE | EAST END CONNECTOR, NC 147 (DURHAM FREEWAY) TO NORTH OF NC 98 IN DURHAM. FOUR-LANE DIVIDED FREEWAY WITH AUXILIARY LANES, PART ON NEW LOCATION. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-0071 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
DURHAM | SR 1004 (OLD OXFORD ROAD) | FIRST AVE (MERCK DRIVEWAY). CONSTRUCT RIGHT TURN LANE. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | HE-0007A | DIVISION 5 | T |  |  |  |  | 2023 | 165000 | 2023 | 25000 | 190000
DURHAM | SR 1118 (FAYETTEVILLE ROAD) | WOODCROFT PARKWAY TO BARBEE ROAD IN DURHAM. WIDEN TO 4-LANE DIVIDED FACILITY WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-6021 | DIVISION 5 | T | 2028 | 9100000 | 2028 | 1700000 | 2031 | 15200000 |  |  | 26000000
DURHAM | SR 1303 (PICKETT ROAD) | SR 1116 (GARRETT ROAD)/(LUNA LANE) INTERSECTION IN DURHAM. INSTALL TRAFFIC SIGNAL. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | HS-2005D | DIVISION 5 | HSIP | 2023 | 2000 |  |  | 2023 | 100000 |  |  | 102000
DURHAM | SR 1317 (MORREENE ROAD) | NEAL ROAD TO SR 1320 (ERWIN ROAD) IN DURHAM. CONSTRUCT BIKE LANES AND SIDEWALKS. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | C-4928 | DIVISION 5 | BGANY, BGDA, CMAQ, L | 2022 | 3060000 |  |  | 2023 | 7371000 |  |  | 10431000 | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF DURHAM - IN PROGRESS
DURHAM | SR 1794 (TEKNIKA PARKWAY) | SR 1632 (RED MILL ROAD) CONSTRUCT TURN LANES AND SIGNALIZE INTERSECTION. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | HE-0007B | DIVISION 5 | T | 2023 | 95000 |  |  | 2023 | 815000 | 2023 | 90000 | 1000000
DURHAM | SR 1945 (S. ALSTON AVE.) | SR 1171 (RIDDLE RD.) TO CAPPS ST. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | C-5183B | EXEMPT | BGDA, CMAQ, L |  |  |  |  | 2022 | 1346000 |  |  | 1346000
DURHAM | SR 1973 (PAGE ROAD) | CHRUCHILL HALL/ARBy'S/MCDONALD DRIVEWAY. INSTALL DIRECTIONAL CROSSOVER. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | HS-2005H | DIVISION 5 | HSIP |  |  |  |  | 2023 | 20000 |  |  | 20000
DURHAM | SR 2220 | SR 1113 (POPE ROAD) TO SR 1116 (GARRETT ROAD) | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-4707B | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
DURHAM | SR 2635 (INTERNATIONAL DRIVE) | SR 1004 (OLD OXFORD RD) TO NEW LOCATION. CONSTRUCT NEW LANES. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | HE-0007C | DIVISION 5 | T | [6 empty] | 2023 | 600000 | 600000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY
DURHAM | US 15 / US 501 | SR 1116 (GARRETT ROAD) IN DURHAM. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5717 | STATEWIDE MOBILITY | NHP |  |  |  |  | 2026 | 32001000 |  |  | 32001000 | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH U-6067
DURHAM | US 15 / US 501 | I-40, SR (MOUNT MORIAH ROAD), AND SOUTHWEST DURHAM PARKWAY IN DURHAM. IMPROVE INTERCHANGE / INTERSECTION AREA. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-6067 | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 42800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 62898000 |  |  | 109398000 | COORDINATE WITH U-5717
DURHAM | US 15 / US 501 BUSINESS | NC 751 (ACADEMY ROAD) INTERCHANGE IN DURHAM. INSTALL GUARDRAIL. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | HS-2005E | REGION C | HSIP |  |  |  |  | 2022 | 175000 |  |  | 175000
DURHAM | US 15 / US 501 NORTHBOUND | REPLACE BRIDGE 310080 OVER SR 1308 (CORNWALLIS ROAD) IN DURHAM. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | B-5674 | REGION C | BFP | 2023 | 110000 |  |  | 2025 | 2209000 |  |  | 2319000
DURHAM | US 501 (ROXBORO ROAD) | SR 1448 (LATTA ROAD) / SR 1639 (INFINITY ROAD) INTERSECTION IN DURHAM. INTERSECTION IMPROVEMENTS. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5516 | REGION C | L, NHP | 2026 | 11292000 | 2026 | 2076000 | 2028 | 12401000 |  |  | 25769000 | RIGHT-OF-WAY PARTICIPATION $2 MILLION BY CITY OF DURHAM
DURHAM | US 70 | SR 1959 (SOUTH MIAMI BOULEVARD) / SR 1811 (SHERRON ROAD) TO EAST OF SR 2095 (PAGE ROAD EXTENSION). | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5720C | [11 empty] | PROJECT DELETED - WORK TO BE ACCOMPLISHED UNDER U-5720B
DURHAM | US 70 (MIAMI BOULEVARD) | LYNN ROAD TO EAST OF SR 2095 (PAGE ROAD EXTENSION). UPGRADE TO CONTROLLED-ACCESS FACILITY AND CONVERT SR 1811 AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5720
DURHAM | US 70 (MIAMI BOULEVARD) | LYNN ROAD TO SR 1959 (SOUTH MIAMI BOULEVARD) / SR 1811 (SHERRON ROAD). | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5720A | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 46400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1306000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 36502000 |  |  | 84208000
DURHAM | US 70 (MIAMI BOULEVARD) | SR 1959 (SOUTH MIAMI BOULEVARD) / SR 1811 (SHERRON ROAD) TO EAST OF SR 2095 (PAGE ROAD EXTENSION). | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5720B | STATEWIDE MOBILITY | T | 2027 | 140500000 | 2027 | 1218000 | 2030 | 81701000 |  |  | 223419000 | INCLUDES INTERCHANGE AT SR 1811
DURHAM | VARIOUS | CONSTRUCT SIDEWALKS IN DURHAM. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | C-5183 | EXEMPT
DURHAM | VARIOUS | SR 1004 (OLD OXFORD ROAD), SR 1794 (TEKNIKA PARKWAY), SR 2635 (INTERNATIONAL DRIVE). CONSTRUCT ACCESS ROAD AND INTERSECTION IMPROVEMENTS. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | HE-0007 | [11 empty] | ECONOMIC DEVELOPMENT PROJECT
DURHAM | VARIOUS | CITY OF DURHAM. UPGRADE ITS / SIGNAL SYSTEM. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5968 | REGION C | T |  |  |  |  | 2021 | 17469000 |  |  | 17469000 | UNDER CONSTRUCTION; BUILD NC BONDS: $13.574 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
DURHAM | WOODCROFT PARKWAY EXTENSION | SR 1116 (GARRETT ROAD) TO NC 751 (HOPE VALLEY ROAD) IN DURHAM. CONSTRUCT ROADWAY ON NEW ALIGNMENT. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5823 | DIVISION 5 | BGANY, L | 2024 | 900000 | 2024 | 400000 | 2025 | 3750000 |  |  | 5050000 | NON-STATE SYSTEM FACILITY - LOCAL MATCH BY CITY OF DURHAM
DURHAM | AUTHORITY DURHAM AREA TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, SERVICE VEHICLES, ETC. | PUBLIC TRANSIT | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | TG-4738 | PUBLIC TRANSIT | 5307, 5339, CMAQ, L | [6 empty] | 2020 | 2376000 | 2376000 | FUNDS AUTHORIZED IN PROGRESS
DURHAM | AUTHORITY DURHAM AREA TRANSIT | PREVENTIVE MAINTENANCE | PUBLIC TRANSIT | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | TG-4738A | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 15000000 | 15000000 | FUNDS AUTHORIZED IN PROGRESS
DURHAM | CHAPEL HILL TRANSIT | PARATRANSIT VEHICLES, BUS REFURBISHMENT, AND BUS SHELTERS. | PUBLIC TRANSIT | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | TA-5019A | DIVISION 5 | [10 empty] | IN PROGRESS BY CHAPEL HILL TRANSIT
DURHAM | DURHAM AREA TRANSIT AUTHORITY | REPLACEMENT BUS. | PUBLIC TRANSIT | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | TA-4923 | DIVISION 5 | 5307, 5339, L | [6 empty] | 2021 | 6184000 | 6184000 | IN PROGRESS BY DURHAM AREA TRANSIT AUTHORITY
DURHAM | DURHAM AREA TRANSIT AUTHORITY | OPERATING ASSISTANCE | PUBLIC TRANSIT | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | TO-5130 | PUBLIC TRANSIT | SMAP | [6 empty] | 2020 | 11224000 | 11224000 | FUNDS AUTHORIZED IN PROGRESS
DURHAM | DURHAM AREA TRANSIT AUTHORITY | PLANNING ASSISTANCE - 5303 | PUBLIC TRANSIT | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | TP-5108 | PUBLIC TRANSIT | 5303, L, S | [6 empty] | 2020 | 560000 | 560000 | FUNDS AUTHORIZED IN PROGRESS
DURHAM | DURHAM AREA TRANSIT AUTHORITY | PLANNING ASSISTANCE - 5307 | PUBLIC TRANSIT | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | TP-5109 | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 1920000 | 1920000 | FUNDS AUTHORIZED IN PROGRESS
DURHAM | DURHAM AREA TRANSIT AUTHORITY | SAFETY & SECURITY - MIN. 1% SET ASIDE | PUBLIC TRANSIT | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | TS-5108 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 172000 | 172000 | FUNDS AUTHORIZED IN PROGRESS
DURHAM | DURHAM COUNTY ACCESS | ADMINISTRATION | PUBLIC TRANSIT | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | TK-6126 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 252000 | 252000 | FUNDS AUTHORIZED IN PROGRESS
DURHAM | GO TRIANGLE | GOTRIANGLE TRANSIT CORRIDORS. IMPROVEMENT OF ROXBORO TRANSIT CORRIDOR FROM DENFIELD STREET TO PETTIGREW STREET, DURHAM STATION ACCESS, STOP IMPROVEMENTS, AND BUS SHELTERS. | PUBLIC TRANSIT | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | TD-5286 | REGION C | 5307, L, T |  |  |  |  | 2021 | 1590000 |  |  | 1590000
DURHAM | GO TRIANGLE | NC 98 (HOLLOWAY STREET) TRANSIT CORRIDOR. CONSTRUCT ACCESS AND BUS STOP IMPROVEMENTS. | PUBLIC TRANSIT | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | TD-5294 | REGION C | [10 empty] | UNDER CONSTRUCTION BY GO TRIANGLE
DURHAM | GO TRIANGLE | SAFETY AND SECURITY - CAMERAS. | PUBLIC TRANSIT | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | TG-5235 | DIVISION 5 | BGDA, L | [9 empty] | IN PROGRESS
DURHAM | GO TRIANGLE | ESTABLISH NEIGHBORHOOD TRANSIT CENTERS IN DURHAM. | PUBLIC TRANSIT | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | TG-5255 | REGION C | [10 empty] | IN PROGRESS
DURHAM | GO TRIANGLE TRANSIT | ROUGEMONT PARK-AND-RIDE. PROFESSIONAL SERVICES AND PROPERTY ACQUISITION. | PUBLIC TRANSIT | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | TD-5273 | EXEMPT | [10 empty] | IN PROGRESS BY TRIANGLE TRANSIT
DURHAM | GODURHAM | GODURHAM IS PLANNING IMPROVEMENTS TO DURHAM STATION TO EXPAND EQUITABLE ACCESS TO TRANSIT, IMPROVE STATION AMENITIES, AND INCREASE CONNECTIONS TO EMPLOYMENT, HEALTHCARE AND EDUCATION OPPORTUNITIES AND CONSTRUCT 8 BUS BAYS, REDESIGNED BUS LANES, AND PLACE | PUBLIC TRANSIT | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | TU-0013 | PUBLIC TRANSIT | 5339(b), L | [6 empty] | 2023 | 13500000 | 13500000
DURHAM | VARIOUS | NEIGHBORHOOD TRANSIT CENTER IN SOUTH DURHAM IN CONNECTION WITH SOUTHPOINT PARK-AND-RIDE FACILITY. | PUBLIC TRANSIT | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | TG-5255B | REGION C
DURHAM | VARIOUS | NEIGHBORHOOD TRANSIT CENTER IN SOUTHWEST DURHAM IN CONNECTION WITH PATTERSON PLACE T PARK-AND-RIDE FACILITY. | PUBLIC TRANSIT | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | TG-5255E | REGION C
DURHAM | NORFOLK SOUTHERN H LINE | EAST DURHAM RAILROAD SAFETY PROJECT. PROJECT WILL STRAIGHTEN EXISTING RAILROAD CURVATURE BETWEEN CP NELSON AND CP EAST DURHAM AND INCLUDES A COMBINATION OF GRADE SEPARATIONS AND CLOSURES AT ELLIS ROAD SOUTH END (734737A), GLOVER ROAD (734735L), AND WRENN | RAIL | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | P-5706 | STATEWIDE MOBILITY | T | 2023 | 11243000 | 2023 | 2604000 | 2027 | 33801000 |  |  | 47648000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION
DURHAM | NORFOLK SOUTHERN H LINE | CROSSING 734742W AT SR 1121 (CORNWALLIS ROAD) IN DURHAM. CONSTRUCT GRADE SEPARATION. | RAIL | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | P-5717 | REGION C | T | 2022 | 5900000 | 2022 | 1878000 | 2024 | 25699000 |  |  | 33477000 | RIGHT-OF-WAY IN PROGRESS.
DURHAM | SR 1978 (HOPSON ROAD) | NORFOLK SOUTHERN RAILROAD-NORTH CAROLINA RAILROAD. CONSTRUCT RAILROAD GRADE SEPARATION AND SHIFT RAIL LINE | RAIL | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-4716A | [11 empty] | PROJECT COMPLETE
DURHAM | SR 1978 (HOPSON ROAD) | SR 1978 (HOPSON ROAD), EAST OF SR 1999 (DAVIS DRIVE) TO NC 54, WIDEN TO MULTILANES | RAIL | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-4716D | NOT FUNDED | O | NOT FUNDED | 1126000 |  |  | NOT FUNDED | 3160000 |  |  | 4286000
DURHAM | SR 1980 (CHURCH STREET) | NORFOLK SOUTHERN RAILROAD / NC RAILROAD TO SR 1978 (HOPSON ROAD) REALIGN AND CLOSE CROSSING 734 748M OF THE NORFOLK SOUTHERN-NORTH CAROLINA RAILROAD | RAIL | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-4716B | PRE-STI (TRANSITION) | [10 empty] | PROJECT COMPLETE
DURHAM, ORANGE | NC 54 | US 15 / US 501 IN CHAPEL HILL TO NC 55 IN DURHAM. UPGRADE ROADWAY CORRIDOR. | HIGHWAY | 5, 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5774 | [11 empty] | PARTS A THROUGH F ON EXPANDED NHS
DURHAM, ORANGE | SR 2220 (OLD CHAPEL HILL ROAD) SR 1838 (OLD DURHAM | US 15 / US 501 IN ORANGE COUNTY TO SR 1116 (GARRETT ROAD) IN DURHAM COUNTY. BICYCLE, PEDESTRIAN, AND TRANSIT IMPROVEMENTS; AND CONSTRUCTION OF ROUNDABOUT. | HIGHWAY | 5, 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-4707 | PRE-STI (TRANSITION)
DURHAM, ORANGE | DURHAM AREA TRANSIT AUTHORITY | OPERATING ASSISTANCE - NEW FREEDOM - URBAN | PUBLIC TRANSIT | 5, 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TN-5102 | PUBLIC TRANSIT | 5317, L | [6 empty] | 2020 | 504000 | 504000 | FUNDS AUTHORIZED IN PROGRESS
DURHAM, ORANGE | TRIANGLE TRANSIT AUTHORITY | REPLACEMENT BUS | PUBLIC TRANSIT | 5, 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TA-4818B | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2021 | 962000 | 962000
DURHAM, ORANGE | TRIANGLE TRANSIT AUTHORITY | EXPANSION BUS | PUBLIC TRANSIT | 5, 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TA-5123B | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 3242000 | 3242000 | FUNDS AUTHORIZED IN PROGRESS
DURHAM, ORANGE | TRIANGLE TRANSIT AUTHORITY | PLANNING ASSISTANCE | PUBLIC TRANSIT | 5, 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TP-4732A | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 2952000 | 2952000 | FUNDS AUTHORIZED IN PROGRESS
DURHAM, ORANGE | TRIANGLE TRANSIT AUTHORITY | SAFETY & SECURITY - MIN. 1% SET ASIDE | PUBLIC TRANSIT | 5, 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TS-5119 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 76000 | 76000 | FUNDS AUTHORIZED IN PROGRESS
DURHAM, ORANGE, CHATHAM | VARIOUS | DURHAM-CHAPEL HILL-CARRBORO (DCHC) MPO. BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS. | BIKE/PED | 5, 7, 8 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-4726 | DIVISION 5, 7, 8 | BGANY, BGDA, L | 2021 | 1909000 |  |  | 2021 | 11766000 |  |  | 13675000 | IN PROGRESS
DURHAM, ORANGE, CHATHAM | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE DURHAM / CHAPEL HILL / CARRBORO MPO. | HIGHWAY | 5, 7, 8 | DURHAM-CHAPEL HILL-CARRBORO MPO | C-5605 | EXEMPT | CMAQ, L | 2020 | 447000 |  |  | 2020 | 5490000 | 2020 | 2050000 | 7987000 | IN PROGRESS
DURHAM, ORANGE, CHATHAM | VARIOUS | DURHAM-CHAPEL HILL-CARRBORO METROPOLITAN PLANNING ORGANIZATION (DCHCMPO) PLANNING ALLOCATION AND UNIFIED WORK PROGRAM. | HIGHWAY | 5, 7, 8 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-4727 | DIVISION 5, 7, 8 | BGDA, L | [6 empty] | 2022 | 27818000 | 27818000 | PRIOR YEAR AMOUNT INCLUDES $223K FEDERAL TIGER GRANT
DURHAM, ORANGE, CHATHAM | VARIOUS | DURHAM-CHAPEL HILL-CARRBORO METROPOLITAN PLANNING ORGANIZATION (DCHCMPO) SURFACE TRANSPORTATION BLOCK GRANT DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. | HIGHWAY | 5, 7, 8 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5023 | DIVISION 5, 7, 8 | BGDA |  |  |  |  | 2022 | 76451000 |  |  | 76451000 | INCLUDES $137K TO BE ALLOCATED TO TG-5235; $1548K ALLOCATED TO U-4726.
DURHAM, ORANGE, CHATHAM | VARIOUS | DURHAM-CHAPEL HILL-CARRBORO METROPOLITAN PLANNING ORGANIZATION (DCHCMPO) TRANSPORTATION ALTERNATIVES DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. | HIGHWAY | 5, 7, 8 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-6219 | DIVISION 5, 7, 8 | TADA |  |  |  |  | 2022 | 10477000 |  |  | 10477000
DURHAM, WAKE | I-40 SR 1728 (WADE AVENUE) | NC 54 (EXIT 273) TO SR 1728 (WADE AVENUE), I-40 TO SR 1664 (BLUE RIDGE ROAD) CONVERT FACILITY TO A MANAGED FREEWAY WITH RAMP METERING AND OTHER ATM / ITS COMPONENTS. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO, CAPITAL AREA MPO | I-6006 | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 84699000 |  |  | 85699000
DURHAM, WAKE | NORFOLK-SOUTHERN RAILROAD / NC RAILROAD | CLEGG TO NELSON. CONSTRUCT PASSING SIDING | RAIL | 5 | CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | U-4716C | [11 empty] | PROJECT COMPLETE
DURHAM, WAKE | VARIOUS PIEDMONT CORRIDOR | VARIOUS ROUTES AND NORFOLK SOUTHERN RAILROAD-NORTH CAROLINA RAILROAD IN DURHAM AND MORRISVILLE, SOUTH OF I-40 TO NORTH OF MCCRIMMON PARKWAY. CONSTRUCT A GRADE SEPARATION AT SR 1978 (HOPSON ROAD), EXTEND CHURCH STREET TO HOPSON ROAD, CLOSE CHURCH STREET C | RAIL | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO, CAPITAL AREA MPO | U-4716
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | DIVISION 5 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | BIKE/PED | 5 | KERR-TAR RPO, CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | BO-2405 | DIVISION 5 | S, TA |  |  |  |  | 2024 | 10000000 |  |  | 10000000
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | ECOSYSTEM ENHANCEMENT PROGRAM FOR DIVISION 5 PROJECT MITIGATION. | HIGHWAY | 5 | KERR-TAR RPO, CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | EE-4905 | [11 empty] | IN PROGRESS
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 5. | HIGHWAY | 5 | KERR-TAR RPO, CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | HS-2005 | DIVISION 5
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | DIVISION 5 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | HIGHWAY | 5 | KERR-TAR RPO, CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | R-5785 | DIVISION 5 | S, TA |  |  |  |  | 2020 | 3600000 |  |  | 3600000 | IN PROGRESS; "S" FUNDS REFLECT STATE HIGHWAY FUNDS; UNDER CONSTRUCTION
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | DIVISION 5 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | 5 | KERR-TAR RPO, CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | W-5205 | [11 empty] | UNDER CONSTRUCTION
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 5. | HIGHWAY | 5 | KERR-TAR RPO, CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | W-5705 |  | NHP |  |  |  |  | 2020 | 150000 |  |  | 150000 | IN PROGRESS; $150K NHP FUNDING APPLIED TO W-5705S
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 5 | KERR-TAR RPO, CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | W-5705DIV | DIVISION 5 | HSIP | 2020 | 104000 |  |  | 2020 | 540000 |  |  | 644000
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 5 | KERR-TAR RPO, CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | W-5705REG | REGION C | HSIP | 2020 | 104000 |  |  | 2020 | 540000 |  |  | 644000
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 5 | KERR-TAR RPO, CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | W-5705SW | STATEWIDE MOBILITY | HSIP | 2020 | 137000 |  |  | 2020 | 720000 |  |  | 857000
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 5 | HIGHWAY | 5 | KERR-TAR RPO, CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | W-5805 | [11 empty] | W-5805B PROJECT DELETED AT REQUEST OF DIVISION; WORK TO BE ACCOMPLISHED UNDER U-6023.
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 5. | RAIL | 5 | KERR-TAR RPO, CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | RC-2005 | DIVISION 5 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
DURHAM, WAKE, FRANKLIN, GRANVILLE, PERSON, VANCE, WARREN | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 5. | RAIL | 5 | KERR-TAR RPO, CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | RX-2005 | DIVISION 5
EDGECOMBE | TARBORO EDGECOMBE AIRPORT (ETC) | RUNWAY EXTENSION. | AVIATION | 4 | UPPER COASTAL PLAIN RPO | AV-5897 | DIVISION 4 | T |  |  |  |  | 2028 | 3790000 |  |  | 3790000
EDGECOMBE | EAST RALEIGH BOULEVARD | US 64 TO ARLINGTON STREET IN ROCKY MOUNT. PEDESTRIAN IMPROVEMENTS. | BIKE/PED | 4 | ROCKY MOUNT URBAN AREA MPO | EB-5984 | DIVISION 4 | L, TA5200 |  |  |  |  | 2028 | 2700000 | 2026 | 300000 | 3000000
EDGECOMBE | NC 43 BUSINESS | CONSTRUCT SIDEWALK ON COKEY ROAD AND REX STREET. | BIKE/PED | 4 | ROCKY MOUNT URBAN AREA MPO | BL-0032 | DIVISION 4 | CMAQ, L | 2023 | 10000 |  |  | 2023 | 340000 | 2022 | 100000 | 450000
EDGECOMBE | NC 97 (ATLANTIC AVENUE) | US 64 TO EAST RALEIGH BOULEVARD IN ROCKY MOUNT. PEDESTRIAN IMPROVEMENTS. | BIKE/PED | 4 | ROCKY MOUNT URBAN AREA MPO | EB-5729 | DIVISION 4 | L, TA5200 |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7400000 | 2027 | 1200000 | 8600000
EDGECOMBE | NC 111 (WILSON STREET) | US 64 ALTERNATE (WESTERN BOULEVARD) TO NC 122 (MCNAIR ROAD). WIDEN TO THREE LANES. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | U-4424 | DIVISION 4 | T |  |  |  |  | 2023 | 10200000 |  |  | 10200000
EDGECOMBE | NC 111 / NC 122 | REPLACE BRIDGE 320011 OVER TOWN CREEK. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | B-5655 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 1950000 |  |  | 1950000
EDGECOMBE | NC 33 | REPLACE BRIDGE 320080 OVER TAR RIVER. REPLACE BRIDGE 320049 OVER TAR RIVER OVERFLOW. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | B-4933 | REGION A | BFP | 2025 | 860000 |  |  | 2027 | 9200000 |  |  | 10060000
EDGECOMBE | NC 42 | REPLACE BRIDGE 320028 OVER TAR RIVER. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | B-4932 | HIGHWAY FUND | [10 empty] | UNDER CONSTRUCTION
EDGECOMBE | NC 97 | BRIDGE 87 OVER SWIFT CREEK ON NC 97. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | B-5671 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 2279000 |  |  | 2279000 | RIGHT OF WAY IN PROGRESS.
EDGECOMBE | NC 97 | REPLACE BRIDGE 320051 OVER TAR RIVER. | HIGHWAY | 4 | ROCKY MOUNT URBAN AREA MPO | B-5952 | REGION A | BFP | 2026 | 100000 | 2026 | 703000 | 2030 | 6900000 |  |  | 7703000
EDGECOMBE | NEW ROUTE | SR 1252 (DUNBAR ROAD) TO SR 1225 (KINGSBORO ROAD). CONSTRUCT TWO LANE ROAD ON NEW LOCATION AND IMPROVEMENTS TO SR 1225 TO SERVE KINGSBORO MEGASITE. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | R-5868 | DIVISION 4 | [10 empty] | UNDER CONSTRUCTION
EDGECOMBE | SR 1126 (FAITH BAPTIST CHURCH ROAD) | REPLACE BRIDGE 320064 OVER TOWN CREEK. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | B-6002 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 1200000 |  |  | 1200000
EDGECOMBE | SR 1243 (LEGGETT ROAD) | REPLACE BRIDGE 320054 OVER TAR RIVER. | HIGHWAY | 4 | ROCKY MOUNT URBAN AREA MPO | BR-0241 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 3600000 |  |  | 3600000 | PROJECT REPRESENTS HFB 4.R.101 PROJECT. UNDER CONSTRUCTION.
EDGECOMBE | SR 1250 (SPRINGFIELD ROAD) | US 64 ALTERNATE TO SR 1243 (LEGGETT ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 4 | ROCKY MOUNT URBAN AREA MPO | U-4762 | DIVISION 4 | T |  |  |  |  | 2019 | 6255000 | 2021 | 1995000 | 8250000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $2,244,841.69 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $1,547,726 FOR PE, $2,609,121 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE)
EDGECOMBE | SR 1404 (SEVEN BRIDGES ROAD) | REPLACE BRIDGE NO. 320003, 320004, 320005 OVER SWIFT CREEK ON SR 1404 (SEVEN BRIDGES ROAD). | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | BR-0111 | DIVISION 4 | DP | 2020 | 420000 | 2020 | 56000 | 2021 | 5450000 |  |  | 5926000 | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING.
EDGECOMBE | SR 1616 (SHARP POINT ROAD) | REPLACE BRIDGE NO. 320035 OVER OTTER CREEK ON SR 1616 (SHARP POINT ROAD). | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | BR-0112 | DIVISION 4 | DP |  |  |  |  | 2021 | 1112000 |  |  | 1112000 | DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. UNDER CONSTRUCTION.
EDGECOMBE | US 258 | REPLACE BRIDGE 320022 OVER TOWN CREEK. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | B-4931 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 2129000 |  |  | 2129000
EDGECOMBE | US 258 | SR 1601 (COLONIAL ROAD) TO US 64. WIDEN ROADWAY. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | R-5949 | DIVISION 4 | T | 2027 | 1900000 | 2027 | 900000 | 2029 | 25400000 |  |  | 28200000
EDGECOMBE | US 64 (FUTURE I-87) | SR 1233 (THOMAS ROAD) OVERPASS TO NC 33. PAVEMENT REHABILITATION. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO, ROCKY MOUNT URBAN AREA MPO | I-6041 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2023 | 9141000 |  |  | 9141000
EDGECOMBE | US 64 (FUTURE I-87) | REHABILITATE BRIDGES 320104, 320155, 320148, 320153, 320154, 320156, 320157, 320320, 320325, AND 320326. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | I-6041A | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2022 | 3068000 |  |  | 3068000
EDGECOMBE | US 64 (FUTURE I-87) | NC 33 TO MARTIN COUNTY LINE. PAVEMENT REHABILITATION. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | I-6042 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2023 | 7895000 |  |  | 7895000
EDGECOMBE | US 64 (FUTURE I-87) | REHABILITATE BRIDGE 320327 AND 320328. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | I-6042A | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2022 | 283000 |  |  | 283000
EDGECOMBE | US 64 WEST ALTERNATE | WEST HOWARD STREET TO NC 111 (WEST WILSON STREET). CONSTRUCT 10' MULTI-USE PATH ALONG WESTERN BOULEVARD IN TARBORO. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | BL-0064 | EXEMPT | CMAQ, L | 2023 | 51000 |  |  | 2024 | 717000 | 2023 | 134000 | 902000
EDGECOMBE | CSX A LINE | CCX INTERMODAL TERMINAL AND TRACK IMPROVEMENTS. | RAIL | 4 | ROCKY MOUNT URBAN AREA MPO | P-5711A | STATEWIDE MOBILITY | T |  |  |  |  | 2020 | 43100000 |  |  | 43100000 | UNDER CONSTRUCTION
EDGECOMBE, HALIFAX, JOHNSTON, WILSON, NASH, WAYNE | VARIOUS | ECOSYSTEM ENHANCEMENT PROGRAM FOR DIVISION 4 PROJECT MITIGATION. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO, PEANUT BELT RPO, GOLDSBORO URBAN AREA MPO, EASTERN CAROLINA RPO, ROCKY MOUNT URBAN AREA MPO | EE-4904 | [11 empty] | IN PROGRESS
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | DIVISION 4 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | BIKE/PED | 4 | UPPER COASTAL PLAIN RPO, EASTERN CAROLINA RPO, GOLDSBORO URBAN AREA MPO, PEANUT BELT RPO, ROCKY MOUNT URBAN AREA MPO | BO-2404 | DIVISION 4 | S, TA |  |  |  |  | 2024 | 10000000 |  |  | 10000000
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 4. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO, EASTERN CAROLINA RPO, GOLDSBORO URBAN AREA MPO, PEANUT BELT RPO, ROCKY MOUNT URBAN AREA MPO | HS-2004 | DIVISION 4
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | DIVISION 4 PROGRAM TO UPGRADE INTERSECTIONS TO COMPLY WITH THE AMERICANS WITH DISABILITIES ACT (ADA) USING TRANSPORTATION ALTERNATIVES (TA) FUNDS. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO, EASTERN CAROLINA RPO, GOLDSBORO URBAN AREA MPO, PEANUT BELT RPO, ROCKY MOUNT URBAN AREA MPO | R-5784 | DIVISION 4 | S, TA |  |  |  |  | 2020 | 3500000 |  |  | 3500000 | UNDER CONSTRUCTION; "S" FUNDS REFLECT STATE HIGHWAY FUNDS
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | DIVISION 4 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO, EASTERN CAROLINA RPO, GOLDSBORO URBAN AREA MPO, PEANUT BELT RPO, ROCKY MOUNT URBAN AREA MPO | W-5204 | [11 empty] | DIVISION PURCHASE ORDER CONTRACT (DPOC) - IN PROGRESS
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 4. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO, EASTERN CAROLINA RPO, GOLDSBORO URBAN AREA MPO, PEANUT BELT RPO, ROCKY MOUNT URBAN AREA MPO | W-5704 | [11 empty] | IN PROGRESS
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO, EASTERN CAROLINA RPO, GOLDSBORO URBAN AREA MPO, PEANUT BELT RPO, ROCKY MOUNT URBAN AREA MPO | W-5704DIV | DIVISION 4 | HSIP | 2020 | 144000 |  |  | 2022 | 360000 |  |  | 504000
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO, EASTERN CAROLINA RPO, GOLDSBORO URBAN AREA MPO, PEANUT BELT RPO, ROCKY MOUNT URBAN AREA MPO | W-5704REG | REGION A | HSIP | 2022 | 30000 |  |  | 2020 | 455000 |  |  | 485000
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO, EASTERN CAROLINA RPO, GOLDSBORO URBAN AREA MPO, PEANUT BELT RPO, ROCKY MOUNT URBAN AREA MPO | W-5704SW | STATEWIDE MOBILITY | HSIP | 2022 | 40000 |  |  | 2022 | 480000 |  |  | 520000
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | SAFETY IMPROVEMENTS AT VARIOUS LOCATIONS IN DIVISION 4. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO, EASTERN CAROLINA RPO, GOLDSBORO URBAN AREA MPO, PEANUT BELT RPO, ROCKY MOUNT URBAN AREA MPO | W-5804 | [11 empty] | INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES IN DIVISION 4. | RAIL | 4 | UPPER COASTAL PLAIN RPO, EASTERN CAROLINA RPO, GOLDSBORO URBAN AREA MPO, PEANUT BELT RPO, ROCKY MOUNT URBAN AREA MPO | RC-2004 | DIVISION 4 | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY. INDIVIDUAL PROJECTS AND FUNDING TO BE REQUESTED IN THE FUTURE AS NEEDED.
EDGECOMBE, JOHNSTON, NASH, WAYNE, HALIFAX, WILSON | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS IN DIVISION 4. | RAIL | 4 | UPPER COASTAL PLAIN RPO, EASTERN CAROLINA RPO, GOLDSBORO URBAN AREA MPO, PEANUT BELT RPO, ROCKY MOUNT URBAN AREA MPO | RX-2004 | DIVISION 4
EDGECOMBE, NASH | ROCKY MOUNT | US 301 BUSINESS, RIVER DRIVE TO MONK STREET IN ROCKY MOUNT. CONVERT ABANDONED RAILROAD TO MULTI-USE PATH. | BIKE/PED | 4 | ROCKY MOUNT URBAN AREA MPO | EB-5763 | DIVISION 4 | L, TA5200 | 2024 | 300000 |  |  | 2025 | 1500000 | 2022 | 200000 | 2000000
EDGECOMBE, NASH | US 64 (FUTURE I-87) | SR 1603 (OLD CARRIAGE ROAD) TO SR 1225 (KINGSBORO ROAD). PAVEMENT REHABILITATION. | HIGHWAY | 4 | ROCKY MOUNT URBAN AREA MPO, UPPER COASTAL PLAIN RPO | I-6046 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2022 | 24006000 |  |  | 24006000 | UNDER CONSTRUCTION.
EDGECOMBE, NASH | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY MOUNT MPO. | HIGHWAY | 4 | ROCKY MOUNT URBAN AREA MPO | C-5616 | EXEMPT | CMAQ, L | 2020 | 116000 |  |  | 2020 | 910000 | 2020 | 348000 | 1374000
EDGECOMBE, NASH | TAR RIVER TRANSIT | OPERATING ASSISTANCE - ADA PARATRANSIT SERVICE | PUBLIC TRANSIT | 4 | ROCKY MOUNT URBAN AREA MPO | TG-4785A | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 480000 | 480000 | FUNDS AUTHORIZED IN PROGRESS
EDGECOMBE, NASH | TAR RIVER TRANSIT | PREVENTIVE MAINTENANCE | PUBLIC TRANSIT | 4 | ROCKY MOUNT URBAN AREA MPO | TG-4785B | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2400000 | 2400000 | FUNDS AUTHORIZED IN PROGRESS
EDGECOMBE, NASH | TAR RIVER TRANSIT | ADMINISTRATION | PUBLIC TRANSIT | 4 | ROCKY MOUNT URBAN AREA MPO | TK-5180 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 780000 | 780000 | FUNDS AUTHORIZED IN PROGRESS
EDGECOMBE, NASH | TAR RIVER TRANSIT | PURCHASE AND INSTALL 20 BUS SHELTERS | PUBLIC TRANSIT | 4 | ROCKY MOUNT URBAN AREA MPO | TL-0015 | PUBLIC TRANSIT | CARES | [6 empty] | 2022 | 150000 | 150000
EDGECOMBE, NASH | TAR RIVER TRANSIT | UPDATE THE TAR RIVER TANSIT AUTOMATED VEHICLE LOCATOR SYSTEM | PUBLIC TRANSIT | 4 | ROCKY MOUNT URBAN AREA MPO | TL-0016 | PUBLIC TRANSIT | CARES | [6 empty] | 2022 | 300000 | 300000
EDGECOMBE, NASH | TAR RIVER TRANSIT | OPERATING ASSISTANCE | PUBLIC TRANSIT | 4 | ROCKY MOUNT URBAN AREA MPO | TO-5127 | PUBLIC TRANSIT | 5307, L, SMAP | [6 empty] | 2020 | 4000000 | 4000000 | FUNDS AUTHORIZED IN PROGRESS
EDGECOMBE, NASH | CSX A LINE | CONSTRUCT FREIGHT RAIL AND INTERMODAL TERMINAL INFRASTRUCTURE (CCX) ALONG NATIONAL GATEWAY CORRIDOR. | RAIL | 4 | ROCKY MOUNT URBAN AREA MPO, UPPER COASTAL PLAIN RPO | P-5711 | STATEWIDE MOBILITY
EDGECOMBE, NASH | CSX A LINE | HIGHWAY IMPROVEMENTS | RAIL | 4 | ROCKY MOUNT URBAN AREA MPO | P-5711C | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
EDGECOMBE, NASH | VARIOUS | CAROLINIAN CORRIDOR - CSXT MP A 115.9 (ARMSTRONG CROSSING). | RAIL | 4 | ROCKY MOUNT URBAN AREA MPO | P-5005B | PRE-STI (TRANSITION)
FORSYTH | SMITH REYNOLDS AIRPORT (INT) | ACQUIRE LAND AND CLEAR TERRAIN OBSTRUCTIONS EAST OF RUNWAY 15-33 TO DRAIN AND GRADE MATERIAL IN PLACE. | AVIATION | 9 | WINSTON-SALEM URBAN AREA MPO | AV-5738 | DIVISION 9 | T |  |  |  |  | 2023 | 2450000 |  |  | 2450000 | RIGHT-OF-WAY IN PROGRESS BY AIRPORT
FORSYTH | SMITH REYNOLDS AIRPORT (INT) | CONSTRUCT NEW TAXILANE. | AVIATION | 9 | WINSTON-SALEM URBAN AREA MPO | AV-5832 | DIVISION 9 | T |  |  |  |  | 2023 | 15700000 |  |  | 15700000
FORSYTH | BARBARA JANE AVENUE | OLD GREENSBORO ROAD TO WOODROW POWELL DRIVE IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | BIKE/PED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-5810 | DIVISION 9 | BGDA, L, TAANY |  |  |  |  | 2022 | 226000 |  |  | 226000 | IN PROGRESS
FORSYTH | BREWER ROAD | BUCHANAN STREET TO CLEMMONSVILLE ROAD IN WINSTON-SALEM. CONSTRUCT FIVE-FOOT SIDEWALK. | BIKE/PED | 9 | WINSTON-SALEM URBAN AREA MPO | BL-0018 | DIVISION 9 | BGDA, L | 2023 | 513000 |  |  | 2024 | 2326000 | 2023 | 205000 | 3044000
FORSYTH | BROAD STREET | SR 4309 (EAST MOUNTAIN STREET) TO HARMON LANE IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK.. | BIKE/PED | 9 | WINSTON-SALEM URBAN AREA MPO | BL-0015 | DIVISION 9 | BGDA, L | 2026 | 99000 |  |  | 2027 | 994000 | 2025 | 155000 | 1248000
FORSYTH | BRUSHY FORK GREENWAY | WATERWORKS ROAD TO REYNOLDS PARK ROAD IN WINSTON-SALEM. PAVED MULTIUSE TRAIL. | BIKE/PED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-4020 | PRE-STI (TRANSITION)
FORSYTH | BRUSHY FORK GREENWAY | WATERWORKS ROAD TO OLD GREENSBORO ROAD | BIKE/PED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-4020A | [11 empty] | COMPLETE
FORSYTH | BRUSHY FORK GREENWAY | OLD GREENSBORO ROAD TO LOWERY STREET | BIKE/PED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-4020B | [11 empty] | COMPLETE
FORSYTH | BRUSHY FORK GREENWAY | LOWERY STREET TO REYNOLDS PARK ROAD | BIKE/PED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-4020C | PRE-STI (TRANSITION) | BGANY, BGDA, L |  |  |  |  | 2023 | 2158000 |  |  | 2158000 | RIGHT-OF-WAY IN PROGRESS
FORSYTH | DEPOT STREET | US 311 (MAIN STREET) TO SR 1992 (SULLIVANTOWN ROAD) IN WALKERTOWN. CONSTRUCT SIDEWALK. | BIKE/PED | 9 | WINSTON-SALEM URBAN AREA MPO | BL-0020 | DIVISION 9 | BGDA, L | 2023 | 90000 |  |  | 2023 | 389000 |  |  | 479000
FORSYTH | FAIRLAWN DRIVE | NC 67 (REYNOLDA ROAD) TO SR 1528 (SILAS CREEK PKWY) IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | BIKE/PED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-5952 | DIVISION 9 | BGANY, BGDA, L | 2022 | 248000 |  |  | 2023 | 741000 |  |  | 989000 | IN PROGRESS
FORSYTH | GRIFFITH ROAD | KIMWELL DRIVE TO BURKE MILL ROAD IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | BIKE/PED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-5954 | DIVISION 9 | BGANY, L | 2022 | 42000 |  |  | 2023 | 1620000 |  |  | 1662000 | IN PROGRESS
FORSYTH | HARMON LANE | SR 4315 (SOUTH MAIN STREET) TO BROAD STREET IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | BIKE/PED | 9 | WINSTON-SALEM URBAN AREA MPO | BL-0016 | DIVISION 9 | BGDA, L | 2025 | 79000 |  |  | 2026 | 365000 | 2024 | 55000 | 499000
FORSYTH | LONG BRANCH TRAIL PHASE II | SR 2516 (MARTIN LUTHER KING, JR. DRIVE) TO 27TH STREET IN WINSTON-SALEM. CONSTRUCT TEN-FOOT TRAIL. | BIKE/PED | 9 | WINSTON-SALEM URBAN AREA MPO | BL-0019 | DIVISION 9 | BGDA, L |  |  |  |  | 2024 | 100000 | 2021 | 1000000 | 1100000
FORSYTH | NC 67 (SILAS CREEK PARKWAY) | DRUMCLIFFE ROAD TO LOCKLAND AVENUE IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON NORTH SIDE AND SOUTH SIDE OF SILAS CREEK PARKWAY TO CONNECT EXISTING SECTIONS. | BIKE/PED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-5722 | DIVISION 9 | BGANY, BGDA, L, TAANY | 2022 | 910000 |  |  | 2023 | 4038000 |  |  | 4948000 | IN PROGRESS
FORSYTH | SALEM CREEK GREENWAY | FORSYTH TECHNICAL COMMUNITY COLLEGE TO EXISTING GREENWAY AT MARKETPLACE MALL IN WINSTON-SALEM. CONSTRUCT GREENWAY. | BIKE/PED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-5812 | DIVISION 9 | L, TAANY |  |  |  |  | 2026 | 1500000 | 2020 | 150000 | 1650000
FORSYTH | SOUTHERN STREET GREENWAY | SOUTHERN STREET TO KERNERS MILL CREEK GREENWAY IN KERNERSVILLE. CONSTRUCT MULTI-USE PAVED PATH. | BIKE/PED | 9 | WINSTON-SALEM URBAN AREA MPO | BL-0017 | DIVISION 9 | BGDA, L | 2024 | 50000 |  |  | 2025 | 851000 | 2023 | 146000 | 1047000
FORSYTH | SR 1101 (HARPER ROAD) | CONSTRUCT SIDEWALK AND CROSSWALKS WHERE GAPS EXIST BETWEEN JERRY LONG YMCA ON PEACEHAVEN ROAD TO ROUNDABOUT WEST OF FRANK MORGAN ELEMENTARY SCHOOL IN CLEMMONS. | BIKE/PED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-5960 | DIVISION 9 | BGANY, BGDA, L |  |  |  |  | 2023 | 1126000 | 2021 | 125000 | 1251000 | IN PROGRESS
FORSYTH | SR 1101 (HARPER ROAD) | NORTH OF FAIR OAKS DRIVE TO MORGAN ELEMENTARY SCHOOL WESTERN ENTRANCE IN CLEMMONS. CONSTRUCT PEDESTRIAN IMPROVEMENTS, INCLUDING SIDEWALK. | BIKE/PED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-6040 | DIVISION 9 | BGDA, L |  |  |  |  | 2023 | 598000 | 2022 | 66000 | 664000
FORSYTH | SR 1122 (JONESTOWN ROAD) | EAST OF US 421 TO SR 1001 (COUNTRY CLUB ROAD) IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON EAST SIDE AND WEST SIDE OF JONESTOWN RD. | BIKE/PED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-5920 | DIVISION 9 | L, TAANY | 2024 | 80000 | 2024 | 85000 | 2025 | 585000 | 2021 | 50000 | 800000
FORSYTH | SR 1348 (ROBINHOOD ROAD) | SPEAKS FARM ROAD TO MUDDY CREEK GREENWAY IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | BIKE/PED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-5955 | DIVISION 9 | BGANY, L | 2022 | 66000 |  |  | 2024 | 470000 |  |  | 536000 | IN PROGRESS
FORSYTH | SR 1992 (SULLIVANTOWN ROAD) | US 311 AT HARLEY DRIVE TO WALKERTOWN HIGH/MIDDLE SCHOOL IN WALKERTOWN. INSTALL BICYCLE AND PEDESTRIAN FACILITIES AND CONSTRUCT SIDEWALK. | BIKE/PED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-5956 | DIVISION 9 | BGANY, BGDA, L | 2023 | 10000 |  |  | 2023 | 550000 |  |  | 560000
FORSYTH | SR 2648 (OLD WINSTON ROAD) | EXISTING SIDEWALK ACROSS FROM SEVENTH DAY ADVENTIST CHURCH PARKING LOT TO HOPKINS ROAD IN KERNERSVILLE. CONSTRUCT SIDEWALK ON SOUTH SIDE. | BIKE/PED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-5957 | DIVISION 9 | BGANY, BGDA, L | 2021 | 36000 |  |  | 2022 | 232000 |  |  | 268000 | RIGHT OF WAY IN PROGRESS
FORSYTH | SR 3000 (IDOLS ROAD) | SR 1103 (MIDDLEBROOK DRIVE) TO TANGLEWOOD PARK ROAD IN CLEMMONS. CONSTRUCT SIDEWALK. | BIKE/PED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-5959 | DIVISION 9 | BGANY, BGDA, L |  |  |  |  | 2025 | 897000 | 2021 | 110000 | 1007000 | IN PROGRESS
FORSYTH | SR 4000 (UNIVERSITY PARKWAY) | SR-1686 (SHATTALON DRIVE) TO ROBIN WOOD LANE IN WINSTON-SALEM. CONSTRUCT SIDEWALK. | BIKE/PED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-5953 | DIVISION 9 | BGDA, L |  |  |  |  | 2024 | 635000 |  |  | 635000 | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF WINSTON-SALEM
FORSYTH | SR 4278 (SOUTH CHERRY STREET) | OAKHURST STREET TO HOLY CROSS CHURCH IN KERNERSVILLE. CONSTRUCT FIVE-FOOT SIDEWALK. | BIKE/PED | 9 | WINSTON-SALEM URBAN AREA MPO | BL-0014 | DIVISION 9 | BGDA, L | 2023 | 145000 |  |  | 2024 | 2257000 | 2022 | 361000 | 2763000
FORSYTH | US 158 / US 421 (SALEM PARKWAY) | LOCKLAND AVENUE TO NC 150 (PETERS CREEK PARKWAY) IN WINSTON-SALEM. CONSTRUCT MULTIUSE PATH. | BIKE/PED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-6008 | DIVISION 9 | L, TAANY | 2023 | 110000 |  |  | 2023 | 2255000 | 2020 | 339000 | 2704000
FORSYTH | US 158 / US 421 / NC 150 (SALEM PARKWAY) | NC 150 (PETERS CREEK PARKWAY) TO THE STROLLWAY IN WINSTON-SALEM. CONSTRUCT MULTI-USE PATH. | BIKE/PED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-5840 | DIVISION 9 | BGDA, L, TAANY, TADA |  |  |  |  | 2022 | 3730000 |  |  | 3730000 | COORDINATE WITH U-2827B DESIGN-BUILD PROJECT
FORSYTH | FUTURE I-74 | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, I-74 / US 311 TO US 52. MULTILANE FREEWAY ON NEW LOCATION. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-2579 | [11 empty] | GARVEE BONDS / BUILD NC BONDS: SEE INDIVIDUAL SEGMENTS FOR BOND AMOUNTS AND PAYBACK YEARS
FORSYTH | FUTURE I-74 | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, I-74 / US 311 TO I-40 | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-2579AA | REGION D | NHP |  |  |  |  | 2023 | 95099000 |  |  | 95099000 | RIGHT-OF-WAY IN PROGRESS
FORSYTH | FUTURE I-74 | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, I-40 TO US 421 / NC 150 / BUSINESS 40 | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-2579AB | REGION D | NHP, S(M) |  |  |  |  | 2022 | 310367000 |  |  | 310367000 | UNDER CONSTRUCTION; GARVEE BONDS: $60 MILLION FOR CONSTRUCTION - PAYBACK 2022-2036
FORSYTH | FUTURE I-74 | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, US 421 / NC 150 / BUSINESS 40 TO US 158 | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-2579B | PRE-STI (TRANSITION) | NHP |  |  |  |  | 2015 | 68971000 |  |  | 68971000 | UNDER CONSTRUCTION; GARVEE BONDS: $96 MILLION FOR CONSTRUCTION - PAYBACK 2015-2026
FORSYTH | FUTURE I-74 | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, US 421 / NC 150 / BUSINESS 40 TO US 158. STREAM RELOCATION. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-2579BA | PRE-STI (TRANSITION) | NHP |  |  |  |  | 2021 | 9300000 |  |  | 9300000 | UNDER CONSTRUCTION
FORSYTH | FUTURE I-74 | CONSTRUCT NOISE WALL | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-2579BB | PRE-STI (TRANSITION) | T |  |  | 2022 | 234000 | 2023 | 2500000 |  |  | 2734000 | UNDER CONSTRUCTION
FORSYTH | FUTURE I-74 | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, US 158 TO US 311 | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-2579C | REGION D | NHP, T | 2016 | 6138000 |  |  | 2018 | 27222000 |  |  | 33360000 | UNDER CONSTRUCTION; GARVEE BONDS: $6.5 MILLION FOR RIGHT-OF-WAY - PAYBACK 2016-2030; BUILD NC BONDS: $9.061 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
FORSYTH | FUTURE I-74 | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, US 311 TO SR 2211 (BAUX MOUNTAIN ROAD) | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-2579D | STATEWIDE MOBILITY | NHP |  |  |  |  | 2018 | 42380000 |  |  | 42380000 | UNDER CONSTRUCTION - DESIGN-BUILD PROJECT; GARVEE BONDS: $38 MILLION FOR CONSTRUCTION - PAYBACK 2018-2032
FORSYTH | FUTURE I-74 | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, SR 2211 (BAUX MOUNTAIN ROAD) TO NC 8 | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-2579E | STATEWIDE MOBILITY | NHP |  |  |  |  | 2018 | 33462000 |  |  | 33462000 | UNDER CONSTRUCTION - DESIGN-BUILD PROJECT; GARVEE BONDS: $30 MILLION FOR CONSTRUCTION - PAYBACK 2018-2032
FORSYTH | FUTURE I-74 | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, NC 8 TO WEST OF NC 66 (UNIVERSITY PARKWAY) | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-2579F | STATEWIDE MOBILITY | NHP |  |  |  |  | 2018 | 26767000 |  |  | 26767000 | UNDER CONSTRUCTION - DESIGN-BUILD PROJECT; GARVEE BONDS: $24 MILLION FOR CONSTRUCTION - PAYBACK 2018-2032
FORSYTH | I-40 | 1.3 MILES EAST OF NC 150 (PETERS CREEK PARKWAY) TO NC 109 (THOMASVILLE ROAD) IN WINSTON-SALEM. PAVEMENT REHABILITATION. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | I-5766 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION - COORDINATE WITH I-5857
FORSYTH | I-40 | 0.3 MILE EAST OF SR 3153 (HANES MALL BOULEVARD) TO 0.9 MILE EAST OF NC 150 (PETERS CREEK PARKWAY) IN WINSTON-SALEM AND SR 2747 (CLEMMONSVILLE ROAD) IN WINSTON-SALEM TO GUILFORD COUNTY LINE. PAVEMENT REHABILITATION AND REHABILITATION OF BRIDGES 330161, 33 | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | I-5795 | STATEWIDE MOBILITY | NHFP, NHPIM |  |  |  |  | 2020 | 23814000 |  |  | 23814000 | UNDER CONSTRUCTION
FORSYTH | I-40 | SR 1101 (HARPER ROAD) IN CLEMMONS TO EAST OF US 421 / BUSINESS 40 IN WINSTON-SALEM. PAVEMENT REHABILITATION. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | I-5952 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION. DELETE I-5952A. WORK ACCOMPLISHED UNDER I-5795.
FORSYTH | I-40 | I-74 / US 311 TO SR 2643 (UNION CROSS ROAD). | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | I-5981A | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 61293000 |  |  | 67693000
FORSYTH | I-40 | SR 2643 (UNION CROSS ROAD) TO NC 66. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | I-5981B | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 38194000 |  |  | 40394000
FORSYTH | I-40 / US 311 | NC 109 (THOMASVILLE ROAD) / CLEMMONSVILLE ROAD SPLIT-DIAMOND INTERCHANGE IN WINSTON-SALEM. CONVERT HALF DIAMOND INTERCHANGE AT NC 109 TO FULL DIAMOND, AND REMOVE CONNECTOR ROADS AND HALF DIAMOND INTERCHANGE AT CLEMMONSVILLE ROAD | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | I-5880 | REGION D | NHP, T | 2023 | 2600000 | 2023 | 800000 | 2025 | 24000000 |  |  | 27400000
FORSYTH | I-74 / US 311 | I-40 TO GUILFORD COUNTY LINE. PAVEMENT REHABILITATION. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO, HIGH POINT URBAN AREA MPO | I-5767 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION - CONSTRUCTION COST INCLUDED IN I-5736
FORSYTH | KERNERSVILLE SOUTHERN LOOP (PHASE I) | US 421 / BUSINESS 40 TO NC 66 (WEST MOUNTAIN STREET) IN KERNERSVILLE. WIDEN BIG MILL FARM ROAD AND SR 2649 (HOPKINS ROAD) AND CONSTRUCT INTERCHANGE AT US 421 / NC 150 / BUSINESS 40. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-5760 | DIVISION 9 | T | 2022 | 11500000 | 2022 | 4000000 | 2025 | 44462000 |  |  | 59962000 | IN PROGRESS. BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE)
FORSYTH | NC 65 (BETHANIA-RURAL HALL ROAD) | US 52 TO SR 3983 (NORTHRIDGE DRIVE) IN RURAL HALL. WIDEN TO MULTILANES. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-6005 | DIVISION 9 | T | 2023 | 3800000 | 2023 | 900000 | 2025 | 5300000 |  |  | 10000000 | RIGHT OF WAY IN PROGRESS
FORSYTH | NC 65 (BETHANIA-RURAL HALL ROAD) | SR 1647 (GLADE STREET) TO NC 66 IN RURAL HALL. WIDEN TO 3 LANES. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-6190 | DIVISION 9 | T | 2027 | 1700000 | 2027 | 400000 | 2029 | 3100000 |  |  | 5200000
FORSYTH | NC 66 (OLD HOLLOW ROAD) | HARLEY DRIVE TO US 158 IN WALKERTOWN. WIDEN TO MULTILANES. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-5824 | DIVISION 9 | T | 2021 | 18798000 |  |  | 2024 | 16406000 |  |  | 35204000 | RIGHT OF WAY IN PROGRESS
FORSYTH | NC 66 / SR 4309 (WEST MOUNTAIN STREET) | BEAUCREST STREET TO ASBURY DRIVE IN KERNERSVILLE. CONSTRUCT TURN-LANE BETWEEN KERNERSVILLE YMCA AND DEERE-HITACHI EAST ENTRANCE, AND EXTEND EXISTING SIDEWALK FROM BEAUCREST STREET TO ASBURY DRIVE. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | HL-0015 | EXEMPT | BGDA, L | 2022 | 282000 |  |  | 2025 | 3181000 | 2022 | 821000 | 4284000
FORSYTH | NC 67 (WESTBOUND) (SILAS CREEK PARKWAY) | REPLACE BRIDGES 330007 AND 330295 OVER SALEM CREEK IN WINSTON-SALEM. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | B-5950 | REGION D | BFP | 2026 | 750000 |  |  | 2027 | 7500000 |  |  | 8250000
FORSYTH | NC 8 (GERMANTON ROAD) | SR 1686 (OAK SUMMIT ROAD). CONSTRUCT LEFT TURN LANES AND SIGNAL IMPROVEMENTS. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | HL-0059 | EXEMPT | BGDA, CMAQ, S | 2023 | 330000 | 2023 | 250000 | 2023 | 1244000 | 2023 | 75000 | 1899000 | "S" FUNDS REFLECT SPOT MOBILITY FUNDS
FORSYTH | NEW ROUTE | SALEM CREEK CONNECTOR, SR 4326 (RAMS DRIVE) TO SR 4325 (MARTIN LUTHER KING, JR. DRIVE) IN WINSTON-SALEM. MULTILANE FACILITY ON NEW LOCATION. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-2925 | PRE-STI (TRANSITION) | [10 empty] | DESIGN-BUILD PROJECT COMPLETE
FORSYTH | NEW ROUTE | SALEM CREEK CONNECTOR, SR 4326 (RAMS DRIVE TO SR 4325 (MARTIN LUTHER KING, JR DRIVE). LANDSCAPING AND LIGHTING. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-2925C | DIVISION 9 | BGDA, L |  |  |  |  | 2023 | 1358000 | 2021 | 453000 | 1811000 | UNDER CONSTRUCTION
FORSYTH | NEW ROUTE | MACY GROVE ROAD EXTENSION, SR 1005 (EAST MOUNTAIN STREET) TO NC 150 (NORTH MAIN STREET) IN KERNERSVILLE. FOUR-LANE DIVIDED FACILITY ON NEW LOCATION. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-4734 | DIVISION 9 | T |  |  |  |  | 2019 | 11172000 |  |  | 11172000 | UNDER CONSTRUCTION; BUILD NC BONDS: $8.669 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE)
FORSYTH | NEW ROUTE | PROPOSED GREAT WAGON ROAD FROM SHALLOWFORD ROAD (SR 1001) TO LEWISVILLE-VIENNA ROAD (SR 1308) IN LEWISVILLE. MULTILANE FACILITY ON NEW LOCATION WITH BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-5536 | DIVISION 9 | T | 2022 | 14500000 | 2022 | 656000 | 2024 | 12900000 |  |  | 28056000 | IN PROGRESS
FORSYTH | NEW ROUTE | FORUM PARKWAY CONNECTOR, SR 3955 (FORUM PARKWAY) TO NC 66 (UNIVERSITY PARKWAY) IN RURAL HALL. CONSTRUCT 2-LANE ROADWAY ON NEW LOCATION. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-5899 | DIVISION 9 | T | 2022 | 4300000 | 2022 | 1300000 | 2024 | 9001000 |  |  | 14601000 | RIGHT OF WAY IN PROGRESS
FORSYTH | NEW ROUTE | SR 1969 (PINEY GROVE ROAD) TO NC 150 (NORTH MAIN STREET) IN KERNERSVILLE. CONSTRUCT TWO-LANE DIVIDED FACILITY WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-6003 | DIVISION 9 | T |  |  |  |  | 2024 | 12100000 |  |  | 12100000 | RIGHT-OF-WAY IN PROGRESS
FORSYTH | NEW ROUTE | SR 4001 (REYNOLDS BOULEVARD) TO SR 2264 (AKRON DRIVE) AT INTERSECTION OF SR 1763 (INDIANA AVENUE) IN WINSTON-SALEM. CONSTRUCT ACCESS ROAD. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-6231 | DIVISION 9 | L, T |  |  |  |  | 2021 | 4000000 |  |  | 4000000 | UNDER CONSTRUCTION; ECONOMIC DEVELOPMENT PROJECT
FORSYTH | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, I-40 TO US 52. FOUR LANE EXPRESSWAY ON NEW LOCATION., INCLUDING ITS DEPLOYMENT. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247
FORSYTH | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, US 158 TO SOUTH OF I-40 | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247A | NOT FUNDED | NHP, T | NOT FUNDED | 13200000 | NOT FUNDED | 18900000 | NOT FUNDED | 39101000 |  |  | 71201000 | DESIGN-BUILD PROJECT
FORSYTH | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, SOUTH OF I-40 TO SOUTH OF US 421 INTERCHANGE | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247B | NOT FUNDED | NHP, T | NOT FUNDED | 31900000 | NOT FUNDED | 3000000 | NOT FUNDED | 149499000 |  |  | 184399000 | DESIGN-BUILD PROJECT
FORSYTH | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, INTERCHANGE WITH US 421 AND INTERCHANGE WITH SR 1140 (PEACE HAVEN ROAD) | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247CA | REGION D | NHP, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 270000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 140900000 |  |  | 141770000 | DESIGN-BUILD PROJECT
FORSYTH | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, NORTH OF US 421 INTERCHANGE TO SR 1348 (ROBINHOOD ROAD) | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247CB | REGION D | NHP, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 82499000 |  |  | 97299000 | DESIGN-BUILD PROJECT
FORSYTH | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, MUDDY CREEK. REPLACE BRIDGE NO. 221 AND BRIDGE NO. 222 | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247CC | [11 empty] | COMPLETE - WORK ACCOMPLISHED UNDER B-4507
FORSYTH | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, NORTH OF SR 1348 (MEADOWLARK DRIVE-ROBINHOOD ROAD) TO NC 67 | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247D | REGION D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 65001000 |  |  | 68501000
FORSYTH | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, NC 67 TO SOUTH OF US 52 | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247EA | REGION D | NHP, T | 2028 | 14700000 | 2028 | 1100000 | 2030 | 160199000 |  |  | 175999000 | IN PROGRESS
FORSYTH | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, INTERCHANGE AT US 52 | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247EB | STATEWIDE MOBILITY | NHP |  |  |  |  | 2018 | 83655000 |  |  | 83655000 | DESIGN-BUILD PROJECT - UNDER CONSTRUCTION; GARVEE BONDS: $75M FOR CONSTRUCTION, PAYBACK - 2018-2032
FORSYTH | POLO ROAD | REPLACE BRIDGE 330284 OVER SR 4000 (UNIVERSITY PARKWAY) IN WINSTON-SALEM. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | HB-0033 | DIVISION 9 | BFP | 2025 | 300000 | 2025 | 300000 | 2026 | 6000000 |  |  | 6600000
FORSYTH | SALISBURY RIDGE ROAD | REPLACE BRIDGE 330243 OVER NC 150 IN WINSTON-SALEM. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | B-5770 | DIVISION 9 | BGOFF |  |  |  |  | 2022 | 5501000 |  |  | 5501000 | RIGHT-OF-WAY IN PROGRESS
FORSYTH | SIXTEENTH STREET | REPLACE BRIDGE 330244 OVER US 52 / NC 8 IN WINSTON-SALEM. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | HB-0036 | DIVISION 9 | BGOFF | 2026 | 210000 | 2026 | 210000 | 2027 | 4200000 |  |  | 4620000
FORSYTH | SR 1103 (LEWISVILLE- CLEMMONS ROAD) | US 158 TO SR 1891 (PEACE HAVEN ROAD) IN CLEMMONS. ACCESS MANAGEMENT AND OPERATIONAL IMPROVEMENTS. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-6004 | DIVISION 9 | BGANY, T | 2024 | 15400000 | 2024 | 2600000 | 2026 | 23735000 |  |  | 41735000 | BUILD NC BONDS: $5 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE)
FORSYTH | SR 1156 (LEWISVILLE- CLEMMONS ROAD) | SR 1103 (STYERS FERRY ROAD) TO SR 1101 (SHALLOWFORD ROAD) IN LEWISVILLE. WIDEN TO 3 LANES WITH BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-6189 | DIVISION 9 | T | 2027 | 10700000 | 2027 | 800000 | 2029 | 12400000 |  |  | 23900000
FORSYTH | SR 1173 (WILLIAMS ROAD) | IMPROVE ROUNDABOUTS WEST & EAST OF BRIDGE OVER US 421. WIDEN TO MULTI-LANES FROM ROUNDABOUT EAST OF BRIDGE TO WEST OF ROUNDABOUT AT SR 1001 (SHALLOWFORD ROAD) WITH SIDEWALKS ON BOTH SIDES. TOWN OF LEWISVILLE. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-5617 | DIVISION 9 | BGDA, L |  |  |  |  | 2021 | 1160000 |  |  | 1160000 | UNDER CONSTRUCTION.
FORSYTH | SR 1308 (LEWISVILLE-VIENNA ROAD) | SR 1348 (ROBINHOOD ROAD) IN LEWISVILLE. CONVERT EXISTING SIGNALIZED INTERSECTION TO A SINGLE LANE ROUNDABOUT. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-6154 | DIVISION 9 | BGANY, BGDA, L | 2022 | 250000 |  |  | 2023 | 900000 |  |  | 1150000
FORSYTH | SR 1672 (HANES MILL ROAD) | MUSEUM DRIVE TO SR 4000 (UNIVERSITY PARKWAY) IN WINSTON-SALEM. WIDEN TO MULTI-LANES. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-2729 | DIVISION 9 | T | 2019 | 686000 |  |  | 2023 | 17600000 | 2020 | 1092000 | 19378000 | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $914,000 FOR PE AND $567,000 FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE)
FORSYTH | SR 1891 / NON-SYSTEM (PEACE HAVEN ROAD) | SR 1891 / NON-SYSTEM (PEACE HAVEN ROAD) - US 421 INTERCHANGE AND APPROACHES | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247CD | STATEWIDE MOBILITY | [10 empty] | DESIGN-BUILD PROJECT; IN PROGRESS - LET WITH R-2247EC
FORSYTH | SR 1969 (PINEY GROVE ROAD) | NORTH OF NELSON STREET TO SR 2031 (BROWN ROAD) IN KERNERSVILLE. WIDEN TO 3 LANES WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-6188 | DIVISION 9 | T | 2027 | 1100000 | 2027 | 400000 | 2029 | 4100000 |  |  | 5600000
FORSYTH | SR 2377 (OLD GREENSBORO ROAD NE) | REPLACE BRIDGE 330211 OVER NORFOLK SOUTHERN RAILROAD. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-6059A | DIVISION 9 | BGOFF | 2025 | 4228000 | 2025 | 1100000 | 2027 | 6800000 |  |  | 12128000
FORSYTH | SR 2667 (HASTINGS HILL ROAD) | WINSTON-SALEM NORTHERN BELTWAY, EASTERN SECTION, BRIDGE NO. 366 OVER US 421 / NC 150 / BUSINESS 40 | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-2579G | [11 empty] | PROJECT COMPLETE
FORSYTH | SR 3000 (IDOLS ROAD) | SR 2999 (HAMPTON ROAD) TO US 158 IN CLEMMONS. CONSTRUCT TWO-LANE SHOULDER SECTION ON NEW LOCATION AND REPLACE BRIDGE 330109 OVER NORFOLK SOUTHERN RAILROAD. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-2707 | DIVISION 9 | [10 empty] | UNDER CONSTRUCTION
FORSYTH | SR 4315 (SOUTH MAIN STREET); SR 2648 (OLD WINSTON | SR 4315 (SOUTH MAIN STREET), BUSINESS 40 / US 421 / NC 150 TO NORTH OF SR 4278 (SOUTH CHERRY STREET), AND SR 2648 (OLD WINSTON ROAD), WEST OF SOUTH CHERRY STREET TO SOUTH MAIN STREET IN KERNERSVILLE. SAFETY IMPROVEMENTS, INCLUDING RAISED MEDIAN, TURN LANE | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | W-5510 | DIVISION 9 | [10 empty] | UNDER CONSTRUCTION
FORSYTH | THIRD STREET | REPLACE BRIDGE 330185 OVER US 52 / NC 8 IN WINSTON-SALEM. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | HB-0031 | DIVISION 9 | BGOFF | 2025 | 275000 | 2025 | 275000 | 2026 | 5500000 |  |  | 6050000
FORSYTH | US 158 | MULTI-LANES NORTH OF US 421 / I-40 BUSINESS TO SR 1965 (BELEWS CREEK ROAD) | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | R-2577A | REGION D | T | 2021 | 36300000 | 2021 | 469000 | 2024 | 61904000 |  |  | 98673000 | RIGHT OF WAY IN PROGRESS; BUILD NC BONDS: $15 MILLION FOR CONSTRUCTION - PAYBACK 2024-2038 (FY 2024 / YR 6 SALE)
FORSYTH | US 158 / US 421 / NC 150 / BUSINESS 40 | I-40 TO WEST OF US 158 IN WINSTON-SALEM. PAVEMENT REHABILITATION, REPLACE BRIDGES 330178, 330269, 330278, 330286, 330288 330291, 330293, 330305, 330312 330313, 330336 AND VARIOUS SAFETY IMPROVEMENTS. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-2827
FORSYTH | US 158 / US 421 / NC 150 / BUSINESS 40 | WEST OF FOURTH STREET TO EAST OF CHURCH STREET | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-2827B | REGION D | [10 empty] | UNDER CONSTRUCTION - DESIGN-BUILD PROJECT
FORSYTH | US 158 / US 421 / NC 150 / BUSINESS 40 | WEST OF US 311 (MARTIN LUTHER KING, JR. DRIVE) TO WEST OF US 158 | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-2827C | [11 empty] | COMPLETE
FORSYTH | US 311 (MAIN STREET) | SR 1977 (PINE HALL ROAD) IN WALKERTOWN. REALIGN INTERSECTION AND ADD AUXILIARY TURN LANES. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | HL-0016 | EXEMPT | BGDA, L | 2023 | 90000 |  |  | 2023 | 515000 |  |  | 605000
FORSYTH | US 311; SR 4394 (MARTIN LUTHER KING, JR. BOULEVARD | US 158 / US 421 / NC 150 / BUSINESS 40 TO US 52 / NC 8 IN WINSTON-SALEM. STREETSCAPE IMPROVEMENTS. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-5539A | DIVISION 9 | BGANY, BGDA, L | 2022 | 600000 |  |  | 2023 | 2188000 |  |  | 2788000
FORSYTH | US 421 (SALEM PARKWAY) | SR 2662 (LINVILLE ROAD) IN WINSTON-SALEM. UPGRADE INTERCHANGE AND REPLACE BRIDGE 330211 ON SR 2377 (OLD GREENSBORO ROAD NE) OVER NORFOLK SOUTHERN RAILROAD. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-6059
FORSYTH | US 421 (SALEM PARKWAY) | SR 2662 (LINVILLE ROAD). UPGRADE INTERCHANGE | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-6059B | NOT FUNDED | T | NOT FUNDED | 11100000 | NOT FUNDED | 1332000 | NOT FUNDED | 28860000 |  |  | 41292000 | COORDINATE WITH U-6068
FORSYTH | US 421 / BUSINESS 40 | WEST OF OLD VINEYARD ROAD TO EAST OF US 158 (STRATFORD ROAD) | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-2827A | [11 empty] | COMPLETE
FORSYTH | US 52 / FUTURE I-74 | NC 65 INTERCHANGE. RECONSTRUCT INTERCHANGE. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247EC | STATEWIDE MOBILITY | [10 empty] | DESIGN-BUILD PROJECT; IN PROGRESS - LET WITH R-2247CD
FORSYTH | WEST FIRST STREET | REPLACE BRIDGE 330296 OVER NORFOLK SOUTHERN RAILWAY IN WINSTON-SALEM. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | B-5007 | DIVISION 9 | BFPOFF | 2022 | 70000 |  |  | 2023 | 700000 |  |  | 770000
FORSYTH | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | ROUTINE CAPITAL, PASSENGER SHELTERS, PASSENGER AMENITIES, SHOP EQUIPMENT, SPARE PARTS | PUBLIC TRANSIT | 9 | WINSTON-SALEM URBAN AREA MPO | TG-6783 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2022 | 1059000 | 1059000
FORSYTH | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | OPERATING ASSISTANCE | PUBLIC TRANSIT | 9 | WINSTON-SALEM URBAN AREA MPO | TO-6150 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2022 | 5360000 | 5360000
FORSYTH | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION (PA | WINSTON-SALEM EXPRESS. PURCHASE ONE EXPANSION 40-FT BUS. | PUBLIC TRANSIT | 9 | WINSTON-SALEM URBAN AREA MPO | TA-6682 | REGION D
FORSYTH | WINSTON SALEM TRANSIT | FTA SECTION 5339 BUS AND BUS FACILITIES GRANT | PUBLIC TRANSIT | 9 | WINSTON-SALEM URBAN AREA MPO | TD-5303 | PUBLIC TRANSIT | 5339, L | [6 empty] | 2020 | 5840000 | 5840000
FORSYTH | WINSTON SALEM TRANSIT | OPERATING ASSISTANCE | PUBLIC TRANSIT | 9 | WINSTON-SALEM URBAN AREA MPO | TG-5126 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 18210000 | 18210000
FORSYTH | WINSTON SALEM TRANSIT | PREVENTIVE MAINTENANCE | PUBLIC TRANSIT | 9 | WINSTON-SALEM URBAN AREA MPO | TG-5241 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 23610000 | 23610000 | FUNDS AUTHORIZED IN PROGRESS
FORSYTH | WINSTON SALEM TRANSIT |  | PUBLIC TRANSIT | 9 | WINSTON-SALEM URBAN AREA MPO | TG-6731 | PUBLIC TRANSIT | CMAQ, L | [6 empty] | 2020 | 1013000 | 1013000
FORSYTH | WINSTON SALEM TRANSIT | FTA SECTION 5307 WINSTON-SALEM URBANIZED AREA SET ASIDE FOR JOB ACCESS REVERSE COMMUTE (JARC) PROJECTS | PUBLIC TRANSIT | 9 | WINSTON-SALEM URBAN AREA MPO | TM-5309 | PUBLIC TRANSIT | 5316, L | [6 empty] | 2020 | 660000 | 660000
FORSYTH | WINSTON SALEM TRANSIT | OPERATING ASSISTANCE | PUBLIC TRANSIT | 9 | WINSTON-SALEM URBAN AREA MPO | TO-5126 | PUBLIC TRANSIT | 5307, L, SMAP | [6 empty] | 2020 | 5802000 | 5802000 | FUNDS AUTHORIZED IN PROGRESS
FORSYTH | WINSTON SALEM TRANSIT | PLANNING ASSISTANCE - 5303 | PUBLIC TRANSIT | 9 | WINSTON-SALEM URBAN AREA MPO | TP-5105 | PUBLIC TRANSIT | 5303, L, S | [6 empty] | 2020 | 618000 | 618000 | FUNDS AUTHORIZED IN PROGRESS
FORSYTH | WINSTON SALEM TRANSIT | FTA SECTION 5310 WINSTON-SALEM ALLOCATION SET ASIDE FOR COMPET GRANT TO ELIGIBLE AGENCIES TO ASSIST IN MEETING THE TRANSPORTATION NEEDS OF LOW INCOME, DISABLED AND ELDERLY POPULATIONS | PUBLIC TRANSIT | 9 | WINSTON-SALEM URBAN AREA MPO | TQ-6702 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2020 | 2635000 | 2635000
FORSYTH | WINSTON SALEM TRANSIT | FTA SECTION 5310 WINSTON-SALEM ALLOCATION SET ASIDE FOR COMPETE GRANT TO ELIGIBLE AGENCIES TO ASSIST IN MEETING THE NEEDS OF LOW INCOME, DISABLED, AND ELDERLY POPULATIONS | PUBLIC TRANSIT | 9 | WINSTON-SALEM URBAN AREA MPO | TQ-6782 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2020 | 3594000 | 3594000
FORSYTH | WINSTON SALEM TRANSIT | SAFETY & SECURITY - MIN. 1% SET ASIDE | PUBLIC TRANSIT | 9 | WINSTON-SALEM URBAN AREA MPO | TS-5120 | PUBLIC TRANSIT | 5307, L, SMAP | [6 empty] | 2020 | 266000 | 266000
FORSYTH, DAVIDSON, DAVIE | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE WINSTON-SALEM URBAN AREA MPO. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | C-5620 | EXEMPT | CMAQ, L | 2020 | 366000 |  |  | 2020 | 5331000 | 2020 | 1098000 | 6795000 | IN PROGRESS
FORSYTH, DAVIDSON, STOKES, DAVIE | VARIOUS | BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)-ELIGIBLE PROJECTS IN THE WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (MPO) AREA.. | BIKE/PED | 9 | WINSTON-SALEM URBAN AREA MPO | U-4741 | DIVISION 9 | BGANY, BGDA, L, TADA | 2022 | 788000 |  |  | 2020 | 2953000 |  |  | 3741000
FORSYTH, DAVIDSON, STOKES, DAVIE | VARIOUS | INTERSECTION IMPROVEMENT PROJECTS IN THE WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (WSUAMPO) AREA. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-4742 | DIVISION 9 | BGDA, L |  |  |  |  | 2020 | 875000 |  |  | 875000
FORSYTH, DAVIDSON, STOKES, DAVIE | VARIOUS | WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION PLANNING (PL) SUPPLEMENT. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-4951 | DIVISION 9 | BGDA, L | [6 empty] | 2020 | 3575000 | 3575000 | FORMERLY U-9999D - IN PROGRESS
FORSYTH, DAVIDSON, STOKES, DAVIE | VARIOUS | WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (WSUAMPO) SURFACE TRANSPORTATION BLOCK GRANT DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-5022 | DIVISION 9 | BGDA |  |  |  |  | 2023 | 72707000 |  |  | 72707000
FORSYTH, DAVIDSON, STOKES, DAVIE | VARIOUS | WINSTON-SALEM URBAN AREA METROPOLITAN PLANNING ORGANIZATION (WSUAMPO) TRANSPORTATION ALTERNATIVES DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-6221 | DIVISION 9 | TADA |  |  |  |  | 2022 | 11379000 |  |  | 11379000
FORSYTH, DAVIE | I-40 | WEST OF NC 801 IN BERMUDA RUN TO WEST OF SR 1122 (JONESTOWN ROAD) IN WINSTON-SALEM. ADD LANES. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | I-0911 | [11 empty] | PARTS B AND C COMPLETE
FORSYTH, GUILFORD | I-40 | I-74 US 311 IN WINSTON-SALEM TO US 421 / BUSINESS 40 IN GUILFORD COUNTY. WIDEN TO 6 LANES. | HIGHWAY | 7, 9 | WINSTON-SALEM URBAN AREA MPO, HIGH POINT URBAN AREA MPO | I-5981
FORSYTH, GUILFORD | US 158 | MULTLANES NORTH OF US 421 / I-40 BUSINESS IN WINSTON-SALEM TO US 220 IN STOKESDALE. WIDEN TO MULTI-LANES. | HIGHWAY | 7, 9 | WINSTON-SALEM URBAN AREA MPO, GREENSBORO URBAN AREA MPO | R-2577
FORSYTH, GUILFORD | US 158 | SR 1965 (BELEWS CREEK ROAD) IN FORSYTH COUNTY TO SR 2034 (ANTHONY ROAD) IN GUILFORD COUNTY | HIGHWAY | 7, 9 | WINSTON-SALEM URBAN AREA MPO, GREENSBORO URBAN AREA MPO | R-2577B | REGION D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 38800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 60300000 |  |  | 108800000
FORSYTH, GUILFORD | US 421 (SALEM PARKWAY) | FUTURE I-74 IN KERNERSVILLE TO I-40 IN GUILFORD COUNTY. WIDEN TO 6 LANES. | HIGHWAY | 7, 9 | WINSTON-SALEM URBAN AREA MPO, GREENSBORO URBAN AREA MPO | U-6068 | NOT FUNDED | T | NOT FUNDED | 57300000 | NOT FUNDED | 2114000 | NOT FUNDED | 71300000 |  |  | 130714000 | COORDINATE WITH U-6059B
FORSYTH, GUILFORD, RANDOLPH | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION | PURCHASE VEHICLES FOR VANPOOL FLEET EXPANSION. | PUBLIC TRANSIT | 7, 8, 9 | WINSTON-SALEM URBAN AREA MPO, GREENSBORO URBAN AREA MPO, HIGH POINT URBAN AREA MPO | TA-6722 | DIVISION 7, 8, 9 | L, T |  |  |  |  | 2021 | 100000 |  |  | 100000
FORSYTH, GUILFORD, WATAUGA, WILKES, YADKIN | COACH AMERICA | INTERCITY BUS - GREENSBORO TO BOONE | PUBLIC TRANSIT | 7, 9, 11 |  | TI-6103 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 3520000 | 3520000 | FUNDS AUTHORIZED IN PROGRESS
FORSYTH, SURRY | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION (PA | PURCHASE EXPANSION FLEET VEHICLE TO EXPAND SERVICE ON PART SURRY EXPRESS #1 | PUBLIC TRANSIT | 9, 11 | NORTHWEST PIEDMONT RPO, WINSTON-SALEM URBAN AREA MPO | TA-6681 | REGION D, F | FEDT, L, T | [6 empty] | 2020 | 466000 | 466000
FRANKLIN | TRIANGLE NORTH EXECUTIVE AIRPORT (LHZ) | CONSTRUCT RUNWAY EXTENSION, TO INCLUDE RELOCATION OF UTILITIES, NAVAID AND ROADWAYS. | AVIATION | 5 | CAPITAL AREA MPO | AV-5819 | DIVISION 5 | T | 2026 | 3300000 |  |  | 2028 | 22000000 |  |  | 25300000
FRANKLIN | (BUNN ROAD) SR 1230 | KENMORE AVENUE TO US 401 / NC 56 (BICKETT BOULEVARD) IN LOUISBURG. REDUCE 4 LANES TO 2 LANES AND CONSTRUCT BICYCLE AND PEDESTRIAN IMPROVEMENTS. | HIGHWAY | 5 | KERR-TAR RPO | HL-0044 | EXEMPT | CMAQ, L | 2023 | 36000 |  |  | 2023 | 468000 | 2022 | 102000 | 606000
FRANKLIN | FRANKLIN COUNTY RAILS TO TRAILS | DOWNTOWN FRAKLINTON TRAIN DEPOT TO SR 1003 (PERRY'S CHAPEL ROAD) USING ABANDONED RAIL CORRIDOR IN FRANKLINTON. CONSTRUCT GREENWAY. | HIGHWAY | 5 | CAPITAL AREA MPO | BL-0053 | EXEMPT | CMAQ, L | 2023 | 120000 |  |  | 2023 | 3000000 | 2023 | 600000 | 3720000
FRANKLIN | NC 56 | SR 1114 (PEACH ORCHARD ROAD) TO US 401 IN LOUISBURG. WIDEN TO 4 LANES. | HIGHWAY | 5 | KERR-TAR RPO | R-5893 | NOT FUNDED | T | NOT FUNDED | 5900000 | NOT FUNDED | 9000000 | NOT FUNDED | 21899000 |  |  | 36799000
FRANKLIN | SR 1600 (EAST RIVER ROAD) | REPLACE BRIDGE 340076 OVER SYCAMORE CREEK. | HIGHWAY | 5 | KERR-TAR RPO | B-5210 | DIVISION 5 | [10 empty] | UNDER CONSTRUCTION - BRIDGE PURCHASE ORDER CONTRACT (BPOC)
FRANKLIN | SR 1609 (BAPTIST CHURCH ROAD) | REPLACE BRIDGE 340078 OVER TAR RIVER | HIGHWAY | 5 | CAPITAL AREA MPO | B-6003 | DIVISION 5 | BGOFF | 2025 | 405000 |  |  | 2026 | 4050000 |  |  | 4455000
FRANKLIN | US 401 | SR 1103 (FLAT ROCK CHURCH ROAD / CLIFTON POND ROAD) TO SR 1700 (FOX PARK ROAD) SOUTH OF LOUISBURG | HIGHWAY | 5 | CAPITAL AREA MPO, KERR-TAR RPO | R-2814D | DIVISION 5 | BGLT5 | 2028 | 3049000 | 2028 | 3200000 | 2031 | 48700000 |  |  | 54949000
FRANKLIN | US 401 | SR 1700 (FOX PARK ROAD) SOUTH OF LOUISBURG TO NC 39 IN LOUISBURG | HIGHWAY | 5 | KERR-TAR RPO | R-2814E | [11 empty] | COMPLETE
FRANKLIN | US 401 / NC 39 | NC 56 / NC 581 (NASH STREET) TO SR 1229 (MAIN STREET). WIDEN TO MULTILANES. | HIGHWAY | 5 | KERR-TAR RPO | R-3608 | REGION C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 15299000 |  |  | 21099000 | COORDINATE WITH U-6024
FRANKLIN | US 401 / NC 39 (BICKETT BOULEVARD) | BURKE BOULEVARD TO NC 56 / NC 581 (NASH STREET) IN LOUISBURG. CONVERT 5-LANE SECTION TO 4-LANE DIVIDED FACILITY WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | 5 | KERR-TAR RPO | U-6024 | DIVISION 5 | T | 2028 | 3200000 | 2028 | 1800000 | 2031 | 15998000 |  |  | 20998000 | COORDINATE WITH R-3608
FRANKLIN, GRANVILLE, VANCE, WARREN | KERR AREA TRANSPORTATION | ADMINISTRATION | PUBLIC TRANSIT | 5 | KERR-TAR RPO | TK-6139 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 2048000 | 2048000 | FUNDS AUTHORIZED IN PROGRESS
FRANKLIN, GRANVILLE, VANCE, WARREN | KERR AREA TRANSPORTATION | OPERATING ASSISTANCE | PUBLIC TRANSIT | 5 | KERR-TAR RPO | TO-6103 | PUBLIC TRANSIT | 5311, L | [6 empty] | 2020 | 480000 | 480000 | FUNDS AUTHORIZED IN PROGRESS
FRANKLIN, WAKE | US 401 | NORTH OF SR 2044 (LIGON MILL ROAD) TO NC 39 IN LOUISBURG. WIDEN TO FOUR-LANE MEDIAN DIVIDED FACILITY, SOME NEW LOCATION. | HIGHWAY | 5 | CAPITAL AREA MPO, KERR-TAR RPO | R-2814 | [11 empty] | GARVEE BOND FUNDING: PART B $15.8 MILLION FOR RIGHT-OF-WAY - PAYBACK FY 2009 - FY 2020 AND $21.5 MILLION FOR CONSTRUCTION - PAYBACK FY 2011 - FY 2022; PART C $33 MILLION FOR CONSTRUCTION - PAYBACK FY 2018 - FY 2032
FRANKLIN, WAKE | US 401 | NC 96 TO SR 1103 (FLAT ROCK CHURCH ROAD / CLIFTON POND ROAD) | HIGHWAY | 5 | CAPITAL AREA MPO | R-2814C | DIVISION 5 | BGLT5 |  |  |  |  | 2018 | 36803000 |  |  | 36803000 | UNDER CONSTRUCTION. GARVEE BOND FUNDING. PART C $33 MILLION FOR CONSTRUCTION - PAYBACK FY 2018 - FY 2032
GASTON | (TRYON COURTHOUSE RD) NC 274 | PINE SPRINGS DRIVE TO TRYON ELEMENTARY SCHOOL. CONSTRUCT SIDEWALK ON WEST SIDE OF ROADWAY FROM PINE SPRINGS TO COURT TERRACE. INSTALL MID-BLOCK CROSSWALK AND CONSTRUCT SIDEWALK ON EAST SIDE OF ROADWAY TO TRYON ELEMENTARY SCHOOL. | BIKE/PED | 12 | GASTON-CLEVELAND-LINCOLN MPO | BL-0033 | EXEMPT | CMAQ, L | 2023 | 50000 |  |  | 2023 | 1449000 | 2022 | 188000 | 1687000
GASTON | BEATY ROAD | FERSTL AVENUE TO SMITH STREET. CONSTRUCT SIDEWALK ON ONE SIDE. | BIKE/PED | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5748 | DIVISION 12 | L, TA5200 |  |  |  |  | 2022 | 405000 | 2022 | 101000 | 506000
GASTON | BESSEMER CITY | PHASE I: 12TH STREET, CHADWICK COURT TO KAISER ROAD. PHASE II: YELLOW JACKET LANE/BESS TOWN ROAD, 12TH STREET TO 14TH STREET (NC 274). CONSTRUCT SIDEWALKS. | BIKE/PED | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5531 | PRE-STI (TRANSITION) | BGANY |  |  |  |  | 2022 | 300000 |  |  | 300000
GASTON | CRAMERTON | SR 2014 (LAKEWOOD ROAD), SR 2565 (EAGLE ROAD) TO LAKE DRIVE. CONSTRUCT SIDEWALK AND PEDESTRIAN BRIDGE OVER SOUTH FORK RIVER INLET. | BIKE/PED | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5913 | DIVISION 12 | L, TAANY |  |  |  |  | 2025 | 354000 | 2023 | 164000 | 518000
GASTON | GASTONIA | POSTON PARK TO SOUTH FORK RIVER GREENWAY. CONSTRUCT TRAIL. | BIKE/PED | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5533 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
GASTON | NC 279 (NEW HOPE ROAD) | US 29/74 (FRANKLIN BOULEVARD) TO HUNT AVENUE. CONSTRUCT SIDEWALK ON EAST SIDE OF NC 279 (NEW HOPE ROAD) FROM US 29/74 (FRANKLIN BOULEVARD) TO COURT DRIVE AND WEST SIDE OF NC 279 FROM COURT DRIVE TO HUNT AVENUE. | BIKE/PED | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5975 | DIVISION 12 | L, TA5200 |  |  |  |  | 2024 | 2065000 | 2023 | 516000 | 2581000
GASTON | NC 279 (SOUTH NEW HOPE ROAD) | SR 2200 (ARMSTRONG PARK ROAD) TO SR 1255 (HUDSON BOULEVARD). CONSTRUCT MISSING SIDEWALK ON SOUTH SIDE OF NC 279. | BIKE/PED | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5743 | DIVISION 12 | L, TA5200 |  |  |  |  | 2024 | 1285000 | 2023 | 321000 | 1606000
GASTON | SOUTH MARIETTA STREET/ HILLTOP DRIVE | HUDSON BOULEVARD TO CLYDE STREET. CONSTRUCT SIDEWALK ON ONE SIDE OF ROAD. | BIKE/PED | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5768 | DIVISION 12 | L, TA5200 | 2023 | 60000 |  |  | 2024 | 1260000 | 2023 | 315000 | 1635000
GASTON | SR 1255 (HUDSON BLVD) SR 2466 (REDBUD DR) | SR 1255 (HUDSON BOULEVARD) FROM SR 2200 (GASTON DAY SCHOOL ROAD) TO SR 2466 (REDBUD DRIVE). SR 2466 (REDBUD DRIVE) FROM SR 1255 (HUDSON BOULEVARD) TO NC 279 (SOUTH NEW HOPE ROAD). CONSTRUCT SIDEWALK ON ONE SIDE. | BIKE/PED | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5745 | DIVISION 12 | L, TA5200 | 2023 | 135000 |  |  | 2024 | 1230000 | 2023 | 308000 | 1673000
GASTON | SR 2044 (TUCKASEEGEE ROAD) MOUNT HOLLY | NC 273 TO MARINA VILLAGE DRIVE. CONSTRUCT SIDEWALK ON SOUTH SIDE. MARINA VILLAGE DRIVE NORTH TO BROOME STREET. CONSTRUCT SIDEWALK ON WEST SIDE. | BIKE/PED | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5912 | DIVISION 12 | L, TAANY | 2025 | 727000 |  |  | 2027 | 1745000 | 2023 | 436000 | 2908000
GASTON | SR 2200 (COX ROAD) | I-85 TO COURT DRIVE. CONSTRUCT SIDEWALK ON BOTH SIDES OF SR 2200 (COX ROAD). | BIKE/PED | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5976 | DIVISION 12 | L, TA5200 |  |  |  |  | 2024 | 1400000 | 2023 | 350000 | 1750000
GASTON | US 29/74 (EAST FRANKLIN BOULEVARD) | SR 2200 (COX ROAD) TO EAST OF DUHART'S CREEK. CONSTRUCT MISSING SIDEWALK ON SOUTH SIDE OF THE ROADWAY. IMPROVE PEDESTRIAN CROSSING AT THE INTERSECTION OF US29/74 AND SR 2200 (COX ROAD). | BIKE/PED | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5701 | DIVISION 12 | L, TA5200 | 2023 | 220000 | 2023 | 75000 | 2024 | 1533000 |  |  | 1828000
GASTON | BELMONT | RAIL TRAIL, WOODLAWN AVENUE TO BELMONT ABBEY COLLEGE AND DOWNTOWN. CONVERT ABANDONED NCDOT RAILROAD LINE TO A PEDESTRIAN TRAIL. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | C-5505 | EXEMPT | [10 empty] | IN PROGRESS
GASTON | CRAMERTON- MCADENVILLE GREENWAY CONNECTOR | CONSTRUCT GREENWAY CONNECTING PAVED TRAIL AT SOUTH FORK VILLAGE IN CRAMERTON TO RIVERSIDE DRIVE IN MCADENVILLE, FOLLOWING SOUTH FORK OF CATAWBA RIVER. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | C-5704 | EXEMPT | CMAQ, L | 2024 | 51000 |  |  | 2024 | 653000 | 2022 | 98000 | 802000
GASTON | GASTON COUNTY | HIGHLAND BRANCH GREENWAY, PHASE I. CONSTRUCT GREENWAY | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | C-5622 | EXEMPT | L |  |  |  |  | 2022 | 53000 |  |  | 53000 | UNDER CONSTRUCTION
GASTON | GASTONIA | GASTONIA SIGNAL SYSTEM. UPGRADE CITYWIDE SIGNAL SYSTEM. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | C-5703 | REGION F | CMAQ, L, S(M) | 2022 | 750000 |  |  | 2022 | 11362000 |  |  | 12112000 | LOCAL FUNDS PROVIDED BY CITY OF GASTONIA (1.5% OF PROJECT COST). STATE MATCH TO USE REGIONAL IMPACT FUNDS (REGION F). CONSTRUCTION FUNDS INCLUDE FUNDS FOR C-5606C (LET UNDER A SINGLE WBS 48320.3.1).
GASTON | I-85 | CONSTRUCT NEW I-85 NBL WEIGH STATION FROM SR 1302 (CROWDERS MOUNTAIN ROAD) TO SR 1307 (EDGEWOOD ROAD). | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | I-4928 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
GASTON | I-85 | I-85/US 321. GEOMETRIC SAFETY IMPROVEMENTS TO INTERCHANGE. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | I-5000 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
GASTON | I-85 | US 321 TO NC 273. WIDEN TO EIGHT LANES. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | I-5719 | STATEWIDE MOBILITY | NHP, S(M) | 2024 | 132025000 | 2024 | 71100000 | 2024 | 507375000 |  |  | 710500000 | DESIGN-BUILD PROJECT - TO BE LET WITH U-5800. INCLUDES IMPROVEMENTS PREVIOUSLY FUNDED UNDER I-5713 (COX ROAD INTERCHANGE IMPROVEMENTS) AND U-3608 (NC 7 OPERATIONAL IMPROVEMENTS). GARVEE BOND FUNDING: $75M FOR ROW, $225M FOR CONSTRUCTION (2 SALES).
GASTON | I-85 | CLEVELAND COUNTY LINE TO MILE MARKER 14. PAVEMENT REHABILITATION. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | I-5921 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2025 | 16830000 |  |  | 16830000
GASTON | I-85 | US 74 TO US 321 | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | I-5985B | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 219401000 |  |  | 233101000
GASTON | NC 150 | NC 279 AT CHERRYVILLE TO THE LINCOLN COUNTY LINE. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-0617A | [11 empty] | COMPLETE
GASTON | NC 161 | CONSTRUCT SIDEWALK. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | C-5606B | EXEMPT | CMAQ, L | 2022 | 5000 |  |  | 2023 | 496000 |  |  | 501000
GASTON | NC 27 (WEST CHARLOTTE AVENUE) | INTERSECTION OF NC 27 (WEST CHARLOTTE AVENUE) AND SR 2534 (HAWTHORNE STREET). CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5819 | DIVISION 12 | T | 2028 | 700000 | 2028 | 600000 | 2030 | 2800000 |  |  | 4100000
GASTON | NC 273 | SR 2525 (SOUTH POINT ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6150 | NOT FUNDED | T | NOT FUNDED | 300000 | NOT FUNDED | 1500000 | NOT FUNDED | 1700000 |  |  | 3500000
GASTON | NC 273 (SOUTH MAINSTREET) | TUCKASEEGEE ROAD (AT BEATTY DRIVE) TO HIGHLAND STREET (AT A & E DRIVE) IN MOUNT HOLLY. WIDEN TO FOUR-LANES DIVIDED. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-3633 | REGION F | T |  |  |  |  | 2021 | 6315000 |  |  | 6315000 | UNDER CONSTRUCTION; BUILD NC BOND FUNDING: $4.910 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE).PROJECT INCORPORATES WORK PREVIOUSLY UNDER EB-5746
GASTON | NC 274 | SR 1443 (DAMERON ROAD) TO SR 1405 (RAMSEUR ROAD) REALIGNMENT AND WIDENING. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | W-5601R | REGION F | HSIP |  |  |  |  | 2025 | 2500000 |  |  | 2500000
GASTON | NC 274 (UNION ROAD) | OSCEOLA STREET TO NIBLICK DRIVE. UPGRADE ROADWAY. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5961 | REGION F | O, T | 2024 | 13400000 | 2024 | 3700000 | 2027 | 9998000 |  |  | 27098000 | $5M IN OTHER FUNDING PROVIDED BY CITY OF GASTONIA
GASTON | NC 275 | INTERSECTION OF NC 275 AND NC 274, INTERSECTION OF NC 275 AND SR 1327 (FAIRVIEW ROAD), AND INTERSECTION OF SR 1456 (WHITE JENKINS ROAD) AND SR 1327 (FAIRVIEW ROAD). IMPROVE INTERSECTIONS AND CLOSE INTERSECTION OF NC 275 AND SR 1456 (WHITE JENKINS ROAD) | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6078 | DIVISION 12 | T | 2025 | 2000000 | 2025 | 2500000 | 2027 | 3900000 |  |  | 8400000
GASTON | NC 279 | NC 7 TO WEST OF NC 275 IN DALLAS. WIDEN TO MULTI-LANES. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-2523 | REGION F
GASTON | NC 279 | NC 7 (OZARK AVENUE) TO NORTH OF SR 2275 (ROBINSON-CLEMMER ROAD). | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-2523A | [11 empty] | COMPLETE
GASTON | NC 279 | NORTH OF SR 2275 (ROBINSON-CLEMMER ROAD) TO WEST OF NC 275 IN DALLAS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-2523B | REGION F | T | 2026 | 12500000 | 2026 | 2300000 | 2028 | 20199000 |  |  | 34999000 | INCLUDES IMPROVEMENTS AT NC 279 (LOWER DALLAS HIGHWAY) AND NC 275 (DALLAS STANLEY HIGHWAY) INTERSECTION (FORMERLY U-5778).
GASTON | NC 279 (DALLAS CHERRYVILLE HIGHWAY) | SOUTH OF (ST MARK'S CHURCH ROAD) TO NORTH OF NC 275 - CONSTRUCT SAFETY IMPROVEMENTS, INCLUDING PASSING ZONES | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | W-5212N | REGION F | T |  |  |  |  | 2021 | 14445000 |  |  | 14445000 | UNDER CONSTRUCTION; BUILD NC BOND FUNDING: $11.22 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE).
GASTON | NC 279 (NEW HOPE ROAD) | NC 279 (NEW HOPE ROAD), BURTONWOOD DRIVE TO SR 2466 (GARRISON BOULEVARD) IN GASTONIA. ADD TURN LANE. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | C-4934 | EXEMPT | [10 empty] | UNDER CONSTRUCTION
GASTON | NC 279 (NEW HOPE ROAD) | SR 2478 (TITMAN ROAD) TO SR 2435 (UNION-NEW HOPE ROAD). WIDEN TO 4-LANES. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5821 | DIVISION 12 | T | 2023 | 56675000 | 2023 | 6000000 | 2026 | 44900000 |  |  | 107575000 | BUILD NC BOND FUNDING - $25M FOR RIGHT-OF-WAY, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE)
GASTON | NC 279 (NORTH NEW HOPE ROAD) | US 29/74 (FRANKLIN BOULEVARD) INTERSECTION. ADD RIGHT TURN LANE FROM NC 279 (NORTH NEW HOPE ROAD) TO US 29/74 (FRANKLIN BOULEVARD). | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6138 | REGION F | T | 2025 | 5600000 | 2025 | 300000 | 2026 | 800000 |  |  | 6700000
GASTON | NC 7 | INTERSECTION OF NC 7/US 74 AND NC 7/US 29. CONSTRUCT NORTHBOUND THROUGH LANE AND INTERSECTION IMPROVEMENTS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5800 | REGION F | T | 2024 | 2400000 | 2024 | 3600000 | 2024 | 4400000 |  |  | 10400000 | DESIGN-BUILD PROJECT. TO BE LET WITH I-5719.
GASTON | NC 7 (EAST CATAWBA STREET) | US 74 (WILKINSON BOULEVARD) INTERSECTION. CONSTRUCT NORTHBOUND RIGHT-TURN LANE ON NC 7 (EAST CATAWBA STREET) AND EXTEND EXISTING WESTBOUND LEFT-TURN LANE ON US 74 (WILKINSON BOULEVARD). | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6143 | REGION F | L, NHP | 2022 | 1600000 | 2022 | 1100000 | 2023 | 4400000 |  |  | 7100000 | PROJECT TO BE LET WITH B-6051. LOCAL FUNDS PROVIDED BY CITY OF BELMONT.
GASTON | NEAL HAWKINS ROAD | CONSTRUCT SIDEWALKS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | C-5606M | EXEMPT | CMAQ, L | 2023 | 19000 |  |  | 2024 | 1529000 | 2022 | 313000 | 1861000
GASTON | NEW ROUTE | TECHNOLOGY PARK TO GASTON COLLEGE. CONSTRUCT GREENWAY. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | C-5606E | EXEMPT | CMAQ, L |  |  |  |  | 2023 | 588000 |  |  | 588000
GASTON | NEW ROUTE | CONSTRUCT POSTON PARK SIDEWALK CONNECTOR. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | C-5606J | EXEMPT | CMAQ, L |  |  |  |  | 2023 | 186000 |  |  | 186000
GASTON | NEW ROUTE | RANKIN LAKE TO TECH PARK GREENWAY. CONSTRUCT GREENWAY. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | C-5606K | EXEMPT | CMAQ, L | 2023 | 15000 |  |  | 2024 | 1581000 | 2023 | 129000 | 1725000
GASTON | SR 1421 (MARYS GROVE ROAD) | REPLACE BRIDGE 350097 OVER UN-NAMED TRIBUTARY OF MUDDY FORK CREEK. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | B-5961 | DIVISION 12 | BGOFF | 2021 | 67000 |  |  | 2022 | 580000 |  |  | 647000
GASTON | SR 2093 (BELLMONT MONUT HOLLY ROAD) | EXISTING SIDEWALK AT THE CIRCLE K GAS STATION NEAR BELMONT ABBEY COLLEGE TO THE EXISTING SIDEWALK AT MARGARETTE AVENUE. CONSTRUCT SIDEWALK. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | C-5606A | EXEMPT | CMAQ, L |  |  |  |  | 2022 | 127000 |  |  | 127000
GASTON | SR 2200 (COX ROAD) | I-85 TO US 29/74. SELECTIVE WIDENING AND OPERATIONAL IMPROVEMENTS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6044 | DIVISION 12 | T | 2025 | 21100000 | 2025 | 1200000 | 2028 | 5400000 |  |  | 27700000
GASTON | US 29 (FRANKLIN BOULEVARD) | US 29 (FRANKLIN BOULEVARD) AND NC 274. CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5965 | REGION F | T | 2023 | 6900000 | 2023 | 300000 | 2025 | 3600000 |  |  | 10800000
GASTON | US 29 / US 74 | REPLACE BRIDGE 350091 OVER CATAWBA RIVER | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | B-6051 | REGION F | BFP, HIB | 2022 | 4000000 |  |  | 2023 | 40899000 |  |  | 44899000 | PRELIMINARY ENGINEERING TO USE FEDERAL-AID FUNDING. PROJECT ALSO REFERRED TO AS BR-0020. HIB FUNDS ARE 2021 HIGHWAY INFRASTRUCTURE BRIDGE REPLACEMENT FUNDS (Z922). PROJECT TO BE LET WITH U-6143.
GASTON | US 29/74 (FRANKLIN BOULEVARD) | SR 2329 (REDBUD DRIVE) INTERSECTION. IMPROVE INTERSECTION AREA INCLUDING NEW GRADE-SEPARATED CROSSING OF US 29/74. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6141 | NOT FUNDED | NHP | NOT FUNDED | 12200000 | NOT FUNDED | 900000 | NOT FUNDED | 8800000 |  |  | 21900000
GASTON | US 29/74 (WILKINSON BOULEVARD) | MARKET STREET TO SR 2015 (ALBERTA AVENUE. WIDEN TO SIX LANES (INCLUDES REPLACEMENT OF BRDIGE 350082 OVER SOUTH FORK OF CATAWBA RIVER). | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6146 | REGION F | HFB, T | 2022 | 8380000 | 2022 | 5500000 | 2024 | 28302000 |  |  | 42182000 | BFP IS FOR BRIDGE REPLACEMENT OVER SOUTH FORK OF CATAWBA RIVER. BUILD NC BOND FUNDING: $2M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE);
GASTON | US 29/US 74 (FRANKLIN BOULEVARD) | SR 2200 (COX ROAD) TO 400 FEET EAST OF LINEBERGER ROAD. ADD LANE IN THE EASTBOUND DIRECTION. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6043 | DIVISION 12 | T | 2023 | 600000 | 2023 | 900000 | 2025 | 2699000 |  |  | 4199000
GASTON | US 321 (SOUTH YORK ROAD) | 19TH AVENUE TO CLYDE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5970 | REGION F | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1900000 |  |  | 4500000
GASTON | US 321 BUSINESS, NC 275/279 | CONSTRUCT SIDEWALKS ALONG PORTIONS OF US 321 BUSINESS AND NC 275/279 NEAR GASTON COLLEGE, INCLUDING A CROSSWALK ACROSS NC 275/279. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | C-5606D | EXEMPT | CMAQ, L |  |  |  |  | 2023 | 393000 |  |  | 393000
GASTON | US 74 (WILKINSON BOULEVARD) | US 74 (WILKINSON BOULEVARD) AT NC 273 (PARK STREET). CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5959 | REGION F | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6000000 |  |  | 16700000
GASTON | US 74 (WILKINSON BOULEVARD) | NC 7 (CATAWBA STREET) TO SR 2209 (WESLEYAN DRIVE). IMPLEMENT ADAPTIVE SIGNAL SYSTEM. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6038 | DIVISION 12 | T |  |  |  |  | 2019 | 600000 |  |  | 600000 | UNDER CONSTRUCTION; BUILD NC BOND FUNDING: $456,129 FOR CONSTRUCTION, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE)
GASTON | GASTON COUNTY ACCESS | ADMINISTRATION | PUBLIC TRANSIT | 12 | GASTON-CLEVELAND-LINCOLN MPO | TK-6128 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 936000 | 936000 | FUNDS AUTHORIZED IN PROGRESS
GASTON | GASTON TRANSIT | TRANSIT ENHANCEMENTS - PEDESTRIAN WALKWAYS | PUBLIC TRANSIT | 12 | GASTON-CLEVELAND-LINCOLN MPO | TG-6792 | PUBLIC TRANSIT | 5307, L |  |  |  |  | 2022 | 1677000 |  |  | 1677000 | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO.
GASTON | GASTON TRANSIT | TRANSIT ENHANCEMENTS - BENCHES AT BRADLY STATION | PUBLIC TRANSIT | 12 | GASTON-CLEVELAND-LINCOLN MPO | TL-0004 | PUBLIC TRANSIT | 5307, L |  |  |  |  | 2021 | 125000 |  |  | 125000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
GASTON | GASTONIA TRANSIT | EXPANSION BUS | PUBLIC TRANSIT | 12 | GASTON-CLEVELAND-LINCOLN MPO | TA-4926 | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 1242000 | 1242000
GASTON | GASTONIA TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC | PUBLIC TRANSIT | 12 | GASTON-CLEVELAND-LINCOLN MPO | TG-5117 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 904000 | 904000 | FUNDS AUTHORIZED IN PROGRESS
GASTON | GASTONIA TRANSIT | PREVENTIVE MAINTENANCE | PUBLIC TRANSIT | 12 | GASTON-CLEVELAND-LINCOLN MPO | TG-5117A | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2500000 | 2500000 | FUNDS AUTHORIZED IN PROGRESS
GASTON | GASTONIA TRANSIT | ADA SERVICE | PUBLIC TRANSIT | 12 | GASTON-CLEVELAND-LINCOLN MPO | TG-5117B | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2500000 | 2500000 | FUNDS AUTHORIZED IN PROGRESS
GASTON | GASTONIA TRANSIT | ADA PARATRANSIT SERVICE | PUBLIC TRANSIT | 12 | GASTON-CLEVELAND-LINCOLN MPO | TG-6183A | PUBLIC TRANSIT | 5307, L | [6 empty] | 2022 | 767000 | 767000 | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO.
GASTON | GASTONIA TRANSIT | PREVENTATIVE MAINTENANCE | PUBLIC TRANSIT | 12 | GASTON-CLEVELAND-LINCOLN MPO | TG-6184B | PUBLIC TRANSIT | 5307, L | [6 empty] | 2022 | 1160000 | 1160000 | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO.
GASTON | GASTONIA TRANSIT | TRANSIT ENHANCEMENTS SHELTERS | PUBLIC TRANSIT | 12 | GASTON-CLEVELAND-LINCOLN MPO | TG-6793 | PUBLIC TRANSIT | 5307, L |  |  |  |  | 2022 | 559000 |  |  | 559000 | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO.
GASTON | GASTONIA TRANSIT | TRANSIT APP | PUBLIC TRANSIT | 12 | GASTON-CLEVELAND-LINCOLN MPO | TG-6804 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 63000 | 63000 | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO.
GASTON | GASTONIA TRANSIT | OPERATING ASSISTANCE | PUBLIC TRANSIT | 12 | GASTON-CLEVELAND-LINCOLN MPO | TO-5142 | PUBLIC TRANSIT | 5307, L, SMAP | [6 empty] | 2020 | 1068000 | 1068000 | FUNDS AUTHORIZED IN PROGRESS
GASTON | GASTONIA TRANSIT | OPERATING EXPENSES | PUBLIC TRANSIT | 12 | GASTON-CLEVELAND-LINCOLN MPO | TO-6061 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2022 | 2480000 | 2480000 | FUNDING ADDED TO FY 20 AT THE REQUEST OF GASTONIA MPO.
GASTON | GASTONIA TRANSIT | PLANNING ASSISTANCE | PUBLIC TRANSIT | 12 | GASTON-CLEVELAND-LINCOLN MPO | TP-5115 | PUBLIC TRANSIT | 5303, L, S | [6 empty] | 2020 | 112000 | 112000 | FUNDS AUTHORIZED IN PROGRESS
GASTON | GASTONIA TRANSIT | SAFETY & SECURITY - MIN. 1% SET ASIDE | PUBLIC TRANSIT | 12 | GASTON-CLEVELAND-LINCOLN MPO | TS-5110 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 52000 | 52000 | FUNDS AUTHORIZED IN PROGRESS
GASTON | P & N CORRIDOR REACTIVATION | CROSSING SIGNAL CONSTRUCTION | RAIL | 12 | GASTON-CLEVELAND-LINCOLN MPO | P-5200A | [11 empty] | COMPLETE
GASTON | P & N CORRIDOR REACTIVATION | CROSSING SIGN/PAVEMENT MARKING INSTALLATION | RAIL | 12 | GASTON-CLEVELAND-LINCOLN MPO | P-5200B | [11 empty] | COMPLETE
GASTON | P & N CORRIDOR REACTIVATION | RAIL TRACK CONSTRUCTION ENGINEERING OVERSIGHT | RAIL | 12 | GASTON-CLEVELAND-LINCOLN MPO | P-5200C | [11 empty] | COMPLETE
GASTON | P & N CORRIDOR REACTIVIATION | BELMONT SPUR | RAIL | 12 | GASTON-CLEVELAND-LINCOLN MPO | P-5200D | PRE-STI (TRANSITION) | BGANY | 2022 | 50000 |  |  | 2022 | 850000 |  |  | 900000 | UNDER CONSTRUCTION
GASTON, CLEVELAND | I-85 | SOUTH CAROLINA STATE LINE TO US 321. ADD ADDITIONAL LANES. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | I-5985
GASTON, CLEVELAND, LINCOLN | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE GASTON-CLEVELAND-LINCOLN MPO. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | C-5606 | EXEMPT | [10 empty] | STATE FUNDS ON SEGMENT I ARE CONTIGENCY FUNDS
GASTON, IREDELL, CATAWBA | VARIOUS | DIVISION 12 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS IN THE REGIONAL CATEGORY. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO, CHARLOTTE REGIONAL TPO, GREATER HICKORY MPO | W-5212REG | REGION F
GASTON, LINCOLN | LINCOLN COUNTY | ONE EXPANSION LIGHT TRANSIT VEHICLE | PUBLIC TRANSIT | 12 | GASTON-CLEVELAND-LINCOLN MPO | TA-5185 | DIVISION 12 | 5310, L, T
GASTON, MECKLENBURG | PIEDMONT AND NORTHERN RAILROAD | RAIL CORRIDOR BETWEEN GASTONIA AND MOUNT HOLLY INCLUDING THE BELMONT SPUR. REACTIVATION OF RAIL CORRIDOR | RAIL | 10, 12 | GASTON-CLEVELAND-LINCOLN MPO, CHARLOTTE REGIONAL TPO | P-5200
GATES | US 158 | SR 1002 (ACORN HILL ROAD) TO PASQUOTANK COUNTY LINE. MODERNIZE ROADWAY. | HIGHWAY | 1 | ALBEMARLE RPO | R-5808 | DIVISION 1 | NHP | 2022 | 93000 |  |  | 2023 | 14000000 |  |  | 14093000
GATES | GATES COUNTY | ADMINISTRATION | PUBLIC TRANSIT | 1 | ALBEMARLE RPO | TK-6129 | PUBLIC TRANSIT | 5311 | [6 empty] | 2020 | 544000 | 544000 | FUNDS AUTHORIZED IN PROGRESS
GATES, CHOWAN | NC 32 | NC 37 (GLIDEN ROAD) TO VIRGINIA STATE LINE. MODERNIZE ROADWAY. | HIGHWAY | 1 | ALBEMARLE RPO | R-5938 | DIVISION 1 | T | 2028 | 29185000 | 2028 | 26976000 | 2030 | 75900000 |  |  | 132061000
GRAHAM | FUTURE US 74 | WEST OF SR 1231 (TOBACCO BRANCH ROAD) TO CALFPEN GAP | HIGHWAY | 14 | SOUTHWESTERN RPO | A-0009DC | [11 empty] | COMPLETE
GRAHAM | FUTURE US 74 | NC 28 AT STECOAH TO WEST OF SR 1231 (TOBACCO BRANCH ROAD) | HIGHWAY | 14 | SOUTHWESTERN RPO | A-0009DD | [11 empty] | COMPLETE
GRAHAM | NC 143 | SR 1223 (BEECH CREEK ROAD) TO NORTH OF APPALACHIAN TRAIL, UPGRADE ROADWAY. | HIGHWAY | 14 | SOUTHWESTERN RPO | A-0009CB | EXEMPT | ADHS | 2021 | 3300000 | 2021 | 1300000 | 2022 | 60001000 |  |  | 64601000
GRAHAM | NC 143 | NC 143, WEST BUFFALO CREEK TO NC 143 BUSINESS. UPGRADE CORRIDOR. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-2822
GRAHAM | NC 143 | NC 143 BUSINESS, SOUTH OF SR 1115 TO NORTH OF SR 1125 | HIGHWAY | 14 | SOUTHWESTERN RPO | R-2822A | [11 empty] | COMPLETE
GRAHAM | NC 143 | WEST BUFFALO CREEK TO NC 143 BUSINESS. UPGRADE CORRIDOR. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-2822B | REGION G | T | 2023 | 1100000 | 2023 | 700000 | 2025 | 29201000 |  |  | 31001000
GRAHAM | NC 143, NC 28 | NORTH OF APPALACHIAN TRAIL TO NC 28; NC 143 TO EAST OF SR 1235 (GUNTERS GAP ROAD), UPGRADE ROADWAY. | HIGHWAY | 14 | SOUTHWESTERN RPO | A-0009CC | EXEMPT | ADHS | 2021 | 2300000 | 2021 | 1820000 | 2023 | 47802000 |  |  | 51922000
GRAHAM | NC 28 | SWAIN/GRAHAM COUNTY LINE AT LITTLE TENNESSEE RIVER TO WOODS ROAD AT FONTANA DAM VILLAGE. UPGRADE ROADWAY. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5839BA | DIVISION 14 | T | 2027 | 100000 | 2027 | 200000 | 2029 | 13001000 |  |  | 13301000
GRAHAM | NC 28 | WOODS ROAD AT FONTANA DAM VILLAGE TO EAST OF SR 1245 (FONTANA DAM ROAD). UPGRADE ROADWAY, INCLUDING REALIGNMENT OF NC 28/SR 1245 (FONTANA DAM ROAD) INTERSECTION. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5839BB | NOT FUNDED | T | NOT FUNDED | 46332000 | NOT FUNDED | 80000 | NOT FUNDED | 37000000 |  |  | 83412000
GRAHAM | NC 28 | EAST OF SR 1245 (FONTANA DAM ROAD) TO SR 1287 (CABLE COVE ROAD). UPGRADE ROADWAY. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5839C | NOT FUNDED | T | NOT FUNDED | 90000 | NOT FUNDED | 20000 | NOT FUNDED | 58300000 |  |  | 58410000
GRAHAM | NC 28 | SR 1287 (CABLE COVE ROAD) TO SR 1242 (LOWER TUSKEEGEE ROAD). UPGRADE ROADWAY. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5839D | NOT FUNDED | T | NOT FUNDED | 730000 | NOT FUNDED | 80000 | NOT FUNDED | 57500000 |  |  | 58310000
GRAHAM | NC 28 | SR 1242 (LOWER TUSKEEGEE ROAD) TO NC 143. UPGRADE ROADWAY. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5839E | NOT FUNDED | T | NOT FUNDED | 60000 | NOT FUNDED | 100000 | NOT FUNDED | 22000000 |  |  | 22160000
GRAHAM | NEW ROUTE | US 129 (RODNEY ORR BYPASS) TO ROBINSVILLE HIGH SCHOOL AND MIDDLE SCHOOL. CONSTRUCT NEW ROUTE INCLUDING BRIDGE OVER CHEOAH RIVER. | HIGHWAY | 14 | SOUTHWESTERN RPO | U-5866 | DIVISION 14 | [10 empty] | UNDER CONSTRUCTION
GRAHAM | US 129, NC 143 | SOUTH OF SR 1275 (FIVE POINT ROAD) TO NC 143; US 129 TO SR 1223 (BEECH CREEK ROAD), UPGRADE ROADWAY. | HIGHWAY | 14 | SOUTHWESTERN RPO | A-0009CA | EXEMPT | ADHS | 2021 | 1900000 | 2021 | 2030000 | 2022 | 27200000 |  |  | 31130000
GRAHAM, CHEROKEE | FUTURE US 74 | US 19 BUSINESS IN ANDREWS TO US 129 | HIGHWAY | 14 | SOUTHWESTERN RPO | A-0009A | NOT FUNDED | NHP | NOT FUNDED | 14300000 | NOT FUNDED | 925000 | NOT FUNDED | 366000000 |  |  | 381225000
GRAHAM, SWAIN | NC 28 (FONTANA ROAD) | US 129 TO NC 143. UPGRADE ROADWAY. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5839
GRAHAM, SWAIN, CHEROKEE | US 19, US 74, US 129, NC 28, NC 143 | CORRIDOR "K", ANDREWS TO NC 28 EAST OF ALMOND. UPGRADE ROADWAY TO INCLUDE EXISTING FACILITIES AND NEW LOCATION. | HIGHWAY | 14 | SOUTHWESTERN RPO | A-0009 | [11 empty] | APD FUNDS ARE 100% FEDERAL
GRANVILLE | US 15 | SR 1110 IWEST HILLSBORO STREET) TO NC 56 IN CREEDMOOR. CONSTRUCT SIDEWALK / PATH. | BIKE/PED | 5 | CAPITAL AREA MPO | EB-5513 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION BY CITY OF CREEDMOOR; LET WITH C-5166A AND C-5166B
GRANVILLE | NC 56 | GREENWAY IN CREEDMOOR. CONSTRUCT BIKE-PEDESTRIAN TRAIL SYSTEM. | HIGHWAY | 5 | CAPITAL AREA MPO | C-5166 | EXEMPT | [10 empty] | UNDER CONSTRUCTION BY TOWN OF CREEDMOOR; LET WITH EB-5513
GRANVILLE | NC 56 | GREENWAY IN CREEDMOOR - EASTERN SECTION | HIGHWAY | 5 | CAPITAL AREA MPO | C-5166A | EXEMPT | [10 empty] | UNDER CONSTRUCTION
GRANVILLE | NC 56 | GREENWAY IN CREEDMOOR - WESTERN SECTION | HIGHWAY | 5 | CAPITAL AREA MPO | C-5166B | EXEMPT | [10 empty] | UNDER CONSTRUCTION
GRANVILLE | NC 56 | US 15 AND NC 50 IN CREEDMOOR. REALIGN INTERSECTIONS. | HIGHWAY | 5 | CAPITAL AREA MPO | R-5707 | REGION C | T |  |  |  |  | 2019 | 4988000 | 2021 | 989000 | 5977000 | UNDER CONSTRUCTION; BUILD NC BONDS: $2.681 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $768,000 FOR PRELIMINARY ENGINEERING AND $784,000 FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
GRANVILLE | NC 56 (EAST C STREET) | SR 1215 (WEST LYON STATION ROAD) IN BUTNER. REALIGN INTERSECTION. | HIGHWAY | 5 | KERR-TAR RPO | U-6020 | DIVISION 5 | L, T |  |  |  |  | 2025 | 3850000 |  |  | 3850000 | RIGHT-OF-WAY IN PROGRESS; "L" FUNDING REFLECTS PARTICIPATION BY TOWN OF BUTNER
GRANVILLE | SR 1139 (ENON ROAD) | REPLACE BRIDGE 380096 OVER TAR RIVER. | HIGHWAY | 5 | KERR-TAR RPO | B-5320 | DIVISION 5 | [10 empty] | UNDER CONSTRUCTION
GRANVILLE | SR 1602 (MAIN STREET) | SR 1207 (SPRING STREET) INTERSECTION IN OXFORD. CONSTRUCT MINI-ROUNDABOUT. | HIGHWAY | 5 | KERR-TAR RPO | HS-2005A | DIVISION 5 | HSIP |  |  |  |  | 2021 | 100000 |  |  | 100000 | UNDER CONSTRUCTION
GRANVILLE, DURHAM | I-85 / US 15 | NORTH OF SR 1637 (REDWOOD ROAD) IN DURHAM COUNTY TO SOUTH OF US 15 / SR 1100 (GATE ONE ROAD) IN GRANVILLE COUNTY. PAVEMENT REHABILITATION. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO, CAPITAL AREA MPO, KERR-TAR RPO | HI-0001 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2022 | 3450000 |  |  | 3450000 | UNDER CONSTRUCTION
GRANVILLE, FRANKLIN, PERSON | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE KERR-TAR RPO. | HIGHWAY | 5 | KERR-TAR RPO | C-5610 | EXEMPT | CMAQ, L | 2020 | 105000 |  |  | 2020 | 618000 | 2020 | 315000 | 1038000 | IN PROGRESS
GREENE | NC 58 (KINGOLD BOULEVARD) | SR 1105 (GREENRIDGE ROAD) TO CAROLINA DRIVE. UPGRADE ROADWAY. | HIGHWAY | 2 | EASTERN CAROLINA RPO | R-5898 | NOT FUNDED | T | NOT FUNDED | 200000 | NOT FUNDED | 200000 | NOT FUNDED | 7500000 |  |  | 7900000
GREENE | US 13 | SR 1104 (HULL ROAD). UPGRADE INTERSECTION. | HIGHWAY | 2 | EASTERN CAROLINA RPO | R-5943 | DIVISION 2 | T | 2026 | 2000000 | 2026 | 300000 | 2028 | 1200000 |  |  | 3500000
GREENE | US 13 BYPASS | NC 58 (KINGOLD BOULEVARD) TO NC 91. WIDEN TO THREE LANES WITH CENTER TURN LANE. | HIGHWAY | 2 | EASTERN CAROLINA RPO | R-5812 | DIVISION 2 | L, T |  |  |  |  | 2020 | 9165000 | 2020 | 1290000 | 10455000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $953,999 FOR PE, $3,463,495.25 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $47,286 FOR PE, $3,150,897 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE).
GREENE | US 13/US 258 | NC 91 TO US 258 SPLIT. UPGRADE TO FREEWAY. | HIGHWAY | 2 | EASTERN CAROLINA RPO | R-5942 | NOT FUNDED | T | NOT FUNDED | 11800000 | NOT FUNDED | 2300000 | NOT FUNDED | 62202000 |  |  | 76302000
GREENE | US 264 (FUTURE I-587) | PITT COUNTY LINE TO WILSON COUNTY LINE. PAVEMENT REHABILITATION. | HIGHWAY | 2 | EASTERN CAROLINA RPO | I-6032 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2019 | 4830000 |  |  | 4830000 | TO BE LET WITH I-6035. GARVEE BOND FUNDING $4,020,000; PAYBACK FY 2019-2033. UNDER CONSTRUCTION.
GREENE | GREENE COUNTY | ADMINISTRATION | PUBLIC TRANSIT | 2 | EASTERN CAROLINA RPO | TK-6131 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 460000 | 460000 | FUNDS AUTHORIZED IN PROGRESS
GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | RUNWAY 5R-23L EXTENSION PROGRAM | AVIATION | 7 | GREENSBORO URBAN AREA MPO | AV-5701 | STATEWIDE MOBILITY | O, T |  |  |  |  | 2023 | 21000000 |  |  | 21000000
GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | CONSTRUCT TAXIWAY G. | AVIATION | 7 | GREENSBORO URBAN AREA MPO | AV-5707 | STATEWIDE MOBILITY | O, T |  |  |  |  | 2023 | 16900000 |  |  | 16900000 | IN PROGRESS BY PIEDMONT TRIAD AIRPORT AUTHORITY
GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | CONSTRUCT TAXIWAY OVER FUTURE I-73 EAST OF SR 2085 (BRYAN BOULEVARD). | AVIATION | 7 | GREENSBORO URBAN AREA MPO | AV-5708 | STATEWIDE MOBILITY | T |  |  |  |  | 2020 | 1500000 |  |  | 1500000 | IN PROGRESS BY PIEDMONT TRIAD AIRPORT AUTHORITY
GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | SURFACE MOVEMENT GUIDANCE AND CONTROL SYSTEM (SMGCS) UPDATE. | AVIATION | 7 | GREENSBORO URBAN AREA MPO | AV-5711 | STATEWIDE MOBILITY | O, T |  |  |  |  | 2025 | 9000000 |  |  | 9000000 | WORK PERFORMED BY PIEDMONT TRIAD AIRPORT AUTHORITY
GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | RUNWAY 5R-23L GROUP VI UPGRADE. | AVIATION | 7 | GREENSBORO URBAN AREA MPO | AV-5715 | STATEWIDE MOBILITY | O, T |  |  |  |  | 2024 | 11000000 |  |  | 11000000
GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | HIGH SPEED TAXIWAY TO RUNWAY 5R-23L. | AVIATION | 7 | GREENSBORO URBAN AREA MPO | AV-5718 | STATEWIDE MOBILITY | O, T |  |  |  |  | 2023 | 4000000 |  |  | 4000000
GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | TAXIWAY J EXTENSION, TAXIWAY D TO TAXIWAY J2. | AVIATION | 7 | GREENSBORO URBAN AREA MPO | AV-5800 | STATEWIDE MOBILITY | O, T |  |  |  |  | 2023 | 7000000 |  |  | 7000000
GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | CONSTRUCT NORTHWEST APRON TO INCREASE CAPACITY FOR FUTURE EXPANSION. | AVIATION | 7 | GREENSBORO URBAN AREA MPO | AV-5802 | STATEWIDE MOBILITY | O, T |  |  |  |  | 2023 | 11000000 |  |  | 11000000
GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | TAXIWAY F. CONSTRUCT TAXIWAY INCLUDING BRIDGE OVER TED JOHNSON PARKWAY. | AVIATION | 7 | GREENSBORO URBAN AREA MPO | AV-5803 | STATEWIDE MOBILITY | O, T |  |  |  |  | 2024 | 28000000 |  |  | 28000000
GUILFORD | A&Y GREENWAY | SPRING GARDEN STREET TO SOUTH OF ROLLINS ROAD IN GREENSBORO. CONSTRUCT MULTIUSE PATH. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-6037C | DIVISION 7 | BGANY, L, TAANY |  |  |  |  | 2023 | 8936000 |  |  | 8936000
GUILFORD | BENJAMIN PARKWAY; WESTOVER TERRACE | BENJAMIN PARKWAY FROM ELAM AVENUE TO BATTLEGROUND AVENUE, AND WESTOVER TERRACE FROM BENJAMIN PARKWAY TO SEMINOLE DRIVE IN GREENSBORO. CONSTRUCT SIDEWALK ON BENJAMIN PARKWAY FROM ELAM AVENUE TO AYCOCK STREET, CONSTRUCT SIDEPATH ON BENJAMIN PARKWAY FROM AYC | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-5986 | DIVISION 7 | L, TAANY | 2022 | 70000 |  |  | 2024 | 1200000 |  |  | 1270000
GUILFORD | CEDROW DRIVE | WEST OF I-74 TO EAST OF I-74 IN HIGH POINT. CONSTRUCT MULTIUSE FACILITY ACROSS I-74. | BIKE/PED | 7 | HIGH POINT URBAN AREA MPO | EB-5989 | DIVISION 7 | L, TA5200 | 2025 | 50000 |  |  | 2026 | 1200000 | 2024 | 120000 | 1370000
GUILFORD | CONE BOULEVARD | US 29 (O'HENRY BOULEVARD) TO ST. REGIS ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-5985 | DIVISION 7 | L, TAANY | 2023 | 78000 |  |  | 2023 | 471000 | 2022 | 150000 | 699000
GUILFORD | FARMINGTON DRIVE | HOLDEN ROAD TO SR 4121 (WEST GATE CITY BOULEVARD) IN GREENSBORO. CONSTRUCT SIDEWLAKS. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-5877 | DIVISION 7 | L, TAANY | 2022 | 25000 |  |  | 2023 | 300000 |  |  | 325000 | IN PROGRESS
GUILFORD | GREEN VALLEY ROAD | FRIENDLY AVENUE TO WESTOVER TERRACE IN GREENSBORO. CONSTRUCT SIDEWALKS. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-5997 | DIVISION 7 | L, TAANY | 2023 | 45000 |  |  | 2025 | 358000 |  |  | 403000
GUILFORD | HIGH POINT RAILROAD ESPLANADE | LIINDSAY STREET TO CENTENNIAL STREET IN HIGH POINT. CONSTRUCT GREENWAY. | BIKE/PED | 7 | HIGH POINT URBAN AREA MPO | EB-5990 | DIVISION 7 | L, TA5200 |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8000000 | 2028 | 800000 | 8800000
GUILFORD | HOLDEN ROAD | SR 4121 (WEST GATE CITY BOULEVARD) TO NORTH OF SR 4121 (WEST GATE CITY BOULEVARD) IN GREENSBORO. CONSTRUCT SIDEWALKS. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-5876 | DIVISION 7 | [10 empty] | UNDER CONSTRUCTION BY CITY OF GREENSBORO
GUILFORD | HOLDEN ROAD; EAST LINDSAY STREET | HOLDEN ROAD, SOUTH OF MEADOWVIEW ROAD TO SPRING GARDEN ROAD IN GREENSBORO. CONSTRUCT SIDEWALK ON WEST SIDE. EAST LINDSAY STREET, MURROW BOULEVARD TO BESSEMER AVENUE IN GREENSBORO. CONSTRUCT SIDEWALK ON NORTH SIDE. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-5716 | DIVISION 7 | [10 empty] | UNDER CONSTRUCTION
GUILFORD | JOHNSON STREET | PARRIS AVENUE TO SR 1896 (EAST HARTLEY DRIVE) IN HIGH POINT. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | HIGH POINT URBAN AREA MPO | EB-5999 | DIVISION 7 | L, TA5200 |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 145000 |  |  | 145000
GUILFORD | LATHAM PARK GREENWAY | BATTLEGROUND AVENUE TO MENDENHALL STREET IN GREENSBORO. REMOVE THROUGH LANE ON HILL STREET AND CONSTRUCT MULTIUSE PATH. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-5518 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION BY CITY OF GREENSBORO
GUILFORD | LATHAM PARK GREENWAY LAKE DANIEL GREENWAY; | LAKE DANIEL GREENWAY, FRIENDLY AVENUE TO JOSEPHINE BOYD STREET, AND LATHAM PARK GREENWAY AT TENNIS COURTS NEAR WENDOVER AVENUE IN GREENSBORO. REPAIR SURFACES. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | BL-0041 | DIVISION 7 | BGDACV |  |  |  |  | 2024 | 500000 |  |  | 500000
GUILFORD | LAWNDALE DRIVE | PISGAH CHURCH ROAD TO LAKE BRANDT ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-5995 | DIVISION 7 | L, TAANY | 2023 | 48000 |  |  | 2025 | 381000 |  |  | 429000
GUILFORD | NC 68 (EASTCHESTER DRIVE) | JOHNSON STREET TO SR 1278 (NORTH COLLEGE DRIVE) IN HIGH POINT. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | HIGH POINT URBAN AREA MPO | EB-5874 | DIVISION 7 | L, TA5200 |  |  |  |  | 2023 | 142000 |  |  | 142000
GUILFORD | NC 68 (EASTCHESTER DRIVE) | CENTENNIAL STREET TO LASSITER DRIVE IN HIGH POINT. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | HIGH POINT URBAN AREA MPO | EB-5922 | DIVISION 7 | L, TA5200 |  |  |  |  | 2025 | 135000 |  |  | 135000
GUILFORD | NEW PEDESTRIAN BRIDGE AND APPROACHES | EXISTING SIDEWALK TO PIEDMONT ENVIRONMENTAL CENTER ENTRANCE IN HIGH POINT AND JAMESTOWN. CONSTRUCT PEDESTRIAN BRIDGE OVER EAST FORK OF DEEP RIVER. | BIKE/PED | 7 | HIGH POINT URBAN AREA MPO | EB-5517 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION BY TOWN OF JAMESTOWN
GUILFORD | OLD BATTLEGROUND ROAD | LAKE BRANDT ROAD TO BICENTENNIAL GREENWAY IN GREENSBORO. CONSTRUCT MULTIUSE PATH. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-5987 | DIVISION 7 | L, TAANY | 2024 | 11000 |  |  | 2025 | 887000 | 2022 | 99000 | 997000
GUILFORD | SPRING GARDEN STREET | SR 1008 (WEST MARKET STREET) TO POMONA DRIVE AND MERRITT DRIVE TO HOLDEN ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-5992 | DIVISION 7 | L, TAANY |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 315000 | 2027 | 35000 | 350000
GUILFORD | SR 1001 (NORTH CHURCH STREET) | HENRY STREET / ELECTRA DRIVE TO LEES CHAPEL ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-5996 | DIVISION 7 | L, TAANY |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 434000 | 2027 | 49000 | 483000
GUILFORD | SR 1278 (SOUTH COLLEGE DRIVE) | SR 1300 (EAST GREEN DRIVE) TO SR 1113 (EAST KIVETT DRIVE) IN HIGH POINT. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | HIGH POINT URBAN AREA MPO | EB-5873 | DIVISION 7 | L, TA5200 |  |  |  |  | 2023 | 129000 |  |  | 129000
GUILFORD | SR 1486 (WEST MAIN STREET); SR 1539 (PENNY ROAD) | EXISTING SIDEWALK ON SR 1486 (WEST MAIN STREET) TO PARK ACCESS ON SR 1539 (PENNY ROAD) IN JAMESTOWN. CONSTRUCT SIDEWALK WITH CURB AND GUTTER. | BIKE/PED | 7 | HIGH POINT URBAN AREA MPO | EB-5889 | DIVISION 7 | L, TA5200 |  |  |  |  | 2023 | 500000 |  |  | 500000
GUILFORD | SR 1536 (PENNY ROAD) | CITY LAKE PARK TO PIEDMONT ENVIRONMENTAL CENTER IN HIGH POINT. CONSTRUCT MULTIUSE PATH. | BIKE/PED | 7 | HIGH POINT URBAN AREA MPO | EB-6000 | DIVISION 7 | L, TA5200 |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1500000 | 2027 | 150000 | 1650000
GUILFORD | SR 2526 (SUMMIT AVENUE) | SULLIVAN STREET TO FOURTH STREET IN GREENSBORO. CONSTRUCT BICYCLE, PEDESTRIAN AND SAFETY IMPROVEMENTS. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-6009 | DIVISION 7 | L, TAANY |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3719000 | 2028 | 656000 | 4375000
GUILFORD | SR 4121 (EAST MAIN STREET) | EXISTING SIDEWALK NEAR JAMESTOWN MUNICIPAL BUILDING TO YORKLEIGH LANE NEAR GUILFORD TECHNICAL COMMUNITY COLLEGE JAMESTOWN CAMPUS/RAGSDALE HIGH SCHOOL COMPLEX IN JAMESTOWN. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | HIGH POINT URBAN AREA MPO | EB-5519 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION BY TOWN OF JAMESTOWN
GUILFORD | SUMMERFIELD SOUTH GREENWAY | US 220 TO CENTERFIELD ROAD IN SUMMERFIELD. CONSTRUCT MULTIUSE PATH. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-5900 | DIVISION 7 | L, TAANY | 2022 | 390000 |  |  | 2024 | 3896000 |  |  | 4286000
GUILFORD | US 220 (WENDOVER AVENUE) | GRECADE STREET TO SR 1001 (NORTH CHURCH STREET) AND SR 2526 (SUMMIT AVENUE) TO US 29 (NORTH O'HENRY BOULEVARD) IN GREENSBORO. CONSTRUCT SIDEWALKS. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-5883 | DIVISION 7 | L, TAANY | 2023 | 296000 |  |  | 2024 | 2811000 |  |  | 3107000
GUILFORD | US 70 (WEST WENDOVER AVENUE) | NC 68 (EASTCHESTER DRIVE) TO GIBSON PARK ENTRANCE IN HIGH POINT. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | HIGH POINT URBAN AREA MPO | EB-6010 | DIVISION 7 | L, TA5200 |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 220000 |  |  | 220000 | COORDINATE WITH U-6121
GUILFORD | VANCE ARLINGTON GREENWAY | NORTH OF FLORIDA STREET TO BRAGG STREET IN GREENSBORO. CONSTRUCT GREENWAY AND SIDEPATH. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | BL-0042 | DIVISION 7 | BGDACV |  |  |  |  | 2023 | 1200000 |  |  | 1200000
GUILFORD | VARIOUS |  | BIKE/PED | 7 | HIGH POINT URBAN AREA MPO | BL-0071 | EXEMPT | DP, L, S | 2023 |  | 2023 |  | 2024 | 200000 | 2022 |  | 200000 | "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT; "S" FUNDING REFLECTS SPOT SAFETY FUNDS
GUILFORD | VARIOUS | PEDESTRIAN AND BICYCLE PROJECTS IN THE GREENSBORO URBAN AREA METROPOLITAN PLANNING ORGANIZATION (GUAMPO). | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EL-5101 | DIVISION 7 | [10 empty] | PLANNING, DESIGN, RIGHT-OF-WAY AND CONSTRUCTION BY OTHERS - IN PROGRESS
GUILFORD | VARIOUS | GREENSBORO URBAN AREA MPO: BICYCLE, PEDESTRIAN, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)–ELIGIBLE PROJECTS | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | U-5532 | DIVISION 7 | BGANY, BGDA, L, TAANY, TADA | 2021 | 248000 |  |  | 2021 | 6327000 |  |  | 6575000 | IN PROGRESS
GUILFORD | WEST MEADOWVIEW ROAD | SR 1007 (RANDLEMAN ROAD) TO SOUTH ELM-EUGENE STREET IN GREENSBORO. CONSTRUCT SIDEWALKS. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-5878 | DIVISION 7 | L, TAANY | 2022 | 175000 |  |  | 2023 | 259000 |  |  | 434000 | IN PROGRESS
GUILFORD | FUTURE I-73 | FOUR LANES AT SR 2011 (EDGEFIELD ROAD) TO SR 2127 (BROOK BANK ROAD) | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | R-2413A | [11 empty] | COMBINED WITH I-5110 AND R-2413B FOR DESIGN-BUILD LET - UNDER CONSTRUCTION
GUILFORD | (YANCEYVILLE STREET); SR 2876 (SANDS DRIVE); OLD B | SR 2523, LEES CHAPEL ROAD TO FUTURE I-840 (GREENSBORO URBAN LOOP) IN GREENSBORO. WIDEN AND MODERNIZE ROADWAY, ADD CURB AND GUTTER, AND CONSTRUCT SIDEWALKS. SR 2876, EAST CONE BOULEVARD TO MCKNIGHT MILL ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. OLD BATTLEG | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | HL-0047 | DIVISION 7 | BGDA, L | 2023 | 70000 |  |  | 2024 | 550000 |  |  | 620000
GUILFORD | BALLINGER ROAD | REPLACE BRIDGE 400098 OVER A TRIBUTARY OF HORSEPEN CREEK IN GREENSBORO. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | B-5553 | DIVISION 7 | [10 empty] | UNDER CONSTRUCTION BY CITY OF GREENSBORO; MUNICIPAL BRIDGE PROJECT
GUILFORD | BOULEVARD) SR 4240 (EAST GATE CITY | WILLOW ROAD TO FLORIDA STREET IN GREENSBORO. MODERNIZE ROADWAY, ADD CURB AND GUTTER, AND CONSTRUCT SIDEWALKS. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | HL-0046 | DIVISION 7 | BGDA, L | 2023 | 150000 |  |  | 2023 | 3560000 |  |  | 3710000
GUILFORD | FRIENDLY AVENUE | WEST OF GREEN VALLEY ROAD TO LINDELL ROAD IN GREENSBORO. WIDENING AND INTERSECTION IMPROVEMENTS. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-5841 | DIVISION 7 | T |  |  |  |  | 2023 | 1400000 |  |  | 1400000 | UNDER CONSTRUCTION
GUILFORD | FUTURE I-73 | NC 68 TO GREENSBORO WESTERN LOOP. SIX-LANE FREEWAY ON NEW LOCATION. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | I-5110 | PRE-STI (TRANSITION) | [10 empty] | COMBINED WITH R-2413A AND R-2413B FOR DESIGN-BUILD LET - UNDER CONSTRUCTION
GUILFORD | FUTURE I-73 | SR 2127 (BROOK BANK ROAD) TO HAW RIVER | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | R-2413B | [11 empty] | COMBINED WITH I-5110 AND R-2413A FOR DESIGN-BUILD LET - UNDER CONSTRUCTION
GUILFORD | FUTURE I-785 / FUTURE I-840 | GREENSBORO EASTERN LOOP, US 70 RELOCATION TO US 29 NORTH OF GREENSBORO | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-2525B | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
GUILFORD | FUTURE I-840 | GREENSBORO WESTERN LOOP, NORTH OF SR 2176 (BRYAN BOULEVARD) TO US 220 (BATTLEGROUND AVENUE) | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-2524C | PRE-STI (TRANSITION) | NHP |  |  |  |  | 2013 | 54285000 |  |  | 54285000 | UNDER CONSTRUCTION. GARVEE BOND FUNDING $105.9 M FOR SEGMENT C; PAYBACK FY 2013-2024
GUILFORD | FUTURE I-840 | GREENSBORO WESTERN LOOP, US 220 (BATTLEGROUND AVENUE) TO LAWNDALE DRIVE | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-2524D | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
GUILFORD | FUTURE I-840 | GREENSBORO WESTERN LOOP, INTERCHANGE AT PROPOSED LEWISTON-FLEMING ROAD EXTENSION | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-2524F |  | NHP |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 15000000 |  |  | 15000000
GUILFORD | FUTURE I-840 | GREENSBORO EASTERN LOOP, US 29 NORTH OF GREENSBORO TO SR 2303 (LAWNDALE DRIVE) | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-2525C | STATEWIDE MOBILITY | T |  |  |  |  | 2018 | 94830000 | 2021 | 8399000 | 103229000 | UNDER CONSTRUCTION; BUILD NC BONDS: $6.526 MILLION FOR PRELIMINARY ENGINEERING AND $29.3 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
GUILFORD | FUTURE I-840 | INTERCHANGE AT PROPOSED CONE BOULEVARD EXTENSION | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-2525D |  | T |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 15000000 |  |  | 15000000
GUILFORD | HIGH POINT | HIGH POINT SIGNAL SYSTEM RETIMING STUDY | HIGHWAY | 7 | HIGH POINT URBAN AREA MPO | HL-0060 | EXEMPT | CMAQ, L | [6 empty] | 2023 | 1523000 | 1523000
GUILFORD | I-40 | 1.3 MILES EAST OF SR 1850 (SANDY RIDGE ROAD) TO 1.1 MILES EAST OF SR 1556 (GALLIMORE DAIRY ROAD) IN GREENSBORO. PAVEMENT REHABILITATION. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | I-5734 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION - PRIOR YEAR COST IS FOR BRIDGE PRESERVATION; PAVEMENT REHABILITATION COST INCLUDED IN I-5762
GUILFORD | I-40 | FORSYTH COUNTY LINE TO 1.3 MILES EAST OF SR 1850 (SANDY RIDGE ROAD). PAVEMENT REHABILITATION. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO, HIGH POINT URBAN AREA MPO | I-5762 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION - INCLUDES CONSTRUCTION COST FOR I-5734
GUILFORD | I-40 | WEST OF I-73 / US 421 TO HOLDEN ROAD IN GREENSBORO. PAVEMENT REHABILITATION. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | I-5811 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
GUILFORD | I-40 | HOLDEN ROAD TO EAST OF SR 3037 / SR 4240 (EAST GATE CITY BOULEVARD) IN GREENSBORO. PAVEMENT REHABILITATION. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | I-5955 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2023 | 14104000 |  |  | 14104000 | COORDINATE WITH I-5965 AND B-5356
GUILFORD | I-40 | SR 1860 (MACY GROVE ROAD). CONVERT GRADE SEPARATION TO INTERCHANGE. | HIGHWAY | 7 | HIGH POINT URBAN AREA MPO | I-5980 | REGION D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3824000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 33700000 |  |  | 40924000
GUILFORD | I-40 / BUSINESS 85 (WESTBOUND) | REPLACE BRIDGE 400291 AND BRIDGE 400349 OVER US 29 / US 70 / US 220 IN GREENSBORO. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | B-5119 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
GUILFORD | I-40 / BUSINESS 85 / US 29 / US 70 / US 220 | REPLACE BRIDGE 400299 OVER SOUTH BUFFALO CREEK IN GREENSBORO. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | B-5356 | STATEWIDE MOBILITY | BFP |  |  |  |  | 2028 | 11700000 |  |  | 11700000 | RIGHT-OF-WAY IN PROGRESS - COORDINATE WITH I-5965
GUILFORD | I-40 / BUSINESS 85 / US 29 / US 70 / US 220 | ELM-EUGENE STREET IN GREENSBORO. INTERCHANGE IMPROVEMENTS. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | I-5964 | STATEWIDE MOBILITY | NHP |  |  |  |  | 2023 | 575000 |  |  | 575000 | UNDER CONSTRUCTION
GUILFORD | I-40 / BUSINESS 85 / US 29 / US 70 / US 220 | US 220 / SR 1398 (FREEMAN MILL ROAD) TO US 29 / US 70 / US 220 IN GREENSBORO. ADD LANES, IMPROVE SR 1007 (RANDLEMAN ROAD) AND ELM-EUGENE STREET INTERCHANGES, AND REPLACE NORFOLK-SOUTHERN RAILROAD BRIDGE OVERPASS EAST OF ELM-EUGENE STREET. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | I-5965 | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 11000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3732000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 109201000 |  |  | 123933000 | COORDINATE WITH B-5356 AND B-5718
GUILFORD | I-40 / BUSINESS 85 I-40 / I-85 I-85 | I-40 / BUSINESS 85, EAST OF SR 3037 / SR 4240 (EAST GATE CITY BOULEVARD) TO I-85; I-85 NORTH OF SR 3000 (MCCONNELL ROAD) TO I-40; I-40 / I-85, WEST OF SR 3048 (MOUNT HOPE CHURCH ROAD) TO EAST OF SR 3056 (ROCK CREEK DAIRY ROAD). PAVEMENT REHABILITATION. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | I-5812 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
GUILFORD | I-40 / I-85 | SR 3056 (ROCK CREEK DAIRY ROAD) INTERCHANGE. UPGRADE INTERCHANGE AREA. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | I-6004 | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 429000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10900000 |  |  | 12729000
GUILFORD | I-40 / US 421 | SR 1850 (SANDY RIDGE ROAD) IN GREENSBORO. INTERCHANGE IMPROVEMENTS. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | I-5712 | STATEWIDE MOBILITY | NHP | 2025 | 12633000 | 2025 | 502000 | 2027 | 14499000 |  |  | 27634000
GUILFORD | I-73 | I-85 TO SR 2085 (BRYAN BOULEVARD) IN GREENSBORO. PAVEMENT AND BRIDGE REHABILITATION. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | I-5852
GUILFORD | I-73 / I-840 | I-40 TO SR 2085 (BRYAN BOULEVARD) | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | I-5852B | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
GUILFORD | I-73 / I-840 | GREENSBORO WESTERN LOOP, SOUTH OF I-40 TO NORTH OF SR 2147 (WEST FRIENDLY AVENUE) | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-2524BA | [11 empty] | COMPLETE
GUILFORD | I-73 / I-840 | GREENSBORO WESTERN LOOP, NORTH OF SR 2147 (WEST FRIENDLY AVENUE) TO NORTH OF SR 2176 (BRYAN BOULEVARD) | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-2524BB | [11 empty] | COMPLETE
GUILFORD | I-73 / I-840 | SR 2085 (BRYAN BOULEVARD) INTERCHANGE MODIFICATIONS, INCLUDING AUXILIARY LANES, ITS, AND INMAN ROAD BRIDGE REPLACEMENT. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-2524BC | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
GUILFORD | I-73 / I-840 | GREENSBORO WESTERN LOOP, ITS INSTALLATION | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-2524E | [11 empty] | COMPLETE
GUILFORD | I-73 / I-840 / FUTURE I-840 / US 421 | GREENSBORO WESTERN LOOP, NORTH OF I-85 TO LAWNDALE DRIVE IN GREENSBORO. CONSTRUCT FREEWAY ON NEW LOCATION. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-2524 | [11 empty] | GARVEE BOND FUNDING $105.9 M FOR SEGMENT C; PAYBACK FY 2013-2024
GUILFORD | I-73 / US 421 | I-85 TO I-40 | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | I-5852A | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
GUILFORD | I-73 / US 421 | GREENSBORO WESTERN LOOP, NORTH OF I-85 NEAR SR 1129 (GROOMETOWN ROAD) TO NORTH OF SR 4121 (HIGH POINT ROAD) | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-2524AB | [11 empty] | COMPLETE
GUILFORD | I-73 / US 421 | GREENSBORO WESTERN LOOP, NORTH OF SR 4121 (HIGH POINT ROAD) TO SOUTH OF I-40 | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-2524AC | [11 empty] | COMPLETE
GUILFORD | I-73 / US 421 | GREENSBORO WESTERN LOOP, INTERCHANGE AT PROPOSED HIGH POINT ROAD RELOCATION | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-2524AE | [11 empty] | UNDER CONSTRUCTION
GUILFORD | I-74 / US 311 | FORSYTH COUNTY LINE TO SR 1300 (GREEN ROAD) IN HIGH POINT. PAVEMENT REHABILITATION. | HIGHWAY | 7 | HIGH POINT URBAN AREA MPO | I-5736 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION - AMOUNT INCLUDES I-5767 CONSTRUCTION
GUILFORD | I-74 / US 311 | NC 68 (EASTCHESTER DRIVE) IN HIGH POINT. RECONSTRUCT INTERCHANGE AND APPROACHES. | HIGHWAY | 7 | HIGH POINT URBAN AREA MPO | U-5169 | REGION D | [10 empty] | UNDER CONSTRUCTION
GUILFORD | I-74 AND US 29/70 | I-74 AND US 29/70 (I-85 BUSINESS INTERCHANGE). UPGRADE SIGNALS, PAVEMENT MARKINGS, AND SIGNING. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | HS-2007D | DIVISION 7 | HSIP |  |  |  |  | 2023 | 500000 |  |  | 500000
GUILFORD | I-785 / I-840 | I-85 TO US 70. PAVEMENT REHABILITATION. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | I-5953 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
GUILFORD | I-785 / I-840 | GREENSBORO EASTERN LOOP, SOUTH OF SR 3041 (CLAPP FARMS ROAD) TO US 70 RELOCATION | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-2525A | [11 empty] | COMPLETE
GUILFORD | I-785 / I-840; FUTURE I-785; FUTURE I-840 | GREENSBORO EASTERN LOOP, LAWNDALE DRIVE TO NORTH OF I-40 / I-85 IN GREENSBORO. CONSTRUCT FREEWAY ON NEW LOCATION. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-2525
GUILFORD | I-85 | SR 1113 (KIVETT DRIVE) TO 0.4 MILE NORTH OF I-85 BUSINESS IN HIGH POINT. PAVEMENT REHABILITATION. | HIGHWAY | 7 | HIGH POINT URBAN AREA MPO | I-5789 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION - CONSTRUCTION COST INCLUDES I-5738 AND I-5821
GUILFORD | I-85 | 0.2 MILE NORTH OF SR 3039 (NELSON FARM ROAD) TO 1.3 MILES NORTH OF SR 3029 (YOUNGS MILL ROAD) IN GREENSBORO. PAVEMENT REHABILITATION. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | I-5790 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION - AMOUNT INCLUDES I-5855 CONSTRUCTION
GUILFORD | I-85 | RANDOLPH COUNTY LINE TO SR 1113 (KIVETT DRIVE). PAVEMENT REHABILITATION. | HIGHWAY | 7 | HIGH POINT URBAN AREA MPO | I-5821 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION - CONSTRUCTION COST INCLUDED UNDER I-5789
GUILFORD | I-85 | NORTH OF I-73 / US 421 INTERCHANGE TO SR 3300 (SOUTH ELM-EUGENE STREET). PAVEMENT REHABILITATION. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | I-5854 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
GUILFORD | I-85 | SR 3300 (SOUTH ELM-EUGENE STREET) TO 0.2 MILE NORTH OF SR 3039 (NELSON FARM ROAD) IN GREENSBORO. PAVEMENT REHABILITATION. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | I-5855 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION - CONSTRUCTION COST INCLUDED IN I-5790
GUILFORD | I-85 / US 29 / US 70 | 1 MILE SOUTH OF SR 1129 (GROOMETOWN ROAD) TO 0.3 MILE NORTH OF SR 1129 (GROOMETOWN ROAD) IN GREENSBORO. PAVEMENT REHABILITATION. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | I-5853 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
GUILFORD | I-85 BUSINESS/US29/70 | I-85 BUSINESS/US 29/70 SOUTHBOUND AND NORTHBOUND FROM RANDOLPH COUNTY LINE TO NORTH OF SR 1145 (RIVERDALE DRIVE) IN HIGH POINT. INSTALL GUARDRAIL. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | HS-2007A | REGION D | HSIP |  |  |  |  | 2021 | 540000 |  |  | 540000 | UNDER CONSTRUCTION
GUILFORD | I-85 BUSINESS/US29/70 | I-85 BUSINESS/US 29/70 NORTHBOUND FROM NORTH OF SR 1145 (RIVERDALE DRIVE) TO I-85 IN HIGH POINT. INSTALL GUARDRAIL. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | HS-2007B | REGION D | HSIP |  |  |  |  | 2021 | 270000 |  |  | 270000 | UNDER CONSTRUCTION
GUILFORD | MCCONNELL ROAD | GORRELL STREET AND WILLOW HOPE STREET IN GREENSBORO. CONSTRUCT ROUNDABOUT. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6185 | DIVISION 7 | BGANY, L | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1300000 |  |  | 2100000 | NON-SYSTEM FACILITY - LOCAL MATCH BY CITY OF GREENSBORO
GUILFORD | NC 62 | NC 62 FROM WEST OF SR 1138 (TOM BALL ROAD) TO WEST OF THE ALAMANCE COUNTY LINE. INSTALL PAVEMENT MARKINGS. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | HS-2007E | DIVISION 7 | HSIP |  |  |  |  | 2023 | 715000 |  |  | 715000
GUILFORD | NC 62 | SR 1154 (KERSEY VALLEY ROAD) TO SR 1162 (WEANT ROAD) IN ARCHDALE. IMPROVE INTERCHANGE AREA AND REALIGN SR 1154 AND SR 1162 INTERSECTIONS. | HIGHWAY | 7 | HIGH POINT URBAN AREA MPO | U-6018 | DIVISION 7 | T | 2021 | 1803000 | 2021 | 1311000 | 2023 | 14200000 |  |  | 17314000 | RIGHT OF WAY IN PROGRESS
GUILFORD | NC 62 | SR 1007 (RANDLEMAN ROAD). CONSTRUCT TURN LANES. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6212 | DIVISION 7 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1500000 |  |  | 1800000
GUILFORD | NC 62; SR 1129 (GROOMETOWN ROAD) | SR 1129 AT SR 4019 (GROOMETOWN ROAD); NC 62 AT SR 1129 (GROOMETOWN ROAD). REALIGN BOTH INTERSECTIONS AND REMOVE ACCESS BETWEEN SR 4019 AND NC 62. | HIGHWAY | 7 | HIGH POINT URBAN AREA MPO, GREENSBORO URBAN AREA MPO | W-5305 | REGION D | [10 empty] | UNDER CONSTRUCTION
GUILFORD | NC 68 | SR 1523 (HICKSWOOD ROAD) TO SR 1556 (GALLIMORE DAIRY ROAD) IN HIGH POINT. UPGRADE TO SUPERSTREET. | HIGHWAY | 7 | HIGH POINT URBAN AREA MPO | U-5974 | REGION D | T | 2027 | 19400000 | 2027 | 6600000 | 2029 | 48100000 |  |  | 74100000 | COORDINATE WITH U-6122; BUILD NC BONDS: $40 MILLION FOR CONSTRUCTION - PAYBACK 2027-2041
GUILFORD | NC 68 | SR 1556 (GALLIMORE DAIRY ROAD) TO TRIAD CENTER DRIVE IN GREENSBORO. UPGRADE CORRIDOR TO SUPERSTREET. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO, HIGH POINT URBAN AREA MPO | U-6122 | REGION D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 14200000 |  |  | 22700000 | COORDINATE WITH U-5974
GUILFORD | NC 68 | SR 2129 (FOGLEMAN ROAD) TO SR 2017 / SR 2269 (ALCORN ROAD) IN OAK RIDGE. ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6127 | REGION D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9800000 |  |  | 12300000 | COORDINATE WITH R-5725
GUILFORD | NC 68 | SOUTH OF SR 2111 (EAST HARRELL ROAD) TO SR 4831 (BARTONSHIRE DRIVE) IN OAK RIDGE AND SUMMERFIELD. CONSTRUCT TURN LANES, CLOSE ACCESS TO SR 2029 (WEST HARRELL ROAD), AND RELOCATE SR 2111 INTERSECTION AND PORTION OF SR 2111. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | W-5114 | [11 empty] | UNDER CONSTRUCTION
GUILFORD | NC 68; NC 150 | ALONG NC 68 AND NC 150 IN OAK RIDGE. INTERSECTION IMPROVEMENTS. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | R-5725 | REGION D | T | 2022 | 1287000 | 2022 | 500000 | 2023 | 7300000 |  |  | 9087000 | COORDINATE WITH U-6127. RIGHT OF WAY IN PROGRESS
GUILFORD | OAKDALE ROAD | EXISTING SIDEWALK EAST OF EAST MAIN STREET TO CHIMNEY COURT IN JAMESTOWN. EXTEND SIDEWALK. | HIGHWAY | 7 | HIGH POINT URBAN AREA MPO | C-5700 | EXEMPT | CMAQ, L |  |  |  |  | 2022 | 170000 |  |  | 170000
GUILFORD | PATTON AVENUE | REPLACE BRIDGE 400329 OVER I-40 / BUSINESS 85 / US 29 / US 70 / US 220 IN GREENSBORO. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | B-5718 | DIVISION 7 | BFP | 2027 | 218000 | 2027 | 74000 | 2028 | 3350000 |  |  | 3642000 | COORDINATEWITH I-5965
GUILFORD | PISGAH CHURCH ROAD | NORTH ELM STREET IN GREENSBORO. INTERSECTION IMPROVEMENTS. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-5842 | DIVISION 7 | BGANY, L | 2023 | 180000 |  |  | 2024 | 750000 |  |  | 930000 | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO
GUILFORD | SR 1001 (CHURCH STREET) | US 220 (WENDOVER AVENUE) TO EAST CONE BOULEVARD IN GREENSBORO. ADD LANES. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-5851 | DIVISION 7 | T | 2028 | 9400000 | 2028 | 997000 | 2030 | 11999000 |  |  | 22396000
GUILFORD | SR 1001 (NORTH CHURCH STREET) | SR 2516 (ARCHERGATE ROAD) AND SR 2329 (SPENCER-DIXON ROAD) IN GREENSBORO. REALIGN INTERSECTION. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6186 | DIVISION 7 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2850000 |  |  | 4950000
GUILFORD | SR 1007 (RANDLEMAN ROAD) | ELMSLEY DRIVE TO GLENDALE DRIVE IN GREENSBORO. WIDEN TO MULTLANES. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-5850 | DIVISION 7 | T | 2022 | 800000 | 2022 | 500000 | 2025 | 3000000 |  |  | 4300000 | RIGHT OF WAY IN PROGRESS
GUILFORD | SR 1008 (MARKET STREET) | SR 1546 (COLLEGE ROAD) IN GREENSBORO. INTERSECTION IMPROVEMENTS. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-5326 | DIVISION 7 | [10 empty] | UNDER CONSTRUCTION BY CITY OF GREENSBORO
GUILFORD | SR 1158 (JACKSON LAKE ROAD) | REPLACE BRIDGE 400054 OVER RICHLAND CREEK IN HIGH POINT. | HIGHWAY | 7 | HIGH POINT URBAN AREA MPO | B-5723 | DIVISION 7 | BGOFF | 2024 | 280000 |  |  | 2025 | 2800000 |  |  | 3080000
GUILFORD | SR 1486 (GREENSBORO RD) / SR 4121 (HIGH POINT RD) | US 311 BYPASS TO SR 4228 (VICKREY CHAPEL ROAD) | HIGHWAY | 7 | HIGH POINT URBAN AREA MPO | U-2412A | DIVISION 7 | T |  |  |  |  | 2018 | 79158000 |  |  | 79158000 | UNDER CONSTRUCTION; BUILD NC BONDS: $21.508 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $23.573 MILLION FOR CONSTRCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
GUILFORD | SR 1486 (GREENSBORO RD) / SR 4121 (HIGH POINT RD) | SR 4228 (VICKREY CHAPEL ROAD) TO SR 1424 (HILLTOP ROAD) | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO, HIGH POINT URBAN AREA MPO | U-2412B | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
GUILFORD | SR 1486 (GREENSBORO ROAD) / SR 4121 (HIGH POINT RO | PROPOSED US 311 BYPASS IN HIGH POINT TO SR 1424 (HILLTOP ROAD) IN GREENSBORO. WIDEN TO MULTILANES, PART ON NEW LOCATION. | HIGHWAY | 7 | HIGH POINT URBAN AREA MPO, GREENSBORO URBAN AREA MPO | U-2412
GUILFORD | SR 1546 (GUILFORD COLLEGE ROAD) | SOUTH OF SR 1541 (WENDOVER AVENUE) TO NORTH OF SR 1560 (SAPP ROAD) | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-2524AA | [11 empty] | COMPLETE
GUILFORD | SR 1556 (GALLIMORE DAIRY ROAD) | NC 68 TO SR 1008 (WEST MARKET STREET) IN GREENSBORO. WIDEN TO MULTILANES. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-4015
GUILFORD | SR 1556 (GALLIMORE DAIRY ROAD) | NC 68 TO AIRPARK ROAD IN GREENSBORO. WIDEN TO MULTILANES | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-4015A | DIVISION 7 | T | 2021 | 509000 | 2021 | 1270000 | 2023 | 11500000 |  |  | 13279000 | RIGHT OF WAY IN PROGRESS
GUILFORD | SR 1556 (GALLIMORE DAIRY ROAD) | AIRPARK ROAD TO SR 1008 (WEST MARKET STREET) IN GREENSBORO. WIDEN TO MULTILANES. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-4015B | [11 empty] | COMPLETE
GUILFORD | SR 1818 (JOHNSON STREET) / SR 1850 (SANDY RIDGE RO | SR 1820 (SKEET CLUB ROAD) TO SOUTH OF I-40 IN HIGH POINT. WIDEN TO FOUR LANES. | HIGHWAY | 7 | HIGH POINT URBAN AREA MPO | U-4758 | DIVISION 7 | BG5200, HP, S(M) | 2022 | 13221000 | 2022 | 7200000 | 2024 | 48200000 |  |  | 68621000
GUILFORD | SR 1820 (SKEET CLUB ROAD) | US 311 TO NC 68 (EASTCHESTER DRIVE) IN HIGH POINT. WIDEN TO FOUR- AND FIVE-LANE DIVIDED FACILITY. | HIGHWAY | 7 | HIGH POINT URBAN AREA MPO | U-3615
GUILFORD | SR 1820 (SKEET CLUB ROAD) | US 311 TO EAST OF SR 1818 (JOHNSON STREET). WIDEN TO FIVE-LANE FACILITY FROM US 311 TO NORTH OF US 311 AND TO FOUR-LANE MEDIAN DIVIDED FACILITY FROM NORTH OF US 311 TO EAST OF SR1818 (JOHNSON STREET). | HIGHWAY | 7 | HIGH POINT URBAN AREA MPO | U-3615A | NOT FUNDED | T | NOT FUNDED | 5700000 |  |  | NOT FUNDED | 15500000 |  |  | 21200000
GUILFORD | SR 1820 (SKEET CLUB ROAD) | EAST OF SR 1818 (JOHNSON STREET) TO WEST OF NC 68 (EASTCHESTER DRIVE). WIDEN TO FOUR-LANE MEDIAN DIVIDED FACILITY. | HIGHWAY | 7 | HIGH POINT URBAN AREA MPO | U-3615B | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
GUILFORD | SR 1850 (SANDY RIDGE ROAD) | I-40 TO SR 1008 (WEST MARKET STREET) IN GREENSBORO. WIDEN TO MULTILANES. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6045 | DIVISION 7 | T | 2027 | 6800000 | 2027 | 1200000 | 2030 | 23100000 |  |  | 31100000
GUILFORD | SR 2085 (BENJAMIN PARKWAY / BRYAN BOULEVARD) | US 70 (WENDOVER AVENUE) TO HOLDEN ROAD IN GREENSBORO. ADD LANES. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-5852 | DIVISION 7 | T | 2023 | 855000 | 2023 | 600000 | 2025 | 11600000 |  |  | 13055000
GUILFORD | SR 2085 (BRYAN BOULEVARD) | NEW GARDEN ROAD AT HORSEPEN CREEK ROAD IN GREENSBORO. INTERCHANGE IMPROVEMENTS, INCLUDING NEW RAMP FROM WESTBOUND NEW GARDEN ROAD TO WESTBOUND SR 2085. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6008 | DIVISION 7 | T | 2027 | 1600000 | 2027 | 300000 | 2029 | 4600000 |  |  | 6500000
GUILFORD | SR 2124 (LEWISTON ROAD) | SR 2136 (FLEMING ROAD). INTERSECTION IMPROVEMENTS. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6016 | DIVISION 7 | T | 2022 | 836000 | 2022 | 215000 | 2023 | 1300000 |  |  | 2351000 | RIGHT OF WAY IN PROGRESS
GUILFORD | SR 2128 (BUNCH ROAD) | REPLACE BRIDGE 400106 OVER REEDY FORK CREEK IN OAK RIDGE. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | B-4958 | DIVISION 7 | [10 empty] | UNDER CONSTRUCTION
GUILFORD | SR 2133 (PLEASANT RIDGE ROAD) | SR 2136 (FLEMING ROAD) IN SUMMERFIELD. CONSTRUCT TURN LANES. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6211 | DIVISION 7 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2100000 |  |  | 3500000
GUILFORD | SR 2334 (AIR HARBOR ROAD) | SR 2347 (LAKE BRANDT ROAD). CONSTRUCT TURN LANES AND SIDEWALKS. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6019 | DIVISION 7 | T |  |  |  |  | 2022 | 1300000 |  |  | 1300000 | UNDER CONSTRUCTION
GUILFORD | SR 2821 (HARVEST ROAD) | REPLACE BRIDGE 400161 OVER SOUTH BUFFALO CREEK. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | B-5344 | DIVISION 7 | [10 empty] | UNDER CONSTRUCTION
GUILFORD | SR 2835 (MCKNIGHT MILL ROAD) | SR 2842 (MINORWOOD ROAD). UPGRADE INTERSECTION. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6181 | DIVISION 7 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 216000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1400000 |  |  | 1916000
GUILFORD | SR 3058 (JUDGE ADAMS ROAD) | REPLACE BRIDGE 400214 OVER LITTLE ALAMANCE CREEK. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO, GREENSBORO URBAN AREA MPO | B-4960 | DIVISION 7 | [10 empty] | UNDER CONSTRUCTION
GUILFORD | SR 4240 (GATE CITY BOULEVARD) | REPLACE BRIDGE 400109 AND BRIDGE 400121 OVER SOUTH BUFFALO CREEK IN GREENSBORO. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | B-5717 | DIVISION 7 | BFP, S | 2021 | 710000 | 2021 | 165000 | 2022 | 7100000 |  |  | 7975000 | UNDER CONSTRUCTION. "S" FUNDS REFLECT STATE BRIDGE PROGRAM FUNDING
GUILFORD | US 158 | NORTH OF SR 2034 (ANTHONY ROAD) TO US 220 | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | R-2577C | NOT FUNDED | T | NOT FUNDED | 74608000 | NOT FUNDED | 625000 | NOT FUNDED | 48400000 |  |  | 123633000
GUILFORD | US 220 | SR 2182 (HORSEPEN CREEK ROAD) TO US 220-NC 68 CONNECTOR (R-2413) IN GREENSBORO AND SUMMERFIELD. WIDEN TO MULTILANES. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | R-2309
GUILFORD | US 220 | COTSWALD TERRACE NORTH OF GREENSBORO TO SR 2182 (HORSEPEN CREEK ROAD) | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | R-2309AA | [11 empty] | COMPLETE
GUILFORD | US 220 | SR 2182 (HORSEPEN CREEK ROAD) TO NORTH OF SR 2313 (WINFREE ROAD) IN GREENSBORO | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | R-2309AB | [11 empty] | UNDER CONSTRUCTION
GUILFORD | US 220 (BATTLEGROUND AVENUE) | INTERSECTION AND SIDEWALK IMPROVEMENTS AT CONE BOULEVARD-BENJAMIN PARKWAY, WESTRIDGE ROAD, NEW GARDEN ROAD, AND BRASSFIELD ROAD INTERSECTIONS IN GREENSBORO. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-5306
GUILFORD | US 220 (BATTLEGROUND AVENUE) | INTERSECTION WITH BENJAMIN PARKWAY / CONE BOULEVARD AND APPROACHES | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-5306A | PRE-STI (TRANSITION) | [10 empty] | PROJECT COMPLETE
GUILFORD | US 220 (BATTLEGROUND AVENUE) | INTERSECTION WITH WESTRIDGE ROAD AND APPROACHES | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-5306B | REGION D | [10 empty] | UNDER CONSTRUCTION
GUILFORD | US 220 (BATTLEGROUND AVENUE) | INTERSECTION WITH NEW GARDEN ROAD AND APPROACHES | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-5306C | PRE-STI (TRANSITION) | [10 empty] | PROJECT COMPLETE
GUILFORD | US 220 (BATTLEGROUND AVENUE) | INTERSECTION WITH BRASSFIELD ROAD AND APPROACHES | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-5306D | [11 empty] | PROJECT COMPLETE
GUILFORD | US 220 (BATTLEGROUND AVENUE) | WESTRIDGE ROAD TO COTSWOLD AVENUE IN GREENSBORO. ADD LANES. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-5892 | REGION D | NHP | 2023 | 7532000 | 2023 | 1472000 | 2026 | 12400000 |  |  | 21404000
GUILFORD | US 220 EASTBOUND | SR 2526 (SUMMIT AVENUE) RAMP TERMINALS IN GREENSBORO. MODIFY CHANNELIZATION ISLAND AND INSTALL TRAFFIC SIGNAL, PEDESTRIAN HEADS, AND CROSSWALKS. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | W-5807A | REGION D | HSIP | 2023 | 150000 |  |  | 2023 | 280000 |  |  | 430000
GUILFORD | US 29 / US 70 / BUSINESS 85 | SR 1009 (SOUTH MAIN STREET) IN HIGH POINT. RECONSTRUCT INTERCHANGE. | HIGHWAY | 7 | HIGH POINT URBAN AREA MPO | U-5896 | DIVISION 7 | T | 2019 | 8834000 |  |  | 2022 | 15400000 | 2019 | 1820000 | 26054000 | UNDER CONSTRUCTION; COORDINATE WITH B-5353; BUILD NC BONDS: $1.51 MILLION FOR PE AND $7.353 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE)
GUILFORD | US 29 / US 70 / US 220 (O'HENRY BOULEVARD) | I-40 / BUSINESS 85 TO SOUTH OF FLORIDA STREET IN GREENSBORO. ADD LANE ON I-40 / BUSINESS 85 EASTBOUND RAMP ONTO NORTHBOUND US 29 / US 70 / US 220 AND EXTEND US 29 / US 70 / US 220 SOUTHBOUND RAMP ONTO SR 3762 (MARTIN LUTHER KING, JR. DRIVE) | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-5754 | REGION D | T |  |  |  |  | 2022 | 5917000 |  |  | 5917000 | UNDER CONSTRUCTION
GUILFORD | US 29; SR 4771 (REEDY FORK PARKWAY) | US 29 / SR 4771 (REEDY FORK PARKWAY) INTERCHANGE IMPROVEMENTS IN GREENSBORO. IMPROVE ROADWAY, MODIFY INTERCHANGE, AND REPLACE BRIDGE 400360 | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | R-4707 | REGION D | T | 2019 | 5824000 |  |  | 2021 | 62660000 | 2019 | 4019000 | 72503000 | UNDER CONSTRUCTION; BUILD NC BONDS: $3.119 MILLION FOR PE AND $4.854 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), AND $25 MILLION FOR CONSTRUCTION - PAYBACK 2022-2036 (FY 2022 / YR 4 SALE)
GUILFORD | US 29; US 70; US 220 | SR 4240 (GATE CITY BOULEVARD) TO SOUTH OF I-785 IN GREENSBORO. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS AND SAFETY ENHANCEMENTS, INCLUDING RAMP CLOSURES AND CONSOLIDATIONS, RECONFIGURE SR 2526 (SUMMIT AVENUE) / PHILLIPS AVENUE INTERCHANGE, AND REPLACE BRI | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6100 | NOT FUNDED | T | NOT FUNDED | 2937000 | NOT FUNDED | 1115000 | NOT FUNDED | 102500000 |  |  | 106552000
GUILFORD | US 421 | SR 3389 (WOODY MILL ROAD) AND SR 3418 (NEELLEY ROAD) SOUTH OF GREENSBORO. CONVERT AT-GRADE INTERSECTIONS TO INTERCHANGES. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | R-2612 | EXEMPT
GUILFORD | US 421 | SR 3389 (WOODY MILL ROAD) INTERSECTION SOUTH OF GREENSBORO | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | R-2612A | [11 empty] | COMPLETE
GUILFORD | US 421 | SR 3418 (NEELLEY ROAD) INTERSECTION SOUTH OF GREENSBORO | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | R-2612B | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
GUILFORD | US 70 | SR 3045 (MOUNT HOPE CHURCH ROAD) TO SR 3056 (ROCK CREEK DAIRY ROAD). WIDEN TO MULTILANES, PART ON NEW LOCATION. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-2581
GUILFORD | US 70 | SR 2851 (PENRY ROAD) TO SR 2828 (WILLOWLAKE ROAD) | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-2581A | [11 empty] | PROJECT COMPLETE
GUILFORD | US 70 | SR 3045 (MOUNT HOPE CHURCH ROAD) TO SR 2826 (BIRCH CREEK ROAD) | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-2581BA | DIVISION 7 | T | 2020 | 2618000 |  |  | 2020 | 15535000 | 2020 | 1669000 | 19822000 | UNDER CONSTRUCTION; BUILD NC BONDS: $1.172 MILLION FOR PE, $2.184 MILLION FOR RIGHT-OF-WAY, AND $7,298 FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE) $197,000 FOR PE AND $9.255 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
GUILFORD | US 70 | SR 2826 (BIRCH CREEK ROAD) TO SR 3051 (KNOX ROAD) | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-2581BB | NOT FUNDED | T | NOT FUNDED | 2113000 | NOT FUNDED | 626000 | NOT FUNDED | 8200000 |  |  | 10939000
GUILFORD | US 70 | SR 3051 (KNOX ROAD) TO SR 3056 (ROCK CREEK DAIRY ROAD) | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-2581BC | NOT FUNDED | T | NOT FUNDED | 3040000 | NOT FUNDED | 901000 | NOT FUNDED | 11800000 |  |  | 15741000
GUILFORD | US 70 (WENDOVER AVENUE) | NC 68 (EASTCHESTER DRIVE) IN HIGH POINT TO SR 1541 (GUILFORD COLLEGE ROAD) IN GREENSBORO. WIDEN TO 6 LANES AND CONSTRUCT SIDEWALKS. | HIGHWAY | 7 | HIGH POINT URBAN AREA MPO, GREENSBORO URBAN AREA MPO | U-6121 | DIVISION 7 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 19101000 |  |  | 27301000 | COORDINATE WITH EB-6010
GUILFORD | US 70 / US 220 (WENDOVER AVENUE) | US 220 (BATTLEGROUND AVENUE) IN GREENSBORO. RECONFIGURE BATTLEGROUND AVENUE, LAWNDALE DRIVE, AND WESTOVER TERRACE BETWEEN FERNWOOD DRIVE AND WENDOVER AVENUE. IMPROVE TRAFFIC FLOW AND SAFETY. IMPROVE WENDOVER AVENUE CONNECTIONS AT WESTOVER TERRACE, BATTLEG | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6108 | REGION D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 44600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 12500000 |  |  | 58700000
GUILFORD | VARIOUS | SIDEWALK PROJECTS AT SELECTED LOCATIONS IN GREENSBORO. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | C-5555 | EXEMPT | [10 empty] | PLANNING / DESIGN / RIGHT-OF-WAY / CONSTRUCTION BY CITY OF GREENSBORO
GUILFORD | VARIOUS | SR 1546 (COLLEGE ROAD) AND SR 2179 (NEW GARDEN ROAD) IN GREENSBORO. CONSTRUCT SIDEWALKS. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | C-5555E | EXEMPT | BGDA, CMAQ, L |  |  |  |  | 2022 | 1000000 |  |  | 1000000 | RIGHT-OF-WAY IN PROGRESS
GUILFORD | VARIOUS | CITY OF HIGH POINT SIGNAL SYSTEM EXPANSION AND UPGRADE. | HIGHWAY | 7 | HIGH POINT URBAN AREA MPO | C-5558 | EXEMPT | [10 empty] | UNDER CONSTRUCTION
GUILFORD | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE GREENSBORO URBAN AREA MPO. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | C-5607 | EXEMPT | CMAQ, L | 2020 | 360000 |  |  | 2020 | 2154000 | 2020 | 1080000 | 3594000
GUILFORD | VARIOUS | PIEDMONT TRIAD INTERNATIONAL AIRPORT MANUFACTURING SITE IN GREENSBORO. ROADWORK AND WETLANDS MITIGATION. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | HE-0005 | DIVISION 7 | S | 2022 | 1000000 | 2022 | 500000 | 2023 | 30000000 |  |  | 31500000 | ECONOMIC DEVELOPMENT PROJECT; "S" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION.
GUILFORD | VARIOUS | PEDESTRIAN SIGNAL INSTALLATION, ACCESSIBLE RAMP CONSTRUCTION, AND TRAFFIC SIGNAL REPLACEMENT AT VARIOUS INTERSECTIONS IN GREENSBORO. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | HL-0048 | DIVISION 7 | BGDA, BGDACV, L | 2023 | 10000 |  |  | 2024 | 1000000 | 2022 | 240000 | 1250000
GUILFORD | VARIOUS | GREENSBORO URBAN AREA METROPOLITAN PLANNING ORGANIZATION (GUAMPO) SURFACE TRANSPORTATION BLOCK GRANT DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-5021 | DIVISION 7 | BGDA |  |  |  |  | 2023 | 59874000 |  |  | 59874000
GUILFORD | VARIOUS | LAWNDALE DRIVE AND PISGAH CHURCH ROAD IN GREENSBORO. INTERSECTION IMPROVEMENTS AT LAWNDALE ROAD AND PISGAH CHURCH ROAD, AT LAWNDALE ROAD AND MARTINSVILLE ROAD, AND AT MARTINSVILLE ROAD AND PISGAH CHURCH ROAD | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-5812 | DIVISION 7 | BGANY, L | 2023 | 180000 |  |  | 2024 | 750000 |  |  | 930000 | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO
GUILFORD | VARIOUS | SUPPLEMENTAL FUNDING FOR GREENSBORO URBAN AREA MPO UNIFIED PLANNING WORK PROGRAM. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6085 | DIVISION 7 | BGDA, L | [6 empty] | 2022 | 3125000 | 3125000 | IN PROGRESS
GUILFORD | VARIOUS | GREENSBORO URBAN AREA METROPOLITAN PLANNING ORGANIZATION (GUAMPO) TRANSPORTATION ALTERNATIVES DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6220 | DIVISION 7 | TADA |  |  |  |  | 2022 | 9077000 |  |  | 9077000
GUILFORD | WEST FRIENDLY AVENUE | PEMBROKE ROAD INTERSECTION AND GREEN VALLEY ROAD INTERSECTION IN GREENSBORO. CONSTRUCT INTERSECTION AND PEDESTRIAN IMPROVEMENTS. FROM PEMBROKE ROAD TO GREEN VALLEY ROAD, CONSTRUCT ROADWAY AND ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6129 | DIVISION 7 | BGANY, L | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 150000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 52000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 550000 |  |  | 752000 | NON-STATE-SYSTEM FACILITY - LOCAL MATCH BY CITY OF GREENSBORO
GUILFORD | WILLOW ROAD | REPLACE BRIDGE 400352 OVER I-40 / BUSINESS 85 IN GREENSBORO. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | B-5713 | DIVISION 7 | BFP | 2025 | 166000 |  |  | 2026 | 3318000 |  |  | 3484000 | "S" FUNDS REFLECT STATE BRIDGE PROGRAM FUNDING
GUILFORD | AUTHORITY GREENSBORO TRANSIT | OPERATING-ADA PARATRANSIT SERVICE | PUBLIC TRANSIT | 7 | GREENSBORO URBAN AREA MPO | TG-4957 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2022 | 5761000 | 5761000 | FUNDING ADDED TO FY 20, FY 21, FY22, FY23 AT THE REQUEST OF GREENSBORO MPO
GUILFORD | AUTHORITY GREENSBORO TRANSIT | ROUTINE CAPITAL | PUBLIC TRANSIT | 7 | GREENSBORO URBAN AREA MPO | TG-5105 | PUBLIC TRANSIT | 5307, 5339, L | [6 empty] | 2022 | 1967000 | 1967000 | FUNDS AUTHORIZED IN PROGRESS
GUILFORD | BURLINGTON/GIBSONVILLE FIXED ROUTE SYSTEM | OPERATING | PUBLIC TRANSIT | 7 | BURLINGTON-GRAHAM MPO | TO-6151 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2016000 | 2016000
GUILFORD | GREENSBORO TRANSIT AGENCY | PREVENTIVE MAINTENANCE | PUBLIC TRANSIT | 7 | GREENSBORO URBAN AREA MPO | TG-4759 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2022 | 27153000 | 27153000 | FUNDING ADDED TO FY 20, FY 21, FY22, FY23 AT THE REQUEST OF GREENSBORO MPO
GUILFORD | GREENSBORO TRANSIT AUTHORITY | RENOVATION OF J. DOUGLAS GAYLON DEPOT | PUBLIC TRANSIT | 7 | GREENSBORO URBAN AREA MPO | TD-5279 | PUBLIC TRANSIT | 5339, L, S | [6 empty] | 2020 | 2284000 | 2284000 | IN PROGRESS; FUNDING ADDED TO FY 20 AT THE REQUEST OF GREENSBORO MPO
GUILFORD | GREENSBORO TRANSIT AUTHORITY | OPERATING- FIXED ROUTE | PUBLIC TRANSIT | 7 | GREENSBORO URBAN AREA MPO | TO-4971 | PUBLIC TRANSIT | 5307, L, SMAP | [6 empty] | 2022 | 54460000 | 54460000 | REDUCING FUNDS IN FY 20, FY 21, FY 22, FY 23 AT THE REQUEST OF GREENSBRO MPO
GUILFORD | GREENSBORO TRANSIT AUTHORITY | SECTION 5310 OPERATING | PUBLIC TRANSIT | 7 | GREENSBORO URBAN AREA MPO | TO-6139 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2022 | 384000 | 384000 | REDUCING FUNDS IN FY 20, FY 21, FY 22, FY 23 AT THE REQUEST OF GREENSBRO MPO
GUILFORD | GREENSBORO TRANSIT AUTHORITY | PLANNING ASSISTANCE-5303 | PUBLIC TRANSIT | 7 | GREENSBORO URBAN AREA MPO | TP-5101 | PUBLIC TRANSIT | 5303, L, SMAP | [6 empty] | 2021 | 1458000 | 1458000 | FUNDING ADDED TO FY 20, FY 21, FY22, FY23 AT THE REQUEST OF GREENSBORO MPO
GUILFORD | GREENSBORO TRANSIT AUTHORITY | SECTION 5310 CAPITAL PROJECT | PUBLIC TRANSIT | 7 | GREENSBORO URBAN AREA MPO | TQ-6783 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2022 | 1677000 | 1677000
GUILFORD | GREENSBORO TRANSIT AUTHORITY | SECTION 5310 PROGRAM ADMINISTRATION | PUBLIC TRANSIT | 7 | GREENSBORO URBAN AREA MPO | TQ-7000 | PUBLIC TRANSIT | 5310 | [6 empty] | 2022 | 166000 | 166000 | FUNDING ADDED TO FY 20, FY 21, FY22, FY23 AT THE REQUEST OF GREENSBORO MPO
GUILFORD | GREENSBORO TRANSIT AUTHORITY | SAFETY & SECURITY | PUBLIC TRANSIT | 7 | GREENSBORO URBAN AREA MPO | TS-4758 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2022 | 567000 | 567000 | FUNDING ADDED TO FY 20, FY 21, FY22, FY23 AT THE REQUEST OF GREENSBORO MPO
GUILFORD | GTA | REPLACEMENT PARATRANSIT BUSES | PUBLIC TRANSIT | 7 | GREENSBORO URBAN AREA MPO | TA-4767 | PUBLIC TRANSIT | 5309, L | [6 empty] | 2022 | 4844000 | 4844000 | FUNDING ADDED TO FY 20, FY 21, FY22, FY23 AT THE REQUEST OF GREENSBORO MPO
GUILFORD | GTA | CLEAN DIESEL REPLACEMENT BUSES | PUBLIC TRANSIT | 7 | GREENSBORO URBAN AREA MPO | TA-4771 | PUBLIC TRANSIT | 5307, CMAQ, L | [6 empty] | 2022 | 4457000 | 4457000
GUILFORD | GTA | ELECTRIC VEHICLE AND CHARGING INFRASTRUCTURE | PUBLIC TRANSIT | 7 | GREENSBORO URBAN AREA MPO | TA-6714 | PUBLIC TRANSIT | 5339, L | [6 empty] | 2023 | 3540000 | 3540000 | "O" FUNDS REFLECT PROCEEDS FROM VOLKSWAGEN SETTLEMENT
GUILFORD | GTA | EXPANDED SUNDAY SERVICE, NEW SERVICE OPERATIONAL FUNDING | PUBLIC TRANSIT | 7 | GREENSBORO URBAN AREA MPO | TL-0012 | PUBLIC TRANSIT | CMAQ, L | [6 empty] | 2021 | 2705000 | 2705000
GUILFORD | GTA | TRANSIT SAFETY INNOVATIONS | PUBLIC TRANSIT | 7 | GREENSBORO URBAN AREA MPO | TT-5207 |  | 5312, L | [6 empty] | 2020 | 86000 | 86000 | FUNDING ADDED TO FY20, FY21, FY22 AT THE REQUEST OF GREENSBORO MPO
GUILFORD | GTA | THE CITY OF GREENSBORO WILL RECEIVE FUNDING TO PREPARE A TECHNICAL PLAN TO ESTABLISH WHAT WILL BE REQUIRED TO PROVIDE FREE BROADBAND INTERNET ACCESS IN LOW - INCOME AREAS USING TRANSIT, TRANSPORTATION AND OTHER PUBLIC INFRASTRUCTURE. | PUBLIC TRANSIT | 7 | GREENSBORO URBAN AREA MPO | TU-0002 | PUBLIC TRANSIT | 5305, L | [6 empty] | 2021 | 260000 | 260000
GUILFORD | GUILFORD COUNTY TRANSPORTATION | ADMINISTRATION | PUBLIC TRANSIT | 7 | GREENSBORO URBAN AREA MPO | TK-6132 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 908000 | 908000 | FUNDS AUTHORIZED IN PROGRESS
GUILFORD | GUILFORD COUNTY TRANSPORTATION | OPERATING FUNDING FOR GUILFORD COUNTY THROUGH HIGH-POINT MPO | PUBLIC TRANSIT | 7 | HIGH POINT URBAN AREA MPO | TO-5216 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 1330000 | 1330000 | FUNDS AUTHORIZED IN PROGRESS
GUILFORD | GUILFORD COUNTY TRANSPORTATION | OPERATING- RURAL TRANSIT | PUBLIC TRANSIT | 7 | GREENSBORO URBAN AREA MPO | TO-5221 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2022 | 490000 | 490000 | REDUCING FUNDS IN FY 20, FY 21, FY 22, FY 23 AT THE REQUEST OF GREENSBRO MPO
GUILFORD | HIGH POINT TRANSIT SYSTEM / HI-TRAN | PLANNING ASSISTANCE - 5303 | PUBLIC TRANSIT | 7 | HIGH POINT URBAN AREA MPO | TP-5104 | PUBLIC TRANSIT | 5303, L, S | [6 empty] | 2020 | 176000 | 176000 | FUNDS AUTHORIZED IN PROGRESS
GUILFORD | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | ROUTINE CAPITAL | PUBLIC TRANSIT | 7 | GREENSBORO URBAN AREA MPO | TG-6185 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2022 | 651000 | 651000 | FUNDING ADDED TO FY 20 AT THE REQUEST OF GREENSBORO MPO
GUILFORD | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | OPERATING- FIXED ROUTE | PUBLIC TRANSIT | 7 | GREENSBORO URBAN AREA MPO | TO-5209 | PUBLIC TRANSIT | 5307, L, SMAP | [6 empty] | 2022 | 14294000 | 14294000 | AMEND STIP TO-5209 WITH UPDATED FY 20 SECTION 5307 FUNDS ALLOCATED TO PART WITH NEW FEDERAL APPROPRIATIONS FOR ELIGIBLE OPERATING SUBSIDY
GUILFORD | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION (P | VEHICLE REPLACEMENT AND EXPANSION | PUBLIC TRANSIT | 7 | GREENSBORO URBAN AREA MPO | TA-6732 | PUBLIC TRANSIT | 5339, L |  |  |  |  | 2020 | 8480000 |  |  | 8480000 | PROJECT ADDED AT THE REQUEST OF GREENSBORO MPO
GUILFORD | PIEDMONT AUTHORITY FOR PIEDMONT AUTHORITY FOR | ROUTINE CAPITAL, PREVENTIVE MAINTENANCE, SECURITY AND PESSENGER AMENITIES. | PUBLIC TRANSIT | 7 | GREENSBORO URBAN AREA MPO | TG-6173B | PUBLIC TRANSIT | 5307, L | [6 empty] | 2021 | 1138000 | 1138000
GUILFORD | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION (PA | PURCHASE ONE EXPANSION 40-FT BUS. | PUBLIC TRANSIT | 7 | GREENSBORO URBAN AREA MPO | TA-6679 | REGION D | [10 empty] | IN ACQUISITION
GUILFORD | REGIONAL TRANS. PIEDMONT AUTHORITY FOR | REPLACEMENT VEHICLES | PUBLIC TRANSIT | 7 | GREENSBORO URBAN AREA MPO | TA-6690 | PUBLIC TRANSIT | 5339, L | [6 empty] | 2022 | 315000 | 315000
GUILFORD | SYSTEM / HI-TRAN HIGH POINT TRANSIT | PURCHASE REPLACEMENT BUSES | PUBLIC TRANSIT | 7 | HIGH POINT URBAN AREA MPO | TA-6729 | PUBLIC TRANSIT | 5307, CMAQ, L | [6 empty] | 2022 | 500000 | 500000
GUILFORD | SYSTEM / HI-TRAN HIGH POINT TRANSIT | BUILDING / FACILITY RENOVATION AND UPGRADE FOR PARATRANSIT ADMINISTRATION. | PUBLIC TRANSIT | 7 | HIGH POINT URBAN AREA MPO | TD-5283 | REGION D | [10 empty] | IN PROGRESS
GUILFORD | LOWDERMILK STREET SYKES AVENUE | PINE STREET CROSSING CLOSURE AND LOWDERMILK STREET / SYKES AVENUE REALIGNMENT IN GREENSBORO. | RAIL | 7 | GREENSBORO URBAN AREA MPO | Y-4807B | DIVISION 7 | O, RR |  |  | 2021 | 500000 | 2022 | 2548000 |  |  | 3048000 | "O" FUNDING REFLECTS FREIGHT RAIL AND RAIL CROSSING SAFETY IMPROVEMENT (FRRCSI) FUNDS
GUILFORD | NCRR / NORFOLK SOUTHERN MAIN LINE | HOSKINS STREET IN HIGH POINT. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722351T. | RAIL | 7 | HIGH POINT URBAN AREA MPO | P-5752 | DIVISION 7 | O, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2900000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 19000000 |  |  | 21900000
GUILFORD | NCRR NORFOLK SOUTHERN | POMONA YARD. EXTEND AUXILIARY TRACK AND ADD POWER TURNOUTS. | RAIL | 7 | GREENSBORO URBAN AREA MPO | P-5714 | REGION D | O, T |  |  |  |  | 2024 | 3100000 |  |  | 3100000 | "O" FUNDING REFLECTS CONTRIBUTION BY NORFOLK SOUTHERN CORPORATION
GUILFORD | NCRR NORFOLK SOUTHERN H LINE | SOUTH ENGLISH STREET IN GREENSBORO. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722955X. | RAIL | 7 | GREENSBORO URBAN AREA MPO | P-5747 | REGION D | O, T | 2025 | 2300000 |  |  | 2026 | 14899000 |  |  | 17199000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION
GUILFORD | NORFOLK SOUTHERN | JAMESTOWN SIDING IN JAMESTOWN. CONSTRUCT EXTENSION. | RAIL | 7 | HIGH POINT URBAN AREA MPO | P-5721 | STATEWIDE MOBILITY | O, T |  |  |  |  | 2024 | 4070000 |  |  | 4070000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION
GUILFORD | NORFOLK SOUTHERN H LINE | CONSTRUCT GRADE SEPARATION AT FRANKLIN BOULEVARD CROSSING (722959A) IN GREENSBORO, AND CLOSE O'FERRELL STREET CROSSING (722961B). | RAIL | 7 | GREENSBORO URBAN AREA MPO | P-5709 | REGION D | O, T | 2022 | 3484000 | 2022 | 1566000 | 2024 | 17400000 |  |  | 22450000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION
GUILFORD | NORFOLK SOUTHERN MAIN LINE | SR 1584 (YANCEYVILLE STREET) IN GREENSBORO. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722542D. | RAIL | 7 | GREENSBORO URBAN AREA MPO | P-5735 | STATEWIDE MOBILITY | O, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3500000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 12700000 |  |  | 16200000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN RAILROAD
GUILFORD | NORFOLK SOUTHERN MAINLINE | NORFOLK SOUTHERN "ROUNDHOUSE" PROPERTY. CONSTRUCT PARKING LOT WITH SPACE FOR INTERNATIONAL CONTAINERS, INCLUDING SECURITY FENCE, POLE-MOUNTED LIGHTING, AND PAVED ENTRANCE. | RAIL | 7 | GREENSBORO URBAN AREA MPO | P-5700 | DIVISION 7 | O, T |  |  |  |  | 2023 | 1700000 |  |  | 1700000 | "OTHER" FUNDS REFLECT NORFOLK SOUTHERN CORPORATION PARTICIPATION
GUILFORD | NORTH CAROLINA RAILROAD (NCRR) / NORFOLK SOUTHERN | SR 1424 (HILLTOP ROAD) IN GREENSBORO. CONVERT AT-GRADE CROSSING TO GRADE SEPARATION. | RAIL | 7 | GREENSBORO URBAN AREA MPO | P-5713 | STATEWIDE MOBILITY | O, T | 2024 | 3431000 | 2024 | 952000 | 2026 | 8901000 |  |  | 13284000 | "O" FUNDING REFLECTS NORFOLK SOUTHERN RAILROAD PARTICIPATION
GUILFORD | SR 2531 (HILLCROFT ROAD) | NORFOLK SOUTHERN RAILROAD CROSSING 722545Y NEAR GREENSBORO. INSTALL ACTIVE WARNING DEVICES. | RAIL | 7 | GREENSBORO URBAN AREA MPO | RX-2007C | DIVISION 7 | RR |  |  |  |  | 2023 | 800000 |  |  | 800000
GUILFORD | SR 2748 (SPRINGWOOD AVENUE) | NORFOLK SOUTHERN RAILROAD CROSSING 722990L IN GIBSONVILLE. INSTALL ACTIVE WARNING DEVICES. | RAIL | 7 | BURLINGTON-GRAHAM MPO | RX-2007A | DIVISION 7 | RR |  |  |  |  | 2023 | 800000 |  |  | 800000
GUILFORD, ALAMANCE | I-40 / I-85 | EAST OF SR 3056 (ROCK CREEK DAIRY ROAD) IN GUILFORD COUNTY TO WEST OF SR 1226 (UNIVERSITY DRIVE) IN ALAMANCE COUNTY. PAVEMENT REHABILITATION. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO, GREENSBORO URBAN AREA MPO | I-5956 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
GUILFORD, ALAMANCE, FORSYTH | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | SAFETY & SECURITY - MIN. 1% SET ASIDE | PUBLIC TRANSIT | 7, 9 | WINSTON-SALEM URBAN AREA MPO | TS-5115 | PUBLIC TRANSIT | 5307 | [6 empty] | 2020 | 8000 | 8000 | FUNDS AUTHORIZED IN PROGRESS
GUILFORD, DAVIDSON, RANDOLPH | SYSTEM / HI-TRAN HIGH POINT TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC ($40K CAPITAL COST OF CONTRACTING) | PUBLIC TRANSIT | 7, 8, 9 | HIGH POINT URBAN AREA MPO | TG-4814 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 916000 | 916000 | FUNDS AUTHORIZED IN PROGRESS
GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | PIEDMONT CORRIDOR | TRAIN 74 / 75 OPERATIONS BETWEEN CHARLOTTE AND RALEIGH, EQUIPMENT AND CAPITAL YARD MAINTENANCE FACILITY. | RAIL | 5, 7, 8, 9, 10 | CABARRUS-ROWAN MPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, BURLINGTON-GRAHAM MPO, GREENSBORO URBAN AREA MPO, CAPITAL AREA MPO, CHARLOTTE REGIONAL TPO | P-2918 | EXEMPT | CMAQ, S | [6 empty] | 2021 | 17586000 | 17586000 | "S" FUNDING REFLECTS STATE RAIL FUNDS
GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | PIEDMONT CORRIDOR | EQUIPMENT REBUILD - 2 F59PHI LOCOMOTIVES | RAIL | 5, 7, 8, 9, 10 | CABARRUS-ROWAN MPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, BURLINGTON-GRAHAM MPO, GREENSBORO URBAN AREA MPO, CAPITAL AREA MPO, CHARLOTTE REGIONAL TPO | P-2918A | [11 empty] | IN PROGRESS
GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | PIEDMONT CORRIDOR | PURCHASE 2 USED LOCOMOTIVES | RAIL | 5, 7, 8, 9, 10 | CABARRUS-ROWAN MPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, BURLINGTON-GRAHAM MPO, GREENSBORO URBAN AREA MPO, CAPITAL AREA MPO, CHARLOTTE REGIONAL TPO | P-2918B | [11 empty] | COMPLETE
GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | PIEDMONT CORRIDOR | EQUIPMENT REHABILITATION - 3 LOCOMOTIVES | RAIL | 5, 7, 8, 9, 10 | CABARRUS-ROWAN MPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, BURLINGTON-GRAHAM MPO, GREENSBORO URBAN AREA MPO, CAPITAL AREA MPO, CHARLOTTE REGIONAL TPO | P-2918C | [11 empty] | IN PROGRESS
GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | PIEDMONT CORRIDOR | EQUIPMENT REHABILITATION - 3 PASSENGER CARS | RAIL | 5, 7, 8, 9, 10 | CABARRUS-ROWAN MPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, BURLINGTON-GRAHAM MPO, GREENSBORO URBAN AREA MPO, CAPITAL AREA MPO, CHARLOTTE REGIONAL TPO | P-2918D | [11 empty] | COMPLETE
GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | PIEDMONT CORRIDOR | PASSENGER TRAIN SECURITY SYSTEM, CCTV DATA NETWORK AND GENERATORS | RAIL | 5, 7, 8, 9, 10 | CABARRUS-ROWAN MPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, BURLINGTON-GRAHAM MPO, GREENSBORO URBAN AREA MPO, CAPITAL AREA MPO, CHARLOTTE REGIONAL TPO | P-2918E | [11 empty] | IN PROGRESS
GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | PIEDMONT CORRIDOR | PURCHASE 4 USED PASSENGER CARS AND REHABILITATE 7 PASSENGER CARS | RAIL | 5, 7, 8, 9, 10 | CABARRUS-ROWAN MPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, BURLINGTON-GRAHAM MPO, GREENSBORO URBAN AREA MPO, CAPITAL AREA MPO, CHARLOTTE REGIONAL TPO | P-2918G | [11 empty] | IN PROGRESS
GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | PIEDMONT CORRIDOR | EQUIP 9 STATIONS AND PLATFORMS WITH ADA/FRA PIDS | RAIL | 5, 7, 8, 9, 10 | CABARRUS-ROWAN MPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, BURLINGTON-GRAHAM MPO, GREENSBORO URBAN AREA MPO, CAPITAL AREA MPO, CHARLOTTE REGIONAL TPO | P-2918I | [11 empty] | IN PROGRESS
GUILFORD, DAVIDSON, ROWAN, ALAMANCE, CABARRUS, ORANGE, WAKE, DURHAM, MECKLENBURG, RANDOLPH | PIEDMONT CORRIDOR | PURCHASE AND REFURBISH RAIL CARS FOR PIEDMONT SERVICE EXPANSION. | RAIL | 5, 7, 8, 9, 10 | CABARRUS-ROWAN MPO, HIGH POINT URBAN AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, BURLINGTON-GRAHAM MPO, GREENSBORO URBAN AREA MPO, CAPITAL AREA MPO, CHARLOTTE REGIONAL TPO | P-5719 | [11 empty] | "DP" FUNDING REFLECTS FEDERAL-STATE PARTNERSHIP FOR STATE OF GOOD REPAIR GRANT
GUILFORD, FORSYTH | I-40 | NC 66 TO US 421 / BUSINESS 40. | HIGHWAY | 7, 9 | HIGH POINT URBAN AREA MPO, WINSTON-SALEM URBAN AREA MPO | I-5981C | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 38798000 |  |  | 39198000
GUILFORD, FORSYTH | PIEDMONT AUTHORITY FOR REGIONAL TRANS. | OPERATING ASSISTANCE | PUBLIC TRANSIT | 7, 9 | HIGH POINT URBAN AREA MPO | TO-5134C | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 6000000 | 6000000
GUILFORD, FORSYTH, CASWELL, DAVIDSON, MONTGOMERY, RANDOLPH, ROCKINGHAM | VARIOUS | PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION (PART). IMPLEMENT A REGIONAL AIR QUALITY AWARENESS PROGRAM. | HIGHWAY | 7, 8, 9 | GREENSBORO URBAN AREA MPO, NORTHWEST PIEDMONT RPO, WINSTON-SALEM URBAN AREA MPO | C-4936 | EXEMPT | [10 empty] | IN PROGRESS BY PIEDMONT AUTHORITY FOR REGIONAL TRANSPORTATION
GUILFORD, ORANGE | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE BURLINGTON-GRAHAM MPO. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | C-5602 | EXEMPT | CMAQ, L | 2020 | 18000 |  |  | 2020 | 99000 | 2020 | 54000 | 171000
GUILFORD, ROCKINGHAM | FUTURE I-73 | NC 68 AT SR 2011 (EDGEFIELD ROAD) IN GUILFORD COUNTY TO US 220-NC 68 INTERSECTION IN ROCKINGHAM COUNTY. FOUR-LANE FREEWAY, ON NEW LOCATION, NC 68 TO US 220 AND FOUR LANES ALONG US 220 TO NC 68 IN ROCKINGHAM COUNTY. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO, PIEDMONT TRIAD RPO | R-2413 | PRE-STI (TRANSITION)
GUILFORD, WAKE, MECKLENBURG | PIEDMONT CORRIDOR | ACQUIRE AND REBUILD 2 ADDITIONAL LOCOMOTIVES. | RAIL | 5, 7, 10 | GREENSBORO URBAN AREA MPO, CAPITAL AREA MPO, CHARLOTTE REGIONAL TPO | P-5719A | EXEMPT | [10 empty] | COMPLETE
GUILFORD, WAKE, MECKLENBURG | PIEDMONT CORRIDOR | ACQUIRE AND REFURBISH 2 COACH AND 1 LOUNGE/BAGGAGE RAIL CARS. | RAIL | 5, 7, 10 | GREENSBORO URBAN AREA MPO, CAPITAL AREA MPO, CHARLOTTE REGIONAL TPO | P-5719B | EXEMPT | [10 empty] | IN PROGRESS
HALIFAX | (IXA) HALIFAX NORTHAMPTON REGIONAL AIRPORT | CONSTRUCT TAXI LANE AND PREPARATION FOR ADDITIONAL T-HANGARS. | AVIATION | 4 | PEANUT BELT RPO | AV-5822 | DIVISION 4 | T |  |  |  |  | 2024 | 744000 |  |  | 744000
HALIFAX | HALIFAX NORTHAMPTON REGIONAL AIRPORT (IXA) | CONSTRUCT TAXILANE AND APRON. | AVIATION | 4 | PEANUT BELT RPO | AV-5833 | DIVISION 4 | T |  |  |  |  | 2026 | 715000 |  |  | 715000
HALIFAX | EAST 10TH STREET | MARSHALL STREET TO PARKE AVENUE IN ROANOKE RAPIDS. CONSTRUCT SIDEWALK ON BOTH SIDES OF ROAD. | BIKE/PED | 4 | PEANUT BELT RPO | EB-5843 | DIVISION 4 | L, TA5200 |  |  |  |  | 2025 | 200000 |  |  | 200000
HALIFAX | I-95 | NC 481 (MILE MARKER 154) TO MILE MARKER 167. PAVEMENT REHABILITATION. | HIGHWAY | 4 | PEANUT BELT RPO | I-5932
HALIFAX | I-95 | NC 561 (MILE MARKER 160) TO MILE MARKER 167. | HIGHWAY | 4 | PEANUT BELT RPO | I-5932A | STATEWIDE MOBILITY | BGLT5 |  |  |  |  | 2021 | 7376000 |  |  | 7376000
HALIFAX | I-95 | NC 481 (MILE MARKER 154) TO NC 561 (MILE MARKER 160) | HIGHWAY | 4 | PEANUT BELT RPO | I-5932B | STATEWIDE MOBILITY | BGLT5 |  |  |  |  | 2021 | 7086000 |  |  | 7086000
HALIFAX | NC 125 | I-95 TO SR 1745 (OLD FARM ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 4 | PEANUT BELT RPO | U-5725 | DIVISION 4 | T |  |  |  |  | 2019 | 27240000 | 2021 | 2130000 | 29370000 | CONSTRUCTION IN PROGRESS - COMBINED FOR LETTING WITH R-3822. BUILD NC BOND FUNDING: $1,652,087 FOR PE, $11,562,760 FOR CON, PAYBACK 2021 - 2035 (FY 2021 / SALE YEARS 2&3)
HALIFAX | NC 48 | INSTALL ALL WAY STOP AND REVISE EXISTING OVERHEAD AND SHOULDER-MOUNTED FLASHERS AT NC 48 AND NC 903. | HIGHWAY | 4 | PEANUT BELT RPO | HS-2004G | REGION A | HSIP |  |  |  |  | 2022 | 50000 |  |  | 50000 | LETTING COMBINED WITH HS-2004F AND HS-2004H.
HALIFAX | NC 561 | BRIDGE 93 OVER CONOCONNARA SWAMP ON NC 561. | HIGHWAY | 4 | PEANUT BELT RPO | B-5662 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 2581000 |  |  | 2581000 | RIGHT OF WAY IN PROGRESS.
HALIFAX | NEW ROUTE | NC 125 TO SOUTH OF US 158. CONSTRUCT THREE LANE FACILITY ON NEW LOCATION. | HIGHWAY | 4 | PEANUT BELT RPO | R-3822 | DIVISION 4 | [10 empty] | UNDER CONSTRUCTION - COMBINED FOR LETTING WITH U-5725. CONSTRUCTION FUNDS SHOWN UNDER U-5725.
HALIFAX | SR 1100 (BELLS BRIDGE ROAD) | REPLACE BRIDGE 410065 AND 410066 OVER DEEP CREEK. | HIGHWAY | 4 | PEANUT BELT RPO | B-5660 | DIVISION 4 | [10 empty] | UNDER CONSTRUCTION
HALIFAX | SR 1309 (SPRUILLS BRIDGE ROAD) | REPLACE BRIDGE 410138 OVER LITTLE FISHING CREEK. | HIGHWAY | 4 | PEANUT BELT RPO | B-5665 | HIGHWAY FUND | [10 empty] | UNDER CONSTRUCTION - DIVISION PURCHASE ORDER CONTRACT
HALIFAX | SR 1601 (SLEDGE ROAD) | REPLACE BRIDGE 410115 OVER ROCKY SWAMP ON SR 1601 (SLEDGE ROAD). | HIGHWAY | 4 | PEANUT BELT RPO | BR-0113 | DIVISION 4 | DP, HFB | 2020 | 130000 |  |  | 2021 | 796000 |  |  | 926000 | UNDER CONSTRUCTION. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING
HALIFAX | SR 1710 (GRACE DRIVE/ WATKINS DRIVE) AND SR 1737 | FROM US-158 TO NORTH OF SR 1734 (KENNAMETAL DRIVE). WIDEN ROADWAY. REALIGN SR 1737 (POWER PLACE) AND US-158 INTERSECTION. | HIGHWAY | 4 | PEANUT BELT RPO | HE-0003 | DIVISION 4 | T |  |  |  |  | 2022 | 1500000 |  |  | 1500000 | ECONOMIC DEVELOPMENT PROJECT. UNDER CONSTRUCTION.
HALIFAX | VARIOUS | CAROLINIAN CORRIDOR - CSXT MP A 101.0 (ENFIELD CROSSING). | RAIL | 4 | PEANUT BELT RPO | P-5005A | PRE-STI (TRANSITION)
HALIFAX | VARIOUS | CAROLINIAN CORRIDOR - CSXT MP A 86.4 (SOUTH WELDON CROSSING). | RAIL | 4 | PEANUT BELT RPO | P-5005C | PRE-STI (TRANSITION)
HALIFAX, JOHNSTON | VARIOUS | INSTALL LONG LIFE PAVEMENT MARKINGS. | HIGHWAY | 4 | PEANUT BELT RPO, UPPER COASTAL PLAIN RPO | HS-2004J | DIVISION 4 | HSIP |  |  |  |  | 2022 | 2053000 |  |  | 2053000 | UNDER CONSTRUCTION.
HALIFAX, NORTHAMPTON | CSX A LINE | CONSTRUCT NEW MAIN TRACK BETWEEN MP A-80.7 AND MP A-82.4 INCLUDING REHABILITATION OF CSX SA-LINE BRIDGE OVER ROANOKE RIVER. NEW CONNECTION BETWEEN A-LINE AND SA-LINE AT MP A-80.7. RECONSTRUCT MAIN TRACK BETWEEN MP A-82.4 AND MP A-84.7. CREATE SECOND MAIN. | RAIL | 1, 4 | PEANUT BELT RPO | P-5741 | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5000000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 62000000 |  |  | 67000000
HALIFAX, WAKE, NASH, EDGECOMBE | CSXT RR | CONGESTION MITIGATION CROSSOVERS. | RAIL | 4, 5 | PEANUT BELT RPO, CAPITAL AREA MPO, ROCKY MOUNT URBAN AREA MPO | P-5005 | [11 empty] | IN PROGRESS
HARNETT | CAMPBELL UNIVERSITY SIDEWALK | WADE STEWART CIRCLE TO PEARSON ROAD IN BUIES CREEK. CONSTRUCT SIDEWALK. | BIKE/PED | 6 | MID-CAROLINA RPO | EB-6014 | DIVISION 6 | L, TALT5 | 2021 | 35000 |  |  | 2021 | 565000 |  |  | 600000
HARNETT | SR 1501 (JUNNY ROAD); NORTH WILLOW STREET; WEST LI | NORTH WILLOW STREET, EAST JULIA STREET TO JUNNY ROAD; JUNNY ROAD, EAST JULIA STREET TO GLEN MEADOW DRIVE; AND WEST LILLINGTON STREET, SOUTH PARK STREET TO NC 210, IN ANGIER. CONSTRUCT SIDEWALK EXTENSIONS. | BIKE/PED | 6 | CAPITAL AREA MPO | EB-6020 | DIVISION 6 | BGDA, L | 2023 | 150000 |  |  | 2023 | 1457000 | 2021 | 175000 | 1782000
HARNETT | CHURCH ROAD) SR 1214 (MOUNT PISGAH | REPLACE BRIDGE 420034 OVER UPPER LITTLE RIVER. | HIGHWAY | 6 | MID-CAROLINA RPO | HB-0008 | DIVISION 6 | BGOFF | 2023 | 330000 |  |  | 2024 | 3300000 |  |  | 3630000
HARNETT | I-95 | CUMBERLAND COUNTY LINE TO THE JOHNSTON COUNTY LINE. PAVEMENT REPAIR. | HIGHWAY | 6 | MID-CAROLINA RPO | I-4906 | PRE-STI (TRANSITION) | [10 empty] | COMPLETE - GARVEE BOND FUNDING $3.15 MILLION; PAYBACK FY 2008 - FY 2019
HARNETT | I-95 | SR 1811 (BUD HAWKINS ROAD) (EXIT 70) AND SR 1001 (LONG BRANCH ROAD) (EXIT 71). IMPROVE INTERCHANGES. | HIGHWAY | 6 | MID-CAROLINA RPO | I-5877 | STATEWIDE MOBILITY | T |  |  |  |  | 2020 | 69733000 |  |  | 69733000 | DESIGN BUILD. LETTING TO BE COMBINED WITH I-5986A. UNDER CONSTRUCTION.
HARNETT | I-95 | US 421 (EXIT 73) AND SR 1793 (POPE ROAD) (EXIT 72). IMPROVE INTERCHANGES. | HIGHWAY | 6 | MID-CAROLINA RPO | I-5878 | STATEWIDE MOBILITY | T |  |  |  |  | 2022 | 78316000 |  |  | 78316000 | LETTING TO BE COMBINED WITH I-5986B AND I-5883. UNDER CONSTRUCTION.
HARNETT | I-95 | US 421 (EXIT 73) AND SR 1793 (POPE ROAD) (EXIT 72). CLEARING FOR UTILITIES. | HIGHWAY | 6 | MID-CAROLINA RPO | I-5878A | STATEWIDE MOBILITY | T |  |  |  |  | 2020 | 139000 |  |  | 139000 | COMPLETE.
HARNETT | I-95 | SR 1808 (JONESBORO ROAD) (EXIT 75) AND SR 1709 (HODGES CHAPEL ROAD) (EXIT 77). IMPROVE INTERCHANGES. | HIGHWAY | 6 | MID-CAROLINA RPO | I-5883 | STATEWIDE MOBILITY | T |  |  |  |  | 2022 | 101701000 |  |  | 101701000 | LETTING TO BE COMBINED WITH I-5986B AND I-5878. UNDER CONSTRUCTION.
HARNETT | NC 27 | NC 24/27 FROM THE MOORE COUNTY LINE AND THE NC 24/27 SPLIT, NC 27 FROM NC 24 TO LILLINGTON, NC 27 FROM US 421 TO COATS, AND NC 27 FROM COATS TO THE JOHNSTON COUNTY LINE. INSTALL RUMBLE STRIPES, RUMBLE STRIPS, AND LONG-LIFE PAVEMENT MARKINGS. | HIGHWAY | 6 | MID-CAROLINA RPO | HS-2006H | DIVISION 6 | HSIP |  |  |  |  | 2023 | 1065000 |  |  | 1065000
HARNETT | NC 27, SR 1581 | NC 27 AT SR 1581 (BAILEY'S CROSSROADS) / SR 1705 (FAIRGROUND). REALIGNMENT / INTERSECTION IMPROVEMENTS. | HIGHWAY | 6 | MID-CAROLINA RPO | W-5806D | REGION C | HSIP | 2021 | 100000 |  |  | 2022 | 667000 |  |  | 767000 | RIGHT-OF-WAY IN PROGRESS.
HARNETT | NC 55 | JUST SOUTH OF SR 1532 (OAK GROVE CHURCH ROAD) TO NC 210. PART ON NEW LOCATION. | HIGHWAY | 6 | CAPITAL AREA MPO | R-5705A | DIVISION 6 | T | 2021 | 11834000 | 2021 | 2000000 | 2023 | 45300000 |  |  | 59134000 | RIGHT-OF-WAY IN PROGRESS.
HARNETT | NC 55 | NC 27 IN COATS TO SR 1006 (OLD STAGE ROAD (NORTH)). WIDEN ROADWAY. | HIGHWAY | 6 | MID-CAROLINA RPO | R-5953 | NOT FUNDED | T | NOT FUNDED | 12476000 | NOT FUNDED | 869000 | NOT FUNDED | 62300000 |  |  | 75645000
HARNETT | NC 87/24 | SR 1117 (NURSERY ROAD). INTERSECTION IMPROVEMENTS. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-5933 | STATEWIDE MOBILITY | T | 2023 | 16000 | 2023 | 22000 | 2025 | 3000000 |  |  | 3038000
HARNETT | SR 1117, SR 3242, SR 1615 | SR 1117 (NURSERY ROAD) FROM NC 27 TO SR 3242 (OVERHILLS ROAD). SR 3242 (OVERHILLS ROAD) FROM NC 24/87 TO SR 1117 (NURSERY ROAD). SR 1121 (RAY ROAD) FROM SR 1117 (NURSERY ROAD) TO SR 3242 (OVERHILLS ROAD). WIDEN CURVES AND INSTALL RUMBLE STRIPS. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO, MID-CAROLINA RPO | W-5806B | DIVISION 6 | HSIP |  |  |  |  | 2022 | 468000 |  |  | 468000
HARNETT | SR 1121 (RAY ROAD) | NC 210 TO SR 1120 (OVERHILLS ROAD). WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-3465 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
HARNETT | SR 1210 (HOOVER ROAD) | REPLACE BRIDGE 420234 OVER BARBEQUE SWAMP. | HIGHWAY | 6 | MID-CAROLINA RPO | B-6005 | DIVISION 6 | [10 empty] | UNDER CONSTRUCTION
HARNETT | SR 1234 (LEAFLET CHURCH ROAD) | REPLACE BRIDGE 420195 OVER BRANCH OF UPPER LITTLE RIVER. | HIGHWAY | 6 | CAPITAL AREA MPO | B-5414 | DIVISION 6 | [10 empty] | UNDER CONSTRUCTION
HARNETT | US 401 (NORTH MAIN STREET) | PARKER LANE TO MCKINNEY PARKWAY. CONSTRUCT MEDIAN. | HIGHWAY | 6 | MID-CAROLINA RPO | R-5890 | REGION C | T | 2028 | 100000 | 2028 | 200000 | 2030 | 4500000 |  |  | 4800000
HARNETT | HARNETT COUNTY | ADMINISTRATION | PUBLIC TRANSIT | 6 | MID-CAROLINA RPO | TK-6133 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 880000 | 880000 | FUNDS AUTHORIZED IN PROGRESS
HARNETT, BLADEN, CUMBERLAND, COLUMBUS | VARIOUS | INSTALL LONG LIFE PAVEMENT MARKINGS AT VARIOUS LOCATIONS. | HIGHWAY | 6 | MID-CAROLINA RPO, FAYETTEVILLE AREA MPO, CAPE FEAR RPO | HS-2006E | DIVISION 6 | HSIP |  |  |  |  | 2022 | 4023000 |  |  | 4023000 | UNDER CONSTRUCTION.
HARNETT, JOHNSTON | I-95 | SR 1002 (LONG BRANCH ROAD - EXIT 71) TO I-40 (EXIT 81). WIDEN TO EIGHT LANES. | HIGHWAY | 4, 6 | MID-CAROLINA RPO, UPPER COASTAL PLAIN RPO | I-5986B | STATEWIDE MOBILITY | T | 2020 | 42100000 | 2020 | 700000 | 2022 | 91912000 |  |  | 134712000 | LETTING TO BE COMBINED WITH I-5878 AND I-5883.
HARNETT, JOHNSTON | I-95 | SR 1001 (LONG BRANCH ROAD - EXIT 71) TO I-40 (EXIT 81). CLEARING FOR UTILITIES. | HIGHWAY | 4, 6 | MID-CAROLINA RPO, UPPER COASTAL PLAIN RPO | I-5986BA | STATEWIDE MOBILITY | T |  |  |  |  | 2020 | 144000 |  |  | 144000
HARNETT, WAKE | NC 55 | JUST SOUTH OF SR 1532 (OAK GROVE CHURCH ROAD) TO NC 42 IN FUQUAY-VARINA. WIDEN TO MULTI-LANES. PART ON NEW LOCATION. | HIGHWAY | 5, 6 | CAPITAL AREA MPO | R-5705
HAYWOOD | HAZELWOOD AVENUE (PLOTT CREEK ROAD) | HAZELWOOD AVENUE (PLOTT CREEK ROAD), RICHLAND CREEK BRIDGE TO WILL HYATT ROAD. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | BIKE/PED | 14 | FRENCH BROAD RIVER MPO | EB-5859 | DIVISION 14 | [10 empty] | UNDER CONSTRUCTION
HAYWOOD | TOWN OF CANTON | CHAMPION DRIVE, NORTH CANTON ROAD TO THICKETY ROAD. CONSTRUCT MULTI-USE PATH. | BIKE/PED | 14 | FRENCH BROAD RIVER MPO | EB-5945 | DIVISION 14 | BGDA, L | 2022 | 200000 | [6 empty] | 200000
HAYWOOD | US 19 (SOCO ROAD) | US 276 TO FIE TOP ROAD. CONSTRUCT BICYCLE AND PEDESTRIAN IMPROVEMENTS. | BIKE/PED | 14 | FRENCH BROAD RIVER MPO | EB-5926 | DIVISION 14 | BGANY, L |  |  |  |  | 2022 | 1800000 |  |  | 1800000 | $1.44M IN BGANY USED AS PART OF FUND SWAP
HAYWOOD | CANTON | NC 110 (PISGAH DRIVE) AT LOCUST STREET. IMPROVE INTERSECTION. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-6055 | EXEMPT | [10 empty] | UNDER CONSTRUCTION. STBGDA FUNDS ARE EXEMPT BECAUSE THEY ARE BEING USED ON REGIONAL CATEGORY PROJECT - STATE IS PAYING MATCH BECAUSE PROJECT CAME IN RANK ORDER OFF P3.0 PRIORITIZATION LIST
HAYWOOD | GREAT SMOKY MOUNTAINS NATIONAL PARK | REGIONAL OUTREACH AND EDUCATIONAL PROGRAM. | HIGHWAY | 14 | LAND-OF-SKY RPO | HO-0003 | EXEMPT | CMAQ, L | [6 empty] | 2022 | 250000 | 250000
HAYWOOD | I-40 | REPLACE BRIDGE 430236 OVER SR 1513. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | B-5541 | HIGHWAY FUND | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY
HAYWOOD | I-40 | REPLACE BRIDGES (430057, 430159, 430171, 430124, AND 430142) ON I-40 IN HAYWOOD COUNTY. | HIGHWAY | 14 | LAND-OF-SKY RPO | B-6054 | STATEWIDE MOBILITY
HAYWOOD | I-40 | REPLACE BRIDGE 430057 OVER US FOREST SERVICE ROAD/COLD SPRINGS CREEK AT HARMON'S DEN. | HIGHWAY | 14 | LAND-OF-SKY RPO | B-6054A | STATEWIDE MOBILITY | T |  |  |  |  | 2022 | 21788000 | 2020 | 500000 | 22288000
HAYWOOD | I-40 | REPLACE BRIDGE 430159 OVER SR 1338 (WHITE OAK ROAD). | HIGHWAY | 14 | LAND-OF-SKY RPO | B-6054B | STATEWIDE MOBILITY | T |  |  | 2022 | 5000 | 2023 | 5000000 | 2020 | 500000 | 5505000
HAYWOOD | I-40 | REPLACE BRIDGE 430171 OVER SR 1338 (WHITE OAK ROAD) AND JONATHAN CREEK. | HIGHWAY | 14 | LAND-OF-SKY RPO | B-6054C | STATEWIDE MOBILITY | T | 2022 | 5000 | 2022 | 5000 | 2022 | 41727000 | 2020 | 2500000 | 44237000
HAYWOOD | I-40 | REPLACE BRIDGE 430124 OVER SR 1338 (WHITE OAK ROAD) AND FINES CREEK. | HIGHWAY | 14 | LAND-OF-SKY RPO | B-6054D | STATEWIDE MOBILITY | T | 2022 | 5000 | 2022 | 5000 | 2024 | 5000000 | 2021 | 500000 | 5510000
HAYWOOD | I-40 | REPLACE BRIDGE 430142 OVER PIGEON RIVER. | HIGHWAY | 14 | LAND-OF-SKY RPO | B-6054E | STATEWIDE MOBILITY | T | 2022 | 5000 | 2022 | 5000 | 2024 | 20001000 | 2021 | 2000000 | 22011000
HAYWOOD | I-40 | REPLACE BRIDGES 430248 AND 430249 OVER SR 1613 (BEAVERDAM ROAD). | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | HB-0002 | STATEWIDE MOBILITY | BFP | 2023 | 2000000 |  |  | 2023 | 7800000 |  |  | 9800000
HAYWOOD | I-40 | REPLACE BRIDGE 430239 OVER SR 1550 (INCINERATOR ROAD). | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | HB-0003 | STATEWIDE MOBILITY | BFP | 2023 | 1000000 |  |  | 2024 | 7100000 |  |  | 8100000
HAYWOOD | I-40 | REPLACE BRIDGE 430243 OVER NC 215 (CHAMPION DRIVE). | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | HB-0004 | STATEWIDE MOBILITY | BFP | 2023 | 1000000 |  |  | 2023 | 7300000 |  |  | 8300000
HAYWOOD | I-40 | REPLACE BRIDGES 430205 AND 430208 OVER SR 1364 (COLEMAN MOUNTAIN ROAD). | HIGHWAY | 14 | LAND-OF-SKY RPO | HB-0005 | STATEWIDE MOBILITY | BFP | 2024 | 2000000 |  |  | 2027 | 9400000 |  |  | 11400000
HAYWOOD | I-40 | MILE MARKER 27 TO MILE MARKER 34. PAVEMENT REHABILITATION. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO, LAND-OF-SKY RPO | I-5834 | [11 empty] | 6-13-2022: $2.566M IN NHPIM FUNDS SWITCHED WITH $2.566M IN BGDA AS PART OF FUND SWAP.
HAYWOOD | I-40 | MILE MARKER 27 TO MILE MARKER 30. PAVEMENT REHABILITATION. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO, LAND-OF-SKY RPO | I-5834A | STATEWIDE MOBILITY | BGDA, NHPIM |  |  |  |  | 2021 | 7300000 |  |  | 7300000
HAYWOOD | I-40 | MILE MARKER 30 TO MILE MARKER 34. PAVEMENT REHABILITATION. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | I-5834B | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2022 | 13475000 |  |  | 13475000
HAYWOOD | I-40 | MILE MARKER 15 TO MILE MARKER 20.5. PAVEMENT REHABILITATION. | HIGHWAY | 14 | LAND-OF-SKY RPO | I-5924 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2026 | 14500000 |  |  | 14500000
HAYWOOD | I-40 | MILE MARKER 34 TO BUNCOMBE COUNTY LINE. PAVEMENT REHABILITATION. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | I-5928 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2027 | 8750000 |  |  | 8750000
HAYWOOD | I-40 | US 74 (SMOKY MOUNTAIN EXPRESSWAY) TO NC 215 (CHAMPION DRIVE). ADD ADDITIONAL LANES. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | I-6054A | NOT FUNDED | NHP | NOT FUNDED | 2700000 | NOT FUNDED | 500000 | NOT FUNDED | 57300000 |  |  | 60500000
HAYWOOD | SR 1216 (STEEL BRIDGE ROAD) | REPLACE BRIDGE 430246 OVER WEST FORK PIGEON CREEK. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | B-5920 | DIVISION 14 | BGOFF | 2023 | 30000 |  |  | 2024 | 640000 |  |  | 670000
HAYWOOD | SR 1355 (PANTHER CREEK ROAD) | REPLACE BRIDGE 430206 OVER FINES CREEK. | HIGHWAY | 14 | LAND-OF-SKY RPO | HB-0027 | DIVISION 14 | BGOFF | 2024 | 50000 | 2024 | 50000 | 2025 | 1000000 |  |  | 1100000
HAYWOOD | SR 1876 (MAX THOMPSON ROAD) | REPLACE BRIDGE 430170 OVER EAST FORK PIGEON RIVER. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | HB-0024 | DIVISION 14 | BGOFF | 2024 | 80000 | 2024 | 80000 | 2025 | 1600000 |  |  | 1760000
HAYWOOD | SR 1876 (SONOMA ROAD) | REPLACE BRIDGE 430169 OVER WEST FORK PIGEON RIVER. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | HB-0023 | DIVISION 14 | BGOFF | 2023 | 80000 | 2023 | 80000 | 2024 | 1600000 |  |  | 1760000
HAYWOOD | US 19 (SOCO ROAD) | SR 1304 (FIE TOP ROAD AT GHOST TOWN IN THE SKY) TO BLUE RIDGE PARKWAY. MODERNIZE ROADWAY. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-6160 | NOT FUNDED | BGLT5 | NOT FUNDED | 14700000 | NOT FUNDED | 400000 | NOT FUNDED | 20201000 |  |  | 35301000
HAYWOOD | US 19/23/74 | REPLACE BRIDGE 430133 OVER JONES COVE ROAD (SR 1527). | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | HB-0015 | HIGHWAY FUND | [10 empty] | PROGRAMMED FOR PRELIMINARY ENGINEERING ONLY
HAYWOOD | US 23 BUSINESS | INTERSECTION OF US 23 BUSINESS (NORTH MAIN STREET) AND WALNUT STREET. CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-5888 | DIVISION 14 | T |  |  |  |  | 2022 | 6800000 |  |  | 6800000 | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH U-5839.
HAYWOOD | US 23 BUSINESS (SOUTH MAIN STREET) | SR 1164 (HYATT CREEK ROAD) TO US 276 (PIGEON STREET). WIDEN TO MULTI-LANES. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-4712 | DIVISION 14 | T | 2027 | 25200000 | 2027 | 3800000 | 2030 | 20000000 |  |  | 49000000
HAYWOOD | US 23/ US 74 | REPLACE BRIDGE 430168 OVER US 19 AND US 23. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | B-5898 | STATEWIDE MOBILITY | NHPB | 2021 | 150000 |  |  | 2024 | 3100000 |  |  | 3250000 | TO BE LET WITH B-3186.
HAYWOOD | US 23/US 74 | REPLACE BRIDGE 430155, AND BRIDGE 430158 OVER RICHLAND CREEK. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | B-3186 | STATEWIDE MOBILITY | NHPB | 2021 | 800000 |  |  | 2024 | 6100000 |  |  | 6900000 | TO BE LET WITH B-5898.
HAYWOOD | US 276 | SR 1134 (CRYMES COVE ROAD) AND RACCOON ROAD. INTERSECTION REALIGNMENT. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-6158 | DIVISION 14 | T | 2028 | 500000 | 2028 | 200000 | 2030 | 3100000 |  |  | 3800000
HAYWOOD | US 276 | CONSTRUCT LEFT TURN LANE 0.3 MILES SOUTH OF SR 1326 (BOB BOYD ROAD). | HIGHWAY | 14 | LAND-OF-SKY RPO | W-5814A | REGION G | HSIP |  |  |  |  | 2022 | 200000 |  |  | 200000
HAYWOOD | US 276 (JONATHAN CREEK) | US 19 TO I-40 UPGRADE. MODERNIZE ROADWAY. | HIGHWAY | 14 | LAND-OF-SKY RPO, FRENCH BROAD RIVER MPO | R-5921 | DIVISION 14 | BGLT5 | 2023 | 600000 | 2023 | 3200000 | 2024 | 32600000 |  |  | 36400000
HAYWOOD | US 276 (RUSS AVENUE) | US 23/74 TO US 23 BUSINESS (MAIN STREET). UPGRADE CORRIDOR. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-5839 | DIVISION 14 | T | 2019 | 6830000 | 2020 | 750000 | 2023 | 21700000 | 2020 | 3330000 | 32610000 | BUILD NC BOND FUNDING: $2.585M FOR PRELIMINARY ENGINEERING, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $2.160M FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE). TO BE LET WITH U-5888.
HAYWOOD | US 276 (RUSS AVENUE) | US 23-74 (GREAT SMOKEY MOUNTAIN EXPRESSWAY) TO US 19 (DELLWOOD ROAD). ACCESS MANAGEMENT. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-6159 | DIVISION 14 | BGANY | 2028 | 14500000 | 2028 | 2300000 | 2030 | 13401000 |  |  | 30201000
HAYWOOD | US 74 | REPLACE BRIDGE 430095 OVER SOUTHERN RAILROAD. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | B-5982 | STATEWIDE MOBILITY | HFB | 2022 | 392000 | 2022 | 140000 | 2024 | 5399000 |  |  | 5931000
HAYWOOD | US 74 | REPLACE BRIDGE 430126 OVER I-40. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | HB-0006 | STATEWIDE MOBILITY | BFP | 2024 | 1000000 |  |  | 2027 | 9000000 |  |  | 10000000
HAYWOOD | WAYNESVILLE (DEPOT STREET) | REPLACE BRIDGE 430262 OVER RICHLAND CREEK. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | B-5013 | DIVISION 14 | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY BY THE TOWN OF WAYNESVILLE - MUNICIPAL BRIDGE
HAYWOOD | CITY OF ASHEVILLE | MOUNTAIN PROJECTS ( HAYWOOD COUNTY) DEVIATED FIXED ROUTE CAPITAL AND CARES FUNDS. | PUBLIC TRANSIT | 14 | FRENCH BROAD RIVER MPO | TG-6788 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 448000 | 448000
HAYWOOD | MOUNTAIN PROJECTS, INC. | ADMINISTRATION | PUBLIC TRANSIT | 14 |  | TK-6149 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 932000 | 932000 | FUNDS AUTHORIZED IN PROGRESS
HAYWOOD, BUNCOMBE | I-40 | NC 215 (CHAMPION DRIVE) TO SR 1200 (WIGGINS ROAD). ADD ADDITIONAL LANES. | HIGHWAY | 13, 14 | FRENCH BROAD RIVER MPO | I-6054B | NOT FUNDED | NHP | NOT FUNDED | 5300000 | NOT FUNDED | 700000 | NOT FUNDED | 163500000 |  |  | 169500000
HAYWOOD, BUNCOMBE | US 19, US 23 | SR 1836 (CHESTNUT MOUNTAIN ROAD) TO SR 1200 (WIGGINS ROAD). UPGRADE ROADWAY. | HIGHWAY | 13, 14 | FRENCH BROAD RIVER MPO | U-6048 | DIVISION 13, 14 | T | 2028 | 300000 | 2028 | 700000 | 2030 | 28200000 |  |  | 29200000
HAYWOOD, HENDERSON, MACON, POLK, SWAIN | VARIOUS | INSTALL SNOWPLOWABLE MARKERS AND PAVEMENT MARKINGS FOR WRONG WAY RAMP ARROWS ON VARIOUS FREEWAY RAMPS. | HIGHWAY | 14 | SOUTHWESTERN RPO, FRENCH BROAD RIVER MPO, FOOTHILLS RPO | HS-2014C | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2023 | 50000 |  |  | 50000
HAYWOOD, JACKSON | US 23/US 74 (GREAT SMOKEY MOUNTAINS EXPRESSWAY) | SR 1777 (BALSAM VIEW DRIVE) TO SR 1158 (OLD BALSAM ROAD) MODERNIZE ROADWAY. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO, SOUTHWESTERN RPO | U-6172 | DIVISION 14 | BGLT5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9650000 |  |  | 10950000
HAYWOOD, JACKSON | US 74 | IMPROVE PAVEMENT FROM SR 1392 TO EAST OF SR 1388 AND FROM JACKSON COUNTY LINE TO BRIDGES 107 AND 110 | HIGHWAY | 14 | FRENCH BROAD RIVER MPO, SOUTHWESTERN RPO | HS-2014E | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2023 | 975000 | 2022 | 25000 | 1000000
HAYWOOD, SWAIN | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE LAND OF SKY RPO AND SOUTHWESTERN RPO. | HIGHWAY | 14 | LAND-OF-SKY RPO, SOUTHWESTERN RPO | C-5612 | EXEMPT | CMAQ, L | 2020 | 4000 |  |  | 2020 | 19000 | 2020 | 12000 | 35000
HENDERSON | BLYTHE STREET | BLYTHE STREET, US 64 (BREVARD ROAD) TO NC 191 (HAYWOOD ROAD). CONSTRUCT SIDEWALKS. | BIKE/PED | 14 | FRENCH BROAD RIVER MPO | EB-5860 | DIVISION 14 | L, TAANY | 2025 | 45000 | 2025 | 35000 | 2026 | 1300000 | 2024 | 120000 | 1500000
HENDERSON | CLEAR CREEK GREENWAY/ HENDERSONVILLE | CONSTRUCT MULTI-USE PATH FROM BERKELEY MILLS PARK TO LAKEWOOD ROAD. | BIKE/PED | 14 | FRENCH BROAD RIVER MPO | BL-0008 | DIVISION 14 | BGANY, BGDA, L | 2023 | 98000 |  |  | 2024 | 1819000 | 2022 | 193000 | 2110000 | $78K IN BGANY USED AS PART OF FUND SWAP
HENDERSON | ECUSTA RAIL-TRAIL | KANUGA ROAD TO US 64/BATTLE CREEK. CONSTRUCT MULTI-USE PATH. | BIKE/PED | 14 | FRENCH BROAD RIVER MPO | BL-0007 | DIVISION 14 | BGANY, BGDA, L |  |  |  |  | 2023 | 5661000 | 2022 | 683000 | 6344000 | $4.470M in STBG-DA FUNDS SWAPPED FOR $4.470M IN STBG-ANYAREA FUNDS ON 1-25-2021
HENDERSON | GROVE STREET | BARNWELL STREET TO US 176 (SPARTANBURG HIGHWAY). CONSTRUCT SIDEWALK. | BIKE/PED | 14 | FRENCH BROAD RIVER MPO | EB-5963 | DIVISION 14 | L, TAANY | 2025 | 800000 | 2025 | 95000 | 2026 | 900000 | 2024 | 157000 | 1952000
HENDERSON | TOWN OF MILLS RIVER | NC 280, FRENCH BROAD RIVER TO HAYWOOD ROAD (NC 191). CONSTRUCT MULTI-USE PATH. | BIKE/PED | 14 | FRENCH BROAD RIVER MPO | EB-5946 | DIVISION 14 | [10 empty] | UNDER CONSTRUCTION
HENDERSON | I-26 | US 25 TO US 64 | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | I-4400A | NOT FUNDED | NHP | NOT FUNDED | 1600000 | NOT FUNDED | 500000 | NOT FUNDED | 114800000 |  |  | 116900000
HENDERSON | I-26 | US 64 INTERCHANGE IMPROVEMENTS | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | I-4400BA | STATEWIDE MOBILITY | T |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 29100000 |  |  | 29500000
HENDERSON | I-26 | US 64 TO US 25 BUSINESS | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | I-4400BB | STATEWIDE MOBILITY | NHP |  |  |  |  | 2019 | 52752000 |  |  | 52752000 | UNDER CONSTRUCTION. GARVEE BOND FUNDING: $43,911,307 FOR CONSTRUCTION, PAYBACK FY 2019-2033
HENDERSON | I-26 | MILE MARKER 50 TO POLK COUNTY LINE. PAVEMENT REHABILITATION. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | I-5925 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2025 | 15200000 |  |  | 15200000
HENDERSON | NC 191 | US 25 IN HENDERSONVILLE TO NC 280 SOUTH OF MILLS RIVER. WIDEN TO MULTI-LANES. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | R-2588
HENDERSON | NC 191 | US 25 TO SR 1381 (MOUNTAIN ROAD). | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | R-2588A | NOT FUNDED | BGANY | NOT FUNDED | 15200000 | NOT FUNDED | 1800000 | NOT FUNDED | 18800000 |  |  | 35800000
HENDERSON | NC 191 | SR 1381 (MOUNTAIN ROAD) TO NC 280 SOUTH OF MILLS RIVER. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | R-2588B | DIVISION 14 | T | 2022 | 15500000 | 2022 | 12100000 | 2024 | 92500000 |  |  | 120100000 | INCLUDES REPLACEMENT OF BRIDGE 440121 OVER FRENCH BROAD RIVER OVERFLOW (FORMERLY B-5901).
HENDERSON | NC 225 (SOUTH MAIN STREET) | SOUTH MAIN STREET AT SOUTH KING STREET TO US 176. WIDEN BRIDGE 440143 TO 5-LANES. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-6049 | REGION G | T | 2023 | 3400000 | 2023 | 400000 | 2026 | 4000000 |  |  | 7800000 | COORDINATE WITH U-5886
HENDERSON | NC 225 SR 1164 (ERKWOOD DRIVE) | NC 225/SR 1164 (ERKWOOD DRIVE)/SR 1779(SHEPHERD STREET) IN HENDERSONVILLE. IMPROVE INTERSECTION. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-5105 | PRE-STI (TRANSITION) | [10 empty] | DIVISION PROJECT - UNDER CONSTRUCTION
HENDERSON | NC 280 (BOYLSTON HIGHWAY) | NC 191 (HAYWOOD ROAD) TO NC 191 (OLD HAYWOOD ROAD). CONSTRUCT ACCESS MANAGEMENT AND INTERSECTION IMPROVEMENTS. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-6124 | NOT FUNDED | NHP | NOT FUNDED | 3300000 | NOT FUNDED | 1800000 | NOT FUNDED | 23000000 |  |  | 28100000
HENDERSON | SR 1127 (KANUGA ROAD) | US 25 BUSINESS (CHURCH STREET) TO SR 1123 (LITTLE RIVER ROAD). UPGRADE ROADWAY. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | R-5748 | DIVISION 14 | T | 2027 | 12500000 | 2027 | 17600000 | 2029 | 22100000 |  |  | 52200000
HENDERSON | SR 1170 (WHITE STREET) | SR 1171 (WILLOW ROAD) TO US 176 (SPARTANBURG HIGHWAY). REALIGN AND EXTEND ROADWAY. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-5886 | DIVISION 14 | T | 2023 | 18700000 | 2023 | 2600000 | 2026 | 15200000 |  |  | 36500000 | COORDINATE WITH U-6049.
HENDERSON | SR 1547 (OLD AIRPORT ROAD) | US 25 TO MILLS GAP ROAD. WIDEN ROADWAY. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-5840 | DIVISION 14 | T | 2020 | 855000 |  |  | 2020 | 12150000 | 2020 | 1575000 | 14580000 | COMPLETE. BUILD NC BOND FUNDING: $1.221 M FOR PE, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $667,196 FOR ROW, $5.865 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $3.573 M FOR CON, PAYBACK 2021-2035 (FY 2021/ YR 2&3 SALE).
HENDERSON | SR 1690 (BROADPOINTE DRIVE) | IMPROVE EXISTING SR 1690 (BROADPOINTE DRIVE) TO 24 FEET PAVED ROADWAY AND REPLACE BRIDGE 440107. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | R-5771 | EXEMPT | [10 empty] | ARC PROJECT NO. 18340 - UNDER CONSTRUCTION
HENDERSON | SR 1783 (HIGHLAND LAKE ROAD) | NC 225 TO US 176. UPGRADE ROADWAY. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-5887 | DIVISION 14 | T | 2020 | 2295000 |  |  | 2021 | 7676000 |  |  | 9971000
HENDERSON | SR 1970 (COMMERCIAL BLVD) | CONSTRUCT ROADWAY EXTENSION TO INDUSTRIAL PARK. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | HA-0003 | EXEMPT | ADHSL | 2021 | 70000 |  |  | 2021 | 1830000 |  |  | 1900000 | ARC PROJECT NO. 20227, AWARD AMOUNT = $1,900,000
HENDERSON | TRACY GROVE ROAD | REPLACE BRIDGE 440350 OVER DEVILS FORK CREEK. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | B-5929 | DIVISION 14 | BGOFF, L |  |  |  |  | 2023 | 1150000 |  |  | 1150000 | PLANNING/DESIGN BY CITY OF HENDERSONVILLE - MUNICIPAL BRIDGE
HENDERSON | US 64 | SR 1180 (BLYTHE STREET) TO SR 1173 (WHITE PINE DRIVE)/SR 1186 (DANIEL DRIVE). WIDEN ROADWAY. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-5783 | REGION G | T | 2022 | 17400000 | 2022 | 3900000 | 2024 | 20199000 |  |  | 41499000
HENDERSON | APPLE COUNTRY TRANSIT | REPLACEMENT TRANSIT VEHICLE ACQUISITION | PUBLIC TRANSIT | 14 | FRENCH BROAD RIVER MPO | TA-5229 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 60000 | 60000
HENDERSON | APPLE COUNTRY TRANSIT | ROUTINE CAPITAL - COST OF CONTRACTING | PUBLIC TRANSIT | 14 | FRENCH BROAD RIVER MPO | TG-4951 | PUBLIC TRANSIT | 5307, L, SMAP | [6 empty] | 2020 | 1921000 | 1921000 | FUNDS AUTHORIZED IN PROGRESS
HENDERSON | APPLE COUNTRY TRANSIT | TRANSIT ROUTINE CAPITAL COST OF CONTRACTING | PUBLIC TRANSIT | 14 | FRENCH BROAD RIVER MPO | TG-6181 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2856000 | 2856000
HENDERSON | APPLE COUNTRY TRANSIT | ADMINISTRATION | PUBLIC TRANSIT | 14 | FRENCH BROAD RIVER MPO | TK-5176 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 540000 | 540000 | FUNDS AUTHORIZED IN PROGRESS
HENDERSON | APPLE COUNTRY TRANSIT | OPERATING ASSISTANCE | PUBLIC TRANSIT | 14 | FRENCH BROAD RIVER MPO | TO-6106 | PUBLIC TRANSIT | 5311, L | [6 empty] | 2020 | 224000 | 224000 | FUNDS AUTHORIZED IN PROGRESS
HENDERSON | APPLE COUNTRY TRANSIT | PROGRAM SUPPORT. | PUBLIC TRANSIT | 14 | FRENCH BROAD RIVER MPO | TU-0010 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2022 | 600000 | 600000
HENDERSON | APPLE COUNTRY TRANSIT, W. CAROLINA COMMUNITY | SAFETY & SECURITY - MIN. 1% SET ASIDE | PUBLIC TRANSIT | 14 | FRENCH BROAD RIVER MPO | TS-5101 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 11000 | 11000 | FUNDS AUTHORIZED IN PROGRESS
HENDERSON | CITY OF ASHEVILLE | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE NEW TECHNOLOGY FOR SYSTEM WITH CARES 2021 FUNDING. | PUBLIC TRANSIT | 14 | FRENCH BROAD RIVER MPO | TG-6143 | PUBLIC TRANSIT | 5307, 5311, L | [6 empty] | 2021 | 202000 | 202000 | FUNDS AUTHORIZED IN PROGRESS
HENDERSON, BUNCOMBE | I-26 | US 25 TO NC 280. WIDEN TO ADD ADDITIONAL LANES. | HIGHWAY | 13, 14 | FRENCH BROAD RIVER MPO | I-4400
HENDERSON, BUNCOMBE | I-26 | US 25 BUSINESS TO NC 280 | HIGHWAY | 13, 14 | FRENCH BROAD RIVER MPO | I-4400C | REGION G | NHP |  |  |  |  | 2019 | 61776000 |  |  | 61776000 | UNDER CONSTRUCTION. GARVEE BOND FUNDING: $30M FOR CONSTRUCTION, PAYBACK FY 2019-2033; $20M FOR CONSTRUCTION, PAYBACK FY 2021-2035
HENDERSON, TRANSYLVANIA | ECUSTA TRAIL | BREVARD BIKE PATH IN BREVARD TO KANUGA ROAD IN HENDERSONVILLE. CONSTRUCT MULTIUSE PATH. | BIKE/PED | 14 | FRENCH BROAD RIVER MPO, LAND-OF-SKY RPO | EB-6037B | DIVISION 14 | L, TAANY | 2021 | 8000000 | [6 empty] | 8000000 | PROJECT CURRENTLY FUNDED FOR RIGHT-OF-WAY ONLY.
HERTFORD | TRI-COUNTY AIRPORT (ASJ) | RUNWAY EXTENSION. | AVIATION | 1 | PEANUT BELT RPO | AV-5778 | DIVISION 1 | T |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1658000 |  |  | 1658000
HERTFORD | TRI-COUNTY AIRPORT (ASJ) | CONSTRUCT ACCESS ROAD TO T-HANGARS. | AVIATION | 1 | PEANUT BELT RPO | AV-5878 | NOT FUNDED | T |  |  |  |  | NOT FUNDED | 2106000 |  |  | 2106000
HERTFORD | NC 461 | NC 45 TO END OF STATE MAINTENANCE. MODERNIZE ROADWAY. | HIGHWAY | 1 | PEANUT BELT RPO | R-5811 | DIVISION 1 | T |  |  |  |  | 2023 | 3260000 |  |  | 3260000
HERTFORD | SR 1311 (BOONE'S BRIDGE ROAD) | REPLACE BRIDGE 450137 OVER MEHERRIN RIVER OVERFLOW. | HIGHWAY | 1 | PEANUT BELT RPO | B-5603 | DIVISION 1 | [10 empty] | UNDER CONSTRUCTION
HERTFORD | US 13/NC 11 | NC 11/NC 561 INTERSECTION NEAR AHOSKIE TO US 13/US 158/NC 45 INTERSECTION NEAR WINTON. WIDEN TO MULTI-LANES. | HIGHWAY | 1 | PEANUT BELT RPO | R-5311
HERTFORD | US 13/NC 11 | WEST OF MODLIN ROAD TO EAST OF NC 11/SR 1213 (OLD NC 11 ROAD). CONSTRUCT GRADE SEPARATION AT SR 1130 (MODLIN ROAD) AND INTERCHANGE AT OLD NC 11/SR 1213 (OLD NC 11 ROAD). | HIGHWAY | 1 | PEANUT BELT RPO | R-5311A | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
HERTFORD | US 13/NC 11 | NC 11/NC 561 INTERSECTION NEAR AHOSKIE TO US 13/US 158/NC 45 INTERSECTION NEAR WINTON. | HIGHWAY | 1 | PEANUT BELT RPO | R-5311B | REGION A | T | 2028 | 6300000 | 2028 | 1200000 | 2030 | 101401000 |  |  | 108901000
HERTFORD | US 13/NC 42/NC 561 (MEMORIAL DRIVE) | PEACHTREE STREET TO NC 42. WIDEN TO MULTI-LANES. | HIGHWAY | 1 | PEANUT BELT RPO | R-5796 | REGION A | T | 2024 | 2575000 | 2024 | 1570000 | 2025 | 13735000 |  |  | 17880000 | INCLUDES B-5605. BUILD NC BOND FUNDING: $5,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE).
HOKE | SR 1203 (TURNPIKE ROAD) | REPLACE BRIDGE 460008 OVER LUMBER RIVER. | HIGHWAY | 8 | LUMBER RIVER RPO | B-4967 | DIVISION 8 | [10 empty] | UNDER CONSTRUCTION
HOKE | SR 1305 (WAYSIDE ROAD); SR 1418 (LINDSAY ROAD) | SR 1305, US 401 TO PLANK ROAD, AND SR 1418, US 401 TO SR 1406 (ROCKFISH ROAD). WIDEN TO MULTILANES. | HIGHWAY | 8 | FAYETTEVILLE AREA MPO | U-5753 | DIVISION 8 | BGANY, T | 2022 | 42100000 | 2022 | 5000000 | 2024 | 48270000 |  |  | 95370000 | INCLUDES H111245; COORDINATE WITH U-5798 AND U-5857; BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2024-2038 (FY 2024 / YR 6 SALE)
HOKE | SR 1406 (ROCKFISH ROAD) | REPLACE BRIDGE 460057 OVER PUPPY CREEK. | HIGHWAY | 8 | FAYETTEVILLE AREA MPO | B-5755 | DIVISION 8 | [10 empty] | UNDER CONSTRUCTION
HOKE | SR 1406 (ROCKFISH ROAD); NEW ROUTE (GILLIS HILL RO | SR 1406 (ROCKFISH ROAD) FROM SR 1003 (CAMDEN ROAD) TO NORTH OF WESTFIELD DRIVE AND GILLIS HILL ROAD EXTENSION FROM NORTH OF WESTFIELD DRIVE TO SR 1418 (LINDSAY ROAD). WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | HIGHWAY | 8 | FAYETTEVILLE AREA MPO | U-5857 | DIVISION 8 | T | 2027 | 18000000 | 2027 | 5700000 | 2029 | 46000000 |  |  | 69700000 | COORDINATE WITH U-5753 AND U-5798.
HOKE | HOKE COUNTY | OPERATING ASSISTANCE FY20-21 | PUBLIC TRANSIT | 8 | FAYETTEVILLE AREA MPO | TO-6157 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 932000 | 932000
HOKE, MOORE | NC 211 | US 15 / US 501 IN ABERDEEN TO EAST OF SR 1244 (WEST PALMER STREET) / SR 1311 (MOCKINGBIRD HILL ROAD) IN RAEFORD. WIDEN TO MULTILANES. | HIGHWAY | 8 | LUMBER RIVER RPO, TRIANGLE AREA RPO | R-5709 | REGION E | T | 2021 | 50805000 | 2021 | 4976000 | 2024 | 132600000 |  |  | 188381000 | RIGHT OF WAY IN PROGRESS
HOKE, MOORE | NC 211 | US 15 / US 501 IN ABERDEEN TO EAST OF SR 1244 (WEST PALMER STREET) / SR 1311 (MOCKINGBIRD HILL ROAD) IN RAEFORD. CLEARING, GRUBBING, AND EROSION CONTROL. | HIGHWAY | 8 | LUMBER RIVER RPO, TRIANGLE AREA RPO | R-5709A | REGION E | T |  |  |  |  | 2022 | 17625000 |  |  | 17625000 | UNDER CONSTRUCTION
HOKE, SCOTLAND | US 401 | US 401 BUSINESS NORTH OF LAURINBURG TO US 401 BUSINESS EAST OF RAEFORD. CONSTRUCT PASSING LANES, TURN LANES, AND PAVED SHOULDERS. | HIGHWAY | 8 | LUMBER RIVER RPO, FAYETTEVILLE AREA MPO | R-3333 | NOT FUNDED | NHP | NOT FUNDED | 273000 | NOT FUNDED | 15507000 | NOT FUNDED | 38800000 |  |  | 54580000
HYDE | HYDE COUNTY AIRPORT (7W6) | EXTEND RUNWAY TO 5000 FEET. | AVIATION | 1 | ALBEMARLE RPO | AV-5812 | DIVISION 1 | T |  |  |  |  | 2023 | 822000 |  |  | 822000 | UNDER CONSTRUCTION.
HYDE | NC 12 | OCRACOKE PEDESTRIAN WAITING AND ACCESS ACCOMMODATIONS | FERRY | 1 | ALBEMARLE RPO | F-5702B | DIVISION 1 | [10 empty] | COMPLETE
HYDE | NC 45 | SWAN QUARTER VISITORS CENTER. REPLACEMENT. | FERRY | 1 | ALBEMARLE RPO | F-5003 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
HYDE | (SLADESVILLE CREDLE ROAD) SR 1143 | REPLACE BRIDGE 470035 OVER CREEK. | HIGHWAY | 1 | ALBEMARLE RPO | BR-0234 | HIGHWAY FUND | [10 empty] | UNDER CONSTRUCTION. PROJECT REPRESENTS HFB 1.R.83 PROJECT.
HYDE | SR 1143 (SLADESVILLE CREDLE ROAD) | REPLACE BRIDGE 470036 OVER SMITH CREEK. | HIGHWAY | 1 | ALBEMARLE RPO | BR-0237 | HIGHWAY FUND | [10 empty] | UNDER CONSTRUCTION. PROJECT REPRESENTS HFB 1.R.63 PROJECT.
HYDE | US 264 | REHABILITATE BRIDGE 470020 OVER INTRACOASTAL WATERWAY. | HIGHWAY | 1 | ALBEMARLE RPO | B-5942 | REGION A | [10 empty] | UNDER CONSTRUCTION
HYDE | HYDE COUNTY NON-PROFIT | ADMINISTRATION | PUBLIC TRANSIT | 1 | ALBEMARLE RPO | TK-6135 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 400000 | 400000 | FUNDS AUTHORIZED IN PROGRESS
IREDELL | STATESVILLE REGIONAL AIRPORT (SVH) | RELOCATE EAST AVIATION DRIVE TO ALLOW FOR FUTURE RUNWAY EXTENSION. | AVIATION | 12 | CHARLOTTE REGIONAL TPO | AV-5896 | DIVISION 12 | T | 2026 | 5610000 |  |  | 2027 | 3725000 |  |  | 9335000
IREDELL | MOORE AVENUE | SOUTH CHURCH STREET TO NORTH ACADEMY STREET. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | BIKE/PED | 12 | CHARLOTTE REGIONAL TPO | BL-0013 | DIVISION 12 | BGDA, L |  |  |  |  | 2025 | 2000000 |  |  | 2000000
IREDELL | MOORESVILLE | SOUTH ELEMENTARY SCHOOL TO MOORESVILLE MIDDLE SCHOOL. CONSTRUCT GREENWAY CONNECTORS. | BIKE/PED | 12 | CHARLOTTE REGIONAL TPO | BL-0055 | DIVISION 12 | BGDA, L |  |  |  |  | 2026 | 2081000 | 2025 | 363000 | 2444000
IREDELL | MOORESVILLE | BELLINGHAM PARK GREENWAY EXTENSION TO JOHNSON DAIRY ROAD. CONSTRUCT GREENWAY. | BIKE/PED | 12 | CHARLOTTE REGIONAL TPO | EB-5787 | DIVISION 12 | BGDA, L |  |  |  |  | 2023 | 4444000 |  |  | 4444000
IREDELL | NC 152 (NORTH MAIN STREET) | PINE STREET TO NORTH MAIN PARK. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | BIKE/PED | 12 | CHARLOTTE REGIONAL TPO | BL-0009 | DIVISION 12 | BGDA, L | 2024 | 617000 |  |  | 2025 | 732000 | 2024 | 138000 | 1487000
IREDELL | SR 2162 (WHITE OAK ROAD) MAPLE AVENUE McNEELY AVEN | CONSTRUCT SIDEWALKS AT VARIOUS LOCATIONS IN MOORESVILLE. | BIKE/PED | 12 | CHARLOTTE REGIONAL TPO | BL-0056 | DIVISION 12 | BGDA, L | 2025 | 104000 |  |  | 2026 | 1972000 | 2024 | 563000 | 2639000
IREDELL | STATESVILLE | SHELTON AVENUE MULTI-USE PATH, GARNER BAGNAL BOULEVARD TO AMITY HILL ROAD. CONSTRUCT GREENWAY. | BIKE/PED | 12 | CHARLOTTE REGIONAL TPO | EB-5788 | DIVISION 12 | BGDA, L | 2023 | 251000 | [6 empty] | 251000 | RIGHT-OF-WAY IN PROGRESS
IREDELL | STATESVILLE | CONSTRUCT GREENWAY CONNECTOR UNDER US 21 (TURNERSBURG HIGHWAY). | BIKE/PED | 12 | CHARLOTTE REGIONAL TPO | EB-5818 | DIVISION 12 | BGDA, L |  |  |  |  | 2023 | 1670000 |  |  | 1670000
IREDELL | TROUTMAN | OLD MOUNTAIN ROAD, NORTH MAIN STREET TO SOUTH IREDELL HIGH SCHOOL IN TROUTMAN. CONSTRUCT SIDEWALK ON SOUTH SIDE OF ROAD. | BIKE/PED | 12 | CHARLOTTE REGIONAL TPO | EB-5530 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
IREDELL | TROUTMAN | DOWNTOWN SIDEWALK IMPROVEMENTS. RUMPLE STREET FROM US 21/NC 115 TO THOMAS STREET; WAGNER STREET FROM US 21/NC 115 TO WEST AVENUE; TALLEY STREET FROM US 21/NC 115 TO WEST AVENUE. | BIKE/PED | 12 | CHARLOTTE REGIONAL TPO | EB-5930 | DIVISION 12 | L, TADA | 2022 | 199000 |  |  | 2023 | 1623000 | 2021 | 312000 | 2134000
IREDELL | TROUTMAN | RICHARDSON GREENWAY SOUTH. US 21/NC 115 (SOUTH MAIN STREET) FROM TROUTMAN ELEMENTARY SCHOOL TO JACOBS WOODS SUBDIVISION. | BIKE/PED | 12 | CHARLOTTE REGIONAL TPO | EB-5932 | DIVISION 12 | L, TADA | 2022 | 217000 |  |  | 2023 | 1250000 | 2021 | 122000 | 1589000
IREDELL | I-40 | REPLACE BRIDGE 480102 ON I-40 WESTBOUND OVER THIRD CREEK. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | BR-0024 | STATEWIDE MOBILITY | HFB |  |  |  |  | 2026 | 5500000 |  |  | 5500000
IREDELL | I-40 | REPLACE BRIDGES 480006 AND 480007 OVER CATAWBA RIVER. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | HB-0018 | STATEWIDE MOBILITY | BFP | 2022 | 2500000 |  |  | 2025 | 25000000 |  |  | 27500000
IREDELL | I-40 | SR 2158 (OLD MOCKSVILLE ROAD) TO DAVIE COUNTY LINE. PAVEMENT REHABILITATION. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | I-5805 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2028 | 70500000 |  |  | 70500000
IREDELL | I-40/I-77 | STATESVILLE, MODIFICATION OF I-40/I-77 INTERCHANGE AREA. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | I-3819 | [11 empty] | GARVEE BOND FUNDING - SEGMENT A: $10M FOR CONSTRUCTION, PAYBACK FY 2012-2023
IREDELL | I-40/I-77 | INITIAL I-40/I-77 INTERCHANGE IMPROVEMENTS | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | I-3819A | PRE-STI (TRANSITION) | NHP |  |  |  |  | 2012 | 4388000 |  |  | 4388000 | COMPLETE. GARVEE BOND FUNDING - SEGMENT A: $10M FOR CONSTRUCTION, PAYBACK FY 2012-2023
IREDELL | I-40/I-77 | FINAL I-40/I-77 INTERCHANGE IMPROVEMENTS | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | I-3819B | STATEWIDE MOBILITY | T |  |  |  |  | 2019 | 327665000 |  |  | 327665000 | UNDER CONSTRUCTION; BUILD NC BOND FUNDING: $110.79M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE)
IREDELL | I-77 | MILE MARKER 57.83 TO MILE POST 61.74. PAVEMENT REHABILITATION. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | I-5106 | PRE-STI (TRANSITION) | NHP |  |  |  |  | 2009 | 439000 |  |  | 439000 | COMPLETE - GARVEE BOND FUNDING: $4M FOR CONSTRUCTION, PAYBACK FY 2009-2020
IREDELL | I-77 | EXIT 45 TO EXIT 54, EXCLUDING PROJECT AREA FOR I-3819 A. PAVEMENT REHABILITATION. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | I-5606 | [11 empty] | COMPLETE
IREDELL | I-77 | MILEMARKER 36.5 TO MILEMARKER 50.0. PAVEMENT REHABILITATION. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | I-5918 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2025 | 24400000 |  |  | 24400000
IREDELL | I-77 | MILEMARKER 53.7 TO MILEMARKER 56.8. PAVEMENT REHABILITATION. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | I-5919 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2025 | 10500000 |  |  | 10500000
IREDELL | I-77 | MILE MARKER 58.4 TO YADKIN COUNTY LINE. PAVEMENT REHABILITATION. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | I-5920 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2026 | 19275000 |  |  | 19275000
IREDELL | I-77 | I-77 AT SR 1302 (CORNELIUS ROAD). CONVERT GRADE SEPARATION TO INTERCHANGE. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | I-5962 | STATEWIDE MOBILITY | NHP, O | 2026 | 3000000 | 2026 | 500000 | 2028 | 36101000 |  |  | 39601000 | OTHER FUNDS PROVIDED BY TOWN OF MOORESVILLE
IREDELL | MOORESVILLE | NC 115 AND NC 150 IN MOORESVILLE. CONSTRUCT SOUTHBOUND NC 115 RIGHT TURN LANE AT NC 150 AND WESTBOUND NC 150 SHARED THROUGH-RIGHT LANE AT NC 115. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | C-5200 | EXEMPT | BGDA, L |  |  |  |  | 2020 | 1514000 |  |  | 1514000 | UNDER CONSTRUCTION. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR CONSTRUCTION TO COVER ANTICIPATED EXPENDITURES.
IREDELL | MOORESVILLE | INTERSECTION OF NC 115 AND FAITH ROAD-CAMPUS LANE IN MOORESVILLE. REALIGN FAITH ROAD TO TIE INTO EXISTING NC 115/CAMPUS LANE INTERSECTION AND CONSTRUCT DEDICATED TURN LANES ON FAITH ROAD AND CAMPUS LANE APPROACHES TO THE INTERSECTION. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | C-5529 | EXEMPT | BGDA, L |  |  |  |  | 2023 | 1128000 |  |  | 1128000 | UNDER CONSTRUCTION
IREDELL | MOORESVILLE | KISTLER FARM-BRIARCLIFF-BELLINGHAM-WHITE OAK SIDEWALK NETWORK IN MOORESVILLE. CONSTRUCT SIDEWALKS IN VARIOUS LOCATIONS. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | C-5531 | EXEMPT | BGDA, L |  |  |  |  | 2020 | 801000 |  |  | 801000 | UNDER CONSTRUCTION; ADDITIONAL FUNDING FOR CONSTRUCTION TO COVER ANTICIPATED EXPENDITURES.
IREDELL | MOORESVILLE | INTERSECTION OF NC 801 AND NC 150. CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | C-5701 | EXEMPT | BA, BGDA, CMAQ, L | 2020 | 324000 |  |  | 2020 | 3236000 |  |  | 3560000 | UNDER CONSTRUCTION. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $2.168M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
IREDELL | MOORESVILLE | SILICON SHORES EAST-WEST CONNECTOR ROAD PROJECT. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-6239 | EXEMPT | DP, L | 2022 | 6149000 |  |  | 2023 | 15056000 | 2021 | 525000 | 21730000 | DP REPRESENTS FEDERAL 2019 BUILD GRANT FUNDS AWARDED TO THE TOWN OF MOORESVILLE
IREDELL | NC 115 | SR 1645 (OLD WILKESBORO ROAD) TO HARTNESS ROAD. WIDEN TO MULTI-LANES. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-5779 | REGION F | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 22100000 |  |  | 37600000
IREDELL | NC 115 | SR 1102 (LANGTREE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-6249 | EXEMPT | BGDA, L | 2023 | 500000 |  |  | 2025 | 4006000 | 2021 | 560000 | 5066000 | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT
IREDELL | NC 150 | INTERSECTION OF NC 150 AND SR 2399 (WIGGINS ROAD). REALIGN INTERSECTION. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-5780 | REGION F | T | 2019 | 550000 |  |  | 2024 | 1450000 |  |  | 2000000 | RIGHT-OF-WAY IN PROGRESS. PROJECT TO BE LET WITH W-5601U.
IREDELL | NC 150 | NC 150 AT NC 152 (WESTERN INTERSECTION) | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | W-5601U | REGION F | HSIP | 2022 | 472000 |  |  | 2024 | 1150000 |  |  | 1622000
IREDELL | NC 150 (OAK RIDGE FARM HIGHWAY) | NC 115 TO NC 801 (PARK AVENUE). WIDEN TO MULTI-LANES. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-5960 | REGION F | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 18700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 27000000 |  |  | 49500000
IREDELL | NC 3 | CABARRUS-IREDELL COUNTY LINE TO SR 1147 (ROCKY RIVER ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-6145 | NOT FUNDED | T | NOT FUNDED | 5200000 | NOT FUNDED | 3300000 | NOT FUNDED | 28801000 |  |  | 37301000
IREDELL | SR 1004 (HUDSON CHAPEL ROAD) | REPLACE BRIDGE 480081 CATAWBA RIVER. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | HB-0032 | DIVISION 12 | BGOFF | 2025 | 775000 | 2025 | 775000 | 2026 | 15500000 |  |  | 17050000
IREDELL | SR 1005 (OLD MOUNTAIN ROAD) | US 21/NC 115 (NORTH MAIN STREET) TO SR 1004 (BUFFALO SHOALS ROAD). WIDEN TO FOUR LANES WITH A MEDIAN. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-6175 | NOT FUNDED | BGLT5 | NOT FUNDED | 21800000 | NOT FUNDED | 3540000 | NOT FUNDED | 28602000 |  |  | 53942000
IREDELL | SR 1100 (BRAWLEY SCHOOL ROAD) | SR 1177 (CHUCKWOOD ROAD) TO US 21. WIDEN TO MULTI-LANES WITH INTERCHANGE AT I-77. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | R-3833 | [11 empty] | $890,000 CONTRIBUTION FROM TOWN OF MOORESVILLE.
IREDELL | SR 1100 (BRAWLEY SCHOOL ROAD) | SR 1177 (CHUCKWOOD ROAD) TO SR 1109 (CENTRE CHURCH ROAD) | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | R-3833A | [11 empty] | COMPLETE
IREDELL | SR 1100 (BRAWLEY SCHOOL ROAD) | SR 1109 (CENTRE CHURCH ROAD) TO I-77 | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | R-3833B | [11 empty] | COMPLETE
IREDELL | SR 1100 (BRAWLEY SCHOOL ROAD) | I-77 TO US 21 | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | R-3833C | DIVISION 12 | L, T | 2019 | 5050000 |  |  | 2024 | 24970000 |  |  | 30020000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $10M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE).
IREDELL | SR 1109 (WILLIAMSON ROAD) | I-77 TO NC 150. WIDEN TO MULTI-LANES. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | R-5100 | [11 empty] | COORDINATE WITH U-5817.
IREDELL | SR 1109 (WILLIAMSON ROAD) | I-77 TO SR 1100 (BRAWLEY SCHOOL ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | R-5100A | DIVISION 12 | T | 2020 | 8850000 | 2022 | 5300000 | 2025 | 39300000 | 2020 | 600000 | 54050000 | BUILD NC BOND FUNDING: $466,370 FOR PE, PAYBACK FY 2020-2034 (FY 2019/YR 1 SALE); $142,461 FOR ROW, PAYBACK FY 2020-2034 (FY 2019/YR 1 SALE); $3M FOR ROW, PAYBACK FY 2022-2036 (FY 2022/YR 4 SALE).
IREDELL | SR 1109 (WILLIAMSON ROAD) | SR 1100 (BRAWLEY SCHOOL ROAD) TO NC 150. WIDEN TO MULTI-LANES. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | R-5100B | DIVISION 12 | T | 2019 | 9515000 | 2022 | 1300000 | 2025 | 5900000 |  |  | 16715000 | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $347,148 FOR ROW, PAYBACK FY 2020-2034 (FY 2019/YR 1 SALE); $2M FOR ROW, PAYBACK FY 2022-2036 (FY 2022/YR 4 SALE).
IREDELL | SR 1125 (SHEARERS ROAD) | SR 1147 (ROCKY RIVER ROAD) INTERSECTION. INSTALL TRAFFIC SIGNAL. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | HS-2012C | DIVISION 12 | HSIP |  |  |  |  | 2022 | 190000 | 2022 | 20000 | 210000
IREDELL | SR 1206 (ALCOVE ROAD) | RELOCATION OF ROADWAY IN MOORESVILLE. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | R-4757 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY - PLANNING BY TOWN OF MOORESVILLE
IREDELL | SR 1246 (FAIRVIEW ROAD) | EXTEND SR 1246 (FAIRVIEW ROAD) OVER I-77 TO CONNECT WITH SR 1206 (ALCOVE ROAD) AND CONSTRUCT PARALLEL NORTH-SOUTH CONNECTOR ROADS TO SR 1109 (WILLIAMSON ROAD). | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-5817 | DIVISION 12 | BA, BGANY, BGDA, T | 2019 | 5800000 | 2019 | 1900000 | 2025 | 19225000 |  |  | 26925000 | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5100. BUILD NC BOND FUNDING: $5.3M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE).
IREDELL | SR 1302 (PERTH ROAD) | SR 1302 (PERTH ROAD) AT SR 1378 (JUDAS ROAD) AND SR1302 (CORNELIUS ROAD) INTERSECTIONS. CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | W-5212J | DIVISION 12 | BGDA, S(M) | [6 empty] | 2020 | 356000 | 356000 | $178K IN BGANY USED AS PART OF FUND SWAP.
IREDELL | SR 1302 (PERTH ROAD) | INSTALL SIGNAL AT SR 1302 (PERTH ROAD) AND SR 1378 (JUDAS ROAD) INTERSECTION. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | W-5212JA | DIVISION 12 | BGANY, BGDA, S(M) | 2020 | 25000 |  |  | 2022 | 125000 |  |  | 150000 | $62K IN BGANY USED AS PART OF FUND SWAP.
IREDELL | SR 1303 (PERTH ROAD) | INSTALL SIGNAL AND TURN LANES AT SR 1302 (CORNELIUS ROAD) AND SR 1303 (PERTH ROAD) INTERSECTION. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | W-5212JB | DIVISION 12 | BGANY, BGDA, S(M) | 2022 | 885000 |  |  | 2022 | 1581000 |  |  | 2466000 | $791K IN BGANY USED AS PART OF FUND SWAP.
IREDELL | SR 1305 (OATES ROAD - MIDNIGHT LANE) | US 21 (CHARLOTTE HIGHWAY) TO SR 1474 (BLUEFIELD ROAD). WIDEN TO THREE-LANES WITH OVERPASS OVER I-77. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-5816 | DIVISION 12 | T | 2026 | 12600000 | 2026 | 3200000 | 2029 | 29601000 |  |  | 45401000
IREDELL | SR 1577 | REPLACE BRIDGE 480131 OVER UT TO SNOW CREEK. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | BR-0107 | HIGHWAY FUND | HFB |  |  |  |  | 2022 | 800000 |  |  | 800000 | LEVERAGE PROJECT FOR GREATTER BUILD GRANT
IREDELL | SR 1595 (COOLBROOK ROAD) | REPLACE BRIDGE 480166 ON SR 1595 OVER ROCKY CREEK. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | BR-0115 | DIVISION 12 | DP, HFB | 2020 | 170000 |  |  | 2021 | 1600000 |  |  | 1770000 | DP REPRESENT FEDERAL BUILD GRANT FUNDING
IREDELL | SR 1601 (BRANTON ROAD) | REPLACE BRIDGE 480165 ON SR 1601 OVER ROCKY CREEK. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | BR-0114 | DIVISION 12 | DP, HFB | 2020 | 150000 |  |  | 2021 | 1150000 |  |  | 1300000 | DP REPRESENT FEDERAL BUILD GRANT FUNDING
IREDELL | SR 1639 (MEACHAM RD) | REPLACE BRIDGE 480118 OVER I-40. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | BR-0025 | DIVISION 12 | BFP |  |  |  |  | 2025 | 5500000 |  |  | 5500000
IREDELL | SR 1892 | REPLACE BRIDGE 480212 OVER PATTERSON CREEK. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | BR-0202 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 1250000 |  |  | 1250000 | THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.12.R.49
IREDELL | SR 1892 | REPLACE BRIDGE 480219 OVER OLIN CREEK. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | BR-0204 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 900000 |  |  | 900000 | THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.12.R.51
IREDELL | SR 1892 (JENNINGS ROAD) | REPLACE BRIDGE 480189 OVER SOUTH YADKIN RIVER. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | B-5846 | DIVISION 12 | BGOFF | 2022 | 85000 | 2022 | 325000 | 2023 | 3300000 |  |  | 3710000
IREDELL | SR 1896 | REPLACE BRIDGE 480214 OVER PATTERSON CREEK | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | BR-0203 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 1000000 |  |  | 1000000 | THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.12.R.50
IREDELL | SR 2321 (EAST BROAD STREET) | VINE STREET TO SR 2422 (SIGNAL HILL DRIVE). UPGRADE ROADWAY AND IMPLEMENT ACCESS MANAGEMENT SOLUTIONS. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-6039 | DIVISION 12 | T |  |  |  |  | 2019 | 5350000 |  |  | 5350000 | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT - TO BE LET WITH I-3819 B
IREDELL | SR 2402 (HOOVER ROAD) | REPLACE BRIDGE 480020 OVER I-L CREEK. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | B-5843 | DIVISION 12 | BGOFF | 2023 | 67000 |  |  | 2024 | 675000 |  |  | 742000
IREDELL | STATESVILLE | CONSTRUCT BROOKDALE DRIVE-US 21 CONNECTOR. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-6054 | DIVISION 12 | BGANY, BGDA, L | 2023 | 1540000 |  |  | 2024 | 2218000 | 2020 | 326000 | 4084000 | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $1.644M IN BGANY USED AS PART OF FUND SWAP.
IREDELL | STATESVILLE | SR 1363 (BETHLEHEM ROAD). RELOCATE ROADWAY ADJACENT TO STATESVILLE REGIONAL AIRPORT. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-6153 | DIVISION 12 | BA, O, T |  |  |  |  | 2024 | 4648000 | 2020 | 452000 | 5100000 | OTHER FUNDS PROVIDED BY THE CITY OF STATESVILLE. STATE TRUST FUNDS ALLOCATED DUE TO FUNDING SWAP WITH U-5816 FOR BA FUNDS. $2.098M IS MAXIMUM STATE TRUST FUNDS ALLOCATED TO THE PROJECT.
IREDELL | US 21 | INTERSECTION OF US 21 AND SR 2375 (HOUSTON ROAD)/SR 1312 (FLOWER HOUSE ROAD). REALIGN AND SIGNALIZE. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | R-5711 | REGION F | T |  |  |  |  | 2025 | 2950000 |  |  | 2950000 | RIGHT-OF-WAY IN PROGRESS
IREDELL | US 21 | SR 1933 TO FORT DOBBS ROAD. WIDEN TO MULTI-LANES AND REALIGN OFFSET INTERSECTIONS OF SR 1922 AND SR 2171. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-5799 | REGION F | T | 2020 | 22360000 | 2020 | 1600000 | 2024 | 15200000 | 2020 | 2265000 | 41425000 | BUILD NC BOND FUNDING: $1.757M FOR PE, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $42,703 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE)
IREDELL | US 21 - NC 115 | CEDAR LANE IN TROUTMAN TO BARIUM LANE IN BARIUM SPRINGS. WIDEN TO MULTI-LANES. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | R-2522 | REGION F | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 14900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 16800000 |  |  | 34800000
IREDELL | US 21 (CHARLOTTE HIGHWAY) | NC 150 (PLAZA DRIVE) TO SR 1245 (MEDICAL PARK ROAD). WIDEN TO 4-LANES DIVIDED. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-6037 | DIVISION 12 | T | 2027 | 15500000 | 2027 | 4600000 | 2030 | 23800000 |  |  | 43900000
IREDELL | US 64 (DAVIE AVENUE) | US 64 (DAVIE AVENUE) AND US 21 (SULLIVAN ROAD). CONVERT 5-APPROACH INTERSECTION TO A SINGLE LANE ROUNDABOUT. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-5964 | REGION F | T | 2024 | 11000000 | 2024 | 700000 | 2026 | 3298000 |  |  | 14998000
IREDELL | VARIOUS | VARIOUS MAINTENANCE ACTIVITIES INCLUDING RESURFACING AND PAVEMENT RESTRIPING. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | HL-0037 | DIVISION 12 | BGDACV |  |  |  |  | 2023 | 975000 |  |  | 975000
IREDELL | IREDELL COUNTY | ADMINISTRATION | PUBLIC TRANSIT | 12 |  | TK-6179 | PUBLIC TRANSIT | 5311 | [6 empty] | 2020 | 1040000 | 1040000 | FUNDS AUTHORIZED IN PROGRESS
IREDELL | IREDELL COUNTY | OPERATING ASSISTANCE FOR THE IREDELL COUNTY AREA TRANSPORTATION SYSTEM (ICATS) | PUBLIC TRANSIT | 12 | CHARLOTTE REGIONAL TPO | TO-5149 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 687000 | 687000 | FUNDS AUTHORIZED IN PROGRESS
IREDELL | IREDELL COUNTY | OPERATION FOR FY20-21 | PUBLIC TRANSIT | 12 | CHARLOTTE REGIONAL TPO | TO-6158 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2372000 | 2372000 | ADDING FUNDS FOR FFY2020
IREDELL | SR 2395 (MAZEPPA ROAD) | NC 115 INTERSECTION. CONSTRUCT GRADE SEPARATION OVER NC 115 AND NORFOLK SOUTHERN RAILROAD. | RAIL | 12 | CHARLOTTE REGIONAL TPO | RL-0001 | EXEMPT | DP, L | 2023 | 320000 |  |  | 2025 | 7860000 | 2021 | 800000 | 8980000 | DP REPRESENTS FEDERAL INFRA GRANT FUNDS
IREDELL, CATAWBA | I-40 | MILEMARKER 130.7 TO MILEMARKER 150.2. PAVEMENT AND BRIDGE REHABILITATION. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO, GREATER HICKORY MPO | I-5915
IREDELL, CATAWBA | I-40 | MILEMARKER 130.7 TO MILEMARKER 150.2. PAVEMENT REHABILITATION. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO, GREATER HICKORY MPO | I-5915A | STATEWIDE MOBILITY | [10 empty] | COMPLETE
IREDELL, CATAWBA | I-40 | BRIDGE REHABILITATION. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO, GREATER HICKORY MPO | I-5915B | STATEWIDE MOBILITY | BGDA, NHPIM, S(M) |  |  |  |  | 2022 | 10943000 |  |  | 10943000 | $7.319M IN NHPIM FUNDS SWITCHED WITH $7.319M IN BGDA AS PART OF FUND SWAP.
IREDELL, CATAWBA | NC 150 | EAST OF SR 1840 (GREENWOOD ROAD) IN CATAWBA COUNTY TO WEST OF SR 1303/SR 1180 (PERTH ROAD/DOOLIE ROAD) IN IREDELL COUNTY. WIDEN TO 4-LANES. SR 1383/SR 1180 TO US 21 IN IREDELL COUNTY. WIDEN TO 6-LANES. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO, GREATER HICKORY MPO | R-2307B | REGION F | S(M), T, T(DA) |  |  |  |  | 2025 | 164500000 |  |  | 164500000 | RIGHT-OF-WAY IN PROGRESS. $5M IN STBG-DA FUNDS SWITCHED WITH $5M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP.
IREDELL, CATAWBA | VARIOUS | DIVISION 12 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS IN THE DIVISION CATEGORY. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO, GREATER HICKORY MPO | W-5212DIV | DIVISION 12 | HSIP | 2020 | 50000 |  |  | 2020 | 2500000 |  |  | 2550000
IREDELL, MECKLENBURG | I-77 | SR 5544 (WEST CATAWBA AVENUE - EXIT 28) TO NC 150. WIDEN AND RECONSTRUCT ROADWAY. | HIGHWAY | 10, 12 | CHARLOTTE REGIONAL TPO | I-4750 | [11 empty] | FUNDING FOR I-4750 AA INCLUDED IN I-5405
IREDELL, MECKLENBURG | I-77 | SR 5544 (WEST CATAWBA AVENUE - EXIT 28) TO NC 150 (EXIT 36). CONSTRUCT HIGH OCCUPANCY/TOLL (HOT) LANES. | HIGHWAY | 10, 12 | CHARLOTTE REGIONAL TPO | I-4750AA | [11 empty] | COMPLETE - UNDER CONSTRUCTION WITH PROJECT I-5405
IREDELL, MECKLENBURG | I-77 | SR 5544 (WEST CATAWBA AVENUE - EXIT 28) TO NC 150 (EXIT 36). CONSTRUCT ONE ADDITIONAL LANE IN EACH DIRECTION. | HIGHWAY | 10, 12 | CHARLOTTE REGIONAL TPO | I-4750AB | NOT FUNDED | NHP | NOT FUNDED | 10500000 | NOT FUNDED | 675000 | NOT FUNDED | 133000000 |  |  | 144175000
IREDELL, MECKLENBURG | ICATS INTERCOUNTY EXPRESS BUS | PURCHASE 3 OVER-THE-ROAD COACH BUSES AND 5 SETS OF BUS STOP SHELTERS TO EXPAND INTERCOUNTY SERVICE BETWEEN STATESVILLE, TROUTMAN, MOORESVILLE, AND CATS ROUTES BETWEEN HUNTERSVILLE AND CHARLOTTE. | PUBLIC TRANSIT | 10, 12 | CHARLOTTE REGIONAL TPO | TA-6713 | REGION E, F | T |  |  |  |  | 2021 | 1000000 |  |  | 1000000
JACKSON | SR 1432 (SKYLAND DRIVE) | SR 1429 (CHIPPER CURVE ROAD) TO US 23 BUSINESS. CONSTRUCT SIDEWALK. | BIKE/PED | 14 | SOUTHWESTERN RPO | EB-5923 | DIVISION 14 | L, TALT5 |  |  |  |  | 2023 | 960000 |  |  | 960000 | RIGHT-OF-WAY IN PROGRESS
JACKSON | SR 1737 (CANEY FORK ROAD), SR 1432 (SKYLAND DRIVE) | CONSTRUCT BICYCLE PULLOUTS AT STRATEGIC LOCATIONS. | BIKE/PED | 14 | SOUTHWESTERN RPO | BF-0001 | EXEMPT | FLAP, S(M) |  |  |  |  | 2022 | 190000 | 2022 | 10000 | 200000 | FLAP PROJECT ID: NC 49. AWARD AMOUNT = $200,000. STATE MATCH ARE HIGHWAY FUNDS.
JACKSON | NC 107 | SR 1002 TO NC 281. UPGRADE EXISTING ROADWAY. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-4753 | DIVISION 14 | [10 empty] | UNDER CONSTRUCTION
JACKSON | NC 107 | 500 FEET SOUTH OF SR 1135 (SHOOK COVE ROAD) TO APPROXIMATELY 1 MILE NORTH OF SR 1157 (PINE CREEK ROAD). WIDEN PAVEMENT TO 24 FEET WITH 5 FEET PAVED SHOULDERS. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5841
JACKSON | NC 107 | 500 FEET SOUTH OF SR 1135 (SHOOK COVE ROAD) TO 1000 FEET NORTH OF THE LAKE TUCKASEEGEE DAM. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5841A | DIVISION 14 | T | 2028 | 2600000 | 2028 | 200000 | 2030 | 17899000 |  |  | 20699000
JACKSON | NC 107 | 1000 FEET NORTH OF THE LAKE TUCKASEEGEE DAM TO APPROXIMATELY 1 MILE NORTH OF SR 1157 (PINE CREEK ROAD). | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5841B | NOT FUNDED | T | NOT FUNDED | 6400000 | NOT FUNDED | 300000 | NOT FUNDED | 102800000 |  |  | 109500000
JACKSON | NC 107 (US 23 BUSINESS) | NC 116 TO US 23 BUSINESS. US 23 BUSINESS, SR 1432 (SKYLAND DRIVE) TO MUNICIPAL DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5600 | REGION G | T | 2022 | 58440000 | 2022 | 7200000 | 2025 | 56199000 |  |  | 121839000 | BUILD NC BOND FUNDING: $20M FOR RIGHT OF WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE).
JACKSON | SR 1120 (CEDAR CREEK ROAD) | REPLACE BRIDGE 490008 CEDAR CREEK. | HIGHWAY | 14 | SOUTHWESTERN RPO | B-5921 | DIVISION 14 | BGOFF | 2023 | 20000 |  |  | 2024 | 400000 |  |  | 420000
JACKSON | SR 1157 (CULLOWHEE MOUNTAIN ROAD) | INSTALL GUARDRAIL FROM MILEPOST 2.6 TO 6.6, NEAR CULLOWHEE. | HIGHWAY | 14 | SOUTHWESTERN RPO | HS-2014B | DIVISION 14 | HSIP |  |  |  |  | 2022 | 140000 |  |  | 140000
JACKSON | SR 1300 (PUMPKINTOWN ROAD) | REPLACE BRIDGE 490069 OVER SAVANNAH CREEK. | HIGHWAY | 14 | SOUTHWESTERN RPO | B-6031 | DIVISION 14 | BGOFF | 2024 | 80000 |  |  | 2025 | 800000 |  |  | 880000
JACKSON | SR 1300 (PUMPKINTOWN ROAD) | REPLACE BRIDGE 490065 OVER SAVANNAH CREEK. | HIGHWAY | 14 | SOUTHWESTERN RPO | B-6034 | DIVISION 14 | BGOFF | 2024 | 80000 |  |  | 2025 | 800000 |  |  | 880000
JACKSON | SR 1325 (CENTENNIAL DRIVE) | INSTALL RECTANGULAR RAPID FLASHING BEACONS (RRFB) AT THREE MIDBLOCK CROSSINGS NEAR SR 1169 (CENTRAL DRIVE). | HIGHWAY | 14 | SOUTHWESTERN RPO | HS-2014D | DIVISION 14 | HSIP |  |  |  |  | 2022 | 59000 |  |  | 59000
JACKSON | SR 1397 (THOMAS VALLEY ROAD) | REPLACE BRIDGE 490144 OVER NATIONS CREEK. | HIGHWAY | 14 | SOUTHWESTERN RPO | B-6032 | DIVISION 14 | BGOFF | 2021 | 50000 |  |  | 2022 | 500000 |  |  | 550000
JACKSON | SR 1445 (LEE BUMGARNER ROAD) | REPLACE BRIDGE 490129 OVER SCOTT CREEK. | HIGHWAY | 14 | SOUTHWESTERN RPO | B-6033 | DIVISION 14 | BGOFF |  |  |  |  | 2026 | 1200000 |  |  | 1200000 | RIGHT-OF-WAY IN PROGRESS
JACKSON | SR 1737 (CANEY FORK ROAD) | REPLACE BRIDGE 490081 OVER JOHNS CREEK. | HIGHWAY | 14 | SOUTHWESTERN RPO | B-6036 | DIVISION 14 | BGOFF | 2023 | 70000 |  |  | 2025 | 700000 |  |  | 770000
JACKSON | SR 1738 (HOOPER CEMETERY ROAD) | REPLACE BRIDGE 490203 OVER CANEY FORK. | HIGHWAY | 14 | SOUTHWESTERN RPO | B-6035 | DIVISION 14 | BGOFF | 2021 | 70000 |  |  | 2022 | 700000 |  |  | 770000
JACKSON | US 64 | CASHIERS TO JACKSON-TRANSYLVANIA COUNTY LINE | HIGHWAY | 14 | SOUTHWESTERN RPO | R-2409A | [11 empty] | COMPLETE
JACKSON | US 64 | 1.1 MILES EAST OF CASHIERS TO 1.6 MILES EAST OF CASHIERS | HIGHWAY | 14 | SOUTHWESTERN RPO | R-2409B | [11 empty] | COMPLETE
JACKSON | US 64 | NC 107 INTERSECTION. IMPROVE INTERSECTION AND ADD AUXILLARY LANE FROM PEBBLE CREEK DRIVE TO US 64/NC 107 INTERSECTION. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5881 | NOT FUNDED | T | NOT FUNDED | 14900000 | NOT FUNDED | 800000 | NOT FUNDED | 6700000 |  |  | 22400000
JACKSON | US 74 (GREAT SMOKEY MOUNTAINS EXPRESSWAY) | US 441 GATEWAY INTERCHANGE TO SR 1391 (WEST PINEY MOUNTAIN ROAD). MODERNIZE ROADWAY, INCLUDING REPLACEMENT OF BRIDGE 490043 OVER THE TUCKASEGEE RIVER. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5907 | DIVISION 14 | BGLT5 | 2028 | 3500000 | 2028 | 200000 | 2030 | 19900000 |  |  | 23600000
JACKSON | JACKSON COUNTY | ADMINISTRATION | PUBLIC TRANSIT | 14 | SOUTHWESTERN RPO | TK-6137 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 752000 | 752000 | FUNDS AUTHORIZED IN PROGRESS
JACKSON, SWAIN | VARIOUS | INDIAN RESERVATION ROAD (IRR) PROGRAM. ROAD AND BRIDGE IMPROVEMENTS TO BE CONSTRUCTED BY EASTERN BAND OF CHEROKEE INDIANS. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5500 | EXEMPT | [10 empty] | PROGRAM IN PROGRESS
JOHNSTON | JOHNSTON COUNTY AIRPORT (JNX) | LAND ACQUISITION & CLEARING PROJECT. | AVIATION | 4 | UPPER COASTAL PLAIN RPO | AV-5745 | DIVISION 4 | T |  |  |  |  | 2023 | 335000 |  |  | 335000
JOHNSTON | EAST CLAYTON CONNECTOR GREENWAY | SR 2851 (EAST FRONT STREET) TO SR 1902 (GLEN LAUREL ROAD). CONSTRUCT GREENWAY. | BIKE/PED | 4 | CAPITAL AREA MPO | EB-6016 | DIVISION 4 | L, TAANY | 2027 | 10000 |  |  | 2028 | 1242000 | 2026 | 258000 | 1510000
JOHNSTON | MOUNTAINS TO SEA TRAIL | FOX RIDGE ROAD TO NEUSE RIVER BRIDGE. CONSTRUCT GREENWAY. | BIKE/PED | 4 | CAPITAL AREA MPO | EB-6017 | DIVISION 4 | L, TAANY |  |  |  |  | 2028 | 414000 | 2026 | 83000 | 497000
JOHNSTON | CLAYTON | CLAYTON SIGNAL SYSTEM. | HIGHWAY | 4 | CAPITAL AREA MPO | U-5943 | REGION A | BGANY | 2023 | 100000 | 2023 | 198000 | 2025 | 2834000 |  |  | 3132000
JOHNSTON | I-40 | ACCESS IMPROVEMENTS IN THE VICINITY OF EXISTING I-40/NC 42 INTERCHANGE (EXIT 312). | HIGHWAY | 4 | CAPITAL AREA MPO | I-4739 | STATEWIDE MOBILITY | NHP | 2019 | 19305000 |  |  | 2018 | 40137000 |  |  | 59442000 | UNDER CONSTRUCTION - DESIGN BUILD PROJECT - COORDINATE WITH I-5111. GARVEE BOND FUNDING: $15M; PAYBACK FY 2019 - 2033 FOR ROW.
JOHNSTON | I-40 | WAKE COUNTY LINE TO NC 42. | HIGHWAY | 4 | CAPITAL AREA MPO | I-5111REG | REGION A | NHP | 2019 | 3479000 |  |  | 2018 | 23795000 |  |  | 27274000 | UNDER CONSTRUCTION - DESIGN-BUILD PROJECT; GARVEE BONDS: $15 MILLION FOR RIGHT OF WAY - PAYBACK 2019-2033
JOHNSTON | I-40 | SR 1010 (CLEVELAND ROAD) (MILE MARKER 312.2) TO WEST OF SR 1211 (MORGAN ROAD) (MILE MARKER 328.5). PAVEMENT REHABILITATION. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | I-5781 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION - NATIONAL HIGHWAY FREIGHT PROGRAM PROJECT
JOHNSTON | I-95 | REPLACE BRIDGES 118 AND 119 OVER THE CSX RAILROAD ON I-95. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | B-4937 | STATEWIDE MOBILITY | BFP |  |  |  |  | 2025 | 9600000 |  |  | 9600000
JOHNSTON | I-95 | REPLACE BRIDGES 500082 AND 500085 OVER BLACK CREEK AND BRIDGES 500100 AND 500101 OVER THE NEUSE RIVER. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | B-6044 | STATEWIDE MOBILITY | BFP | 2023 | 4880000 |  |  | 2025 | 28800000 |  |  | 33680000
JOHNSTON | I-95 | I-95 FROM MILE MARKER 97 TO MILE MARKER 101. PAVEMENT REHABILITATION. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | HI-0008 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2022 | 7230000 |  |  | 7230000
JOHNSTON | I-95 | US 70 (EXIT 97) TO US 301 (EXIT 107). PAVEMENT AND BRIDGE REHABILITATION. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | I-3318
JOHNSTON | I-95 | US 70 (EXIT 97) TO NORTH OF SR 1001 (MILE MARKER 100). | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | I-3318A | [11 empty] | COMPLETE
JOHNSTON | I-95 | REPLACE BRIDGE NO. 114 AND BRIDGE NO. 116 AND APPROACHES OVER LITTLE RIVER. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | I-3318BB | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
JOHNSTON | I-95 | SOUTH OF SR 1001 (LIZZIE MILL ROAD) TO THE JOHNSTON/WILSON COUNTY LINE NORTH OF NC 222. PAVEMENT REHABILITATION. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | I-5786 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
JOHNSTON | I-95 | REPLACE BRIDGE NUMBER 117 ON SR 2399 (TRUCK STOP ROAD) OVER I-95 AND ADJUST SERVICE ROADS AND APPROACHES. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | I-5786A | STATEWIDE MOBILITY
JOHNSTON | I-95 | US 70 BUSINESS. UPGRADE INTERCHANGE. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | I-5972 | REGION A | NHFP, NHP |  |  |  |  | 2024 | 32100000 |  |  | 32100000 | RIGHT-OF-WAY IN PROGRESS
JOHNSTON | I-95 | US 701/NC 96. CONSTRUCT INTERCHANGE. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | I-5974 | REGION A | NHP | 2026 | 5096000 | 2026 | 2026000 | 2028 | 48399000 |  |  | 55521000
JOHNSTON | I-95 | HARNETT COUNTY LINE (MILE MARKER 78) TO SR 1927 (PINE LEVEL-SELMA ROAD - MILE MARKER 98). UPGRADE GUARDRAIL AND MEDIAN DRAINAGE. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | I-6043 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
JOHNSTON | I-95 | SR 1007 (BROGDEN ROAD). IMPROVE INTERCHANGE. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | I-6061 | DIVISION 4 | T | 2027 | 1300000 | 2027 | 1900000 | 2029 | 17200000 |  |  | 20400000
JOHNSTON | I-95 | SR 2339 (BAGLEY ROAD). IMPROVE INTERCHANGE. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | I-6062 | DIVISION 4 | T | 2027 | 3600000 | 2027 | 1300000 | 2029 | 19000000 |  |  | 23900000
JOHNSTON | KELLIE DRIVE | NORTH OF SR 1923 (BOOKER DAIRY ROAD) TO SR 1003 (BUFFALO ROAD). CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | U-5999 | DIVISION 4 | [10 empty] | UNDER CONSTRUCTION
JOHNSTON | NC 210 | NC 50 TO SR 1330 (RALEIGH ROAD). UPGRADE TO SUPERSTREET. | HIGHWAY | 4 | CAPITAL AREA MPO | U-6203 | DIVISION 4 | T | 2026 | 28964000 | 2026 | 4360000 | 2028 | 45201000 |  |  | 78525000
JOHNSTON | NC 242 | CURVE IMPROVEMENTS BETWEEN 0.08 MILES AND 0.31 MILES NORTH OF SR 1116 (GODWIN LAKE ROAD). | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | HS-2004L | DIVISION 4 | HSIP | 2022 | 272000 |  |  | 2023 | 555000 |  |  | 827000
JOHNSTON | NC 242 | SR 1168 (TARHEEL ROAD) TO I-40. WIDEN ROADWAY. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | R-5761 | DIVISION 4 | T | 2027 | 2200000 | 2027 | 500000 | 2029 | 13300000 |  |  | 16000000
JOHNSTON | NC 42 | NC 50 TO US 70 BUSINESS. WIDEN TO MULTI-LANES. | HIGHWAY | 4 | CAPITAL AREA MPO | R-3410 | REGION A | BGANY | 2027 | 14696000 | 2027 | 19600000 | 2029 | 74201000 |  |  | 108497000
JOHNSTON | NC 42 | US 70 TO SR 1003 (BUFFALO ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 4 | CAPITAL AREA MPO | R-3825
JOHNSTON | NC 42 | US 70 AT CLAYTON TO EAST OF SR 1902 (GLEN LAUREL ROAD). | HIGHWAY | 4 | CAPITAL AREA MPO | R-3825A | [11 empty] | COMPLETE
JOHNSTON | NC 42 | EAST OF SR 1902 (GLEN LAUREL ROAD) TO SR 1003 (BUFFALOE ROAD). | HIGHWAY | 4 | CAPITAL AREA MPO | R-3825B | DIVISION 4 | T |  |  |  |  | 2019 | 68448000 |  |  | 68448000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $16,239,286.10 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $17,683,202 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE).
JOHNSTON | NC 42 | SR 1003 (BUFFALO ROAD) TO WILSON COUNTY LINE. MODERNIZE ROADWAY. | HIGHWAY | 4 | CAPITAL AREA MPO, UPPER COASTAL PLAIN RPO | U-5998 | DIVISION 4 | T | 2025 | 3400000 | 2025 | 3000000 | 2027 | 14800000 |  |  | 21200000
JOHNSTON | NEW ROUTE | SR 1010 (CLEVELAND ROAD) TO NC 42. CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | 4 | CAPITAL AREA MPO | U-6208 | DIVISION 4 | T | 2027 | 3000000 | 2027 | 10000000 | 2029 | 14500000 |  |  | 27500000
JOHNSTON | SR 1003 (BUFFALO ROAD) | US 70 TO SR 1934 (OLD BEULAH ROAD). WIDEN TO THREE LANES. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | R-5718 | DIVISION 4 | BG5200, T | 2022 | 6937000 | 2022 | 1190000 | 2025 | 14300000 |  |  | 22427000 | RIGHT-OF-WAY IN PROGRESS.
JOHNSTON | SR 1004 (EAST MAIN STREET) | SECOND STREET TO US 70 BUSINESS / NC 42 IN CLAYTON. COMPLETE SIDEWALK GAP AND INCLUDE CROSSING IMPROVEMENTS. | HIGHWAY | 4 | CAPITAL AREA MPO | BL-0050 | EXEMPT | CMAQ, L | 2023 | 200000 |  |  | 2023 | 450000 |  |  | 650000
JOHNSTON | SR 1010 (CLEVELAND ROAD) | NC 42 TO SR 1555 (BARBER MILL ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 4 | CAPITAL AREA MPO | U-6216 | DIVISION 4 | T | 2027 | 35700000 | 2027 | 14900000 | 2029 | 42000000 |  |  | 92600000
JOHNSTON | SR 1153 (MILL CREEK ROAD) | REPLACE BRIDGE 500068 OVER JUNIPER SWAMP. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | B-6001 | DIVISION 4 | BGOFF |  |  |  |  | 2021 | 1015000 |  |  | 1015000 | RIGHT-OF-WAY IN PROGRESS
JOHNSTON | SR 1399 (ZACK'S MILL ROAD) | REPLACE BRIDGE 500277 OVER POLECAT BRANCH. | HIGHWAY | 4 | CAPITAL AREA MPO | B-5997 | DIVISION 4 | [10 empty] | UNDER CONSTRUCTION
JOHNSTON | SR 1501 (SWIFT CREEK ROAD) | AIRPORT INDUSTRIAL DRIVE TO DRIVEWAY JUST NORTH OF JOHNSTON COUNTY AIRPORT. WIDEN ROADWAY. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | R-5950 | DIVISION 4 | T | 2027 | 1400000 | 2027 | 200000 | 2029 | 2900000 |  |  | 4500000
JOHNSTON | SR 1524 (OLD DRUG STORE ROAD) | IMPROVE SUPERELEVATION IN CURVE ON SR 1524 (OLD DRUG STORE ROAD) SOUTH OF SR 1525 (CORNWALLIS ROAD). INSTALL SIGNAL AT INTERSECTION OF SR 1524 (OLD DRUG STORE ROAD) AND SR 1525 (CORNWALLIS ROAD). | HIGHWAY | 4 | CAPITAL AREA MPO | W-5204E | DIVISION 4 | HSIP | 2023 | 200000 |  |  | 2023 | 650000 |  |  | 850000
JOHNSTON | SR 1555 (BARBOUR MILL ROAD) | REPLACE BRIDGE 500145 OVER SWIFT CREEK. | HIGHWAY | 4 | CAPITAL AREA MPO | B-5664 | DIVISION 4 | [10 empty] | UNDER CONSTRUCTION
JOHNSTON | SR 1560 (RANCH ROAD EXTENSION) | US 70 BUSINESS/NC 42 TO SR 1560 (RANCH ROAD) IN CLAYTON. NEW LOCATION EXTENSION OF RANCH ROAD. | HIGHWAY | 4 | CAPITAL AREA MPO | U-6223 | DIVISION 4 | BGDA, S | 2021 | 3400000 | 2021 | 600000 | 2022 | 6249000 |  |  | 10249000 | RIGHT-OF-WAY IN PROGRESS. “S” FUNDING REFLECTS LEGISLATIVE CONTINGENCY FUNDS.
JOHNSTON | SR 1923 (BOOKER DAIRY ROAD EXTENSION) | US 70 BUSINESS WEST OF SMITHFIELD TO US 301 (BRIGHT LEAF BOULEVARD) IN SMITHFIELD. WIDEN TO MULTI-LANES. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | U-3334 | DIVISION 4
JOHNSTON | SR 1923 (BOOKER DAIRY ROAD) EXTENSION | US 70 BUSINESS TO SR 1003 (BUFFALO ROAD). | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | U-3334A | [11 empty] | COMPLETE
JOHNSTON | SR 1923 (BOOKER DAIRY ROAD) EXTENSION | SR 1003 (BUFFALO ROAD) TO US 301 (BRIGHTLEAF BOULEVARD). | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | U-3334B | DIVISION 4 | [10 empty] | UNDER CONSTRUCTION
JOHNSTON | SR 2137 (PITTMAN ROAD) SR 2130 (E MAIN STREET) SR | REPLACE BRIDGE 500109 ON SR 2137 (PITTMAN ROAD) OVER I-95, BRIDGE 500110 ON SR 2130 (EAST MAIN STREET) OVER I-95, AND BRIDGE 500112 ON SR 2339 (BAGLEY ROAD) OVER I-95. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | B-6050 | DIVISION 4 | BFP | 2024 | 1500000 |  |  | 2027 | 15000000 |  |  | 16500000
JOHNSTON | SR 2143 (BEULAHTOWN ROAD) | REPLACE BRIDGE 500216 OVER LITTLE BUFFALO CREEK. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | B-4562 | DIVISION 4 | [10 empty] | UNDER CONSTRUCTION - DESIGN BUILD PROJECT
JOHNSTON | SR 2302 (RICKS ROAD) | US 70 TO US 301. WIDEN TO THREE LANES. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | U-5795 | DIVISION 4 | [10 empty] | UNDER CONSTRUCTION
JOHNSTON | US 301 (BRIGHTLEAF BOULEVARD) | US 301 (BRIGHTLEAF BOULEVARD) AT NORTH STREET IN SMITHFIELD. INSTALL / UPGRADE HIGH VISIBILITY CROSSWALKS, AUDIBLE COUNTDOWN PEDESTRIAN SIGNAL HEADS, PEDESTRIAN IMPROVEMENTS, TRAFFIC SIGNAL, AND TRAFFIC SIGNAL SYSTEM. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | HS-2004P | REGION A | HSIP |  |  |  |  | 2023 | 70000 |  |  | 70000
JOHNSTON | US 301/NC 39/NC 96 | SR 1623 (BOOKER DAIRY ROAD) TO SR 2302 (RICKS ROAD). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | U-5726 | DIVISION 4 | T | 2025 | 11200000 | 2025 | 1400000 | 2027 | 14600000 |  |  | 27200000
JOHNSTON | US 70 | US 301 TO I-95. ACCESS MANAGEMENT. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | R-5795 | REGION A | T | 2027 | 4631000 | 2027 | 4400000 | 2029 | 11700000 |  |  | 20731000
JOHNSTON | US 70 | WEST OF SR 2372 (EDWARDS ROAD / NORTH PEARL STREET) TO EAST OF SR 2314 (PONDFIELD ROAD). UPGRADE TO FREEWAY STANDARDS. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | R-5829B | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 13076000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4774000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 71903000 |  |  | 89753000
JOHNSTON | US 70 | US 70 BUSINESS TO NEUSE RIVER BRIDGE. CONVERT TO FREEWAY WITH INTERCHANGES AT SR 1501 (SWIFT CREEK ROAD) AND SR 1919 (WILSON'S MILLS ROAD). | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | W-5600 | REGION A | NHP |  |  |  |  | 2021 | 67695000 |  |  | 67695000
JOHNSTON | US 70 (FUTURE I-42) | SR 1003 (BUFFALO ROAD) TO WAYNE COUNTY LINE. PAVEMENT REHABILITATION. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | I-6044 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2019 | 6090000 |  |  | 6090000 | UNDER CONSTRUCTION. GARVEE BOND FUNDING $5,075,132; PAYBACK FY 2019-2033.
JOHNSTON | JOHNSTON COUNTY | PURCHASE EXPANSION VEHICLES. | PUBLIC TRANSIT | 4 | UPPER COASTAL PLAIN RPO, CAPITAL AREA MPO | TA-6720 | DIVISION 4 | 5311, L, T |  |  |  |  | 2026 | 330000 |  |  | 330000
JOHNSTON | JOHNSTON COUNTY COUNCIL ON AGING, INC. | ADMINISTRATION | PUBLIC TRANSIT | 4 | UPPER COASTAL PLAIN RPO | TK-6138 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 1176000 | 1176000 | FUNDS AUTHORIZED IN PROGRESS
JOHNSTON | NS/NCRR H LINE | CONSTRUCT GRADE SEPARATION AT SR 1553 (SHOTWELL ROAD). CLOSE EXISTING AT-GRADE CROSSING IN CLAYTON. | RAIL | 4 | CAPITAL AREA MPO | P-5743 | NOT FUNDED | O, T | NOT FUNDED | 3000000 |  |  | NOT FUNDED | 11100000 |  |  | 14100000 | OTHER FUNDS PROVIDED BY NS.
JOHNSTON | SR 1100 (CHICOPEE ROAD) | INSTALLATION OF ACTIVE WARNING DEVICES AT CSX CROSSING 629742K NEAR BENSON. | RAIL | 4 | UPPER COASTAL PLAIN RPO | RX-2004B | DIVISION 4 | RR |  |  |  |  | 2023 | 800000 |  |  | 800000
JOHNSTON | SR 1357 (GILBERT ROAD) | INSTALLATION OF ACTIVE WARNING DEVICES AT CSX CROSSING 629731X NEAR BENSON. | RAIL | 4 | UPPER COASTAL PLAIN RPO | RX-2004C | DIVISION 4 | RR |  |  |  |  | 2023 | 800000 |  |  | 800000
JOHNSTON, EDGECOMBE, NASH | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE UPPER COASTAL PLAIN RPO. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | C-5619 | EXEMPT | CMAQ, L | 2020 | 420000 |  |  | 2020 | 2495000 | 2020 | 1260000 | 4175000
JOHNSTON, WAKE | US 70 BUSINESS | GREENFIELD PARKWAY TO NC 42. UPGRADE ROADWAY TO SUPERSTREET. | HIGHWAY | 4, 5 | CAPITAL AREA MPO | U-6113 | NOT FUNDED | T | NOT FUNDED | 7600000 | NOT FUNDED | 1500000 | NOT FUNDED | 83200000 |  |  | 92300000
JOHNSTON, WAKE | VARIOUS | BUS RAPID TRANSIT SERVICE, GARNER TO CLAYTON. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | PUBLIC TRANSIT | 4, 5 | CAPITAL AREA MPO | TO-6166D | REGION A, C | L, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 21993000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6114000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 115650000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1500000 | 145257000
JOHNSTON, WILSON | VARIOUS | DIVISION 4 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | 4 | CAPITAL AREA MPO, UPPER COASTAL PLAIN RPO | W-5204DIV | DIVISION 4
JOHNSTON, WILSON | VARIOUS | DIVISION 4 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | 4 | CAPITAL AREA MPO, UPPER COASTAL PLAIN RPO | W-5204REG | REGION A
JONES | SR 1142 (WEYERHAEUSER ROAD) | REPLACE BRIDGE 510032 OVER TUCKAHOE SWAMP. | HIGHWAY | 2 | DOWN EAST RPO | B-5994 | DIVISION 2 | [10 empty] | UNDER CONSTRUCTION
JONES | US 17 | NORTH OF MAYSVILLE TO SOUTH OF NC 58. | HIGHWAY | 2 | DOWN EAST RPO | R-2514C | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
JONES | US 17 | SOUTH OF NC 58 TO THE NEW BERN BYPASS. | HIGHWAY | 2 | DOWN EAST RPO | R-2514D | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
JONES | US 70 (FUTURE I-42) | EAST OF SR 1002 (WYSE FORK ROAD) TO EXISTING FREEWAY NEAR DOVER. | HIGHWAY | 2 | DOWN EAST RPO | R-2553E | NOT FUNDED | T | NOT FUNDED | 6805000 | NOT FUNDED | 1756000 | NOT FUNDED | 53000000 |  |  | 61561000
JONES, LENOIR | US 70 (FUTURE I-42) | EAST OF NC 58 TO EAST OF SR 1002 (WYSE FORK ROAD). | HIGHWAY | 2 | DOWN EAST RPO, EASTERN CAROLINA RPO | R-2553D | NOT FUNDED | T | NOT FUNDED | 14731000 | NOT FUNDED | 1964000 | NOT FUNDED | 60000000 |  |  | 76695000
JONES, ONSLOW | US 17 | MULTI-LANES NORTH OF JACKSONVILLE TO NEW BERN BYPASS. WIDEN TO MULTI-LANES WITH BYPASSES OF BELGRADE, MAYSVILLE AND POLLOCKSVILLE ON NEW LOCATION. | HIGHWAY | 2, 3 | DOWN EAST RPO, JACKSONVILLE URBAN AREA MPO | R-2514
LEE | RALEIGH EXECUTIVE JETPORT (TTA) | RUNWAY 21 AND RUNWAY 3 BYPASS TAXIWAY. CONSTRUCT AIRPLANE RUN-UP LANE AT EACH END OF TAXIWAY. | AVIATION | 8 | TRIANGLE AREA RPO | AV-5899 | DIVISION 8 | T |  |  |  |  | 2024 | 1400000 |  |  | 1400000
LEE | RALEIGH EXECUTIVE SANFORD - LEE COUNTY AIRPORT (TT | CONSTRUCT CORPORATE AREA APRON PHASE I. | AVIATION | 8 | TRIANGLE AREA RPO | AV-5762 | DIVISION 8 | [10 empty] | UNDER CONSTRUCTION; INCLUDES $1.5 M IN ECONOMIC DEVELOPMENT FUNDING
LEE | MCIVER STREET | MOORE STREET TO OAKWOOD AVENUE IN SANFORD. CONSTRUCT SIDEWALKS. | BIKE/PED | 8 | TRIANGLE AREA RPO | EB-6003 | NOT FUNDED | L, TA5200 |  |  |  |  | NOT FUNDED | 864000 | NOT FUNDED | 128000 | 992000
LEE | NC 42 (WICKER STREET) | LEGION DRIVE TO NORTH OF HIGH RIDGE DRIVE AT KIWANIS FAMILY PARK IN SANFORD. CONSTRUCT MULTIUSE PATH. | BIKE/PED | 8 | TRIANGLE AREA RPO | EB-5742 | DIVISION 8 | L, TA5200 |  |  |  |  | 2024 | 1011000 | 2022 | 77000 | 1088000 | PLANNING / DESIGN / RIGHT OF WAY / CONSTRUCTION BY CITY OF SANFORD - IN PROGRESS
LEE | SR 1002 (CHARLOTTE AVENUE) | CHATHAM STREET TO SR 1002 (11TH STREET) IN SANFORD. CONSTRUCT SIDEWALKS AND IMPLEMENT ROAD DIET WITH BICYCLE LANES. | BIKE/PED | 8 | TRIANGLE AREA RPO | EB-6002 | DIVISION 8 | L, TA5200 |  |  |  |  | 2025 | 1285000 | 2023 | 191000 | 1476000
LEE | SR 1107 (FIELDS DRIVE) | SR 1237 (CARTHAGE STREET) TO US 421 BUSINESS (HORNER BOULEVARD) IN SANFORD. CONSTRUCT SIDEWALK. | BIKE/PED | 8 | TRIANGLE AREA RPO | EB-5867 | DIVISION 8 | L, TA5200 | 2023 | 102000 | 2023 | 90000 | 2024 | 1015000 | 2022 | 149000 | 1356000
LEE | SR 1579 (SOUTH MAIN STREET) | SR 1531 (MANSFIELD DRIVE) TO END OF EXISTING SIDEWALK IN BROADWAY. CONSTRUCT SIDEWALK. | BIKE/PED | 8 | TRIANGLE AREA RPO | EB-5870 | DIVISION 8 | L, TALT5 |  |  |  |  | 2023 | 86000 |  |  | 86000
LEE | US 1 BUSINESS (CARTHAGE STREET) | NC 42 (WICKER STREET) TO CHATHAM STREET IN SANFORD. REDUCE NUMBER OF LANES AND CONSTRUCT BICYCLE / PEDESTRIAN ACCOMMODATIONS. | BIKE/PED | 8 | TRIANGLE AREA RPO | EB-5863 | DIVISION 8 | L, TA5200 | 2023 | 150000 |  |  | 2024 | 1469000 | 2022 | 295000 | 1914000
LEE | WOODLAND STREET | EVERGREEN LANE TO GLOBE STREET IN SANFORD. CONSTRUCT SIDEWALK. | BIKE/PED | 8 | TRIANGLE AREA RPO | EB-5868 | DIVISION 8 | L, TA5200 | 2023 | 111000 | 2023 | 100000 | 2024 | 1105000 | 2021 | 116000 | 1432000
LEE | NC 42 | RAILROAD MITIGATION | HIGHWAY | 8 | TRIANGLE AREA RPO | R-3830A | DIVISION 8 | T |  |  |  |  | 2021 | 1900000 |  |  | 1900000 | UNDER CONSTRUCTION
LEE | NC 42; SR 1579 (BROADWAY ROAD / NORTH MAIN STREET | NC 42, US 421 (HORNER BOULEVARD) IN SANFORD TO SR 1579 (BROADWAY ROAD) AND SR 1579 (BROADWAY ROAD / NORTH MAIN STREET), NC 42 (AVENTS FERRY ROAD) TO SR 1538 (EAST HARRINGTON AVENUE) IN BROADWAY. WIDEN TO MULTILANES. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-3830 | DIVISION 8 | T | 2019 | 10228000 |  |  | 2023 | 45870000 |  |  | 56098000 | UNDER CONSTRUCTION; BUILD NC BONDS: $7.947 MILLION RIGHT-OF-WAY AND UTILITIES - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), AND $10 MILLION FOR CONSTRUCTION - PAYBACK 2023-2036 (FY 2022 / YR 4 SALE)
LEE | NEW ROUTE | SR 1133 (LEE AVENUE) TO EXISTING COMMERCE DRIVE IN SANFORD. CONSTRUCT 2-LANE EXTENSION OF COMMERCE DRIVE. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5960 | DIVISION 8 | T | 2028 | 138000 | 2028 | 104000 | 2030 | 6500000 |  |  | 6742000
LEE | SR 1237 (CARTHAGE STREET) | SR 1152 (FIRE TOWER ROAD) TO NC 42 (WICKER STREET) IN SANFORD. WIDEN ROADWAY. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5709 | DIVISION 8 | T | 2022 | 3000000 | 2022 | 1700000 | 2024 | 13199000 |  |  | 17899000
LEE | SR 1400 (CUMNOCK ROAD) | REPLACE BRIDGE 520069 AND BRIDGE 520070 OVER NORFOLK SOUTHERN RAILROAD. | HIGHWAY | 8 | TRIANGLE AREA RPO | B-5976 | DIVISION 8 | BGOFF | 2024 | 196000 |  |  | 2025 | 3934000 |  |  | 4130000
LEE | SR 1521 (KELLY DRIVE) | SR 1519 (NASH STREET) TO NORTHEAST OF CENTRAL CAROLINA COMMUNITY COLLEGE. CONSTRUCT 3-LANE REALIGNMENT OF KELLY DRIVE. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5959 | DIVISION 8 | T | 2023 | 1900000 | 2023 | 700000 | 2025 | 7300000 |  |  | 9900000
LEE | US 1 / US 15 / US 501 | SOUTH OF SR 1198 (BRYAN DRIVE) TO SR 1237 (CARTHAGE STREET) IN SANFORD. UPGRADE TO SUPERSTREET AND RELOCATE NC 78 (TRAMWAY ROAD). | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5727 | REGION E | NHP, T | 2023 | 12000000 | 2023 | 900000 | 2026 | 17300000 |  |  | 30200000 | COORDINATE WITH U-5975
LEE | US 1 / US 15 / US 501 | US 15 / US 501 (WHITE HILL ROAD) / SR 1179 (ROCKY FORK CHURCH ROAD) TO SOUTH OF SR 1198 (BRYAN DRIVE). UPGRADE TO SUPERSTREET. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5975 | REGION E | T | 2023 | 4100000 | 2023 | 2800000 | 2026 | 13900000 |  |  | 20800000 | COORDINATE WITH U-5727
LEE | US 421 BUSINESS / NC 87 | US 1 / US 15 / US 501 TO FORMER ATLANTIC COAST LINE RAILROAD CROSSING EAST OF WASHINGTON AVENUE IN SANFORD. RECONSTRUCT AS A "COMPLETE STREET" WITH IMPROVEMENTS SUCH AS MEDIANS, SIDEWALKS, BICYCLE FACILITIES, AND STREETSCAPING. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5722 | REGION E | T | 2027 | 24700000 | 2027 | 7564000 | 2030 | 15099000 |  |  | 47363000
LEE | LEE COUNTY | ADMINISTRATION | PUBLIC TRANSIT | 8 | TRIANGLE AREA RPO | TK-6140 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 632000 | 632000 | FUNDS AUTHORIZED IN PROGRESS
LENOIR | NC 11 | NC 11 AT SR 1716 (HARVEY ROUSE ROAD), NC 11 AT NC 118/SR 1091 (GRIFTON-HUGO ROAD), AND NC 11 AT SR 1714 (CREEK ROAD). CONVERT MEDIAN OPENINGS TO REDUCED CONFLICT INTERSECTIONS. | HIGHWAY | 2 | EASTERN CAROLINA RPO | HS-2002K | DIVISION 2 | HSIP |  |  | 2023 | 80000 | 2023 | 846000 |  |  | 926000
LENOIR | NC 148 (CF HARVEY PARKWAY) | NC 58 TO NC 11. CONSTRUCT MULTI-LANE FACILITY ON NEW LOCATION. | HIGHWAY | 2 | EASTERN CAROLINA RPO | R-5703 | REGION B | T |  |  |  |  | 2018 | 74609000 |  |  | 74609000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $35,950,590 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE)
LENOIR | NC 903 | REPLACE BRIDGE 45 OVER THE NEUSE RIVER ON NC 903. | HIGHWAY | 2 | EASTERN CAROLINA RPO | B-4566 | REGION B | BFP |  |  |  |  | 2025 | 6500000 |  |  | 6500000
LENOIR | SR 1389 (HARDY BRIDGE ROAD) | REPLACE BRIDGE 530052 OVER NEUSE RIVER AND 530152 OVER NEUSE RIVER OVERFLOW. | HIGHWAY | 2 | EASTERN CAROLINA RPO | B-5619 | DIVISION 2 | BGOFF | 2020 | 500000 |  |  | 2021 | 9170000 |  |  | 9670000
LENOIR | SR 1569 (CAREY ROAD EXTENSION) | SR 1572 (ROUSE ROAD) TO US 258. CONSTRUCT MULTI-LANES ON NEW LOCATION. | HIGHWAY | 2 | EASTERN CAROLINA RPO | U-3618 | DIVISION 2 | T | 2026 | 4700000 | 2026 | 1000000 | 2028 | 28301000 |  |  | 34001000
LENOIR | US 70 | INSTALL RESTRICTED CROSSING INTERSECTIONS AT US 70 AND SR 1324 (KENNEDY HOME ROAD) / SR 1519 (EASON ROAD) AND AT ADJACENT CROSSOVER TO THE WEST. | HIGHWAY | 2 | EASTERN CAROLINA RPO | HS-2002C | REGION B | HSIP |  |  | 2022 | 20000 | 2022 | 250000 |  |  | 270000 | UNDER CONSTRUCTION.
LENOIR | US 70 | SR 1227 (JIM SUTTON ROAD)/SR 1252 (WILLIE MEASLEY ROAD). CONSTRUCT AT GRADE INTERSECTION TO INTERCHANGE | HIGHWAY | 2 | EASTERN CAROLINA RPO | R-5813 | NOT FUNDED | T | NOT FUNDED | 10100000 | NOT FUNDED | 3262000 | NOT FUNDED | 55501000 |  |  | 68863000
LENOIR | US 70 (FUTURE I-42) | EXISTING FREEWAY NEAR LAGRANGE TO EXISTING FREEWAY NEAR DOVER. UPGRADE ROADWAY TO FREEWAY, PART ON NEW LOCATION. | HIGHWAY | 2 | EASTERN CAROLINA RPO | R-2553
LENOIR | US 70 (FUTURE I-42) | EXISTING FREEWAY NEAR LAGRANGE TO SR 1522 (ALBERT SUGGS ROAD). | HIGHWAY | 2 | EASTERN CAROLINA RPO | R-2553A | NOT FUNDED | T | NOT FUNDED | 45842000 | NOT FUNDED | 1447000 | NOT FUNDED | 44000000 |  |  | 91289000
LENOIR | US 70 (FUTURE I-42) | SR 1522 (ALBERT SUGGS ROAD) TO NC 148 (HARVEY PARKWAY). | HIGHWAY | 2 | EASTERN CAROLINA RPO | R-2553B | NOT FUNDED | T | NOT FUNDED | 8300000 | NOT FUNDED | 6000000 | NOT FUNDED | 55801000 |  |  | 70101000
LENOIR | US 70 (FUTURE I-42) | NC 148 (HARVEY PARKWAY) TO US 70 EAST OF NC 58. | HIGHWAY | 2 | EASTERN CAROLINA RPO | R-2553C | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 82600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 320700000 |  |  | 407200000
LENOIR | LENOIR COUNTY | ADMINISTRATION | PUBLIC TRANSIT | 2 | EASTERN CAROLINA RPO | TK-6178 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 1048000 | 1048000 | FUNDS AUTHORIZED IN PROGRESS
LENOIR, GREENE | US 258 | SR 1101 (BROWNTOWN ROAD) TO SR 2010 (C. F. HARVEY PARKWAY). WIDEN TO MULTI-LANES. | HIGHWAY | 2 | EASTERN CAROLINA RPO | R-5814 | DIVISION 2 | T | 2027 | 11900000 | 2027 | 3400000 | 2029 | 31302000 |  |  | 46602000
LINCOLN | LINCOLNTON-LINCOLN COUNTY AIRPORT (IPJ) | OBSTRUCTION REMOVAL IN RUNWAY 5 APPROACH. | AVIATION | 12 | GASTON-CLEVELAND-LINCOLN MPO | AV-5753 | DIVISION 12 | T | 2023 | 295000 | [6 empty] | 295000
LINCOLN | LINCOLNTON-LINCOLN COUNTY AIRPORT (IPJ) | LAND ACQUISITION FOR RUNWAY 5 APPROACH. | AVIATION | 12 | GASTON-CLEVELAND-LINCOLN MPO | AV-5755 | DIVISION 12 | T | 2023 | 176000 | [6 empty] | 176000
LINCOLN | NC 150 | REPLACE BRIDGE 540026 OVER S.A.L. RAILROAD. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | B-6042 | REGION F | HFB | 2025 | 290000 |  |  | 2026 | 2900000 |  |  | 3190000
LINCOLN | NC 150 | GASTON COUNTY LINE TO WEST OF INDIAN CREEK. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-0617BA | [11 empty] | COMPLETE
LINCOLN | NC 150 | WEST OF INDIAN CREEK TO US 321 AT LINCOLNTON. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-0617BB | NOT FUNDED | T | NOT FUNDED | 5300000 | NOT FUNDED | 2500000 | NOT FUNDED | 40900000 |  |  | 48700000
LINCOLN | NC 150 | US 321 AT LINCOLNTON TO US 321 BYPASS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-0617C | NOT FUNDED | T | NOT FUNDED | 600000 | NOT FUNDED | 3900000 | NOT FUNDED | 71600000 |  |  | 76100000
LINCOLN | NC 16 | SR 1389 (FAIRFIELD FOREST ROAD) TO SR 1379 (WEBBS ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6144 | NOT FUNDED | T | NOT FUNDED | 5500000 | NOT FUNDED | 4900000 | NOT FUNDED | 21599000 |  |  | 31999000
LINCOLN | NC 16 BUSINESS | INTERSECTION OF NC 16 BUSINESS AND SR 1439 (UNITY CHURCH ROAD)/SR 1387 (TRIANGLE CIRCLE). ADD TURN LANES. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-5712 | REGION F | T |  |  |  |  | 2023 | 2300000 |  |  | 2300000 | RIGHT-OF-WAY IN PROGRESS
LINCOLN | NC 16 BUSINESS | NC 16 BUSINESS, SR 1373 (CAMPGROUND ROAD), SR 1386 (WILL PROCTOR ROAD). REALIGN OFFSET INTERSECTIONS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5962 | REGION F | O, T | 2024 | 3300000 | 2024 | 300000 | 2026 | 4200000 |  |  | 7800000 | OTHER FUNDING PROVIDED BY LINCOLN COUNTY
LINCOLN | NC 16 BYPASS | SR 1380 (OPTIMIST CLUB ROAD) INTERSECTION. UPGRADE AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6134 | REGION F | T | 2024 | 500000 | 2024 | 100000 | 2026 | 25400000 |  |  | 26000000
LINCOLN | NC 182 | REPLACE BRIDGE 540007 OVER INDIAN CREEK. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | B-4571 | REGION F | BFP |  |  |  |  | 2023 | 3500000 |  |  | 3500000
LINCOLN | NC 27 | EXISTING SIDEWALKS ALONG NC 27 IN LINCOLNTON CITY LIMITS. CONSTRUCT SIDEWALKS IN GAPS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | C-5606I | EXEMPT | CMAQ, L, S |  |  |  |  | 2023 | 406000 |  |  | 406000
LINCOLN | NC 27 (EAST MAIN STREET) | US 321 BUS TO NC 150 (EAST). CONSTRUCT ACCESS MANAGEMENT AND INTERSECTION IMPROVEMENTS. INCLUDES CONSTRUCTION OF NORTHBOUND TURN LANE FROM SR 1294 (LITHINA INN ROAD) TO NC 27 (E MAIN STREET) AND WIDENING OF BRIDGE #540042 OVER SEABOARD RR ON NC 150. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6140 | REGION F | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 35000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 33500000 |  |  | 77800000
LINCOLN | NC 73 | SR 1383 (INGLESIDE FARM ROAD) TO NC 16. WIDEN TO MULTI-LANES. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6139 | NOT FUNDED | NHP | NOT FUNDED | 5900000 | NOT FUNDED | 1500000 | NOT FUNDED | 42000000 |  |  | 49400000
LINCOLN | NC 73 EXTENSION | US 321 TO SR 1356 (CAMP CREEK ROAD) CONSTRUCT MULTI-LANES ON NEW LOCATION. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6142 | NOT FUNDED | T | NOT FUNDED | 32300000 | NOT FUNDED | 4800000 | NOT FUNDED | 69302000 |  |  | 106402000
LINCOLN | LINCOLN COUNTY | PURCHASE EXPANSION VEHICLE FOR ROUTE CONNECTING LINCOLNTON WITH THE NC 16 CORRIDOR NEAR LAKE NORMAN. | PUBLIC TRANSIT | 12 | GASTON-CLEVELAND-LINCOLN MPO | TA-6676 | DIVISION 12 | 5311, L, T | [6 empty] | 2020 | 70000 | 70000
LINCOLN | LINCOLN COUNTY | ADMINISTRATION | PUBLIC TRANSIT | 12 | EASTERN CAROLINA RPO | TK-6141 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 876000 | 876000 | FUNDS AUTHORIZED IN PROGRESS
LINCOLN, GASTON | NC 150 | NC 279 AT CHERRYVILLE TO RELOCATED US 321. WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-0617 | REGION F
LINCOLN, MECKLENBURG | NC 73 | NC 16 TO VANCE ROAD EXTENSION/BEATTIES FORD ROAD. | HIGHWAY | 10, 12 | GASTON-CLEVELAND-LINCOLN MPO, CHARLOTTE REGIONAL TPO | R-5721A | REGION E, F | T | 2026 | 46400000 | 2026 | 10400000 | 2029 | 102002000 |  |  | 158802000
MACON | MACON COUNTY AIRPORT | EXTEND RUNWAY. | AVIATION | 14 | SOUTHWESTERN RPO | AV-5850 | DIVISION 14 | T | 2028 | 166000 |  |  | 2029 | 4834000 |  |  | 5000000
MACON | EAST MAIN ST/US 441 BUS | NC 28 (HIGHLANDS ROAD). CONSTRUCT SIDEWALK LOOP. | BIKE/PED | 14 | SOUTHWESTERN RPO | EB-5964 | DIVISION 14 | L, TA5200 | 2023 | 20000 |  |  | 2024 | 180000 | 2022 | 20000 | 220000
MACON | SR 1729 (DEPOT STREET) | US 441 BUSINESS (EAST MAIN STREET) TO SR 1667 (WAYAH STREET). CONSTRUCT MISSING SECTIONS OF SIDEWALK ALONG WEST SIDE AND CONSTRUCT NEW SIDEWALK ALONG EAST SIDE. | BIKE/PED | 14 | SOUTHWESTERN RPO | EB-5756 | DIVISION 14 | L, TA5200 |  |  |  |  | 2023 | 294000 | 2022 | 18000 | 312000
MACON | SR 1001 (ELLIJAY ROAD) | REPLACE BRIDGE 550009 OVER NORTH PRONG ELLIJAY CREEK. | HIGHWAY | 14 | SOUTHWESTERN RPO | B-6029 | DIVISION 14 | BGOFF | 2023 | 70000 |  |  | 2023 | 700000 |  |  | 770000
MACON | SR 1114 (SHOPE ROAD) | REPLACE BRIDGE 550244 OVER NORTH FORK COWEETA CREEK. | HIGHWAY | 14 | SOUTHWESTERN RPO | B-6025 | DIVISION 14 | BGOFF | 2023 | 15000 |  |  | 2023 | 550000 |  |  | 565000
MACON | SR 1351 (MATLOCK CREEK ROAD) | REPLACE BRIDGE 550220 OVER MATLOCK CREEK. | HIGHWAY | 14 | SOUTHWESTERN RPO | B-6030 | DIVISION 14 | BGOFF |  |  |  |  | 2026 | 625000 |  |  | 625000 | RIGHT-OF-WAY IN PROGRESS
MACON | SR 1500 (WATAUGA ROAD) | REPLACE BRIDGE 550214 OVER WATAUGA CREEK. | HIGHWAY | 14 | SOUTHWESTERN RPO | B-6026 | DIVISION 14 | BGOFF | 2024 | 50000 |  |  | 2025 | 500000 |  |  | 550000
MACON | SR 1528 (LITTLE ELLIJAY ROAD) | REPLACE BRIDGE 550150 OVER ELLIJAY CREEK. | HIGHWAY | 14 | SOUTHWESTERN RPO | B-6028 | DIVISION 14 | BGOFF |  |  |  |  | 2022 | 1607000 |  |  | 1607000
MACON | SR 1679 (GOLD MINE ROAD) | REPLACE BRIDGE 550056 OVER CULLASAJA RIVER. | HIGHWAY | 14 | SOUTHWESTERN RPO | HB-0037 | DIVISION 14 | BGOFF | 2026 | 50000 | 2026 | 50000 | 2027 | 1000000 |  |  | 1100000
MACON | SR 1679 (PEEKS CREEK ROAD) | REPLACE BRIDGE 550055 OVER CULLASAJA RIVER. | HIGHWAY | 14 | SOUTHWESTERN RPO | HB-0030 | DIVISION 14 | BGOFF | 2025 | 100000 | 2025 | 100000 | 2026 | 2000000 |  |  | 2200000
MACON | US 23/US 441 | US 64 TO SR 1649 (PRENTISS BRIDGE ROAD). IMPLEMENT ACCESS MANAGEMENT STRATEGIES. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5734 | [11 empty] | SEGMENT A INCLUDES THE REPLACEMENT OF BRIDGE 314 FORMERLY SCHEDULED TO BE REPLACED UNDER 17BP.14.R.154
MACON | US 23/US 441 | US 64 TO SR 1652 (WIDE HORIZON DRIVE)/SR 1152 (BELDEN CIRCLE). | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5734A | DIVISION 14 | T |  |  |  |  | 2021 | 12600000 | 2021 | 2310000 | 14910000 | UNDER CONSTRUCTION; BUILD NC BOND FUNDING: $1.788 M FOR PE, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE); $9.797 M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE)
MACON | US 23/US 441 | SR 1652 (WIDE HORIZON DRIVE)/SR 1152 (BELDEN CIRCLE) TO SR 1649 (PRENTISS BRIDGE ROAD). | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5734B | NOT FUNDED | T | NOT FUNDED | 13800000 | NOT FUNDED | 3200000 | NOT FUNDED | 26600000 |  |  | 43600000
MACON | US 23/US 441 | SR 1649 (PRENTISS BRIDGE ROAD) TO GEORGIA STATE LINE. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5734C | NOT FUNDED | T | NOT FUNDED | 5000000 | NOT FUNDED | 600000 | NOT FUNDED | 53600000 |  |  | 59200000
MACON | US 441 | SR 1515 (HYATT ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS AND RIGHT-IN/RIGHT-OUT AT INGLES DEVELOPMENT SITE. | HIGHWAY | 14 | SOUTHWESTERN RPO | HA-0004 | EXEMPT | ADHSL |  |  |  |  | 2022 | 1871000 |  |  | 1871000 | ARC PROJECT NO. 20226, AWARD AMOUNT = $1,500,000
MACON | US 441 BUSINESS | US 23/US 64/US 441 TO PORTER STREET. INTERSECTION IMPROVEMENTS AT WOMAK STREET, MAPLE STREET, PORTER STREET, AND DEPOT STREET IN FRANKLIN. | HIGHWAY | 14 | SOUTHWESTERN RPO | U-5604 | REGION G | T |  |  |  |  | 2020 | 7080000 | 2021 | 1830000 | 8910000 | UNDER CON; BUILD NC BOND FUNDING: $1.416M FOR PE, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE); $2.473M FOR CON, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $3.019 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE).
MACON | US 64/NC 28 | INSTALL CENTERLINE RUMBLESTRIPS, LONG LIFE PAVEMENT MARKINGS, AND INTERMITTMENT PAVED SHOULDERS FROM SR 1560 TO SR 1533, NEAR FRANKLIN. | HIGHWAY | 14 | SOUTHWESTERN RPO | HS-2014A | REGION G | HSIP |  |  |  |  | 2021 | 1200000 |  |  | 1200000
MACON | MACON COUNTY | ADMINISTRATION | PUBLIC TRANSIT | 14 | SOUTHWESTERN RPO | TK-6142 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 764000 | 764000 | FUNDS AUTHORIZED IN PROGRESS
MADISON | MARSHALL | US 25/70, SR 1601 (DERINGER DRIVE) TO BEGINNING OF INGLE'S PARKING LOT. CONSTRUCT SIDEWALKS, INSTALL CROSSWALKS, ADA RAMPS, PEDESTRIAN SIGNAL AND PEDESTRIAN REFUGE. | BIKE/PED | 13 | LAND-OF-SKY RPO | EB-5918 | DIVISION 13 | L, TALT5 |  |  |  |  | 2024 | 150000 | 2023 | 45000 | 195000
MADISON | I-26 | TENNESSEE STATE LINE TO MILE MARKER 9. PAVEMENT AND BRIDGE REHABILITATION. | HIGHWAY | 13 | LAND-OF-SKY RPO | I-5831
MADISON | I-26 | TENNESSEE STATE LINE TO MILE MARKER 9. REPLACE CURB AND DRAINAGE BOXES, AND REHABILITATE BRIDGES. | HIGHWAY | 13 | LAND-OF-SKY RPO | I-5831A | STATEWIDE MOBILITY | BGLT5 |  |  |  |  | 2022 | 8729000 |  |  | 8729000
MADISON | I-26 | TENNESSEE STATE LINE TO MILE MARKER 9. REHABILITATE PAVEMENT. | HIGHWAY | 13 | LAND-OF-SKY RPO | I-5831B | STATEWIDE MOBILITY | BGLT5 |  |  |  |  | 2025 | 9000000 |  |  | 9000000
MADISON | I-26 (US 19/US 23) | NORTH OF NC 213 TO NORTH OF US 19 | HIGHWAY | 13 | LAND-OF-SKY RPO | A-0010BB | [11 empty] | COMPLETE
MADISON | I-26 (US 19/US 23) | NORTH OF US 19 TO SR 1318 (BIG LAUREL ROAD) AT LAUREL CREEK | HIGHWAY | 13 | LAND-OF-SKY RPO | A-0010C | [11 empty] | COMPLETE
MADISON | I-26 (US 19/US 23) | SR 1318 (BIG LAUREL ROAD) AT LAUREL CREEK TO THE TENNESSEE STATE LINE AT SAMS GAP | HIGHWAY | 13 | LAND-OF-SKY RPO | A-0010D | [11 empty] | COMPLETE
MADISON | SR 1127 (ROBERTS BRANCH ROAD) | REPLACE BRIDGE 560311 OVER ROBERTS BRANCH. | HIGHWAY | 13 | LAND-OF-SKY RPO | B-6019 | DIVISION 13 | [10 empty] | UNDER CONSTRUCTION
MADISON | SR 1151 (BALTIMORE BRANCH ROAD) | REPLACE BRIDGE 560222 OVER BACK BRANCH. | HIGHWAY | 13 | LAND-OF-SKY RPO | B-6017 | DIVISION 13 | [10 empty] | UNDER CONSTRUCTION
MADISON | SR 1183 (UPPER SHUT-IN ROAD) | REPLACE BRIDGE 560302 OVER SHUT IN CREEK. | HIGHWAY | 13 | LAND-OF-SKY RPO | B-6010 | DIVISION 13 | [10 empty] | UNDER CONSTRUCTION
MADISON | SR 1341 (FOSTER CREEK ROAD) | REPLACE BRIDGE 560073 OVER FOSTER CREEK. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | B-6012 | DIVISION 13 | T |  |  |  |  | 2019 | 4828000 |  |  | 4828000 | UNDER CONSTRUCTION; BUILD NC BOND FUNDING: $3.45M FOR CONSTRUCTION, PAYBACK FY 2021-2035 (FY 2021 / YR 2&3 SALE).
MADISON | SR 1395 | REPLACE BRIDGE 560071 OVER BIG LAUREL CREEK. | HIGHWAY | 13 | LAND-OF-SKY RPO | B-5989 | DIVISION 13 | BGOFF | 2022 | 13000 | 2023 | 130000 | 2023 | 2600000 |  |  | 2743000 | TO BE LET WITH B-3186.
MADISON | SR 1503 (LAUREL VALLEY) | REPLACE BRIDGE 560246 OVER LAUREL CREEK. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO, LAND-OF-SKY RPO | B-4182 | DIVISION 13 | [10 empty] | CONSTRUCTION FUNDED WITH STATE LEGISLATIVE BRIDGE PROGRAM FUNDS (17BP.13.R.105)
MADISON | SR 1631 (CROSSROADS PARKWAY) | EXTEND SR 1631 (CROSSROADS PARKWAY) TO SR 1632. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | R-5779 | DIVISION 13 | ADHSL, O, T |  |  |  |  | 2021 | 4071000 |  |  | 4071000 | UNDER CONSTRUCTION. ARC PROJECT NO. 18339; AWARD AMOUNT = $2,379,515 - OTHER FUNDS ARE $700,000 IN SMALL CONSTRUCTION AND $250,000 IN CONTINGENCY (WBS 48170)
MADISON | US 25 | US 25/70 BUSINESS (NORTH MAIN STREET) TO SR 1143 (BRUSH CREEK ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 13 | LAND-OF-SKY RPO | R-5837 | NOT FUNDED | T | NOT FUNDED | 5100000 | NOT FUNDED | 9700000 | NOT FUNDED | 18500000 |  |  | 33300000
MADISON | US 25/70 | REPLACE BRIDGE 560067 OVER THE FRENCH BROAD RIVER. | HIGHWAY | 13 | LAND-OF-SKY RPO | B-5895 | REGION G | HFB | 2022 | 415000 |  |  | 2023 | 8300000 |  |  | 8715000
MADISON | US 25/70 | EAST OF SR 1392 (SKYWAY DRIVE) TO US 25/70 BUSINESS (NORTH MAIN STREET). MODERNIZE ROADWAY. | HIGHWAY | 13 | LAND-OF-SKY RPO | R-5924 | NOT FUNDED | BGLT5 | NOT FUNDED | 1800000 | NOT FUNDED | 3000000 | NOT FUNDED | 32101000 |  |  | 36901000
MADISON | MADISON COUNTY TRANSPORTATION | ADMINISTRATION | PUBLIC TRANSIT | 13 |  | TK-6143 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 548000 | 548000 | FUNDS AUTHORIZED IN PROGRESS
MARTIN | MARTIN COUNTY AIRPORT (MCZ) | CONSTRUCT TAXILANES AND APRON. | AVIATION | 1 | MID-EAST RPO | AV-5788 | DIVISION 1 | T |  |  |  |  | 2023 | 734000 |  |  | 734000
MARTIN | EAST MAIN STREET | BOULEVARD STREET TO RIVER ROAD IN WILLIAMSTON. INSTALL SIDEWALKS AND CURB RAMPS. | BIKE/PED | 1 | MID-EAST RPO | EB-5979 | DIVISION 1 | L, TA5200 |  |  |  |  | 2027 | 90000 | 2025 | 10000 | 100000
MARTIN | NC 125 | SR 1182 (EAST COLLEGE ROAD) TO NC 125 NORTHWEST OF WILLIAMSTON. TWO LANES, PART ON NEW LOCATION. | HIGHWAY | 1 | MID-EAST RPO | R-3826 | REGION A | [10 empty] | UNDER CONSTRUCTION
MARTIN | SR 1142 (PRISON CAMP ROAD) | REPLACE BRIDGE 570053 OVER COLLIE SWAMP. | HIGHWAY | 1 | MID-EAST RPO | B-5503 | DIVISION 1 | [10 empty] | UNDER CONSTRUCTION
MARTIN | SR 1142 (PRISON CAMP ROAD) | NC 903 TO SR 1182 (EAST COLLEGE ROAD). UPGRADE FACILITY. | HIGHWAY | 1 | MID-EAST RPO | R-4705 | DIVISION 1 | BGLT5 |  |  |  |  | 2022 | 48147000 |  |  | 48147000 | UNDER CONSTRUCTION.
MARTIN | US 13/US 17 | MAIN STREET IN WILLIAMSTON. IMPROVE INTERSECTION. | HIGHWAY | 1 | MID-EAST RPO | R-5879 | REGION A | NHP | 2025 | 100000 | 2025 | 200000 | 2027 | 2350000 |  |  | 2650000
MARTIN | US 13/US 64 (FUTURE I-87) | EDGECOMBE COUNTY LINE TO US 13/17 AND US 64 INTERCHANGE. PAVEMENT REHABILITATION. | HIGHWAY | 1 | MID-EAST RPO | I-6028 | STATEWIDE MOBILITY | [10 empty] | "A" BREAK DELETED - WORK WAS COMPLETED WITH CONTRACT RESURFACING.
MARTIN | US 17 | SR 1119 (RALPH TAYLOR ROAD) TO SR 1205 (HOLLY CREEK ROAD). ACCESS MANAGEMENT. | HIGHWAY | 1 | MID-EAST RPO | R-5810 | DIVISION 1 | T | 2023 | 15000 | 2023 | 180000 | 2025 | 7300000 |  |  | 7495000
MARTIN | US 64 (FUTURE I-87) | US 64 ALTERNATE TO NC 125. | HIGHWAY | 1 | MID-EAST RPO | I-6028B | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2020 | 5873000 |  |  | 5873000
MARTIN | US 64 (FUTURE I-87) | NC 125 TO US 13/17 AND US 64 INTERCHANGE. | HIGHWAY | 1 | MID-EAST RPO | I-6028C | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2022 | 1089000 |  |  | 1089000
MARTIN | MARTIN COUNTY | ADMINISTRATION | PUBLIC TRANSIT | 1 | MID-EAST RPO | TK-6144 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 724000 | 724000 | FUNDS AUTHORIZED IN PROGRESS
MARTIN, BEAUFORT | US 17 | WASHINGTON BYPASS NORTH OF NC 171 TO MULTI-LANES SOUTH OF WILLIAMSTON. WIDEN TO MULTI-LANES. | HIGHWAY | 1, 2 | MID-EAST RPO | R-2511 | DIVISION 1, 2 | T | 2019 | 10625000 | 2019 | 2200000 | 2022 | 99343000 |  |  | 112168000 | UNDER CONSTRUCTION.
MARTIN, BERTIE | US 13, US 17, NC 171 | UPGRADE CURVE WARNING SIGNS AT VARIOUS LOCATIONS. | HIGHWAY | 1 | MID-EAST RPO, PEANUT BELT RPO | HS-2001B | REGION A | HSIP |  |  |  |  | 2023 | 35000 |  |  | 35000
McDOWELL | FONTA FLORA TRAIL | US 70 TO RESISTOFLEX ROAD. CONSTRUCT GREENWAY. | BIKE/PED | 13 | FOOTHILLS RPO | EB-5916 | DIVISION 13 | L, TA5200 | 2023 | 75000 |  |  | 2024 | 3063000 | 2021 | 560000 | 3698000
McDOWELL | SR 1703 (BALDWIN AVENUE) | PERRY STREET TO US 70 (E COURT ST). CONSTRUCT CURB AND GUTTER, AND SIDEWALK ALONG EAST SIDE AND INSTALL CROSSWALKS. | BIKE/PED | 13 | FOOTHILLS RPO | EB-5753 | DIVISION 13 | L, TA5200 | 2023 | 100000 |  |  | 2024 | 312000 | 2021 | 25000 | 437000
McDOWELL | I-40 | SR 1001 (SUGAR HILL ROAD)/MILE MARKER 81 TO NC 226/MILE MARKER 86. PAVEMENT REHABILITATION. | HIGHWAY | 13 | FOOTHILLS RPO | HI-0009 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2027 | 14900000 |  |  | 14900000
McDOWELL | I-40 | MILE MARKER 67 TO MILE MARKER 73 (OLD FORT MOUNTAIN). CONSTRUCT SAFETY AND DRAINAGE IMPROVEMENTS, REHABILITATE PAVEMENT, AND RECONSTRUCT MEDIAN BARRIER. | HIGHWAY | 13 | FOOTHILLS RPO | HI-0010 | STATEWIDE MOBILITY | HSIP, NHPIM |  |  |  |  | 2023 | 13500000 |  |  | 13500000
McDOWELL | I-40 | MILE MARKER 73 TO MILE MARKER 86. PAVEMENT REHABILITATION. | HIGHWAY | 13 | FOOTHILLS RPO | I-5900 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2025 | 25099000 |  |  | 25099000
McDOWELL | NC 226 | US 221 TO NC 226A. WIDEN ROADWAY TO 3 LANES. | HIGHWAY | 13 | FOOTHILLS RPO | R-5923 | NOT FUNDED | BGLT5 | NOT FUNDED | 100000 | NOT FUNDED | 600000 | NOT FUNDED | 4300000 |  |  | 5000000
McDOWELL | NEW ROUTE | CONSTRUCT ACCESS ROAD TO UNIVERSAL PROPERTY. | HIGHWAY | 13 | FOOTHILLS RPO | R-5964 | EXEMPT | ADHSL |  |  |  |  | 2021 | 987000 |  |  | 987000 | ARC # 19098; AWARD AMOUNT = $987,112
McDOWELL | SR 1001 (SUGAR HILL ROAD) | I-40 WESTBOUND RAMPS TO 0.3 MILE WEST OF I-40 EASTBOUND RAMPS. WIDEN ROADWAY. | HIGHWAY | 13 | FOOTHILLS RPO | U-5818 | DIVISION 13 | T | 2020 | 90000 |  |  | 2020 | 16125000 | 2020 | 1710000 | 17925000 | UNDER CON. BUILD NC BOND: $1.206M FOR PE, $64,473 FOR ROW, $4.28 M FOR CON - PAYBACK 2020-2034 (FY 2019 / YR1 SALE); $120,139 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $8.250M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE).
McDOWELL | SR 1781 (POLLY SPOUT ROAD) | REPLACE BRIDGE 580312 OVER SECOND BROAD RIVER. | HIGHWAY | 13 | FOOTHILLS RPO | B-6014 | DIVISION 13 | BGOFF | 2022 | 100000 |  |  | 2022 | 4831000 |  |  | 4931000 | DESIGN-BUILD; COMBINED LETTING WITH B-6011, B-6013, & B-6016
McDOWELL | US 221 | US 221-NC 226 INTERSECTION SOUTH OF MARION TO NORTH OF I-40 | HIGHWAY | 13 | FOOTHILLS RPO | R-0204D | NOT FUNDED | T | NOT FUNDED | 3000000 | NOT FUNDED | 500000 | NOT FUNDED | 32500000 |  |  | 36000000
McDOWELL | US 221 | NORTH OF I-40 TO SR 1153 (GOOSE CREEK ROAD) | HIGHWAY | 13 | FOOTHILLS RPO | R-0204E | DIVISION 13 | T | 2025 | 8000000 | 2025 | 1200000 | 2028 | 38698000 |  |  | 47898000
McDOWELL | US 221 | SR 1781 (POLLY SPROUT ROAD) NORTHERN INTERSECTION TO SR 1153 (GOOSE CREEK ROAD). | HIGHWAY | 13 | FOOTHILLS RPO | R-2597C | NOT FUNDED | NHP | NOT FUNDED | 9800000 | NOT FUNDED | 5800000 | NOT FUNDED | 117500000 |  |  | 133100000
McDOWELL | US 221 - NC 226 | SR 1434 TO SR 1153. WIDEN TO MULTI-LANES, WITH A BYPASS OF MARION. | HIGHWAY | 13 | FOOTHILLS RPO | R-0204
McDOWELL | US 221 - NC 226 | SR 1434 NORTH OF MARION TO US 221-NC 226 BUSINESS | HIGHWAY | 13 | FOOTHILLS RPO | R-0204A | [11 empty] | COMPLETE
McDOWELL | US 221 (MARION BYPASS) | US 221-NC 226 BUSINESS TO SOUTH OF SOUTHERN RAILWAY. | HIGHWAY | 13 | FOOTHILLS RPO | R-0204B | [11 empty] | COMPLETE
McDOWELL | US 221 (MARION BYPASS) | SOUTH OF SOUTHERN RAILWAY TO US 221-NC 226 INTERSECTION SOUTH OF MARION | HIGHWAY | 13 | FOOTHILLS RPO | R-0204C | [11 empty] | COMPLETE
McDOWELL | US 221 BUSINESS | US 221/NC 226 TO GEORGIA AVENUE. WIDEN EXISTING ROADWAY. | HIGHWAY | 13 | FOOTHILLS RPO | U-5835 | DIVISION 13 | T | 2023 | 6600000 | 2023 | 2000000 | 2025 | 15945000 |  |  | 24545000 | BUILD NC BOND FUNDING: $4M FOR CONSTRUCTION, PAYBACK FY 2026-2040 (FY 2026 / YR 8 SALE)
McDOWELL | US 70 | REPLACE BRIDGE 580127 OVER SOUTHERN RAILROAD. | HIGHWAY | 13 | FOOTHILLS RPO | B-6040 | REGION G | HFB | 2023 | 420000 |  |  | 2024 | 4200000 |  |  | 4620000
McDOWELL, RUTHERFORD | US 221 | (1) US 221 IN RUTHERFORD COUNTY FROM US 64 TO THE MCDOWELL COUNTY LINE. (2) US 221 IN MCDOWELL COUNTY ROM THE RUTHERFOD COUNTY LINE TO I-40. INSTALL SINUSIODAL CENTERLINE RUMBLESTRIPES WITH LONG-LIFE PAVEMENT MARKINGS. | HIGHWAY | 13 | FOOTHILLS RPO | W-5813J | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2022 | 501000 |  |  | 501000
MECKLENBURG | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT (CLT) | CONSTRUCT FOURTH PARALLEL RUNWAY. | AVIATION | 10 | CHARLOTTE REGIONAL TPO | AV-5879 | STATEWIDE MOBILITY | O, T |  |  |  |  | 2024 | 607500000 |  |  | 607500000 | OTHER FUNDING PROVIDED BY CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT
MECKLENBURG | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT (CLT) | EXPAND WEST RAMP NEAR CONCOURSE A - PHASE II. | AVIATION | 10 | CHARLOTTE REGIONAL TPO | AV-5881 | STATEWIDE MOBILITY | O, T |  |  |  |  | 2021 | 40100000 |  |  | 40100000 | OTHER FUNDING PROVIDED BY CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT
MECKLENBURG | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT (CLT) | EXPAND CONCOURSE A (PHASE II). | AVIATION | 10 | CHARLOTTE REGIONAL TPO | AV-5893 | REGION E | O, T |  |  |  |  | 2025 | 202500000 |  |  | 202500000 | OTHER FUNDING PROVIDED BY CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT
MECKLENBURG | CHARLOTTE | STEWART CREEK GREENWAY, STATE STREET TO ROZZELLES FERRY ROAD. CONSTRUCT GREENWAY. | BIKE/PED | 10 | CHARLOTTE REGIONAL TPO | EB-5781 | DIVISION 10 | BGDA, CMAQ, L |  |  |  |  | 2021 | 3159000 |  |  | 3159000 | $1.09M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
MECKLENBURG | CHARLOTTE | CHARLOTTE BICYCLE EXPANSION. | BIKE/PED | 10 | CHARLOTTE REGIONAL TPO | EB-5820 | DIVISION 10 | [10 empty] | UNDER CONSTRUCTION
MECKLENBURG | CHARLOTTE | SR 2833 (MALLARD CREEK CHURCH ROAD), SR 2472 (MALLARD CREEK ROAD) TO SR 2746 (CLAUDE FREEMAN DRIVE). CONSTRUCT MULTI-USE TRAIL ON SOUTH SIDE OF ROAD. | BIKE/PED | 10 | CHARLOTTE REGIONAL TPO | EB-5832 | DIVISION 10 | BGDA, L, TAANY |  |  |  |  | 2022 | 1678000 |  |  | 1678000 | RIGHT-OF-WAY IN PROGRESS.
MECKLENBURG | CHARLOTTE | BELK GREENWAY CONNECTOR PHASE ONE. EAST STONEWALL STREET AT SOUTH DAVIDSON STREET TO SOUTH KINGS DRIVE. | BIKE/PED | 10 | CHARLOTTE REGIONAL TPO | EB-5929 | DIVISION 10 | CMAQ, L | 2021 | 99000 |  |  | 2025 | 1557000 |  |  | 1656000 | $1.159M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
MECKLENBURG | CHARLOTTE | HORNETS NEST PARK ACCESS IMPROVEMENTS INCLUDING SIDEWALKS, A MULTI-USE PATH, AND A TRAFFIC SIGNAL WITH LEFT TURN LANES. | BIKE/PED | 10 | CHARLOTTE REGIONAL TPO | EB-6036 | DIVISION 10 | BGDA, L |  |  |  |  | 2023 | 1875000 |  |  | 1875000
MECKLENBURG | CORNELIUS | MCDOWELL CREEK TRIBUTARY GREENWAY; CONSTRUCT GREENWAY FROM SMITHVILLE PARK TO J.V. WASHAM ELEMENTARY. CONSTRUCT MULTI-USE PATH ALONG WESTMORELAND ROAD TO LAKE PINES DRIVE. | BIKE/PED | 10 | CHARLOTTE REGIONAL TPO | EB-5777 | DIVISION 10 | CMAQ, L | 2021 | 960000 |  |  | 2023 | 2040000 |  |  | 3000000 | $2.4M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
MECKLENBURG | CORNELIUS | MCDOWELL CREEK GREENWAY, MAGNOLIA PLAZA TO WESTMORELAND ROAD. CONSTRUCT GREENWAY. | BIKE/PED | 10 | CHARLOTTE REGIONAL TPO | EB-5817 | DIVISION 10 | BGDA, L, TADA |  |  |  |  | 2020 | 3882000 |  |  | 3882000
MECKLENBURG | DAVIDSON | WEST BRANCH NATURE PRESERVE - CONSTRUCT GREENWAY | BIKE/PED | 10 | CHARLOTTE REGIONAL TPO | BL-0003 | DIVISION 10 | BGDA, L | [6 empty] | 2023 | 151000 | 151000
MECKLENBURG | DAVIDSON | KINCAID MULTI-USE PATH. EUGENIA STREET AND SPRING STREET TO SOUTH PRONG ROCKY RIVER GREENWAY NEAR DAVIDSON ELEMENTARY. | BIKE/PED | 10 | CHARLOTTE REGIONAL TPO | EB-5933 | DIVISION 10 | BGDA, L |  |  |  |  | 2024 | 878000 |  |  | 878000
MECKLENBURG | GREENWAY MCALPINE CREEK | NC 51 TO FOUR MILE CREEK GREENWAY IN CHARLOTTE. CONSTRUCT GREENWAY. | BIKE/PED | 10 | CHARLOTTE REGIONAL TPO | EB-5782 | DIVISION 10 | CMAQ, L, TAANY |  |  |  |  | 2022 | 7876000 |  |  | 7876000 | $3.926M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
MECKLENBURG | HUNTERSVILLE | UPPER MCDOWELL CREEK GREENWAY, CHILGROVE LANE TO NC 73. CONSTRUCT GREENWAY. | BIKE/PED | 10 | CHARLOTTE REGIONAL TPO | EB-5785 | DIVISION 10 | BGDA, L |  |  |  |  | 2022 | 5339000 |  |  | 5339000
MECKLENBURG | IRWIN CREEK GREENWAY | CLANTON ROAD TO LESTER STREET. CONSTRUCT IRWIN CREEK GREENWAY. | BIKE/PED | 10 | CHARLOTTE REGIONAL TPO | BL-0057 | DIVISION 10 | BGDA, CMAQ, L |  |  |  |  | 2025 | 6090000 |  |  | 6090000
MECKLENBURG | IRWIN CREEK GREENWAY EASTERN EXTENSION | EXISTING IRWIN CREEK GREENWAY TO HAMILTON STREET. CONSTRUCT GREENWAY. | BIKE/PED | 10 | CHARLOTTE REGIONAL TPO | EB-5970 | DIVISION 10 | L, TAANY |  |  |  |  | 2028 | 4637000 |  |  | 4637000
MECKLENBURG | JETTON STREET | GRIFFITH STREET TO POTTS STREET. CONSTRUCT SIDEWALK ON SOUTH SIDE OF JETTON STREET. | BIKE/PED | 10 | CHARLOTTE REGIONAL TPO | EB-5971 | DIVISION 10 | L, TAANY |  |  |  |  | 2025 | 290000 |  |  | 290000
MECKLENBURG | LAWYERS ROAD, WILGROVE-MINT HILL ROAD, WILSON GROV | EXTEND EXISTING SIDEWALKS. | BIKE/PED | 10 | CHARLOTTE REGIONAL TPO | EB-6051 | DIVISION 10 | L, TADA | 2023 | 60000 |  |  | 2025 | 2574000 | 2022 | 376000 | 3010000
MECKLENBURG | MATTHEWS | SAM NEWELL ROAD MULTI-USE PATH, NORTHEAST PARKWAY TO CROWN POINT ELEMENTARY SCHOOL. CONSTRUCT GREENWAY. | BIKE/PED | 10 | CHARLOTTE REGIONAL TPO | EB-5783 | DIVISION 10 | BGANY, BGDA, L | 2022 | 335000 |  |  | 2024 | 1526000 | 2021 | 231000 | 2092000 | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES; $30K IN BGANY USED AS PART OF FUND SWAP.
MECKLENBURG | MATTHEWS | CONSTRUCT FOUR MILE CREEK GREENWAY CROSSING UNDER SR 3448 (SOUTH TRADE STREET) | BIKE/PED | 10 | CHARLOTTE REGIONAL TPO | EB-5829 | DIVISION 10 | L, TADA |  |  |  |  | 2023 | 2440000 |  |  | 2440000
MECKLENBURG | NC 24 (W.T. HARRIS BOULEVARD) | PLAZA ROAD TO GRIER ROAD. CONSTRUCT SIDEWALK. | BIKE/PED | 10 | CHARLOTTE REGIONAL TPO | EB-6050 | DIVISION 10 | L, TADA | 2023 | 130000 |  |  | 2025 | 1927000 | 2022 | 10000 | 2067000
MECKLENBURG | NC 51 MULTI-USE PATH | TRADE STREET TO INDEPENDENCE POINTE PARKWAY. CONSTRUCT MULTI-USE PATH ON SOUTH SIDE OF NC 51. | BIKE/PED | 10 | CHARLOTTE REGIONAL TPO | EB-5969 | DIVISION 10 | L, TAANY |  |  |  |  | 2025 | 1075000 |  |  | 1075000
MECKLENBURG | RAIL TRAIL PEDESTRIAN BRIDGE | SR 3815 (EAST MOREHEAD STREET) TO STONEWALL LIGHT RAIL STATION. CONSTRUCT RAIL TRAIL PEDESTRIAN BRIDGE OVER I-277 (BELK FREEWAY). | BIKE/PED | 10 | CHARLOTTE REGIONAL TPO | BL-0058 | DIVISION 10 | BGDA, L |  |  |  |  | 2023 | 6343000 |  |  | 6343000
MECKLENBURG | THE PARK - HUNTERSVILLE GREENWAY | TORRENCE CREEK GREENWAY TO MOUNT HOLLY-HUNTERSVILLE ROAD. CONSTRUCT GREENWAY. | BIKE/PED | 10 | CHARLOTTE REGIONAL TPO | BL-0010 | DIVISION 10 | BGDA, L | 2024 | 516000 |  |  | 2026 | 2696000 | 2023 | 280000 | 3492000
MECKLENBURG | W.T. HARRIS BOULEVARD | NORTH TRYON STREET TO JW CLAY BOULEVARD. CONSTRUCT SHARED-USE PATH. | BIKE/PED | 10 | CHARLOTTE REGIONAL TPO | EB-6052 | DIVISION 10 | L, TADA | 2023 | 410000 |  |  | 2025 | 1260000 | 2022 | 10000 | 1680000
MECKLENBURG | ARDREY KELL ROAD | US 521 (JOHNSTON ROAD) TO SR 3624 (REA ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6167 | NOT FUNDED | BGANY | NOT FUNDED | 94300000 | NOT FUNDED | 1500000 | NOT FUNDED | 31401000 |  |  | 127201000
MECKLENBURG | BAILEY ROAD EXTENSION | US 21 (STATESVILLE ROAD) TO FUTURE NORTHCROSS DRIVE EXTENSION. CONSTRUCT 2 LANE ROADWAY ON NEW LOCATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6171 | NOT FUNDED | T | NOT FUNDED | 900000 | NOT FUNDED | 2300000 | NOT FUNDED | 19500000 |  |  | 22700000
MECKLENBURG | CAMPUS RIDGE ROAD REALIGNMENT | SR 1009 (JOHN STREET) TO SR 3457 (CAMPUS RIDGE ROAD) | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-4713B | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
MECKLENBURG | CHARLOTTE | TOBY CREEK GREENWAY (PHASE II). CONNECT UNCC TO NEARBY RETAIL AND RESIDENTIAL DEVELOPMENT. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | C-5225
MECKLENBURG | CHARLOTTE | TOBY CREEK GREENWAY, UNIVERSTIY CITY BOULEVARD TO ROCKLAND DRIVE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | C-5225A | EXEMPT | [10 empty] | UNDER CONSTRUCTION
MECKLENBURG | CHARLOTTE | TOBY CREEK GREENWAY, ROCKLAND DRIVE TO BLUE ROCK DRIVE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | C-5225B | EXEMPT | [10 empty] | COMPLETE
MECKLENBURG | CHARLOTTE | SR 4979 (BALLANTYNE COMMONS PARKWAY-MCKEE ROAD) AND NC 16 (PROVIDENCE ROAD) IN CHARLOTTE. CONSTRUCT AN ADDITIONAL LEFT TURN LANE ON SR 4979 AND A SECOND LEFT TURN LANE ON SOUTHBOUND NC 16. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | C-5534 | EXEMPT | BGDA |  |  |  |  | 2020 | 640000 |  |  | 640000 | UNDER CONSTRUCTION. ADDITIONAL STBG-DA FUNDS TO COVER ANTICIPDATED EXPENDITURES.
MECKLENBURG | CHARLOTTE | MECKLENBURG COUNTY AIR QUALITY -GRADE (GRANTS TO REPLACE AGING DIESEL ENGINES). REPLACE, REPOWER OR RETROFIT AGING DIESEL VEHICLES AND EQUIPMENT. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | C-5536 | EXEMPT | CMAQ |  |  |  |  | 2021 | 139000 |  |  | 139000
MECKLENBURG | CHARLOTTE | INTERSECTION OF TUCKASEEGEE-BERRYHILL-THRIFT ROADS IN CHARLOTTE. CONSTRUCT A TRAFFIC CIRCLE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | C-5538 | DIVISION 10 | CMAQ, L |  |  |  |  | 2021 | 3676000 |  |  | 3676000 | COMPLETE; $1.053M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
MECKLENBURG | CHARLOTTE | SR 2940 (EASTWAY DRIVE) AND SHAMROCK DRIVE. CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5803 | DIVISION 10 | L, T, T(DA) | 2024 | 3000000 |  |  | 2025 | 25638000 |  |  | 28638000 | LOCAL CONTRIBUTION OF $5M BY CITY OF CHARLOTTE FOR RIGHT-OF-WAY AND CONSTRUCTION - CITY PAYING 100% OF PRELIMINARY ENGINEERING AND UTILITIES. $7.82M IN STBG-DA FUNDS SWITCHED WITH $7.82M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP.
MECKLENBURG | CORNELIUS | INTERSECTION OF NC 115 AND POTTS STREET. CONSTRUCT IMPROVEMENTS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5873 | EXEMPT | BA, CMAQ, S(M) | 2020 | 1700000 |  |  | 2023 | 3416000 | 2020 | 100000 | 5216000 | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. PROJECT PART OF I-77 PPSL FUND SWAP.
MECKLENBURG | CORNELIUS | SR 2195 (TORRENCE CHAPEL ROAD) AND SR 5544 (WEST CATAWBA AVENUE). INTERSECTION IMPROVEMENTS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5906 | DIVISION 10 | BA, CMAQ, S(M) | 2020 | 1153000 |  |  | 2023 | 11841000 | 2020 | 849000 | 13843000 | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $8.644M IN STBG-DA AND $829K IN BA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
MECKLENBURG | CORNELIUS | SR 2415 (BAILEY ROAD), POOLE PLACE DRIVE TO US 21 (STATESVILLE ROAD). CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6105 | DIVISION 10 | BGANY, BGDA, L | 2022 | 2064000 |  |  | 2024 | 4633000 |  |  | 6697000 | $3M IN BGANY USED AS PART OF FUND SWAP
MECKLENBURG | DAVIDSON | POTTS-SLOAN-BEATTY CONNECTOR. CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5907 | DIVISION 10 | BA, T(DA) | 2020 | 1048000 |  |  | 2023 | 5056000 | 2021 | 207000 | 6311000 | RIGHT-OF-WAY IN PROGRESS. FUNDING IS SUBJECT TO ROADS BEING ADDED TO STATE MAINTAINED SYSTEM. ADDITIONAL FUNDS FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES.
MECKLENBURG | DAVIDSON | DAVIDSON-CONCORD ROAD AT ROBERT WALKER DRIVE. CONSTRUCT ROUNDABOUT. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6092 | EXEMPT | BGDA, CMAQ, L | 2022 | 795000 |  |  | 2023 | 2471000 | 2020 | 150000 | 3416000 | ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING TO COVER ANTICIPATED EXPENDITURES. $1.206M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
MECKLENBURG | GREYLOCK RIDGE ROAD | EAST JOHN STREET TO TANK TOWN ROAD. CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | HL-0025 | EXEMPT | BA | 2023 | 701000 |  |  | 2024 | 5892000 | 2022 | 1016000 | 7609000
MECKLENBURG | HUNTERSVILLE | INTERSECTION OF US 21 AND GILEAD ROAD IN HUNTERSVILLE. CONSTRUCT INTERSECTION IMPROVEMENTS, INCLUDING BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5114 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
MECKLENBURG | HUNTERSVILLE | MAIN STREET, NC 115 (OLD STATESVILLE ROAD)/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD) TO SOUTH OF RAMAH CHURCH ROAD. WIDEN AND REALIGN. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5908 | [11 empty] | RIGHT-OF-WAY IN PROGRESS; SEGMENTS A & B TO BE LET TOGETHER. STBG-DA FUNDS ON SEGMENT B ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. ADD'L FUNDING FOR ROW TO COVER ANTICIPATED EXPENDITURES. BGANY USED AS PART OF FUND SWAP.
MECKLENBURG | HUNTERSVILLE | MAIN STREET, NC 115 (OLD STATESVILLE ROAD)/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD) TO SOUTH OF RAMAH CHURCH ROAD. WIDEN AND REALIGN. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5908A | DIVISION 10 | BGANY, BGDA, L | 2020 | 825000 |  |  | 2021 | 4653000 |  |  | 5478000 | RIGHT-OF-WAY IN PROGRESS
MECKLENBURG | HUNTERSVILLE | INSTALL ROUNDABOUTS AT INTERSECTIONS OF NC 115/REALIGNED MAIN STREET (SOUTH OF SR 2439 (RAMAH CHURCH ROAD)) AND NC 115/SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD). | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5908B | EXEMPT | BGANY, BGDA, L | 2020 | 825000 |  |  | 2021 | 9204000 |  |  | 10029000 | RIGHT-OF-WAY IN PROGRESS
MECKLENBURG | HUNTERSVILLE | SR 2136 (GILEAD ROAD), SR 2120 (MCCOY ROAD) TO WYNFIELD CREEK PARKWAY. WIDEN ROADWAY TO 4-LANES DIVIDED. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6106 | DIVISION 10 | BGANY, BGDA, L | 2022 | 3134000 |  |  | 2025 | 10684000 |  |  | 13818000 | $8.750M IN BGANY USED AS PART OF FUND SWAP 12/20. 4-25-2022: $1.343M IN STBG-DA FUNDS SWITCHED WITH $1.343M IN BG-ANY AS PART OF FUND SWAP.
MECKLENBURG | I-277 | INSTALL SMART CUSHIONS AT VARIOUS EXITS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | HS-2010B | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2021 | 144000 |  |  | 144000
MECKLENBURG | I-277 | I-77 TO EAST 10TH STREET. RESURFACING AND BRIDGE REHABILITATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-5746
MECKLENBURG | I-277 | KENILWORTH AVENUE TO GRAHAM STREET. UPGRADE INTERCHANGES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6022 | [11 empty] | COORDINATE WITH U-6013
MECKLENBURG | I-277 | KENILWORTH AVENUE TO NORTH DAVIDSON STREET AND US 74 (INDEPENDENCE BOULEVARD) FROM I-277 TO PECAN AVENUE. UPGRADE INTERCHANGES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6022A | NOT FUNDED | NHP | NOT FUNDED | 55600000 | NOT FUNDED | 1100000 | NOT FUNDED | 250401000 |  |  | 307101000
MECKLENBURG | I-277 | NORTH DAVIDSON STREET TO GRAHAM STREET. UPGRADE INTERCHANGES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6022B | NOT FUNDED | NHP |  |  | NOT FUNDED | 200000 | NOT FUNDED | 148900000 |  |  | 149100000
MECKLENBURG | I-277 (BELK FRWY) | I-77 TO EAST STONEWALL STREET. BRIDGE REHABILITATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-5746A | STATEWIDE MOBILITY | [10 empty] | COMPLETE
MECKLENBURG | I-277 (BELK FRWY) | EAST STONEWALL STREET TO EAST 10TH STREET. BRIDGE REHABILITATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-5746B | STATEWIDE MOBILITY | [10 empty] | COMPLETE
MECKLENBURG | I-277 (BROOKSHIRE FREEWAY) | WEST OF I-77 TO EAST OF I-77. BRIDGE REHABILITATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6052 | STATEWIDE MOBILITY | BGDA, NHPIM |  |  |  |  | 2023 | 8000000 |  |  | 8000000 | $5M IN NHPIM FUNDS SWITCHED WITH $5M IN BGDA AS PART OF FUND SWAP.
MECKLENBURG | I-277 (BROOKSHIRE FRWY) | I-77 TO EAST 10TH STREET. RESURFACE ROADWAY AND REHABILITATE BRIDGES FROM JOHNSON STREET TO EAST 10TH STREET. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-5746C | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2022 | 29400000 |  |  | 29400000 | UNDER CONSTRUCTION.
MECKLENBURG | I-485 | REPLACE OVERHEAD SIGNS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | HL-0038D | EXEMPT | BGDACV |  |  |  |  | 2022 | 705000 |  |  | 705000
MECKLENBURG | I-485 | I-485, I-77 SOUTH OF CHARLOTTE TO US 74 (INDEPENDENCE BOULEVARD). ADD ONE EXPRESS LANE IN EACH DIRECTION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-5507 | STATEWIDE MOBILITY | T |  |  |  |  | 2019 | 306756000 |  |  | 306756000 | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT
MECKLENBURG | I-485 | I-85 TO ROCKY RIVER ROAD. PAVEMENT REHABILITATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-5798 | STATEWIDE MOBILITY | [10 empty] | COMPLETE
MECKLENBURG | I-485 | I-77 TO NC 49. PAVEMENT REHABILITATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-5828 | STATEWIDE MOBILITY | HFB, NHPIM |  |  |  |  | 2025 | 10630000 |  |  | 10630000 | $2.9M IS FROM HIGH VALUE BRIDGE FUNDS
MECKLENBURG | I-485 | PAVEMENT AND BRIDGE REHABILITATION AT OAKDALE ROAD INTERCHANGE AT MILEMARKER 17.2. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-5861 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2023 | 1000000 |  |  | 1000000
MECKLENBURG | I-485 | BLAIR ROAD TO IDLEWILD ROAD. PAVEMENT REHABILITATION | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-5904 | STATEWIDE MOBILITY | NHPIM, S(M) |  |  |  |  | 2020 | 9801000 |  |  | 9801000 | GARVEE BOND FUNDING - $6,049,190 FOR CONSTRUCTION, PAYBACK FY 2020-2034
MECKLENBURG | I-485 | I-485 AND NC 16 (PROVIDENCE ROAD). CONSTRUCT INTERCHANGE IMPROVEMENTS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-5963 | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 11100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 28900000 |  |  | 41300000
MECKLENBURG | I-485 | NC 16 (BROOKSHIRE BOULEVARD) INTERCHANGE. CONSTRUCT INTERCHANGE IMPROVEMENTS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-5973 | REGION E | T |  |  | 2022 | 165000 | 2023 | 8000000 |  |  | 8165000 | BUILD NC BOND FUNDING: $3.5M FOR CONSTRUCTION, PAYBACK FY 2023-2036 (FY 2022 / YR 4 SALE)
MECKLENBURG | I-485 | NC 51 (PINEVILLE-MATTHEWS ROAD) INTERCHNAGE. IMPROVE INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6015 | NOT FUNDED | T | NOT FUNDED | 8400000 | NOT FUNDED | 1100000 | NOT FUNDED | 9999000 |  |  | 19499000
MECKLENBURG | I-485 | NC 49 (SOUTH TRYON STREET) INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6019 | NOT FUNDED | NHP | NOT FUNDED | 14900000 | NOT FUNDED | 4700000 | NOT FUNDED | 20701000 |  |  | 40301000
MECKLENBURG | I-485 | SR 3468 (WEDDINGTON ROAD). CONSTRUCT INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | R-0211EC | DIVISION 10 | T |  |  |  |  | 2019 | 9000000 |  |  | 9000000
MECKLENBURG | I-485 | WEST OF I-77 SOUTH TO US 29-74 | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | R-2248A | [11 empty] | COMPLETE
MECKLENBURG | I-485 | NORTH OF US 29/US 74 (WILKINSON BOULEVARD) TO NORTH OF I-85 | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | R-2248BA | [11 empty] | COMPLETE
MECKLENBURG | I-485 | NORTH OF I-85 TO NORTH OF NC 27 | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | R-2248BB | [11 empty] | COMPLETE
MECKLENBURG | I-485 | NORTH OF NC 27 (MOUNT HOLLY ROAD) TO EAST OF SR 2042 (OAKDALE ROAD) | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | R-2248C | [11 empty] | COMPLETE
MECKLENBURG | I-485 | EAST OF SR 2042 (OAKDALE ROAD) TO EAST OF NC 115 (OLD STATESVILLE ROAD) | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | R-2248D | [11 empty] | COMPLETE
MECKLENBURG | I-485 | EAST OF NC 115 (OLD STATESVILLE ROAD) TO I-85 NORTH | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | R-2248E | PRE-STI (TRANSITION) | NHP |  |  |  |  | 2010 | 10968000 |  |  | 10968000 | COMPLETE. GARVEE BOND FUNDING: $50M FOR CONSTRUCTION, PAYBACK FY 2010-2021
MECKLENBURG | I-485 | ITS FOR R-2248 E | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | R-2248EA | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
MECKLENBURG | I-485 | EDINMEADOW DRIVE NEPA STUDY | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | R-2248EB
MECKLENBURG | I-485 | I-485, WEST OF I-77 TO ARROWOOD ROAD-BROWN GRIER ROAD | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | R-2248F | [11 empty] | COMPLETE
MECKLENBURG | I-485 | I-485 INTERCHANGE WITH SR 2042 (OAKDALE ROAD) | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | R-2248G | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
MECKLENBURG | I-485 | I-485 INTERCHANGE WITH SR 1148 (GARRISON ROAD) | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | R-2248H | [11 empty] | COMPLETE
MECKLENBURG | I-485 (CHARLOTTE SOUTHERN OUTER LOOP) | WEST OF I-77 TO US 74. MULTI-LANE FREEWAY ON NEW LOCATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | R-0211 | [11 empty] | UNDER CONSTRUCTION. PROJECT LET WITH I-5507.
MECKLENBURG | I-485 (CHARLOTTE WESTERN OUTER LOOP) | WEST OF I-77 TO I-85 NORTH. FREEWAY ON NEW LOCATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | R-2248 | [11 empty] | GARVEE BOND FUNDING: $50M FOR CONSTRUCTION, PAYBACK FY 2010-2021
MECKLENBURG | I-77 | I-277 (BROOKSHIRE FREEWAY) IN CHARLOTTE TO SR 5544 (WEST CATAWBA AVENUE - EXIT 28). ADDITIONAL LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-3311 | [11 empty] | PLANNING/DESIGN IN PROGRESS - FUNDING FOR I-3311 C INCLUDED IN I-5405
MECKLENBURG | I-77 | I-85 TO NORTH OF I-485 (CHARLOTTE OUTER LOOP) | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-3311A | [11 empty] | COMPLETE
MECKLENBURG | I-77 | NC 73 (SAM FURR ROAD), WEST OF I-77 TO EAST OF I-77; SR 2136 (GILEAD ROAD), WEST OF I-77 TO EAST OF I-77 | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-3311AA | [11 empty] | COMPLETE
MECKLENBURG | I-77 | I-485 (CHARLOTTE OUTER LOOP) TO SR 5544 (WEST CATAWBA AVENUE) EXIT 28. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-3311B | NOT FUNDED | NHP | NOT FUNDED | 100000 |  |  | NOT FUNDED | 47000000 |  |  | 47100000
MECKLENBURG | I-77 | I-277 TO NORTH OF I-85. CONSTRUCT HIGH OCCUPANCY TOLL (HOT) LANES AND CONVERT EXISTING HIGH OCCUPANCY VEHICLE (HOV) LANES TO HOT LANES. I-277 (BROOKSHIRE FREEWAY), I-77 TO NORTH BREVARD STREET. CONSTRUCT HOT LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-3311C | [11 empty] | UNDER CONSTRUCTION WITH PROJECT I-5405
MECKLENBURG | I-77 | I-485 (CHARLOTTE OUTER LOOP) TO SR 2136 (GILEAD ROAD) | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-3311D | [11 empty] | COMPLETE
MECKLENBURG | I-77 | NORTH OF I-277/NC 16 (BROOKSHIRE FREEWAY) TO NORTH OF I-85. WORK TO BE ACCOMPLISHED IN I-3311 C. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-3311E
MECKLENBURG | I-77 | I-77/EXIT 30 (GRIFFITH STREET) INTERCHANGE. CONSTRUCT ROUNDABOUTS AT NORTHBOUND AND SOUTHBOUND RAMP TERMINI. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-4750AC | EXEMPT | [10 empty] | COMPLETE
MECKLENBURG | I-77 | SR 2136 (GILEAD ROAD) INTERCHANGE. UPGRADE EXISTING INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-5714 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
MECKLENBURG | I-77 | NC 73 INTERCHANGE. UPGRADE EXISTING INTERCHANGE TO SPLIT DIAMOND CONFIGURATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-5715 | STATEWIDE MOBILITY | NHP | 2023 | 1551000 | 2023 | 2400000 | 2025 | 39499000 |  |  | 43450000
MECKLENBURG | I-77 | SOUTH CAROLINA STATE LINE TO I-277/NC 16 (BROOKSHIRE FREEWAY). WIDEN EXISTING FREEWAY TO TEN LANES BY CONSTRUCTING MANAGED LANES, RECONSTRUCT I-277 INTERCHANGES, AND INSTALL RAMP METERS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-5718
MECKLENBURG | I-77 | SOUTH CAROLINA STATE LINE TO I-277/US 74 (BELK FREEWAY). WIDEN EXISTING FREEWAY TO TEN LANES BY CONSTRUCTING MANAGED LANES, RECONSTRUCT I-77/I-277 (BELK FREEWAY) INTERCHANGE, AND INSTALL RAMP METERS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-5718A | STATEWIDE MOBILITY | BOND R, NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 660000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 30900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 699999000 |  |  | 1390899000
MECKLENBURG | I-77 | I-277/US 74 (BELK FREEWAY) TO I-277/NC 16 (BROOKSHIRE FREEWAY). WIDEN EXISTING FREEWAY TO TEN LANES BY CONSTRUCTING MANAGED LANES, RECONSTRUCT I-77/I-277 (BROOKSHIRE FREEWAY) INTERCHANGE, AND INSTALL RAMP METERS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-5718B
MECKLENBURG | I-77 | I-277 TO 0.7 MILE NORTH OF NC 27. PAVEMENT REHABILITATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-5769 | STATEWIDE MOBILITY | NHPIM, S(M) |  |  |  |  | 2020 | 14997000 |  |  | 14997000 | GARVEE BOND FUNDING: $3,038,925 FOR CONSTRUCTION, PAYBACK FY 2020-2034
MECKLENBURG | I-77 | I-85 INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6014 | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 96100000 |  |  | 97700000
MECKLENBURG | I-77 | US 21/SR 2108 (SUNSET ROAD) INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6056 | NOT FUNDED | NHP | NOT FUNDED | 300000 | NOT FUNDED | 200000 | NOT FUNDED | 8200000 |  |  | 8700000
MECKLENBURG | I-85 | CONCRETE PAVEMENT JOINT 0.3 MILES SOUTH OF NC 16 TO CONCRETE PAVEMENT JOINT SOUTH OF SR 1601 (MOORES CHAPEL ROAD). PAVEMENT AND BRIDGE REHABILITATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-5770 | STATEWIDE MOBILITY | [10 empty] | PROJECT COMBINED WITH I-5796 - UNDER CONSTRUCTION
MECKLENBURG | I-85 | 0.1 MILE NORTH OF SR 5901 (BILLY GRAHAM PKWY) TO 0.3 MILE SOUTH OF NC 16 AT MILE MARKER 35.93. PAVEMENT REHABILITATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-5796 | STATEWIDE MOBILITY | [10 empty] | TO BE LET WITH I-5770 - UNDER CONSTRUCTION
MECKLENBURG | I-85 | CONCRETE PAVEMENT JOINT AT US 29/NC 49 CONNECTOR TO CONCRETE PAVEMENT JOINT NORTH OF NC 73. PAVEMENT PRESERVATION, STRUCTURE PRESERVATION, MARKERS, AND MARKINGS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-5826 | STATEWIDE MOBILITY | NHPIM, S(M) |  |  |  |  | 2020 | 8940000 |  |  | 8940000 | I-5860 REMOVED AND COMBINED WITH I-5826. GARVEE BOND FUNDING - $2M FOR CONSTRUCTION, PAYBACK FY 2020-2034
MECKLENBURG | I-85 | GASTON COUNTY LINE TO 0.7 MILES NORTH OF GASTON COUNTY LINE. INCLUDES RAMPS FROM GASTON COUNTY LINE TO GLENWOOD AVENUE. PAVEMENT REHABILITATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-5837 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2022 | 3368000 |  |  | 3368000
MECKLENBURG | I-85 | REHABIILITATE BRIDGES 590203 (I-85 NB) AND 590204 (I-85 SB) OVER SEABOARD COASTLINE RAILROAD. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-5838 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2022 | 900000 |  |  | 900000
MECKLENBURG | I-85 | 0.2 MILE WEST OF NC 16 (BROOKSHIRE BOULEVARD) TO CONCRETE PAVEMENT JOINT AT US 29/NC 49 CONNECTOR. PAVEMENT REHABILITATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-5905 | STATEWIDE MOBILITY | BGDA, NHPIM, S(M) |  |  |  |  | 2021 | 20777000 |  |  | 20777000 | COMBINED WITH I-5906.
MECKLENBURG | I-85 | I-485 INTERCHANGE NORTHEAST OF CHARLOTTE. IMPROVE INTERCHANGE | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6012 | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 11500000 |  |  | 13500000
MECKLENBURG | I-85 | NC 24 (W.T. HARRIS BOULEVARD) INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6013 | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 16000000 |  |  | 17100000
MECKLENBURG | I-85 | I-485 INTERCHANGE WEST OF CHARLOTTE. IMPROVE INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6016 | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 22400000 |  |  | 24800000
MECKLENBURG | I-85 | SR 2472 (MALLARD CREEK CHURCH ROAD) INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6017 | NOT FUNDED | NHP | NOT FUNDED | 1100000 | NOT FUNDED | 1800000 | NOT FUNDED | 13099000 |  |  | 15999000
MECKLENBURG | I-85 | NC 16 (BROOKSHIRE BOULEVARD) INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6020 | NOT FUNDED | NHP | NOT FUNDED | 10000000 | NOT FUNDED | 2000000 | NOT FUNDED | 15299000 |  |  | 27299000
MECKLENBURG | I-85 | SR 2480 (SUGAR CREEK ROAD) INTERCHANGE. IMPROVE INTERCHANGE | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6053 | NOT FUNDED | NHP | NOT FUNDED | 51100000 | NOT FUNDED | 2200000 | NOT FUNDED | 21300000 |  |  | 74600000
MECKLENBURG | MECKLENBURG COUNTY | SR 2108 (SUNSET BOULEVARD), SR 2025 (MIRANDA ROAD) AND SR 2040 (LAWING ROAD) NEAR CHARLOTTE. SAFETY IMPROVEMENTS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | W-5710X | DIVISION 10 | BGANY, HSIP, L |  |  |  |  | 2025 | 9214000 |  |  | 9214000 | $3.482M IN STBG-DA FUNDS SWITCHED WITH $3.482M IN BGANY AS PART OF FUND SWAP.
MECKLENBURG | MICHAEL BAKER ROAD | REPLACE BRIDGE 590210 OVER BRIAR CREEK IN CHARLOTTE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | B-5378 | DIVISION 10 | [10 empty] | PROJECT ADMINISTERED BY CITY OF CHARLOTTE - MUNICIPAL BRIDGE. UNDER CONSTRUCTION
MECKLENBURG | MORRIS FIELD DRIVE | REPLACE BRIDGE 590443 OVER SOUTHERN RAILROAD. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | B-5931 | DIVISION 10 | BGOFF, L |  |  |  |  | 2023 | 2750000 |  |  | 2750000 | UNDER CONSTRUCTION. PLANNING/DESIGN BY CITY OF CHARLOTTE
MECKLENBURG | NC 115 | HICKORY STREET INTERSECTION. IMPROVE INTERSECTION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | C-5613J | EXEMPT | CMAQ, L | 2022 | 75000 |  |  | 2024 | 1227000 |  |  | 1302000
MECKLENBURG | NC 115 | SR 2427 (MCCORD ROAD) TO SAM FURR ROAD. IMPROVE CORRIDOR. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | HL-0056 | EXEMPT | L, T(DA) | 2025 | 2852000 |  |  | 2027 | 4938000 | 2024 | 751000 | 8541000 | $526K IN STBG-DA FUNDS SWITCHED WITH $526K IN T(DA) FOR PE, $1.996M IN STBG-DA FUNDS SWITCHED WITH $1.996M IN T(DA) FOR ROW, AND $3.457M IN STBG-DA FUNDS SWITCHED WITH $3.457M IN T(DA) FOR CON AS PART OF FUND SWAP.
MECKLENBURG | NC 115 (OLD STATESVILLE ROAD) | NC 24 (HARRIS BOULEVARD) TO I-485. WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5772 | REGION E | T | 2028 | 6500000 | 2028 | 4300000 | 2030 | 33700000 |  |  | 44500000
MECKLENBURG | NC 16 (BROOKSHIRE BOULEVARD) |  | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5955 | REGION E
MECKLENBURG | NC 16 (BROOKSHIRE BOULEVARD) | IMPROVE I-85 NORTHBOUND RAMP TO EASTBOUND NC 16. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5955A | REGION E | T |  |  |  |  | 2023 | 1100000 |  |  | 1100000
MECKLENBURG | NC 16 (BROOKSHIRE BOULEVARD) | I-85 TO IDAHO DRIVE. ADD WESTBOUND THROUGH LANE ON NC 16 BETWEEN A POINT WEST OF IDAHO DRIVE AND I-85. CONVERT NC 16 AND IDAHO DRIVE INTERSECTION TO AN INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5955B | REGION E | T | 2025 | 4300000 | 2025 | 345000 | 2028 | 12700000 |  |  | 17345000
MECKLENBURG | NC 16 (BROOKSHIRE BOULEVARD) | NC 16 (BROOKSHIRE BOULEVARD) AT SR 2004 (MOUNT HOLLY HUNTERSVILLE ROAD). CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6084 | REGION E | T |  |  |  |  | 2018 | 1963000 |  |  | 1963000 | ECONOMIC DEVELOPMENT PROJECT
MECKLENBURG | NC 160 | REPLACE BRIDGE 590054 OVER SOUTHERN RAILROAD. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | B-5983 | REGION E | HFB | 2023 | 336000 | 2023 | 336000 | 2024 | 5601000 |  |  | 6273000
MECKLENBURG | NC 160 | SOUTH CAROLINA LINE TO I-485. WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5766
MECKLENBURG | NC 160 | SOUTH CAROLINA LINE TO NC 49 (SOUTH TRYON ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5766A | REGION E | T | 2025 | 20500000 | 2025 | 4100000 | 2028 | 65399000 |  |  | 89999000
MECKLENBURG | NC 160 | NC 49 (SOUTH TRYON ROAD) TO I-485. WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5766B | REGION E | T | 2025 | 65400000 | 2025 | 6500000 | 2028 | 65799000 |  |  | 137699000
MECKLENBURG | NC 24 WT HARRIS BOULEVARD | SR 2004 (MOUNT HOLLY-HUNTERSVILLE ROAD) TO I-85 NORTH RAMP. INSTALL OVERHEAD STREET LIGHTS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | HL-0057 | DIVISION 10 | BA, L |  |  |  |  | 2023 | 1535000 |  |  | 1535000
MECKLENBURG | NC 24, NC 27 | SR 3110 (ARLINGTON CHURCH ROAD) NEAR CHARLOTTE. CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | HS-2010A | REGION E | HSIP | 2022 | 175000 |  |  | 2023 | 1350000 |  |  | 1525000
MECKLENBURG | NC 27 (FREEDOM DRIVE) | SR 1644 (TODDVILLE ROAD) TO SR 1600 (MOORES CHAPEL ROAD). WIDEN TO 4-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5957 | REGION E | T | 2026 | 13100000 | 2026 | 500000 | 2028 | 17899000 |  |  | 31499000
MECKLENBURG | NC 49 | REPLACE BRIDGE 590088 OVER SOUTHERN RAILROAD. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | B-5984 | REGION E | HFB | 2023 | 354000 | 2023 | 354000 | 2024 | 6367000 |  |  | 7075000
MECKLENBURG | NC 49 & BACK CREEK CHURCH ROAD | NC 49, JOHN KIRK DRIVE TO I-485. WIDEN EXISTING ROADWAY. REALIGN BACK CREEK CHURCH ROAD ON NEW LOCATION TO THE NC 49 AND MALLARD CREEK CHURCH ROAD INTERSECTION. CLOSE EXISTING AT GRADE RAIL CROSSING AT NC 49 AND BACK CREEK CHURCH ROAD. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5768 | REGION E | L, T | 2026 | 29400000 | 2026 | 4000000 | 2029 | 56300000 |  |  | 89700000 | LOCAL FUNDING PROVIDED BY THE CITY OF CHARLOTTE
MECKLENBURG | NC 49 (SOUTH TRYON STREET) | NC 49 (SOUTH TRYON STREET) AT GENERAL DRIVE; AND, NC 49 (SOUTH TRYON STREET) AT SR 1347 (NEVADA BOULEVARD). INSTALL TRAFFIC SIGNAL AT NC 49 AND GENERAL DRIVE, AND CONVERT NC 49 AT SR 1347 (NEVADA BOULEVARD) TO A DIRECTIONAL CROSSOVER. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | HS-2010E | REGION E | HSIP |  |  | 2025 | 25000 | 2025 | 534000 |  |  | 559000
MECKLENBURG | NC 51 | NC 51 AND POLK STREET. INSTALL PEDESTRIAN SIGNALS AND ACCOMMODATIONS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | HS-2010G | REGION E | HSIP |  |  |  |  | 2024 | 144000 |  |  | 144000
MECKLENBURG | NC 51 | MATTHEWS TOWNSHIP PARKWAY TO SR 3128 (LAWYERS ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5007 | REGION E | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 100000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 58699000 |  |  | 169199000
MECKLENBURG | NC 51 | PARK ROAD TO CARMEL ROAD IN PINEVILLE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6086 | EXEMPT | BGANY, L |  |  |  |  | 2025 | 7553000 |  |  | 7553000 | PE AND ROW FUNDED UNDER W-5710R; $5.643M IN BGANY USED AS PART OF FUND SWAP
MECKLENBURG | NC 51 (MATTHEWS TOWNSHIP PARKWAY) | SR 3356 (SARDIS ROAD) TO SR 1010 (EAST JOHN STREET/ MONROE ROAD). WIDEN EXISTING ROADWAY. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5763 | REGION E | T | 2026 | 16000000 | 2026 | 5600000 | 2029 | 21700000 |  |  | 43300000
MECKLENBURG | NC 73 | US 21 TO SR 2693 (DAVIDSON-CONCORD ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | R-2632 | [11 empty] | COORDINATE WITH R-5706A & B.
MECKLENBURG | NC 73 | US 21 TO NC 115. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | R-2632AA | [11 empty] | COMPLETE
MECKLENBURG | NC 73 | NC 115 TO SR 2693 (DAVIDSON-CONCORD ROAD). | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | R-2632AB | REGION E | NHP | 2023 | 4400000 | 2023 | 4700000 | 2026 | 46900000 |  |  | 56000000
MECKLENBURG | NC 73 | NC 73 AT NC 115. CONVERT RIGHT TURN LANE ON NC 115 SOUTHBOUND TO A THROUGH LANE AND WIDEN FOR MERGING TAPER. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | R-2632AC | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
MECKLENBURG | NC 73 | VANCE ROAD EXTENSION/BEATTIES FORD ROAD TO SR 5544 (WEST CATAWBA AVENUE). | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | R-5721B | REGION E | T | 2023 | 15497000 | 2023 | 3000000 | 2026 | 28099000 |  |  | 46596000
MECKLENBURG | NC 73 (SAM FURR ROAD) | SR 5544 (WEST CATAWBA AVENUE) TO SR 2316 (NORTHCROSS DRIVE). WIDEN EXISTING ROADWAY. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5765 | REGION E | T | 2023 | 58500000 | 2023 | 7500000 | 2026 | 31499000 |  |  | 97499000 | COORDINATE WITH R-5721.
MECKLENBURG | NEW ROUTE | SR 2467 (MALLARD CREEK ROAD) TO IBM DRIVE. CONSTRUCT NEW CONNECTOR ROAD AND MULTI-USE PATH. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2507AA | PRE-STI (TRANSITION) | [10 empty] | IMPROVEMENTS CONSTRUCTED UNDER U-2507A
MECKLENBURG | NEW ROUTE | SR 3457 (CAMPUS RIDGE ROAD) TO SR 3448 (PLEASANT PLAINS ROAD) IN MATTHEWS. CONSTRUCT TWO LANE ROADWAY ON NEW LOCATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-4713 | [11 empty] | OTHER FUNDS PROVIDED BY TOWN OF MATTHEWS. U-4713A TO BE LET WITH U-4714AC AND B.
MECKLENBURG | NEW ROUTE | SR 3168 (SAM NEWELL ROAD) TO SR 5215 (NORTHEAST PARKWAY. CONSTRUCT MULTI-LANES ON NEW LOCATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6166 | NOT FUNDED | T | NOT FUNDED | 6600000 | NOT FUNDED | 500000 | NOT FUNDED | 8498000 |  |  | 15598000
MECKLENBURG | NORTH DAVIDSON STREET | CONSTRUCT SIDEWALK FROM EAST 37TH STREET TO BEARWOOD AVENUE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5008A | PRE-STI (TRANSITION) | DP | 2022 | 1000000 | 2022 | 25000 | 2023 | 1200000 |  |  | 2225000
MECKLENBURG | NORTH UNIVERSITY RESEARCH PARK I-85 OVERPASS | SR 2722 (LOUIS ROSE PLACE) TO DOUG MAYES PLACE. CONSTRUCT NEW ROUTE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5874 | DIVISION 10 | BGANY, BGDA, L, O | 2020 | 3346000 |  |  | 2022 | 25481000 |  |  | 28827000 | RIGHT-OF-WAY IN PROGRESS; OTHER FUNDS PROVIDED BY THE CITY OF CHARLOTTE; $1.750M IN CMAQ FUNDS PREVIOUSLY AUTHORIZED REPLACED WITH STBG-DA FUNDS, AS PROJECT IS NOT ELIGIBLE FOR CMAQ FUNDS. ADDITIONAL FUNDING FOR ROW TO COVER ANTICIPATED EXPENDITURES.
MECKLENBURG | NORTHCROSS DRIVE EXTENSION | NC 73 IN HUNTERSVILLE TO WESTMORELAND ROAD IN CORNELIUS. CONSTRUCT ROAD ON NEW LOCATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5108 | PRE-STI (TRANSITION) | BA, BGANY, L, S(M) | 2020 | 3500000 |  |  | 2023 | 11772000 | 2020 | 960000 | 16232000 | RIGHT-OF-WAY IN PROGRESS. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $6.150M IN BGANY USED AS PART OF FUND SWAP.
MECKLENBURG | PINEVILLE | NC 51 CORRIDOR ACCESS MANAGEMENT. CLOSURE OF EXISTING JOHNSTON DRIVE INTERSECTION ALONG NC 51 AND RELOCATION OF JOHNSTON DRIVE TO LINE UP WITH EXISTING CHURCH STREET INTERSECTION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | EB-5949 | DIVISION 10 | BGDA, L, O |  |  |  |  | 2022 | 4404000 |  |  | 4404000 | OTHER FUNDS PROVIDED BY THE TOWN OF PINEVILLE; OTHER FUNDS ARE $1,435,000 AN EARMARK THE TOWN OF PINEVILLE RECEIVED WITH $358,750 IN LOCAL MATCH
MECKLENBURG | REA ROAD | I-485 OUTER LOOP TO WILLIAMS POND LANE. WIDEN ROADWAY. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | HL-0023 | EXEMPT | BA, O | 2023 | 1557000 |  |  | 2024 | 5469000 |  |  | 7026000 | OTHER FUNDS PROVIDED BY CITY OF CHARLOTTE
MECKLENBURG | SARDIS LANE | REPLACE BRIDGE 590433 OVER MCALPINE CREEK. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | B-5930 | DIVISION 10 | BGOFF, L |  |  |  |  | 2021 | 2000000 |  |  | 2000000 | PROJECT ADMINISTERED BY CITY OF CHARLOTTE
MECKLENBURG | SR 1009 (JOHN STREET-OLD MONROE ROAD) | SR 3448-SR 3474 (TRADE STREET) TO WEST OF I-485. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-4714AA | DIVISION 10 | BGANY, T | 2028 | 9148000 | 2028 | 1900000 | 2030 | 14300000 |  |  | 25348000
MECKLENBURG | SR 1009 (JOHN STREET-OLD MONROE ROAD) | I-485. IMPROVE INTERCHANGE | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-4714AB | DIVISION 10 | [10 empty] | LET WITH I-5507
MECKLENBURG | SR 1009 (MONROE ROAD) | INTERSECTION OF SR 1009 (MONROE ROAD) AND RAMA ROAD/IDLEWILD ROAD. CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5805 | DIVISION 10 | BGANY, L, T | 2020 | 750000 |  |  | 2023 | 7440000 |  |  | 8190000 | $4.24M IN BGANY USED AS PART OF FUND SWAP.
MECKLENBURG | SR 1138 WESTBOUND | REPLACE BRIDGE 590001 OVER SUGAR CREEK. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | B-5990 | DIVISION 10 | BFP | 2023 | 174000 | 2023 | 174000 | 2025 | 3127000 |  |  | 3475000
MECKLENBURG | SR 1441 (CAROWINDS BOULEVARD EXTENSION) | NC 49 (SOUTH TRYON STREET TO NC 160 (STEELE CREEK ROAD). CONSTRUCT TWO LANE DIVIDED ROADWAY ON NEW LOCATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6168 | NOT FUNDED | T | NOT FUNDED | 9700000 | NOT FUNDED | 1600000 | NOT FUNDED | 18800000 |  |  | 30100000
MECKLENBURG | SR 2112 (LAKEVIEW ROAD) | REAMES ROAD TO NC 115. UPGRADE ROADWAY. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5905 | [11 empty] | SEGMENTS A AND B TO BE LET TOGETHER. STBG-DA FUNDS ON SEGMENT B ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT.
MECKLENBURG | SR 2112 (LAKEVIEW ROAD) | REAMES ROAD TO NC 115. UPGRADE ROADWAY. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5905A | DIVISION 10 | BA, BGDA |  |  |  |  | 2021 | 8661000 |  |  | 8661000 | RIGHT-OF-WAY IN PROGRESS
MECKLENBURG | SR 2112 (LAKEVIEW ROAD) | IMPROVE INTERSECTIONS OF SR 2112 (LAKEVIEW ROAD)/NC 24 (HARRIS BOULEVARD) AND SR 2112 (LAKEVIEW ROAD)/US 21 (STATESVILLE ROAD). | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5905B | EXEMPT | BA, BGDA |  |  |  |  | 2021 | 3162000 |  |  | 3162000
MECKLENBURG | SR 2136 (GILEAD ROAD) | US 21 (STATESVILLE ROAD) TO NC 115. WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5807 | DIVISION 10 | T | 2028 | 33700000 | 2028 | 2000000 | 2030 | 8700000 |  |  | 44400000
MECKLENBURG | SR 2467 (MALLARD CREEK ROAD) | SR 2480 (SUGAR CREEK ROAD) TO SR 2472 (MALLARD CREEK CHURCH ROAD) IN CHARLOTTE. WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2507
MECKLENBURG | SR 2467 (MALLARD CREEK ROAD) | SR 2480 (SUGAR CREEK ROAD) TO SR 2665 (HARRIS BOULEVARD). WIDEN TO FOUR-LANES DIVIDED. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2507A | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
MECKLENBURG | SR 2467 (MALLARD CREEK ROAD) | SR 2665 (W.T. HARRIS BOULEVARD) TO SR 2472 (MALLARD CREEK CHURCH ROAD) | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2507B | [11 empty] | COMPLETE
MECKLENBURG | SR 2467 (MALLARD CREEK ROAD) | SR 2472 (MALLARD CREEK CHURCH ROAD) TO BREEZEWOOD DRIVE. WIDEN TO FOUR-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6028 | DIVISION 10 | T | 2026 | 7700000 | 2026 | 4000000 | 2028 | 20400000 |  |  | 32100000
MECKLENBURG | SR 2822 (ROBINSON CHURCH ROAD) | NC 24 TO PLOTT ROAD. WIDEN CORRIDOR. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | HL-0053 | DIVISION 10 | L, T(DA) |  |  |  |  | 2025 | 12454000 |  |  | 12454000 | $6.227M IN STBG-DA FUNDS SWITCHED WITH $6.227M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP.
MECKLENBURG | SR 2975 (SUGAR CREEK ROAD) | CONSTRUCT GRADE SEPARATION OVER NORTH CAROLINA RAILROAD/NORFOLK SOUTHERN RAILWAY CROSSING 715 352H AND THE CLOSURE OF CRAIGHEAD ROAD CROSSING 715 355D. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5008 | [11 empty] | DP ARE FEDERAL RAILROAD ADMINISTRATION (FRA) PRIIA GRANT, NCRR, NSR AND CITY OF CHARLOTTE FUNDS
MECKLENBURG | SR 3156 (MARGARET WALLACE ROAD) | SR 3156 (MARGARET WALLACE ROAD) AND AREQUIPA DRIVE. IMPROVE INTERSECTION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2509EA | DIVISION 10 | L, T(DA) | 2025 | 8568000 |  |  | 2027 | 5796000 |  |  | 14364000 | PROJECT PREVIOUSLY HL-0054.$5.568M IN STBG-DA FUNDS SWITCHED WITH $5.568M IN STATE TRUST FUNDS "T(DA)" FOR ROW, AND $3.767M IN STBG-DA FUNDS SWITCHED WITH $3.767M IN STATE TRUST FUNDS "T(DA)" FOR CON AS PART OF FUND SWAP.
MECKLENBURG | SR 3440 (MCKEE ROAD) EXTENSION | SR 3448 (PLEASANT PLAINS ROAD) TO SR 1009 (JOHN STREET) | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-4713A | DIVISION 10 | L, T | 2020 | 2680000 | 2021 | 500000 | 2024 | 8260000 | 2020 | 1155000 | 12595000 | BUILD NC BOND FUNDING: $888,488 FOR PE, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $280,117 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $4M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE)
MECKLENBURG | SR 3448 (SOUTH TRADE STREET) | FULLWOOD LANE TO WEDDINGTON ROAD. WIDEN TO FOUR-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5804
MECKLENBURG | SR 3448 (SOUTH TRADE STREET) | FULLWOOD LANE TO FOUR MILE CREEK. WIDEN TO FOUR-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5804A | [11 empty] | COMPLETE - BY TOWN OF MATTHEWS USING TOWN FUNDS.
MECKLENBURG | SR 3448 (SOUTH TRADE STREET) | FOUR MILE CREEK TO WEDDINGTON ROAD. WIDEN TO FOUR-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5804B | DIVISION 10 | T |  |  |  |  | 2019 | 1470000 |  |  | 1470000 | COMPLETE. BUILD NC BOND FUNDING: $1.134 M FOR CONSTRUCTION, PAYBACK FY 2019-2033 (FY 2019 / YR 1 SALE).
MECKLENBURG | SR 3468 (WEDDINGTON ROAD) | SR 3440 (MCKEE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | HL-0024 | EXEMPT | BA | 2023 | 1500000 | 2023 | 800000 | 2025 | 5923000 | 2021 | 1211000 | 9434000
MECKLENBURG | SR 3687 (PARK ROAD) | JOHNSTON ROAD TO NC 51 (PINEVILLE-MATTHEWS ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6165 | NOT FUNDED | BGANY | NOT FUNDED | 21255000 | NOT FUNDED | 2000000 | NOT FUNDED | 9400000 |  |  | 32655000
MECKLENBURG | SR 4979 (BALLANTYNE COMMONS PARKWAY) | ANNALEXA LANE TO WILLIAMS POND LANE. WIDEN TO FOUR-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6030 | NOT FUNDED | T | NOT FUNDED | 22700000 | NOT FUNDED | 4610000 | NOT FUNDED | 24298000 |  |  | 51608000
MECKLENBURG | SR 5544 (WEST CATAWBA AVENUE) | NC 73 (SAM FURR ROAD) TO EAST OF SR 2195 (TORRENCE CHAPEL ROAD). WIDEN TO FOUR-LANES DIVIDED. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | R-2555
MECKLENBURG | SR 5544 (WEST CATAWBA AVENUE) | SR 2151 (JETTON ROAD) TO SR 2195 (TORRENCE CHAPEL ROAD). WIDEN TO FOUR-LANES DIVIDED. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | R-2555A | [11 empty] | COMPLETE
MECKLENBURG | SR 5544 (WEST CATAWBA AVENUE) | NC 73 (SAM FURR ROAD) TO SR 2151 (JETTON ROAD). WIDEN TO FOUR-LANES DIVIDED. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | R-2555B | DIVISION 10 | L, T |  |  |  |  | 2025 | 27719000 |  |  | 27719000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $12M FOR CONSTRUCTION, PAYBACK FY 2025-2026 (FY 2024 / YR 5/6 SALE).
MECKLENBURG | US 21 | SR 5544 (CATAWBA AVENUE) IN CORNELIUS. CONSTRUCT ROUNDABOUTS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | C-5621 | EXEMPT | BA, CMAQ, S(M) | 2020 | 2093000 |  |  | 2023 | 9344000 | 2020 | 1002000 | 12439000 | RIGHT-OF-WAY IN PROGRESS. STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. BA FUNDS IN EXCESS OF 20% MATCH ON PE AND ROW USED TO MATCH PREVIOUSLY AUTHORIZED FEDERAL FUNDS. PROJECT PART OF I-77 PPSL FUND SWAP.
MECKLENBURG | US 21 | SR 2136 (GILEAD ROAD) TO HOLLY POINT DRIVE. WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5771 | REGION E | BA, T | 2022 | 53050000 | 2022 | 1640000 | 2025 | 22401000 |  |  | 77091000
MECKLENBURG | US 21 (STATESVILLE ROAD) | NORTHCROSS CENTER COURT TO SR 2147 (WESTMORELAND ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5767 | REGION E | T | 2026 | 39080000 | 2026 | 4400000 | 2029 | 27302000 |  |  | 70782000 | BUILD NC BOND FUNDING: $11.8M FOR RIGHT OF WAY PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE)
MECKLENBURG | US 29/74 (WILKINSON BLVD) AND US 29 (N TRYON ST) | US 29/74 (WILKINSON BLVD) FROM GASTON COUNTY LINE TO FIELD RIDGE ROAD AND US 29 (NORTH TRYON STREET) FROM WEST SUGAR CREEK ROAD TO OLD CONCORD ROAD. RESURFACE ROADWAYS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | HL-0038A | EXEMPT | BGDACV |  |  |  |  | 2022 | 2596000 |  |  | 2596000
MECKLENBURG | US 521 | PROVIDENCE ROAD WEST TO SR 4979 (BALLANTYNE COMMONS PARKWAY). WIDEN ROADWAY TO 6 LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | HL-0022 | EXEMPT | BA, O | 2021 | 66000 |  |  | 2022 | 6042000 | 2021 | 386000 | 6494000 | OTHER FUNDS PROVIDED BY THE CITY OF CHARLOTTE/DEVELOPER
MECKLENBURG | US 521 (LANCASTER HIGHWAY/ JOHNSTON ROAD) | SOUTH CAROLINA STATE LINE TO SR 4979 (BALLANTYNE COMMONS PARKWAY). WIDEN TO MULTILANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6109 | REGION E | NHP | 2024 | 5000000 | 2024 | 1700000 | 2026 | 47400000 |  |  | 54100000
MECKLENBURG | US 74 | SHARON FOREST DRIVE AND HARRIS BOULEVARD/VILLAGE LAKE DRIVE INTERSECTION AREA. CONSTRUCT GRADE SEPARATION AT SHARON FOREST DRIVE AND INTERCHANGE AT VILLAGE LAKE DRIVE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2509AA | STATEWIDE MOBILITY | NHP | 2024 | 64400000 | 2024 | 1800000 | 2027 | 40400000 |  |  | 106600000 | SEGMENTS C1, C2
MECKLENBURG | US 74 | SARDIS ROAD AND SAM NEWELL ROAD INTERSECTION AREA. CONSTRUCT INTERCHANGES AT SARDIS ROAD NORTH AND SAM NEWELL ROAD, CONSTRUCT EXTENSION OF SARDIS ROAD NORTH FROM US 74 TO AREQUIPA DRIVE EXTENSION, AND CONSTRUCT EXTENSION OF AREQUIPA DRIVE FROM SARDIS ROA | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2509AB | STATEWIDE MOBILITY | NHP | 2024 | 66500000 | 2024 | 2700000 | 2027 | 45306000 |  |  | 114506000 | SEGMENTS C6, C7A, C8
MECKLENBURG | US 74 | INDEPENDENCE POINTE PARKWAY. CONSTRUCT ROADWAY ON NEW LOCATION FROM WINDSOR SQUARE DRIVE TO NC 51 (MATTHEWS TOWNSHIP PARKWAY). | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2509AC | STATEWIDE MOBILITY | NHP | 2024 | 18200000 | 2024 | 3000000 | 2027 | 11200000 |  |  | 32400000 | SEGMENT C11
MECKLENBURG | US 74 | MATTHEWS-MINT HILL ROAD INTERSECTION AREA. CONSTRUCT INTERCHANGE AT MATTHEWS-MINT HILL ROAD AND EXTENSION OF NORTHEAST PARKWAY FROM OVERCASH DRIVE TO WAITING STREET. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2509AD | STATEWIDE MOBILITY | NHP | 2024 | 51600000 | 2024 | 1800000 | 2027 | 27000000 |  |  | 80400000 | SEGMENT C10, C13
MECKLENBURG | US 74 | WEST OF IDLEWILD ROAD TO WALLACE LANE. ADD GENERAL PURPOSE AND EXPRESS LANES AND CONSTRUCT EXPRESS LANE INTERCHANGE ON WEST SIDE OF CONFERENCE DRIVE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2509B | STATEWIDE MOBILITY | NHP | 2024 | 26000000 | 2024 | 0 | 2027 | 25250000 |  |  | 51250000 | SEGMENT M1
MECKLENBURG | US 74 | WALLACE LANE TO SARDIS ROAD. ADD GENERAL PURPOSE AND EXPRESS LANES AND CONSTRUCT EXPRESS LANE INTERCHANGE AT SARDIS ROAD. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2509C | STATEWIDE MOBILITY | NHP | 2024 | 39200000 | 2024 | 5600000 | 2027 | 70350000 |  |  | 115150000 | SEGMENT M2
MECKLENBURG | US 74 | SARDIS ROAD TO I-485. ADD GENERAL PURPOSE AND EXPRESS LANES, CONSTRUCT EXPRESS LANE INTERCHANGES AT I-485 AND EAST SIDE OF CONFERENCE DRIVE, AND RECONSTRUCT INTERCHANGE AT NC 51 (MATTHEWS TOWNSHIP PARKWAY). | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2509D | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 92300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 202206000 |  |  | 304806000 | SEGMENTS C14, M3
MECKLENBURG | US 74 (INDEPENDENCE BOULEVARD) | BROOKSHIRE FREEWAY TO IDLEWILD ROAD IN CHARLOTTE. ADD ADDITIONAL LANES AND CONSTRUCT INTERCHANGES WITH SHARON AMITY ROAD AND IDLEWILD ROAD AND SAFETY IMPROVEMENTS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-0209 | [11 empty] | COMPLETE - GARVEE BOND FUNDING: $50M FOR RIGHT-OF-WAY, PAYBACK FY 2010-2021; $2M FOR CONSTRUCTION, PAYBACK FY 2013-2024
MECKLENBURG | US 74 (INDEPENDENCE BOULEVARD) | NC 24/NC 27 (ALBEMARLE ROAD) TO IDLEWILD ROAD | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-0209B | PRE-STI (TRANSITION) | NHP | 2010 | 10968000 |  |  | 2013 | 1025000 |  |  | 11993000 | COMPLETE - GARVEE BOND FUNDING: $50M FOR RIGHT-OF-WAY, PAYBACK FY 2010-2021; $2M FOR CONSTRUCTION, PAYBACK FY 2013-2024
MECKLENBURG | US 74 (INDEPENDENCE BOULEVARD) | SEPARATE ITS CONTRACT FOR U-209 B | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-0209BA | PRE-STI (TRANSITION) | [10 empty] | WORK TO BE CONSTRUCTED BY PROJECT U-6103
MECKLENBURG | US 74 (INDEPENDENCE BOULEVARD) | WEST OF IDLEWILD ROAD TO I-485. UPGRADE ROADWAY TO EXPRESSWAY WITH EXPRESS LANES AND CONSTRUCT IMPROVEMENTS ON PARALLEL ROUTES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2509
MECKLENBURG | US 74 (INDEPENDENCE BOULEVARD) | I-277 TO WEST OF IDLEWILD ROAD. WIDEN ROADWAY TO ALLOW FOR TWO-WAY EXPRESS LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6103 | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 93200000 |  |  | 104800000
MECKLENBURG | US 74 PARALLEL ROUTES | KREFELD DRIVE, AREQUIPA DRIVE, AND INDEPENDENCE POINTE PARKWAY. CONSTRUCT MULTIPLE SEGMENTS, PART ON NEW LOCATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2509E | NOT FUNDED | T | NOT FUNDED | 55800000 | NOT FUNDED | 4100000 | NOT FUNDED | 69400000 |  |  | 129300000 | SEGMENTS C3, C4, C5, C7B, C9, C12
MECKLENBURG | VARIOUS | VARIOUS MAINTENANCE ACTIVITIES INCLUDING RESURFACING, TRAFFIC SIGNAL LOOP REPLACEMENT, PAVEMENT RESTRIPING AND MARKERS, AND SIGN REPLACEMENT. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | HL-0038 |  | BGDACV | [6 empty] | 2022 | 5000 | 5000
MECKLENBURG | VARIOUS | REPLACE PAVEMENT MARKINGS AND SNOW PLOWABLE MARKERS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | HL-0038B | EXEMPT | BGDACV |  |  |  |  | 2022 | 2319000 |  |  | 2319000
MECKLENBURG | VARIOUS | REPLACE TRAFFIC SIGNAL LOOPS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | HL-0038C | EXEMPT | BGDACV |  |  |  |  | 2022 | 90000 |  |  | 90000
MECKLENBURG | CATS | REPLACEMENT BUS | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO | TA-4710 | PUBLIC TRANSIT | 5307, 5339, L, S | [6 empty] | 2021 | 27252000 | 27252000 | "L" REFLECTS CATS CAPITAL PROGRAM
MECKLENBURG | CATS | EXPANSION VANPOOL | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO | TC-0014 | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2021 | 174000 | 174000 | "L" REFLECTS CATS CAPITAL FUND
MECKLENBURG | CATS | CITY LYNX GOLD LINE - AMERICAN RESCUE PLAN SMALL STARTS | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO | TC-0024 | PUBLIC TRANSIT | 5309 | [6 empty] | 2022 | 11122000 | 11122000
MECKLENBURG | CATS | ADD A LIGHT RAIL STATION ON THE LYNX BLUE LINE NEAR IVERSON WAY IN SOUTH CHARLOTTE | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO | TP-5156 | PUBLIC TRANSIT | L | [6 empty] | 2021 | 7582000 | 7582000 | "L" REFLECTS CATS CAPITAL FUND, CITY OF CHARLOTTE CAPITAL FUNDS, PRIVATE DEVELOPER PARTICIPATION.
MECKLENBURG | CATS | LYNX SILVER LINE LIGHT RAIL PROJECT | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO | TU-0001 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 50000000 | 50000000
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | REPLACEMENT VAN - VANPOOL | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO | TA-4960 | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 3279000 | 3279000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | REPLACEMENT - PARATRANSIT VEHICLE | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO | TA-4711 | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 11762000 | 11762000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | PURCHASE BATTERY ELECTRIC BUSES, CHARGING STATIONS, ONSITE TRAINING AND STARTUP SUPPORT AND TESTING | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO | TG-0010 | PUBLIC TRANSIT | 5339, L | [6 empty] | 2021 | 7448000 | 7448000
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | OPERATING ASSISTANCE | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO | TO-5137 | PUBLIC TRANSIT | SMAP | [6 empty] | 2020 | 75312000 | 75312000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | PLANNING ASSISTANCE | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO | TP-5114 | PUBLIC TRANSIT | 5303, L, S | [6 empty] | 2020 | 2598000 | 2598000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | LYNX SILVER LINE TOD PLANNING IN COOPERATION WITH CATS, CRTPO AND GCLMPO. | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO | TP-5159 | PUBLIC TRANSIT | 5303, L | [6 empty] | 2023 | 507000 | 507000
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | OPERATING PROJECT FOR ENHANCED MOBILITY OF SENIORS AND INDIVIDUALS WITH DISABILITIES | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO | TQ-6957 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2020 | 2790000 | 2790000 | CORRECTED FUNDING LEVEL FOR FY 20-25 FOR OPERATING PROJECTS AS REQUESTED BY THE CRTPO
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | ADMINISTRATIVE OVERSIGHT FOR 5310 | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO | TQ-7009 | PUBLIC TRANSIT | 5310 | [6 empty] | 2020 | 463000 | 463000 | CORRECTED FUNDING LEVEL TO FY 20-25 FOR THE ADMINISTRATIVE OVERSIGHT OF THE 5310 PROGRAM AS REQUESTED BY THE CRTPO
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | ENHANCED MOBILITY TO SENIORS AND INDIVIDUALS WITH DISABILITIES | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO | TQ-9033 | PUBLIC TRANSIT | 5310, L, S | [6 empty] | 2020 | 5292000 | 5292000 | CORRECTED FUNDING LEVEL FOR FY 20-25 FOR OPERATING PROJECTS AS REQUESTED BY THE CRTPO
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | SAFETY & SECURITY - MIN. 1% SET ASIDE | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO | TS-5107 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 3710000 | 3710000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | STATE OF GOOD REPAIR - BUS | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO | TW-4901 | PUBLIC TRANSIT | 5337, FMOD, L, S | [6 empty] | 2020 | 7854000 | 7854000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | BRIDGE INSPECTIONS AND REPAIRS | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO | TW-5102A | PUBLIC TRANSIT | 5307, L, S |  |  |  |  | 2020 | 1800000 |  |  | 1800000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | FIXED GUIDEWAY MODERNIZATION - BRIDGE INSPECTION & EMERGENCY REPAIRS | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO | TW-5102B | PUBLIC TRANSIT | FMOD, L |  |  |  |  | 2020 | 1160000 |  |  | 1160000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM | STATE OF GOOD REPAIR - BUS | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO | TW-5104B | PUBLIC TRANSIT | 5307, 5337, L, S | [6 empty] | 2020 | 13890000 | 13890000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | CHARLOTTE AREA TRANSIT SYSTEM (CATS) | I-77 AND HAMBRIGHT ROAD PARK AND RIDE LOT. CONSTRUCT PARK AND RIDE LOT AND TRANSFER FACILITY. | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO | TA-6724 | DIVISION 10 | BGDA, CMAQ, L, S(M) | 2022 | 1257000 |  |  | 2023 | 9905000 | 2022 | 1510000 | 12672000 | LOCAL FUNDS PROVIDED BY CATS AND FTA 5307; STATE MATCH IS HIGHWAY TRUST FUNDS
MECKLENBURG | CHARLOTTE REGIONAL | INNOVATIVE COORDINATED ACCESS AND MOBILITY PILOT PROGRAM VEHICLES | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO | TA-6706 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2020 | 140000 | 140000 | ADD PROJECT TA-6706 TO STIP FOR FY 20. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT THE REQUEST OF CRTPO MPO
MECKLENBURG | CHARLOTTE REGIONAL | OPERATING PROJECTS FOR ENHANCED MOBILITY TO SENIORS AND INDIVIDUALS WITH DISABILITIES | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO | TQ-6597 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2020 | 2790000 | 2790000 | CORRECTED FUNDING LEVELS FOR FY 20-25 FOR OPERATING PROJECTS AS REQUESTED BY THE CRTPO
MECKLENBURG | MECKLENBURG COUNTY | EXPAND PARATRANSIT FLEET BY PURCHASING ADDITIONAL BUSES. | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO | TA-6673 | DIVISION 10 | O, T | [6 empty] | 2021 | 2500000 | 2500000 | OTHER FUNDING PROVIDED BY CHARLOTTE AREA TRANSIT (CATS) FUNDS
MECKLENBURG | MECKLENBURG TRANSPORTATION | 5307 FUNDING FOR FY20-21 (20-LU-051) | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO | TG-6790 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 1580000 | 1580000 | ADDING FFY20-21
MECKLENBURG | MECKLENBURG TRANSPORTATION | ADMINISTRATION | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO | TK-6145 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 1020000 | 1020000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | MECKLENBURG TRANSPORTATION | OPERATING ASSISTANCE FY20-21 (20-LU-051) | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO | TO-6159 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 3074000 | 3074000 | ADDING CURRENT YEAR TO THE STIP
MECKLENBURG | SYSTEM CHARLOTTE AREA TRANSIT | FACILITY - SOUTH TRYON STREET GARAGE -DEBT SERVICE | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO | TD-4701 | PUBLIC TRANSIT | 5307, L, S |  |  |  |  | 2020 | 21961000 |  |  | 21961000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | SYSTEM CHARLOTTE AREA TRANSIT | FACILITY - TRANSIT CENTER - UPGRADES | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO | TD-4702 | PUBLIC TRANSIT | 5307, L, S |  |  |  |  | 2020 | 720000 |  |  | 720000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | SYSTEM CHARLOTTE AREA TRANSIT | FIXED GUIDEWAY - BLUE LINE EXTENSION - PLANS, DESIGN, ACQUISITION, CONSTRUCTION, TIFIA LOAN | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO | TE-4901 | PUBLIC TRANSIT | 5309, L, S |  |  |  |  | 2020 | 66328000 |  |  | 66328000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | SYSTEM CHARLOTTE AREA TRANSIT | RAPID TRANSIT CORRIDOR STUDIES | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO | TE-4902 | PUBLIC TRANSIT | 5307, FED, L, S |  |  |  |  | 2021 | 200000 |  |  | 200000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | SYSTEM CHARLOTTE AREA TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, ETC | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO | TG-4726 | PUBLIC TRANSIT | 5307, FMOD, L | [6 empty] | 2020 | 17699000 | 17699000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | SYSTEM CHARLOTTE AREA TRANSIT | ROUTINE CAPITAL - SERVICE VEHICLE | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO | TG-4827 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2661000 | 2661000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | SYSTEM CHARLOTTE AREA TRANSIT | STATE OF GOOD REPAIR - RAIL | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO | TG-5118A | PUBLIC TRANSIT | 5337, L, S | [6 empty] | 2020 | 55592000 | 55592000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | SYSTEM CHARLOTTE AREA TRANSIT | LIGHT RAIL VEHICLE OVERHAUL | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO | TG-5118B | PUBLIC TRANSIT | 5307, 5337, L | [6 empty] | 2020 | 14178000 | 14178000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | SYSTEM CHARLOTTE AREA TRANSIT | PREVENTIVE MAINTENANCE - RAIL, BUS AND FACILITIES | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO | TG-5119 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 47589000 | 47589000 | FUNDS AUTHORIZED IN PROGRESS
MECKLENBURG | CHARLOTTE | CHARLOTTE GATEWAY STATION. | RAIL | 10 | CHARLOTTE REGIONAL TPO | P-5705 | [11 empty] | DP REPRESENTS FEDERAL INFRA GRANT FUNDS
MECKLENBURG | CHARLOTTE | WYE CONNECTION TRACK AT CHARLOTTE JUNCTION | RAIL | 10 | CHARLOTTE REGIONAL TPO | P-5705A | STATEWIDE MOBILITY | DP, T | 2021 | 500000 |  |  | 2023 | 10999000 |  |  | 11499000
MECKLENBURG | CHARLOTTE | CHARLOTTE GATEWAY STATION - RIGHT-OF-WAY | RAIL | 10 | CHARLOTTE REGIONAL TPO | P-5705B | REGION E | [10 empty] | UNDER CONSTRUCTION
MECKLENBURG | CHARLOTTE | CHARLOTTE GATEWAY STATION - TRACK, STRUCTURE, AND SIGNALS | RAIL | 10 | CHARLOTTE REGIONAL TPO | P-5705BA | REGION E | [10 empty] | UNDER CONSTRUCTION
MECKLENBURG | CHARLOTTE | CHARLOTTE GATEWAY STATION - PLATFORM AND CANOPY | RAIL | 10 | CHARLOTTE REGIONAL TPO | P-5705BB | REGION E | [10 empty] | UNDER CONSTRUCTION
MECKLENBURG | CHARLOTTE RAILYARD PINEVILLE RAILYARD | GRANTS TO REPLACE AGING DIESEL ENGINES (GRADE). | RAIL | 10 | CHARLOTTE REGIONAL TPO | RL-0002 | EXEMPT | CMAQ, L |  |  |  |  | 2023 | 5450000 |  |  | 5450000
MECKLENBURG | CLANTON ROAD | EXTEND CLANTON ROAD TO US 29/74 (WILKINSON BOULEVARD) WITH A GRADE SEPARATION OF NORFOLK SOUTHERN RAILROAD AND CLOSE THE DONALD ROSS ROAD CROSSING. | RAIL | 10 | CHARLOTTE REGIONAL TPO | P-5730 | REGION E | O, T | 2024 | 4400000 |  |  | 2025 | 16700000 |  |  | 21100000
MECKLENBURG | NORFOLK SOUTHERN MAIN LINE (TRACK MILEPOST 376) | ESTABLISH A NEW THOROUGHBRED BULK TRANSFER (TBT) FACILITY IN CHARLOTTE. | RAIL | 10 | CHARLOTTE REGIONAL TPO | P-5702 | DIVISION 10 | O, T |  |  |  |  | 2021 | 976000 |  |  | 976000 | OTHER FUNDING PROVIDED BY NORFOLK SOUTHERN CORPORATION
MECKLENBURG | P & N CORRIDOR REACTIVATION | THRIFT DEPOT RELOCATION | RAIL | 10 | CHARLOTTE REGIONAL TPO | P-5200EA | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
MECKLENBURG | P & N CORRIDOR REACTIVATION | THRIFT DEPOT STABILIZATION | RAIL | 10 | CHARLOTTE REGIONAL TPO | P-5200EB | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
MECKLENBURG | PIEDMONT CORRIDOR | CRISP CHARLOTTE MAINTENANCE FACILITY - TRACK EXTENSION AND SHOP BUILDING | RAIL | 10 | CHARLOTTE REGIONAL TPO | P-2918F | [11 empty] | IN PROGRESS
MECKLENBURG | SR 2623 (TRAILER DRIVE) | IMPROVE AT-GRADE CROSSING WITH NORFOLK SOUTHERN RAILROAD (CROSSING NUMBER 910 618A, MP O4.11) | RAIL | 10 | CHARLOTTE REGIONAL TPO | P-5754 | EXEMPT | O |  |  |  |  | 2022 | 1200000 | 2020 | 50000 | 1250000 | OTHER FUNDING PROVIDED BY QUIK TRIP; CONSTRUCTION TO BE PERFORMED BY NORFOLK SOUTHERN
MECKLENBURG, ALAMANCE, CABARRUS, CUMBERLAND, DAVIDSON, GUILFORD, HARNETT, HOKE, IREDELL, ORANGE, UNION | STATEWIDE | URBANIZED FORMULA PROGRAM FUNDS MANAGED BY NCDOT FOR ORANGE, ALAMANCE, DAVIDSON, GUILFORD, CABARRUS, IREDELL, HOKE, CUMBERLAND, HARNETT, UNION, MECKLENBURG TRANSPORTATION SYSTEMS – CAPITAL PROGRAM | PUBLIC TRANSIT | 6, 7, 8, 9, 10, 12 | CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO, BURLINGTON-GRAHAM MPO, FAYETTEVILLE AREA MPO, HIGH POINT URBAN AREA MPO, WINSTON-SALEM URBAN AREA MPO | TG-6187 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2438000 | 2438000
MECKLENBURG, CABARRUS | I-85 | US 29/NC 49 CONNECTOR, MECKLENBURG COUNTY TO NC 73 IN CABARRUS COUNTY. WIDEN TO 8-LANES. (COORDINATE WITH U-3415). | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | I-3803 | [11 empty] | GARVEE BOND FUNDING - SEGMENT B: $103M FOR CONSTRUCTION, PAYBACK FY 2010-2021
MECKLENBURG, CABARRUS | I-85 | SOUTH OF US 29/NC 49 CONNECTOR TO SR 2894 (CONCORD MILLS - BRUTON SMITH BOULEVARD). WIDEN TO 8-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | I-3803A | [11 empty] | COMPLETE
MECKLENBURG, CABARRUS | NC 73 (DAVIDSON HIGHWAY) | EAST OF SR 2693 (DAVIDSON-CONCORD ROAD) TO EAST OF SR 1394 (POPLAR TENT ROAD). | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | R-5706A | REGION E | NHP | 2024 | 7000000 | 2024 | 2900000 | 2026 | 29600000 |  |  | 39500000
MECKLENBURG, CABARRUS | SR 2467 (MALLARD CREEK ROAD)/ SR 1445 (DERITA ROAD | I-485 TO CONCORD MILLS BOULEVARD (SR 2894). WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | U-6032 | DIVISION 10 | T | 2022 | 14400000 | 2022 | 2600000 | 2025 | 27525000 |  |  | 44525000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $6M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE)
MECKLENBURG, CABARRUS | CHARLOTTE AREA TRANSIT SYSTEM | PURCHASE 6 BUSES FOR THE UNIVERSITY TO CONCORD MILLS BUS ROUTE. | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | TA-6672 | REGION E | O, T | [6 empty] | 2020 | 3000000 | 3000000 | OTHER FUNDING PROVIDED BY CHARLOTTE AREA TRANSIT (CATS) FUNDS
MECKLENBURG, IREDELL | I-77 | MILE MARKER 11 TO MILE MARKER 20 AND MILE MARKER 24.5 TO MILE MARKER 37. REHABILITATE PAVEMENT. | HIGHWAY | 10, 12 | CHARLOTTE REGIONAL TPO | I-5992 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
MECKLENBURG, IREDELL | I-77 | I-485 TO NC 150. CONSTRUCT PEAK PERIOD SHOULDER USE LANES. | HIGHWAY | 10, 12 | CHARLOTTE REGIONAL TPO | I-6065 | EXEMPT | BA, BGDA, S(M), T(DA) | 2023 | 100000 |  |  | 2024 | 45953000 | 2020 | 950000 | 47003000 | PROJECT FUNDED AS PART OF STBG-DA AND BA FUND SWAP FOR CMAQ FUNDS. PROJECT IS EXEMPT AS DA FUNDS ARE BEING USED ON AN ELIGIBLE STATEWIDE MOBILITY PROJECT. $36.762M IN STBG-DA FUNDS SWITCHED WITH $36.762M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP.
MECKLENBURG, IREDELL, UNION | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) AREA. | HIGHWAY | 10, 12 | CHARLOTTE REGIONAL TPO | C-5613 | EXEMPT | CMAQ, L | 2020 | 518000 |  |  | 2020 | 3108000 | 2020 | 1554000 | 5180000 | IN PROGRESS.
MECKLENBURG, LINCOLN | NC 73 | NC 16 IN LINCOLN COUNTY TO SR 5544 (WEST CATAWBA AVENUE) IN MECKLENBURG COUNTY. WIDEN TO MULTI-LANES. | HIGHWAY | 10, 12 | CHARLOTTE REGIONAL TPO, GASTON-CLEVELAND-LINCOLN MPO | R-5721 | [11 empty] | COORDINATE WITH U-5765.
MECKLENBURG, UNION, IREDELL | VARIOUS | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) TRANSPORTATION ALTERNATIVES (TAP) PROGRAM. | BIKE/PED | 10, 12 | CHARLOTTE REGIONAL TPO | U-5544 | DIVISION 10, 12 | L, TADA |  |  |  |  | 2024 | 40819000 |  |  | 40819000
MECKLENBURG, UNION, IREDELL | VARIOUS | STBG-DA IN CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO). | HIGHWAY | 10, 12 | CHARLOTTE REGIONAL TPO | U-4744 | DIVISION 10, 12 | BGDA, L |  |  |  |  | 2020 | 251739000 |  |  | 251739000
MECKLENBURG, UNION, IREDELL | VARIOUS | CHARLOTTE REGIONAL TRANSPORTATION PLANNING ORGANIZATION (CRTPO) PLANNING (PL) SUPPLEMENT. | HIGHWAY | 10, 12 | CHARLOTTE REGIONAL TPO | U-4950 | DIVISION 10, 12 | BGDA, L | [6 empty] | 2020 | 15031000 | 15031000 | FORMERLY U-9999C - IN PROGRESS
MECKLENBURG, WAKE, GUILFORD, FORSYTH, DURHAM, CABARRUS, GASTON, JOHNSTON, UNION, CATAWBA, DAVIDSON, IREDELL, ORANGE, ROWAN, LINCOLN, NASH, CHATHAM, DAVIE, EDGECOMBE, FRANKLIN, GRANVILLE, HAYWOOD, PERSON, SWAIN | NORTH CAROLINA DEPARTMENT OF ENVIRONMENT AND NATUR | NORTH CAROLINA AIR AWARENESS OUTREACH PROGRAM TO PROVIDE EDUCATION AND PRODUCE DAILY AIR QUALITY FORECAST. | HIGHWAY | 4, 5, 7, 8, 9, 10, 12, 14 | CHARLOTTE REGIONAL TPO, CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, CABARRUS-ROWAN MPO, WINSTON-SALEM URBAN AREA MPO, GASTON-CLEVELAND-LINCOLN MPO, GREENSBORO URBAN AREA MPO, HIGH POINT URBAN AREA MPO, GREATER HICKORY MPO, KERR-TAR RPO, ROCKY MOUNT | HO-0009 | EXEMPT | CMAQ, L, S | [6 empty] | 2022 | 1604000 | 1604000 | "S" FUNDING REFLECTS PARTICIPATION BY DAQ
MECKLENBURG, WAKE, GUILFORD, FORSYTH, DURHAM, CABARRUS, GASTON, JOHNSTON, UNION, CATAWBA, DAVIDSON, IREDELL, ORANGE, ROWAN, NASH, DAVIE, EDGECOMBE, GRANVILLE, HAYWOOD | VARIOUS | NCDOT TRAFFIC SYSTEMS OPERATIONS. INSTALL STATEWIDE ITS DEVICE OPERATIONS. | HIGHWAY | 4, 5, 7, 9, 10, 12, 14 | CHARLOTTE REGIONAL TPO, CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO, WINSTON-SALEM URBAN AREA MPO, GREENSBORO URBAN AREA MPO, CABARRUS-ROWAN MPO, HIGH POINT URBAN AREA MPO, GASTON-CLEVELAND-LINCOLN MPO, GREATER HICKORY MPO, ROCKY MOUNT URBAN AREA MP | HO-0005 | EXEMPT | CMAQ, S(M) |  |  |  |  | 2022 | 21605000 |  |  | 21605000
MITCHELL | NC 226 | US 19E TO SR 1250 (SNOW CREEK ROAD). UPGRADE GUARDRAIL. | HIGHWAY | 13 | HIGH COUNTRY RPO | HS-2013B | REGION G | HSIP |  |  |  |  | 2021 | 290000 |  |  | 290000 | COMPLETE
MITCHELL | NC 226 | SR 1250 (SNOW CREEK ROAD) TO NC 261. UPGRADE GUARDRAIL. | HIGHWAY | 13 | HIGH COUNTRY RPO | HS-2013D | REGION G | HSIP |  |  |  |  | 2021 | 272000 |  |  | 272000 | COMPLETE
MITCHELL | NC 226 | BLUE RIDGE PARKWAY TO SR 1274 (SUMMIT AVENUE). WIDEN TO 3-LANES. | HIGHWAY | 13 | HIGH COUNTRY RPO | R-5804 | NOT FUNDED | T | NOT FUNDED | 15900000 | NOT FUNDED | 3200000 | NOT FUNDED | 33298000 |  |  | 52398000
MITCHELL | SR 1106 (LYNN GAP ROAD) | REPLACE BRIDGE 600207 OVER GRASSY CREEK. | HIGHWAY | 13 | HIGH COUNTRY RPO | B-6013 | DIVISION 13 | BGOFF | 2022 | 40000 |  |  | 2022 | 800000 |  |  | 840000 | DESIGN-BUILD; COMBINED LETTING WITH B-6011, B-6014, & B-6016
MITCHELL | MITCHELL COUNTY TRANSPORTATION | ADMINISTRATION | PUBLIC TRANSIT | 13 | HIGH COUNTRY RPO | TK-6146 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 728000 | 728000 | FUNDS AUTHORIZED IN PROGRESS
MONTGOMERY | NC 134 (NORTH MAIN STREET); SR 1005 (SOUTH MAIN ST | SR 1323 (OKEEWEMEE ROAD) TO BARNHILL STREET IN TROY. CONSTRUCT SIDEWALKS. | BIKE/PED | 8 | PIEDMONT TRIAD RPO | EB-5521 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION BY TOWN OF TROY
MONTGOMERY | NC 731 (EAST ALLENTON STREET) | EXISTING SIDEWALK ON NC 731 TO STANBECK PARK IN MT. GILEAD. CONSTRUCT SIDEWALK. | BIKE/PED | 8 | PIEDMONT TRIAD RPO | EB-5899 | DIVISION 8 | L, TALT5 |  |  |  |  | 2023 | 277000 |  |  | 277000
MONTGOMERY | I-73 / I-74 / US 220 | MONTGOMERY COUNTY LINE TO RANDOLPH COUNTY LINE. PAVEMENT REHABILITATION. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | I-5947
MONTGOMERY | I-73/74 | MONTGOMERY COUNTY LINE TO NC 211. PAVEMENT REHABILITATION. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | I-5947A | STATEWIDE MOBILITY | BGIM |  |  |  |  | 2025 | 15900000 |  |  | 15900000
MONTGOMERY | I-73/74 | NC 211 TO NC 24/27. PAVEMENT REHABILITATION. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | I-5947B | STATEWIDE MOBILITY | BGIM |  |  |  |  | 2023 | 6900000 |  |  | 6900000 | UNDER CONSTRUCTION - LET WITH I-5946A
MONTGOMERY | I-73/74 | NC 24/27 TO RANDOLPH COUNTY LINE. PAVEMENT REHABILITATION. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | I-5947C | STATEWIDE MOBILITY | BGIM |  |  |  |  | 2026 | 13600000 |  |  | 13600000
MONTGOMERY | NC 109 | NC 73 (NORTH MAIN STREET) IN MT. GILEAD TO NC 24 / NC 27. UPGRADE ROADWAY, INCLUDING PAVED SHOULDERS, TURN LANES AND SIGNALS. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-5826
MONTGOMERY | NC 109 | NC 73 (NORTH MAIN STREET) IN MT. GILEAD TO SR 1127 (HEARNE FARM ROAD). | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-5826A | NOT FUNDED | T | NOT FUNDED | 3700000 | NOT FUNDED | 250000 | NOT FUNDED | 9200000 |  |  | 13150000
MONTGOMERY | NC 109 | SR 1127 (HEARNE FARM ROAD) TO SR 1174 (PEE DEE ROAD). | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-5826B | DIVISION 8 | T | 2023 | 500000 | 2023 | 105000 | 2026 | 8800000 |  |  | 9405000
MONTGOMERY | NC 109 | SR 1174 (PEE DEE ROAD) TO NC 24 / NC 27. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-5826C | NOT FUNDED | T | NOT FUNDED | 3000000 | NOT FUNDED | 299000 | NOT FUNDED | 18000000 |  |  | 21299000
MONTGOMERY | NC 24 / NC 27 | TROY BYPASS, WEST OF SR 1138 (DAIRY ROAD) TO EAST OF LITTLE RIVER. FOUR LANES, PART ON NEW LOCATION. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-0623 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
MONTGOMERY | NC 24 / NC 27 | NC 73 TO TROY BYPASS. WIDEN TO MULTILANES. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-2527 | REGION E | BGLT5, T | 2019 | 854000 |  |  | 2024 | 91402000 | 2019 | 7802000 | 100058000 | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $6.062 MILLION FOR PE AND $665,000 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE)
MONTGOMERY | RANDOLPH- MONTGOMERY RESTORE | PURCHASE 20-FT LIGHT TRANSIT VEHICLES FOR SERVICE EXPANSION. | PUBLIC TRANSIT | 8 | PIEDMONT TRIAD RPO | TA-6671 | REGION E | [10 empty] | IN ACQUISITION
MONTGOMERY, RANDOLPH | REGIONAL COORDINATED AREA TRANSPORTION | ADMINISTRATION | PUBLIC TRANSIT | 8 | PIEDMONT TRIAD RPO | TK-6156 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 1392000 | 1392000 | FUNDS AUTHORIZED IN PROGRESS
MOORE | MOORE COUNTY AIRPORT (SOP) | CONSTRUCT HANGAR TAXIWAYS AND INTERNAL AIRFIELD SERVICE ROAD. | AVIATION | 8 | TRIANGLE AREA RPO | AV-5855 | DIVISION 8 | T |  |  |  |  | 2021 | 2900000 |  |  | 2900000 | UNDER CONSTRUCTION
MOORE | KNOLL ROAD | ARBORETUM DRIVE TO NORTH OF PADDOCK LANE IN SOUTHERN PINES. CONSTRUCT SIDEWALK. | BIKE/PED | 8 | TRIANGLE AREA RPO | EB-5864 | DIVISION 8 | L, TA5200 |  |  |  |  | 2023 | 564000 |  |  | 564000
MOORE | SR 1203 (JOHNSON STREET) | US 15 / US 501 TO MIKE PLACE IN ABERDEEN. CONSTRUCT SIDEWALKS. | BIKE/PED | 8 | TRIANGLE AREA RPO | EB-5869 | DIVISION 8 | L, TA5200 |  |  |  |  | 2023 | 190000 |  |  | 190000
MOORE | SR 2055 (NORTH POPLAR STREET) | JOHNSON STREET TO US 1 (SANDHILLS BOULEVARD) IN ABERDEEN. CONSTRUCT SIDEWALK. | BIKE/PED | 8 | TRIANGLE AREA RPO | EB-6001 | DIVISION 8 | L, TA5200 | 2024 | 34000 |  |  | 2025 | 340000 | 2023 | 26000 | 400000 | COORDINATE WITH U-5815
MOORE | US 1 / US 15 / US 501 (SANDHILLS BOULEVARD) | MAPLE AVENUE IN ABERDEEN. CONSTRUCT MID-BLOCK CROSSWALK, MEDIAN REFUGE ISLAND, AND INSTALL PEDESTRIAN SIGNAL. | BIKE/PED | 8 | TRIANGLE AREA RPO | EB-5741 | DIVISION 8 | L, TA5200 |  |  |  |  | 2023 | 100000 |  |  | 100000
MOORE | VARIOUS | CONSTRUCT PEDESTRIAN IMPROVEMENTS AT 5 INTERSECTIONS AND ONE MID-BLOCK LOCATION IN THE CENTRAL BUSINESS DISTRICT OF ABERDEEN. | BIKE/PED | 8 | TRIANGLE AREA RPO | EB-6005 | NOT FUNDED | L, TA5200 |  |  |  |  | NOT FUNDED | 184000 | NOT FUNDED | 29000 | 213000
MOORE | NC 211 | NC 73 IN WEST END TO WEST OF SR 1241 (HOLLY GROVE SCHOOL ROAD). WIDEN TO MULTILANES. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5726 | REGION E | T |  |  |  |  | 2025 | 32500000 |  |  | 32500000 | RIGHT-OF-WAY IN PROGRESS
MOORE | NC 211 | NC 73 IN WEST END TO WEST OF SR 1241 (HOLLY GROVE SCHOOL ROAD). CLEARING, GRUBBING, AND EROSION CONTROL. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5726A | REGION E | T |  |  |  |  | 2022 | 5000000 |  |  | 5000000
MOORE | NC 22 | REPLACE BRIDGE 620062 OVER NICKS CREEK IN CARTHAGE. | HIGHWAY | 8 | TRIANGLE AREA RPO | BR-0035 | REGION E | NHPB |  |  |  |  | 2022 | 4100000 |  |  | 4100000 | PROJECT WILL BE COMPLETED UNDER THE STATE BRIDGE PROGRAM. PROJECT TO NO LONGER UTILIZE BUILD NC BONDS.
MOORE | NC 24 / NC 27 | SR 1006 (GLENDON-CARTHAGE ROAD) IN CARTHAGE. IMPROVE INTERSECTION AND ADJACENT INTERSECTIONS OF EACH FACILITY WITH US 15 / US 501. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5929 | DIVISION 8 | T | 2023 | 200000 | 2023 | 1100000 | 2025 | 6100000 |  |  | 7400000 | COORDINATE WITH U-3628
MOORE | NC 24 / NC 27 | COURTHOUSE WEST OF NC 22 (MCNEILL STREET) TO US 15 / US 501 IN CARTHAGE. WIDEN TO THREE LANES WITH CURB AND GUTTER AND BICYCLE / PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-3628 | REGION E | T |  |  |  |  | 2025 | 3000000 |  |  | 3000000 | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH R-5929
MOORE | NC 5 | US 1 IN ABERDEEN TO THE INTERSECTION OF TROTTER DRIVE / BLAKE BOULEVARD IN PINEHURST. WIDEN TO MULTILANES. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5756 | REGION E | T | 2023 | 5300000 | 2023 | 5818000 | 2025 | 33999000 |  |  | 45117000
MOORE | NC 5 (BEULAH HILL ROAD) | INTERSECTION OF TROTTER DRIVE / BLAKE BOULEVARD TO NC 211 IN PINEHURST. ADD TURN LANES, SIGNAL IMPROVEMENTS, AND OTHER OPERATIONAL IMPROVEMENTS ALONG CORRIDOR AS APPROPRIATE. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5892 | REGION E | T | 2028 | 20105000 | 2028 | 1892000 | 2030 | 17500000 |  |  | 39497000
MOORE | NC 690 (LOBELIA ROAD) | US 1 IN VASS TO CUMBERLAND COUNTY LINE. UPGRADE ROADWAY, TO INCLUDE TURN LANES AT VARIOUS LOCATIONS AND SOME REALIGNMENT. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5824 | REGION E | T | 2023 | 1700000 | 2023 | 1100000 | 2025 | 31200000 |  |  | 34000000
MOORE | SR 2055 (NORTH POPLAR STREET) | WEST MAPLE AVENUE INTERSECTION IN ABERDEEN. INSTALL ALL-WAY STOP. | HIGHWAY | 8 | TRIANGLE AREA RPO | W-5808C | DIVISION 8 | HSIP | 2021 | 2000 |  |  | 2021 | 15000 |  |  | 17000 | UNDER CONSTRUCTION.
MOORE | US 1 (SANDHILLS BOULEVARD) | SR 1112 (ROSELAND ROAD) IN ABERDEEN TO OLD US 1 IN SOUTHERN PINES. ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5815 | REGION E | [10 empty] | COORDINATE WITH U-5814
MOORE | US 1 (SANDHILLS BOULEVARD) | SR 1112 (ROSELAND ROAD) TO KNIGHT STREET IN ABERDEEN. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5815A | REGION E | T | 2025 | 700000 | 2025 | 1600000 | 2027 | 4401000 |  |  | 6701000
MOORE | US 1 (SANDHILLS BOULEVARD) | KNIGHT STREET IN ABERDEEN TO OLD US 1 IN SOUTHERN PINES, TO INCLUDE SR 1112 (ROSELAND ROAD) REALIGNMENT AT US1 AND RADII IMPROVEMENT I AT US 15 / US 501 / NC 211. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5815B | REGION E | T |  |  |  |  | 2025 | 25100000 |  |  | 25100000 | RIGHT-OF-WAY IN PROGRESS
MOORE | US 1 (SANDHILLS BOULEVARD) | KNIGHT STREET IN ABERDEEN TO OLD US 1 IN SOUTHERN PINES. RELOCATE WATER TRANSMISSION LINE. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5815BA | REGION E | T |  |  |  |  | 2023 | 4330000 |  |  | 4330000
MOORE | US 15 / US 501 | NC 2 AND NC 211 TRAFFIC CIRCLE IN PINEHURST TO NC 73. WIDEN TO MULTILANES. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5927 | DIVISION 8 | T | 2026 | 1200000 | 2026 | 4100000 | 2029 | 43701000 |  |  | 49001000
MOORE | US 15 / US 501 | SR 1905 (VOIT GILMORE LANE) IN SOUTHERN PINES TO SR 1208 PAGE ROAD IN PINEHURST. UPGRADE SR 1208 INTERSECTION AND CONSTRUCT IMPROVEMENTS TO PINEHURST TRAFFIC CIRCLE AND APPROACHES. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5976 | DIVISION 8 | T | 2024 | 25800000 | 2024 | 630000 | 2026 | 30971000 |  |  | 57401000 | BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE)
MOORE | US 15 / US 501 / NC 211 | SR 1205 / SR 1309 (MORGANTON ROAD) IN SOUTHERN PINES. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5891 | REGION E | T | 2027 | 1900000 | 2027 | 1180000 | 2029 | 20600000 |  |  | 23680000
MOORE | US 15 / US 501 / NC 211 | US 1 (SANDHILLS BOULEVARD) IN ABERDEEN TO BRUCEWOOD ROAD IN SOUTHERN PINES. ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5814 | REGION E | T |  |  |  |  | 2025 | 14700000 |  |  | 14700000 | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH U-5815
MOORE | MOORE COUNTY | ADMINISTRATION | PUBLIC TRANSIT | 8 | TRIANGLE AREA RPO | TK-6147 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 964000 | 964000 | FUNDS AUTHORIZED IN PROGRESS
MOORE, HOKE, LEE | VARIOUS | VARIOUS NHS AND PRIMARY ROUTES IN DIVISION 8, DISTRICT 2. UPGRADE GUARDRAIL. | HIGHWAY | 8 | TRIANGLE AREA RPO, LUMBER RIVER RPO | HS-2008B | REGION E | HSIP |  |  |  |  | 2021 | 250000 |  |  | 250000 | UNDER CONSTRUCTION
MOORE, MONTGOMERY | NC 24 / NC 27 | I-73 / I-74 / US 220 TO SR 1644 (OLD GLENDON ROAD). MODERNIZE ROADWAY. | HIGHWAY | 8 | TRIANGLE AREA RPO, PIEDMONT TRIAD RPO | R-5932 | NOT FUNDED | T | NOT FUNDED | 5800000 | NOT FUNDED | 14400000 | NOT FUNDED | 50200000 |  |  | 70400000
NASH | ROCKY MOUNT WILSON AIRPORT (RWI) | CONSTRUCT TAXIWAY AND T HANGARS. | AVIATION | 4 | ROCKY MOUNT URBAN AREA MPO | AV-5845 | DIVISION 4 | T |  |  |  |  | 2019 | 3050000 |  |  | 3050000 | UNDER CONSTRUCTION
NASH | US 301 BUSINESS (CHURCH STREET) | US 64 TO NC 97 (RALEIGH BOULEVARD) OVERPASS. CONSTRUCT STREETSCAPE IMPROVEMENTS. ADD SIDEWALK AND BICYCLE LANES. | BIKE/PED | 4 | ROCKY MOUNT URBAN AREA MPO | EB-5761 | DIVISION 4 | L, TA5200 | 2024 | 50000 |  |  | 2025 | 2500000 | 2023 | 200000 | 2750000
NASH | US 64 BUSINESS (SUNSET AVENUE) | SR 1836 (MAY DRIVE) TO US 301 BUSINESS, NORTH BOUND (CHURCH STREET). INSTALL PEDESTRIAN SIGNALS. | BIKE/PED | 4 | ROCKY MOUNT URBAN AREA MPO | Eb-5711 | DIVISION 4 | L, TA5200 |  |  |  |  | 2023 | 125000 |  |  | 125000
NASH | US 64 BUSINESS (THOMAS STREET) | SR 1005 (EAST RALEIGH BOULEVARD TO US 64 BUSINESS (SUNSET AVENUE) IN ROCKY MOUNT. ADD PEDESTRIAN SIGNALS. | BIKE/PED | 4 | ROCKY MOUNT URBAN AREA MPO | EB-5905 | DIVISION 4 | BG5200, L |  |  |  |  | 2027 | 120000 |  |  | 120000
NASH | I-95 | SR 1770 (SUNSET AVENUE) (MILE MARKER 137.4) TO SR 1544 (NORTH HALIFAX ROAD) (MILE MARKER 142.1). PAVEMENT AND BRIDGE REHABILITATION. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO, ROCKY MOUNT URBAN AREA MPO | I-5934 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2024 | 5448000 |  |  | 5448000
NASH | I-95 | SR 1770 (SUNSET AVENUE) IN ROCKY MOUNT. CONVERT GRADE SEPARATION TO AN INTERCHANGE. | HIGHWAY | 4 | ROCKY MOUNT URBAN AREA MPO | U-5026 | DIVISION 4 | L, T | 2020 | 32058000 | 2020 | 336000 | 2020 | 74701000 |  |  | 107095000 | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. COMBINED WITH R-5720 FOR LETTING. BUILD NC BOND FUNDING: $15,595,497 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE)
NASH | NC 33 | BRIDGE 630041 ON NC 33 OVER I-95. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | BR-0036 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 4700000 |  |  | 4700000 | RIGHT OF WAY IN PROGRESS.
NASH | NC 43 | SR 1613 (WOODRUFF AVENUE) TO I-95. WIDEN TO MULTI-LANES. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | U-2561 | DIVISION 4
NASH | NC 43 | SR 1613 (WOODRUFF AVENUE) TO I-95. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | U-2561C | DIVISION 4 | T | 2026 | 3132000 | 2026 | 2968000 | 2028 | 7600000 |  |  | 13700000 | PLANNING/DESIGN IN PROGRESS.
NASH | NC 43 | NC 43 AT SR 1500 (SWIFT CREEK SCHOOL ROAD). REALIGN INTERSECTION. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | W-5804B | REGION A | HSIP | 2023 | 45000 |  |  | 2023 | 651000 |  |  | 696000
NASH | NC 43 (BENVENUE ROAD) | US 64 BYPASS OFFRAMP. CONSTRUCT ROUNDABOUT. | HIGHWAY | 4 | ROCKY MOUNT URBAN AREA MPO | U-5947 | REGION A | T | 2022 | 80000 | 2022 | 800000 | 2022 | 4696000 |  |  | 5576000 | UNDER CONSTRUCTION.
NASH | NC 48 | INSTALL MINI ROUNDABOUTS ALONG NC 48 (GOLDROCK ROAD) AT WATERLOO DRIVE / ROUNDTREE DRIVE AND AT GREYSON ROAD / CUNNINGHAM DRIVE. | HIGHWAY | 4 | ROCKY MOUNT URBAN AREA MPO | HS-2004M | DIVISION 4 | HSIP | 2022 | 365000 |  |  | 2023 | 1210000 |  |  | 1575000
NASH | NC 48 | SR 1524 (RED OAK/BATTLEBORO ROAD) TO NC 4. WIDEN TO MULTI-LANES. | HIGHWAY | 4 | ROCKY MOUNT URBAN AREA MPO | U-5911 | DIVISION 4 | T | 2025 | 69000 | 2025 | 2136000 | 2027 | 5625000 |  |  | 7830000
NASH | NC 581 | REPLACE BRIDGE 630091 OVER TAR RIVER. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | B-5947 | REGION A | NHPB | 2021 | 400000 | 2021 | 35000 | 2023 | 6400000 |  |  | 6835000 | RIGHT-OF-WAY IN PROGRESS.
NASH | NC 97 | INSTALL LEFT TURN LANE AT NC 97 AND SR 1603 (OLD CARRIAGE ROAD). | HIGHWAY | 4 | ROCKY MOUNT URBAN AREA MPO | HS-2004B | REGION A | HSIP | 2022 | 86000 |  |  | 2022 | 145000 |  |  | 231000 | RIGHT-OF-WAY IN PROGRESS.
NASH | ROCKY MOUNT | BENVENUE ROAD (NC 43/NC 48) AT JEFFREYS ROAD. INTERSECTION IMPROVEMENTS. | HIGHWAY | 4 | ROCKY MOUNT URBAN AREA MPO | C-5546 | EXEMPT | CMAQ |  |  |  |  | 2022 | 130000 |  |  | 130000
NASH | ROCKY MOUNT | WINSTEAD AVENUE. CONSTRUCT SIDEWALKS. | HIGHWAY | 4 | ROCKY MOUNT URBAN AREA MPO | C-5549 | EXEMPT | CMAQ |  |  |  |  | 2022 | 688000 |  |  | 688000
NASH | SR 1001 (OLD BAILEY HIGHWAY) | INSTALL ALL WAY STOP AT SR 1001 (OLD BAILEY HIGHWAY) AND SR 1717 (MACEDONIA ROAD / SANDY CROSS ROAD). | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | HS-2004H | DIVISION 4 | HSIP |  |  |  |  | 2022 | 25000 |  |  | 25000 | LETTING COMBINED WITH HS-2004F AND HS-2004G.
NASH | SR 1403 (COOPER ROAD) | REPLACE BRIDGE 630080 OVER GIDEON SWAMP ON SR 1403 (COOPER ROAD). | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | BR-0116 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 1000000 |  |  | 1000000
NASH | SR 1510 | BRIDGE 224 ON SR 1510 OVER I-95. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | BR-0039 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 5200000 |  |  | 5200000 | RIGHT OF WAY IN PROGRESS.
NASH | SR 1522 (HALIFAX ROAD) | REPLACE BRIDGE 630203 OVER I-95. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | B-5980 | STATEWIDE MOBILITY | NHPB | 2020 | 2100000 |  |  | 2021 | 16564000 |  |  | 18664000 | UNDER CONSTRUCTION. PROJECT LET WITH BR-0036 AND BR-0039.
NASH | SR 1603 (OLD CARRIAGE ROAD) | GREEN HILLS ROAD TO SR 1770 (EASTERN AVENUE). ADD CENTER TURN LANE AND WIDEN US 64 BRIDGE OVER SR 1603. | HIGHWAY | 4 | ROCKY MOUNT URBAN AREA MPO | U-5996 | DIVISION 4 | T | 2020 | 529000 |  |  | 2022 | 23940000 |  |  | 24469000 | RIGHT-OF-WAY IN PROGRESS.
NASH | SR 1700 (OAK LEVEL ROAD) | SR 1700 (OAK LEVEL ROAD) AT SR 1603 (OLD CARRIAGE ROAD). REVISE TRAFFIC SIGNAL. | HIGHWAY | 4 | ROCKY MOUNT URBAN AREA MPO | HS-2004N | DIVISION 4 | HSIP |  |  |  |  | 2022 | 29000 |  |  | 29000
NASH | SR 1745 (BEND OF THE RIVER ROAD) | REPLACE BRIDGE 630110 OVER THE TAR RIVER RESERVOIR. | HIGHWAY | 4 | ROCKY MOUNT URBAN AREA MPO | HB-0038 | DIVISION 4 | BGOFF | 2026 | 310000 | 2026 | 310000 | 2027 | 6200000 |  |  | 6820000
NASH | SR 1770 (EASTERN AVENUE) | SR 1003 (RED OAK ROAD) TO SR 1603 (OLD CARRIAGE ROAD) IN ROCKY MOUNT. WIDEN TO MULTI-LANES. | HIGHWAY | 4 | ROCKY MOUNT URBAN AREA MPO | R-5720 | DIVISION 4 | T | 2020 | 12252000 | 2020 | 1470000 |  |  |  |  | 13722000 | UNDER CONSTRUCTION. DESIGN-BUILD PROJECT. COMBINED WITH U-5026 FOR LETTING. CONSTRUCTIONS FUNDS SHOWN UNDER U-5026.
NASH | US 301 BYPASS | NC 43/NC 48 (BENVENUE ROAD) TO SR 1836 (MAY DRIVE) IN ROCKY MOUNT. ADD AN ADDITIONAL LANE IN EACH DIRECTION. | HIGHWAY | 4 | ROCKY MOUNT URBAN AREA MPO | U-3330 | REGION A | [10 empty] | UNDER CONSTRUCTION
NASH | US 64 (FUTURE I-87) | SR 1306 (SOUTH OLD FRANKLIN ROAD) TO SR 1603 (OLD CARRIAGE ROAD). PAVEMENT REHABILITATION. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO, ROCKY MOUNT URBAN AREA MPO | I-6045 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2023 | 19300000 |  |  | 19300000
NASH | US 64 (FUTURE I-87) | BRIDGE REHABILITATION FOR 630072 AND 630074. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO, ROCKY MOUNT URBAN AREA MPO | I-6045A | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2022 | 491000 |  |  | 491000
NASH | TAR RIVER TRANSIT | ENLARGE DRIVERS BREAKROOM | PUBLIC TRANSIT | 4 | ROCKY MOUNT URBAN AREA MPO | TD-5281 | DIVISION 4 | T | [6 empty] | 2025 | 15000 | 15000
NASH, EDGECOMBE | US 64 | NC 58 (WASHINGTON STREET), EXIT 459, TO SR 1233 (THOMAS ROAD) OVERPASS. UPGRADE TO INTERSTATE STANDARDS. | HIGHWAY | 4 | ROCKY MOUNT URBAN AREA MPO | U-6149 | NOT FUNDED | NHP | NOT FUNDED | 11800000 | NOT FUNDED | 2200000 | NOT FUNDED | 137000000 |  |  | 151000000
NASH, WAKE, JOHNSTON | US 264 | US 264 FROM THE US 64 / US 264 SPLIT TO THE WILSON COUNTY LINE. PAVEMENT REHABILITATION. | HIGHWAY | 4, 5 | UPPER COASTAL PLAIN RPO, CAPITAL AREA MPO | HI-0013 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2025 | 16500000 |  |  | 16500000
NEW HANOVER | INTERNATIONAL (ILM) WILMINGTON | INCREASE WIDTH OF ALL TAXIWAYS. | AVIATION | 3 | WILMINGTON URBAN AREA MPO | AV-5796 | NOT FUNDED | O, T |  |  |  |  | NOT FUNDED | 3800000 |  |  | 3800000 | OTHER FUNDS PROVIDED BY ILM.
NEW HANOVER | WILIMINGTON INTERNATION (ILM) | TAXIWAY J IMPROVEMENTS. | AVIATION | 3 | WILMINGTON URBAN AREA MPO | AV-5886 | NOT FUNDED | O, T |  |  |  |  | NOT FUNDED | 5600000 |  |  | 5600000 | OTHER FUNDS PROVIDED BY ILM.
NEW HANOVER | WILMINGTON INTERNATIONAL (ILM) | REHABILITATE GA APRON NORTH. | AVIATION | 3 | WILMINGTON URBAN AREA MPO | AV-5702 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
NEW HANOVER | WILMINGTON INTERNATIONAL (ILM) | UPGRADE AIRFIELD LIGHTING VAULT. | AVIATION | 3 | WILMINGTON URBAN AREA MPO | AV-5704 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
NEW HANOVER | WILMINGTON INTERNATIONAL (ILM) | PIPE DITCHES IN FBO #2 AREA. | AVIATION | 3 | WILMINGTON URBAN AREA MPO | AV-5713 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
NEW HANOVER | WILMINGTON INTERNATIONAL (ILM) | EXTEND RUNWAY 6-24 PHASE 1 | AVIATION | 3 | WILMINGTON URBAN AREA MPO | AV-5730 | STATEWIDE MOBILITY | O, T |  |  |  |  | 2022 | 5000000 |  |  | 5000000
NEW HANOVER | WILMINGTON INTERNATIONAL (ILM) | EXPAND THE GENERAL AVIATION APRON. | AVIATION | 3 | WILMINGTON URBAN AREA MPO | AV-5795 | STATEWIDE MOBILITY | O, T |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1300000 |  |  | 1300000 | OTHER FUNDS PROVIDED BY ILM.
NEW HANOVER | WILMINGTON INTERNATIONAL (ILM) | TAXIWAY IMPROVEMENTS. | AVIATION | 3 | WILMINGTON URBAN AREA MPO | AV-5798 | STATEWIDE MOBILITY | O, T |  |  |  |  | 2028 | 5600000 |  |  | 5600000 | OTHER FUNDS PROVIDED BY ILM.
NEW HANOVER | WILMINGTON INTERNATIONAL (ILM) | WIDEN NORTH-SOUTH TAXIWAY SYSTEM. | AVIATION | 3 | WILMINGTON URBAN AREA MPO | AV-5799 | NOT FUNDED | O, T |  |  |  |  | NOT FUNDED | 6500000 |  |  | 6500000 | OTHER FUNDS PROVIDED BY ILM.
NEW HANOVER | WILMINGTON INTERNATIONAL (ILM) | EXPANSION OF AIR CARRIER APRON. | AVIATION | 3 | WILMINGTON URBAN AREA MPO | AV-5801 | STATEWIDE MOBILITY | O, T |  |  |  |  | 2021 | 3940000 |  |  | 3940000 | UNDER CONSTRUCTION. OTHER FUNDS PROVIDED BY ILM.
NEW HANOVER | WILMINGTON INTERNATIONAL AIRPORT (ILM) | REHABILITATE RUNWAY. | AVIATION | 3 | WILMINGTON URBAN AREA MPO | AV-5885 | NOT FUNDED | O, T |  |  |  |  | NOT FUNDED | 7500000 |  |  | 7500000 | OTHER FUNDS PROVIDED BY ILM.
NEW HANOVER | 3RD STREET FORT FISHER BOULEVARD, K AVENUE, AND NO | INTERSECTION IMPROVEMENTS INCLUDING ADA CROSSWALKS, PEDESTRIAN ACTUATED PUSH BUTTONS, AND SIDEWALK CONNECTIONS IN KURE BEACH. | BIKE/PED | 3 | WILMINGTON URBAN AREA MPO | BL-0059 | DIVISION 3 | BGDACV, L | 2023 | 53000 |  |  | 2024 | 302000 | 2023 | 57000 | 412000
NEW HANOVER | CAROLINA BEACH | CONSTRUCT BIKE LANES ALONG ST. JOSEPH AVENUE AND LEWIS DRIVE FROM LAKE PARK BOULEVARD TO ACCESS DRIVE IN CAROLINA BEACH. | BIKE/PED | 3 | WILMINGTON URBAN AREA MPO | EB-6039 | DIVISION 3 | BGDA, L |  |  |  |  | 2023 | 498000 | 2021 | 74000 | 572000
NEW HANOVER | CLARENDON AVENUE | CONSTRUCT MULTI-USE PATH ALONG CLARENDON AVENUE FROM 4TH STREET TO SR 1573 (DOW ROAD). | BIKE/PED | 3 | WILMINGTON URBAN AREA MPO | EB-6029 | DIVISION 3 | L, TADA |  |  |  |  | 2023 | 645000 |  |  | 645000
NEW HANOVER | SR 1219 (SOUTH 17TH STREET) | HARBOUR DRIVE TO SHIPYARD BOULEVARD. CONSTRUCT MULTI-USE PATH. | BIKE/PED | 3 | WILMINGTON URBAN AREA MPO | EB-5600 | DIVISION 3 | BGANY, L | 2024 | 30000 |  |  | 2024 | 738000 | 2022 | 150000 | 918000 | PLANNING, DESIGN, RIGHT-OF-WAY, AND CONSTRUCTION BY CITY OF WILMINGTON.
NEW HANOVER | SR 1403 (MIDDLE SOUND LOOP ROAD) | OGDEN ELEMENTARY SCHOOL TO SR 1986 (OYSTER DRIVE). CONSTRUCT MULTI-USE PATH. | BIKE/PED | 3 | WILMINGTON URBAN AREA MPO | EB-5543 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
NEW HANOVER | SR 1403 (MIDDLE SOUND LOOP) | CONSTRUCT MULTI-USE PATH SOUTH OF MARKET STREET FROM RED CEDAR ROAD TO EXISTING TRAIL AT CORNER OF MARKET STREET AND MIDDLE SOUND LOOP ROAD. | BIKE/PED | 3 | WILMINGTON URBAN AREA MPO | EB-6027 | DIVISION 3 | L | 2021 | 500000 |  |  | 2023 | 1000000 |  |  | 1500000 | RIGHT-OF-WAY IN PROGRESS.
NEW HANOVER | VARIOUS | MIDDLE SOUND LOOP CONNECTOR CONSTRUCTION AND PORTERS NECK WALMART CONNECTOR. CONSTRUCT MULTI-USE PATH. | BIKE/PED | 3 | WILMINGTON URBAN AREA MPO | BL-0040 | DIVISION 3 | BGDA, L |  |  |  |  | 2022 | 692000 |  |  | 692000
NEW HANOVER | WILMINGTON | WILMINGTON RAIL TRAIL. CONSTRUCT MULTI-USE PATH FROM 3RD STREET IN DOWNTOWN WILMINGTON TO THE LOVE GROVE BRIDGE MULTI-USE PATH FACILITY. | BIKE/PED | 3 | WILMINGTON URBAN AREA MPO | BL-0045 | DIVISION 3 | BGDACV | [6 empty] | 2022 | 680000 | 680000
NEW HANOVER | WILMINGTON | CONSTRUCT SIGNALIZED PEDESTRIAN CROSSING AT US 17 BUSINESS (MARKET STREET) AND 21ST STREET. | BIKE/PED | 3 | WILMINGTON URBAN AREA MPO | EB-6028 | DIVISION 3 | L, TADA |  |  |  |  | 2022 | 125000 |  |  | 125000
NEW HANOVER | CAROLINA BEACH | CONSTRUCT NEW TRAFFIC SIGNAL AND IMPROVE PEDESTRIAN ACCOMMODATIONS AT THE INTERSECTION OF US 421 (LAKE PARK BOULEVARD) AND HAMLET AVENUE IN CAROLINA BEACH. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-6233 | DIVISION 3 | BGDA, S | 2022 | 40000 |  |  | 2022 | 256000 | 2021 | 18000 | 314000 | RIGHT-OF-WAY IN PROGRESS. S FUNDS REPRESENT HIGH IMPACT LOW COST HIGHWAY FUNDS.
NEW HANOVER | I-140 | I-40 TO US 421. PAVEMENT REHABILITATION. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | I-5760 | STATEWIDE MOBILITY | [10 empty] | COMPLETED
NEW HANOVER | I-140 | OPEN GRADED FRICTION COURSE. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | I-5760A | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
NEW HANOVER | I-140 | US 421 TO I-40. PAVEMENT AND BRIDGE REHABILITATION. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | I-6037 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2028 | 7300000 |  |  | 7300000
NEW HANOVER | I-140/US 17 WILMINGTON BYPASS | WEST OF US 421 NORTH OF WILMINGTON TO WEST OF NC 133. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | R-2633CA | [11 empty] | COMPLETE
NEW HANOVER | I-140/US 17 WILMINGTON BYPASS | WEST OF NC 133 TO US 117. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | R-2633CB | [11 empty] | COMPLETE
NEW HANOVER | I-140/US 17 WILMINGTON BYPASS | US 117 TO EAST OF I-40 SOUTH OF CASTLE HAYNE. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | R-2633CC | [11 empty] | COMPLETE
NEW HANOVER | LENDIRE ROAD | LENDIRE ROAD, WEST OF US 17 BUSINESS (MARKET STREET) TO US 17 BUSINESS (MARKET STREET)/SR 1403 (MIDDLE SOUND LOOP ROAD). REALIGN ROADWAY. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-4751A | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
NEW HANOVER | NC 132 (COLLEGE ROAD) | SR 1272 (NEW CENTRE DRIVE) TO US 421 (CAROLINA BEACH ROAD). ACCESS MANAGEMENT AND TRAVEL TIME IMPROVEMENTS. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5702
NEW HANOVER | NC 132 (COLLEGE ROAD) | SR 1272 (NEW CENTRE DRIVE) TO US 117 (SHIPYARD BOULEVARD). ACCESS MANAGEMENT AND TRAVEL TIME IMPROVEMENTS. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5702A | STATEWIDE MOBILITY | NHP | 2028 | 15148000 | 2028 | 5380000 | 2030 | 16000000 |  |  | 36528000 | PLANNING/DESIGN IN PROGRESS. PROJECT TO BE LET WITH U-5704.
NEW HANOVER | NC 132 (COLLEGE ROAD) | US 117 (SHIPYARD BOULEVARD) TO US 421 (CAROLINA BEACH ROAD). ACCESS MANAGEMENT AND TRAVEL TIME IMPROVEMENTS. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5702B | NOT FUNDED | NHP | NOT FUNDED | 14240000 | NOT FUNDED | 8592000 | NOT FUNDED | 33800000 |  |  | 56632000
NEW HANOVER | NC 132 (COLLEGE ROAD) | US 76 (OLEANDER DRIVE). INTERSECTION IMPROVEMENTS. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5704 | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 21183000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2422000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 14100000 |  |  | 37705000 | PROJECT TO BE LET WITH U-5702A.
NEW HANOVER | NC 132 (COLLEGE ROAD) | SR 2048 (GORDON ROAD) TO SR 1272 (NEW CENTRE DRIVE). UPGRADE ROADWAY. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5881 | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 20192000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8128000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 74300000 |  |  | 102620000 | PROJECT TO BE LET WITH U-5792.
NEW HANOVER | NC 133 (CASTLE HAYNE ROAD) | I-140/US 17 (WILMINGTON BYPASS) TO SR 1310 (DIVISION DRIVE) IN WILMINGTON. WIDEN TO MULTI-LANES | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5863 | NOT FUNDED | T | NOT FUNDED | 4800000 | NOT FUNDED | 4600000 | NOT FUNDED | 26800000 |  |  | 36200000
NEW HANOVER | NC 133 (CASTLE HAYNE ROAD) | NORTH 23RD STREET. CONSTRUCT A ROUNDABOUT. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5954 | REGION B | T | 2025 | 721000 | 2025 | 507000 | 2027 | 3800000 |  |  | 5028000
NEW HANOVER | NEW LOCATION | FROM SR 1409 (MILITARY CUTOFF ROAD) AT DRYSDALE DRIVE TO US 74 (EASTWOOD ROAD). ROADWAY ON NEW LOCATION. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5710A | STATEWIDE MOBILITY | BGANY, T | 2019 | 2575000 |  |  | 2022 | 8280000 |  |  | 10855000 | UNDER CONSTRUCTION.
NEW HANOVER | NEW ROUTE | SR 1302 (23RD STREET) TO 26TH STREET. CONSTRUCT ROUTE ON NEW LOCATION. ECONOMIC DEVELOPMENT PROJECT. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5926 | DIVISION 3 | L, T | 2023 | 1406000 | 2023 | 344000 | 2024 | 7301000 |  |  | 9051000 | ECONOMIC DEVELOPMENT PROJECT.
NEW HANOVER | SR 1175 (KERR AVENUE) | RANDALL PARKWAY TO US 74 (MLK, JR. PARKWAY) IN WILMINGTON. WIDEN TO MULTI-LANES. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-3338
NEW HANOVER | SR 1175 (KERR AVENUE) | RANDALL PARKWAY TO US 74 (MLK, JR. PARKWAY). | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-3338B | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
NEW HANOVER | SR 1175 (KERR AVENUE) | SR 1175 (KERR AVENUE) INTERCHANGE AT US 74 (MLK, JR. PARKWAY). | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-3338C | REGION B | BGANY |  |  |  |  | 2026 | 26800000 |  |  | 26800000 | RIGHT-OF-WAY IN PROGRESS
NEW HANOVER | SR 1175 (KERR AVENUE) | SR 1411 (WRIGHTSVILLE AVENUE) TO US 76 (OLEANDER DRIVE). CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-6201 | DIVISION 3 | T | 2028 | 4200000 | 2028 | 400000 | 2030 | 4498000 |  |  | 9098000
NEW HANOVER | SR 1209 (INDEPENDENCE BOULEVARD EXTENSION) | RANDALL PARKWAY TO US 74 (MLK, JR. PARKWAY) IN WILMINGTON. MULTI-LANES ON NEW LOCATION. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-4434 | DIVISION 3 | BGANY | 2026 | 88700000 | 2026 | 3632000 | 2028 | 122350000 |  |  | 214682000
NEW HANOVER | SR 1217 (17TH STREET) | INSTALL NEAR SIDE SIGNAL HEADS ON A PEDESTAL ON BOTH SIDES OF SR 1217 (17TH STREET) AT DOCK STREET IN WILMINGTON. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | HS-2003A | DIVISION 3 | HSIP |  |  |  |  | 2023 | 34000 |  |  | 34000
NEW HANOVER | SR 1409 (MILITARY CUTOFF ROAD EXTENSION) | SR 1409 (MILITARY CUTOFF ROAD) TO US 17 (MARKET STREET) IN WILMINGTON. MULTI-LANES ON NEW LOCATION. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-4751 | STATEWIDE MOBILITY | T |  |  |  |  | 2018 | 64625000 | 2021 | 14850000 | 79475000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $11,536,407 FOR PE, $28,080,288 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE).
NEW HANOVER | SR 2048 (GORDON ROAD) | US 17 (MARKET STREET) TO I-40. WIDEN ROADWAY. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-6202 | DIVISION 3 | T | 2022 | 12835000 | 2022 | 5300000 | 2024 | 33600000 |  |  | 51735000 | BUILD NC BOND FUNDING: $5,000,000 FOR RIGHT-OF-WAY PAYBACK 2022 - 2036 (FY 2022 / YR 4 SALE).
NEW HANOVER | US 117 / NC 132 (COLLEGE ROAD) | US 117 / NC 132 (COLLEGE ROAD) AT LAKE AVENUE-HUGH MCRAE PARK IN WILMINGTON. REVISE TRAFFIC SIGNAL. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | HS-2003H | REGION B | HSIP |  |  |  |  | 2025 | 66000 |  |  | 66000
NEW HANOVER | US 17 (OLEANDER DRIVE) | US 17 (OLEANDER DRIVE) AT 42ND STREET IN WILMINGTON. REVISE TRAFFIC SIGNAL AND PAVEMENT MARKINGS. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | HS-2003J | REGION B | HSIP |  |  |  |  | 2025 | 59000 |  |  | 59000
NEW HANOVER | US 17 BUSINESS (MARKET STREET) | COLONIAL DRIVE TO SR 1402 (PORTERS NECK ROAD). ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-4902
NEW HANOVER | US 17 BUSINESS (MARKET STREET) | SR 1272 (NEW CENTRE DRIVE) TO MARTIN LUTHER KING JR., BOULEVARD. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-4902A | [11 empty] | COMPLETE.
NEW HANOVER | US 17 BUSINESS (MARKET STREET) | CSX RAILROAD TO CINEMA DRIVE; JACKSONVILLE STREET TO NORTH OF US 117/NC 132 (COLLEGE ROAD). | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-4902B | REGION B | T | 2027 | 10000000 | 2027 | 2900000 | 2029 | 9700000 |  |  | 22600000
NEW HANOVER | US 17 BUSINESS (MARKET STREET) | NORTH OF US 117/NC 132 (COLLEGE ROAD) TO STATION ROAD. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-4902C | STATEWIDE MOBILITY | T | 2027 | 46089000 | 2027 | 10811000 | 2029 | 55100000 |  |  | 112000000 | INCLUDES U-5880.
NEW HANOVER | US 17 BUSINESS (MARKET STREET) | SR 1403 (MIDDLE SOUND LOOP ROAD) TO SR 2290 (MENDEHNALL DRIVE)/ SR 2734 (MARSH OAKS DRIVE). | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-4902D | STATEWIDE MOBILITY | T |  |  |  |  | 2019 | 24609000 | 2021 | 4290000 | 28899000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,333,437 FOR PE, $9,936,773 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE).
NEW HANOVER | US 17-76 (OLEANDER DRIVE) | US 17-76 (OLEANDER DRIVE) AND SR 1421 (GREENVILLE LOOP ROAD) / GREENVILLE AVENUE IN WILMINGTON. REVISE TRAFFIC SIGNAL. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | HS-2003L | REGION B | HSIP |  |  |  |  | 2025 | 84000 |  |  | 84000
NEW HANOVER | US 421 | US 421 (BURNETT AVENUE) TO US 117 (SHIPYARD BOULEVARD) IN WILMINGTON. UPGRADE ROADWAY. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5729REG | REGION B | T | 2027 | 21200000 | 2027 | 6560000 | 2029 | 16160000 |  |  | 43920000
NEW HANOVER | US 421 | US 117 (SHIPYARD BOULEVARD). INTERSECTION IMPROVEMENTS. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5729SW | STATEWIDE MOBILITY | T | 2027 | 5300000 | 2027 | 1640000 | 2029 | 4040000 |  |  | 10980000
NEW HANOVER | US 421 (CAROLINA BEACH ROAD) | US 421 (BURNETT AVENUE) TO US 117 (SHIPYARD BOULEVARD) IN WILMINGTON. UPGRADE ROADWAY. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5729
NEW HANOVER | US 421 (CAROLINA BEACH ROAD) | NC 132 (SOUTH COLLEGE ROAD) TO SANDERS ROAD IN WILMINGTON. WIDEN EXISTING ROADWAY AND CONSTRUCT FLYOVERS AT US 421 AND NC 132. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5790 | DIVISION 3 | T | 2027 | 6065000 | 2027 | 6428000 | 2029 | 20500000 |  |  | 32993000
NEW HANOVER | US 421 (CAROLINA BEACH ROAD) | FROM US 117 / NC 132 (COLLEGE ROAD) TO 200 FEET NORTH OF WILOUGHBY PARK. INSTALL CURB AND GUTTER, MULTI-USE PATH, SIDEWALK, PEDESTRIAN SIGNALS, HIGH VISIBILITY CROSSWALKS, AND LIGHTING. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | W-5703C | REGION B | HSIP | 2023 | 1375000 |  |  | 2024 | 3700000 |  |  | 5075000
NEW HANOVER | US 421 (SOUTH FRONT STREET) | US 17 BUSINESS/US 76/US 421 (CAPE FEAR MEMORIAL BRIDGE) TO US 421 (BURNETT BOULEVARD) IN WILMINGTON. WIDEN TO MULTI-LANES. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5734 | REGION B | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 13940000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1032000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10299000 |  |  | 25271000
NEW HANOVER | US 74 | US 17/US 421 IN WILMINGTON. CONSTRUCT A FLY-OVER AND FREE FLOW RAMP AT INTERCHANGE. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5731 | STATEWIDE MOBILITY | T | 2026 | 5200000 | 2026 | 241000 | 2028 | 31499000 |  |  | 36940000
NEW HANOVER | US 74 | US 74 (EASTWOOD ROAD) AT US 17 (MILITARY CUTOFF ROAD), AND US 74 (EASTWOOD ROAD) AT CAVALIER DRIVE IN WILMINGTON. UPGRADE PEDESTRIAN SIGNALS. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | W-5803A | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2023 | 42000 |  |  | 42000
NEW HANOVER | US 74 (EASTWOOD ROAD) | SR 1409 (MILITARY CUTOFF ROAD) INTERSECTION IN WILMINGTON. CONVERT AT-GRADE INTERSECTION TO AN INTERCHANGE. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5710 | STATEWIDE MOBILITY | NHP | 2023 | 22700000 | 2023 | 5200000 | 2025 | 38500000 |  |  | 66400000
NEW HANOVER | US 74 (MARTIN LUTHER KING, JR. PARKWAY) | US 117/NC 132 (COLLEGE ROAD) IN WILMINGTON. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5792 | DIVISION 3 | T | 2024 | 4753000 | 2024 | 2696000 | 2026 | 40305000 |  |  | 47754000 | PROJECT TO BE LET WITH U-5881. BUILD NC BOND FUNDING: $15,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE).
NEW HANOVER | US 74 WESTBOUND ON-RAMP | US 74 WESTBOUND ON-RAMP AND SR 1627 (3RD STREET / MARTIN LUTHER KING JUNIOR BOULEVARD) IN WILMINGTON. REVISE TRAFFIC SIGNAL. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | HS-2003K | REGION B | HSIP |  |  |  |  | 2025 | 16000 |  |  | 16000
NEW HANOVER | US 76 (OLEANDER DRIVE) | GREENVILLE LOOP ROAD AND GREENVILLE AVENUE. UPGRADE INTERSECTION. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-6128 | NOT FUNDED | BGANY | NOT FUNDED | 3700000 | NOT FUNDED | 600000 | NOT FUNDED | 3600000 |  |  | 7900000
NEW HANOVER | WILMINGTON | CONSTRUCT A NEW NORTH GATE ON NORTH CAROLINA PORTS AUTHORITY PROPERTY. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | HL-0040 | DIVISION 3 | BGDA, L | [6 empty] | 2022 | 313000 | 313000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDIES ONLY.
NEW HANOVER | WILMINGTON | WILMINGTON CITYWIDE SIGNAL SYSTEM. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-6199 | DIVISION 3 | T | 2028 | 100000 | 2028 | 950000 | 2030 | 15360000 |  |  | 16410000
NEW HANOVER | WILMINGTON | WILMINGTON MULTI-MODAL TRANSPORTATION CENTER PHASE 1B. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-6234 | DIVISION 3 | BGDA, L |  |  |  |  | 2022 | 2834000 | 2020 | 317000 | 3151000
NEW HANOVER | WILMINGTON | TRAFFIC SIGNAL PRE-EMPTION FOR EMERGENCY VEHICLES PROJECT. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-6235 | DIVISION 3 | BGDA, L |  |  |  |  | 2024 | 784000 | 2020 | 487000 | 1271000
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | ADA | PUBLIC TRANSIT | 3 | WILMINGTON URBAN AREA MPO | TA-6700 | DIVISION 3 | BGDA, L |  |  |  |  | 2020 | 180000 |  |  | 180000
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | THE PREVENTATIVE MAINTENACE PROJECT WILL ENSURE THE FTA FUNDED ASSESTS ARE MAINTAINED TO THE FTA STATE OF GOOD REPAIR REQUIREMENTS AND THAT SERVICE CONTINUES WITHOUT DISRUPTION. | PUBLIC TRANSIT | 3 | WILMINGTON URBAN AREA MPO | TG-5243 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2023 | 1125000 | 1125000
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | THE OPERATING ASSISTANCE PROJECT WILL ALLOW THE CONTINUATION OF COMPLEMENTARY PARATRANSIT SERVICE TO TWO COUNTIES AND FOUR MUNICIPLITIES WITHIN THE UZA. | PUBLIC TRANSIT | 3 | WILMINGTON URBAN AREA MPO | TG-5246 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2023 | 393000 | 393000
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | ROUTE 201 IN WILMINGTON, UPGRADE AMMENITIES AND BUS STOPS | PUBLIC TRANSIT | 3 | WILMINGTON URBAN AREA MPO | TG-6177 | PUBLIC TRANSIT | 5307, L, T |  |  |  |  | 2023 | 66000 |  |  | 66000
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PREVENTIVE MAINTENANCE | PUBLIC TRANSIT | 3 | WILMINGTON URBAN AREA MPO | TG-6784 | DIVISION 3 | BGDA, L |  |  |  |  | 2020 | 420000 |  |  | 420000
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | ADMINISTRATION | PUBLIC TRANSIT | 3 | WILMINGTON URBAN AREA MPO | TK-6176 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 872000 | 872000 | FUNDS AUTHORIZED IN PROGRESS
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | OPERATING ASSISTANCE | PUBLIC TRANSIT | 3 | WILMINGTON URBAN AREA MPO | TO-4751 | PUBLIC TRANSIT | 5307, L, SMAP | [6 empty] | 2022 | 9327000 | 9327000 | FUNDS AUTHORIZED IN PROGRESS
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PLANNING ASSISTANCE - SHORT RANGE DEVELOPMENT | PUBLIC TRANSIT | 3 | WILMINGTON URBAN AREA MPO | TP-5110 | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2023 | 190000 | 190000 | FUNDS AUTHORIZED IN PROGRESS
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PLANNING ASSISTANCE - 5303 | PUBLIC TRANSIT | 3 | WILMINGTON URBAN AREA MPO | TP-5111 | PUBLIC TRANSIT | 5303, L, S | [6 empty] | 2020 | 1648000 | 1648000 | FUNDS AUTHORIZED IN PROGRESS
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PROJECT PROVIDES OPERATING SUPPORT FOR FIXED BUS ROUTE 205 LONG LEAF PARK WHICH SERVICES NOVANT HOSPITAL AND THE MEDICAL CENTER. THIS ROUTE CARRIES A HIGH CONCENTRATION OF INDIVIDUALS WITH DISABILITIES AS IDENTIFIED THROUGH AN EXTENSIVE ONBOARD SURVEY EFF | PUBLIC TRANSIT | 3 | WILMINGTON URBAN AREA MPO | TQ-6513 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2023 | 346000 | 346000 | FUNDS AUTHORIZED IN PROGRESS
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PROJECT IS FOR ADMINISTRATIVE SUPPORT REQUIRED TO EFFECTVELY MANAGE THE SECTION 5310 PROGRAM AND ANNUAL FUNDING ALLOCATION FROM FTA. | PUBLIC TRANSIT | 3 | WILMINGTON URBAN AREA MPO | TQ-7005 | PUBLIC TRANSIT | 5310 | [6 empty] | 2021 | 105000 | 105000
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | MOBILITY MANAGER PROVIDES OVERSIGHT AND MANAGEMENT OF SECTION 5310 FUNDS AND ADMINISTERS THE PROGRAMS AND PROJECTS SUPPORTED BY THESE FUNDS. | PUBLIC TRANSIT | 3 | WILMINGTON URBAN AREA MPO | TQ-8019 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2023 | 150000 | 150000 | FUNDS AUTHORIZED IN PROGRESS
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | PROJECTS FULFILLS THE ALLOCATION FOR NON-TRADITIONAL TRANSPORTATION PROJECTS AS DEFINED IN THE GRANT. THE PROJECT SUPPORTS THE COMMUNITY GRANT OFFERING TO NON-PROFITS AND GOVERNMENTAL ORGANIZAIONS TO REMOVE TRANSPORTATION BARRIERS AND CONNECT ELDERS AND I | PUBLIC TRANSIT | 3 | WILMINGTON URBAN AREA MPO | TQ-9001 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2022 | 278000 | 278000
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY | SAFETY & SECURITY - MIN. 1% SET ASIDE | PUBLIC TRANSIT | 3 | WILMINGTON URBAN AREA MPO | TS-5103 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 96000 | 96000 | FUNDS AUTHORIZED IN PROGRESS
NEW HANOVER | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY - WAVE T | CAPITAL IMPROVEMENT PROJECT TO SECURE AUTOMATIC PASSENGER COUNTER (APC) TECHNOLOGY FOR THE PURPOSE OF COLLECTING STOP LEVEL BOARDINGS AND ALIGHTINGS FOR FIXED ROUTE PUBLIC TRANSPORTATION SERVICES. | PUBLIC TRANSIT | 3 | WILMINGTON URBAN AREA MPO | TL-0017 | DIVISION 3 | BGDA, L | [6 empty] | 2022 | 200000 | 200000
NEW HANOVER | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | REPLACEMENT LTV | PUBLIC TRANSIT | 3 | WILMINGTON URBAN AREA MPO | TA-5221 | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 365000 | 365000 | FUNDS AUTHORIZED IN PROGRESS
NEW HANOVER | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | REPLACEMENT LTV | PUBLIC TRANSIT | 3 | WILMINGTON URBAN AREA MPO | TA-5222 | PUBLIC TRANSIT | 5339, L, S | [6 empty] | 2020 | 624000 | 624000 | FUNDS AUTHORIZED IN PROGRESS
NEW HANOVER | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | REPLACEMENT BUS | PUBLIC TRANSIT | 3 | WILMINGTON URBAN AREA MPO | TA-5223 | PUBLIC TRANSIT | 5339, L, S | [6 empty] | 2020 | 3234000 | 3234000
NEW HANOVER | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | REPLACEMENT TROLLEY | PUBLIC TRANSIT | 3 | WILMINGTON URBAN AREA MPO | TA-5224 | PUBLIC TRANSIT | 5339 | [6 empty] | 2020 | 700000 | 700000
NEW HANOVER | TRANSPORTATION AUTHORITY CAPE FEAR PUBLIC | PREVENTIVE MAINTENANCE | PUBLIC TRANSIT | 3 | WILMINGTON URBAN AREA MPO | TG-5245 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 314000 | 314000
NEW HANOVER | CSX SE LINE | IMPROVEMENTS TO HIGHWAY GRADE CROSSINGS, CLOSE AND IMPROVE VARIOUS EXISTING AT-GRADE CROSSINGS. | RAIL | 3 | WILMINGTON URBAN AREA MPO | P-5740B | STATEWIDE MOBILITY | DP, T | 2022 | 600000 |  |  | 2023 | 4349000 |  |  | 4949000
NEW HANOVER, BRUNSWICK | I-140/US 17 WILMINGTON BYPASS | SR 1430 (CEDAR HILL ROAD) TO WEST OF US 421 NORTH OF WILMINGTON. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | R-2633BB | PRE-STI (TRANSITION) | NHP |  |  |  |  | 2013 | 51250000 |  |  | 51250000 | COMPLETE. GARVEE BOND FUNDING $100 M FOR SEGMENT BB; PAYBACK FY 2013-2024.
NEW HANOVER, BRUNSWICK | CSX SE LINE | WILMINGTON BELTLINE SPEED IMPROVEMENT PROJECT. | RAIL | 3 | WILMINGTON URBAN AREA MPO | P-5740 | STATEWIDE MOBILITY | [10 empty] | DISCRETIONARY FUNDING PROVIDED FROM FEDERAL CRISI GRANT.
NEW HANOVER, BRUNSWICK | CSX SE LINE | TIE AND RAIL REHABILITATION, CURVE REALIGNMENT, AND UPGRADE RAIL BRIDGES. | RAIL | 3 | WILMINGTON URBAN AREA MPO | P-5740A | STATEWIDE MOBILITY | DP, T |  |  |  |  | 2022 | 26550000 |  |  | 26550000
NEW HANOVER, BRUNSWICK | CSX SE LINE | INSTALLATION OF RAILROAD GRADE CROSSING SIGNALS AND GATES AT VARIOUS AT-GRADE CROSSINGS. | RAIL | 3 | WILMINGTON URBAN AREA MPO | P-5740C | STATEWIDE MOBILITY | DP, T |  |  |  |  | 2023 | 9900000 |  |  | 9900000
NEW HANOVER, BRUNSWICK, CARTERET | VARIOUS | CEDAR ISLAND, SOUTHPORT AND FORT FISHER DOCKS. REPLACE DOLPHINS. | FERRY | 2, 3 | DOWN EAST RPO, WILMINGTON URBAN AREA MPO | F-5301 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
NEW HANOVER, BRUNSWICK, PENDER | VARIOUS | WILMINGTON URBAN AREA MPO TRANSPORTATION ALTERNATIVES PROGRAM. | BIKE/PED | 3 | WILMINGTON URBAN AREA MPO | U-5527 | DIVISION 3 | TADA |  |  |  |  | 2022 | 11714000 |  |  | 11714000 | IN PROGRESS
NEW HANOVER, BRUNSWICK, PENDER | VARIOUS | WILMINGTON URBAN AREA METROPOLITAN PLANNING ORGANIZATION PLANNING (PL) SUPPLEMENT. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5525 | DIVISION 3 | BGDA, L | [6 empty] | 2020 | 19340000 | 19340000
NEW HANOVER, BRUNSWICK, PENDER | VARIOUS | WILMINGTON URBAN AREA MPO STP-DA PROGRAM. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5534 | DIVISION 3 | BGANY, BGDA, BGDACV, L | 2022 | 220000 |  |  | 2020 | 10006000 |  |  | 10226000 | IN PROGRESS
NEW HANOVER, BRUNSWICK, PENDER | VARIOUS | WILMINGTON URBAN METROPOLITAN PLANNING ORGANIZATION STBGDA RESERVE ACCOUNT. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5989 | DIVISION 3 | BGDA |  |  |  |  | 2022 | 71063000 |  |  | 71063000
NEW HANOVER, PENDER | I-40 | I-40 FROM END I-40 (MILEMARKER 420) TO NC 210 (MILEMARKER 408). PAVEMENT REHABILITATION. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | I-6039 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2023 | 13200000 |  |  | 13200000
NEW HANOVER, PENDER | US 17 (HAMPSTEAD BYPASS) | US 17 BYPASS SOUTH OF HAMPSTEAD TO US 17 NORTH OF HAMPSTEAD. CONSTRUCT FREEWAY ON NEW LOCATION | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | R-3300
NORTHAMPTON | I-95 | CHOCKOYOTTE CREEK (MILE MARKER 172) TO VIRGINIA STATE LINE (MILE MARKER 181.4). PAVEMENT REHABILITATION. | HIGHWAY | 1 | PEANUT BELT RPO | I-5839 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
NORTHAMPTON | NC 305 | SEABOARD TOWN LIMITS TO HERTFORD COUNTY LINE. UPGRADE ROADWAY. | HIGHWAY | 1 | PEANUT BELT RPO | R-5757 | DIVISION 1 | BGLT5 | 2023 | 1524000 | 2023 | 4122000 | 2024 | 46500000 |  |  | 52146000
NORTHAMPTON | NC 46 | NC 48 IN GASTON TO THE VIRGINIA STATE LINE. UPGRADE AND WIDEN EXISTING FACILITY. | HIGHWAY | 1 | PEANUT BELT RPO | R-5739 | DIVISION 1 | T | 2022 | 2765000 | 2022 | 10800000 | 2025 | 28100000 |  |  | 41665000 | RIGHT-OF-WAY IN PROGRESS.
NORTHAMPTON | SR 1126 (BARROWS MILL ROAD) | REPLACE BRIDGE 650063 OVER OCCONEECHEE CREEK. | HIGHWAY | 1 | PEANUT BELT RPO | BR-0222 | HIGHWAY FUND | [10 empty] | UNDER CONSTRUCTION. PROJECT REPRESENTS HFB 1.R.81 PROJECT.
NORTHAMPTON | SR 1203 (JACKS SWAMP ROAD) | REPLACE BRIDGE NO. 650093 OVER JACKS SWAMP ON SR 1203 (JACKS SWAMP ROAD). | HIGHWAY | 1 | PEANUT BELT RPO | BR-0118 | DIVISION 1 | DP, HFB | 2020 | 60000 |  |  | 2021 | 1046000 |  |  | 1106000 | HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. UNDER CONSTRUCTION.
NORTHAMPTON | SR 1300 (BIG JOHNS STORE ROAD) | REPLACE BRIDGE 650049 OVER BRANCH OF JACKS SWAMP. | HIGHWAY | 1 | PEANUT BELT RPO | BR-0221 | HIGHWAY FUND | [10 empty] | UNDER CONSTRUCTION. PROJECT REPRESENTS HFB 1.R.80 PROJECT.
NORTHAMPTON | SR 1313 (HARGRAVES ROAD) | REPLACE BRIDGE NO. 650052 OVER GUMBERRY SWAMP ON SR 1313 (HARGRAVES ROAD). | HIGHWAY | 1 | PEANUT BELT RPO | BR-0117 | DIVISION 1 | DP, HFB | 2020 | 20000 |  |  | 2021 | 1050000 |  |  | 1070000 | HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. UNDER CONSTRUCTION.
NORTHAMPTON | SR 1341 (DEBERRYS MILL ROAD) | REPLACE BRIDGE 650010 OVER CORDURY CREEK. | HIGHWAY | 1 | PEANUT BELT RPO | BR-0220 | HIGHWAY FUND | [10 empty] | UNDER CONSTRUCTION. PROJECT REPRESENTS HFB 1.R.79 PROJECT.
NORTHAMPTON | SR 1505 (NORTHAMPTON COUNTY HIGH SCHOOL ROAD) | REPLACE BRIDGE 650015 OVER WILDCAT SWAMP. | HIGHWAY | 1 | PEANUT BELT RPO | BR-0240 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 1100000 |  |  | 1100000 | PROJECT REPRESENTS HFB 1.R.90 PROJECT.
NORTHAMPTON | US 158/NC 46 | I-95/NC 46 IN ROANOKE RAPIDS TO SR 1333 (MT. CARMEL CHURCH ROAD) EAST OF JACKSON. WIDEN TO MULTI-LANES WITH BYPASS OF JACKSON, SOME NEW LOCATION. | HIGHWAY | 1 | PEANUT BELT RPO | R-2582
NORTHAMPTON | US 158/NC 46 | I-95/NC 46 IN ROANOKE RAPIDS TO SR 1312 (ST. JOHN CHURCH ROAD) IN NORTHAMPTON COUNTY. | HIGHWAY | 1 | PEANUT BELT RPO | R-2582A | DIVISION 1 | T | 2020 | 3345000 |  |  | 2020 | 105995000 | 2020 | 8820000 | 118160000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,984,085 FOR PE, $2,602,458.05 FOR ROW, $11,917,318.84 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $2,863,074 FOR PE, $29,231,559 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE)
NORTHAMPTON | US 158/NC 46 | SR 1312 (ST. JOHN CHURCH ROAD) TO SR 1333 (MT. CARMEL CHURCH ROAD) EAST OF JACKSON. | HIGHWAY | 1 | PEANUT BELT RPO | R-2582B | NOT FUNDED | T | NOT FUNDED | 5400000 |  |  | NOT FUNDED | 61400000 |  |  | 66800000
ONSLOW | ALBERT J. ELLIS AIRPORT (OAJ) | DESIGN AND CONSTRUCT RUNWAY 23 HOLDING APRON. | AVIATION | 3 | JACKSONVILLE URBAN AREA MPO | AV-5733 | REGION B | O, T |  |  |  |  | 2022 | 750000 |  |  | 750000
ONSLOW | ALBERT J. ELLIS AIRPORT (OAJ) | ACQUIRE LAND FOR ROADWAY RELOCATION, RPZ AND RUNWAY EXTENSION. | AVIATION | 3 | JACKSONVILLE URBAN AREA MPO | AV-5804 | REGION B | O, T | 2023 | 697000 | [6 empty] | 697000 | OTHER FUNDS ARE AIRPORT FUNDS
ONSLOW | ALBERT J. ELLIS AIRPORT (OAJ) | ACQUIRE LAND FOR RUNWAY EXTENSION AND ROADWAY RELOCATION. | AVIATION | 3 | JACKSONVILLE URBAN AREA MPO | AV-5805 | REGION B | O, T | 2023 | 361000 | [6 empty] | 361000 | OTHER FUNDS ARE AIRPORT FUNDS
ONSLOW | ALBERT J. ELLIS AIRPORT (OAJ) | EXTEND RUNWAY 23 AND TAXIWAY A. | AVIATION | 3 | JACKSONVILLE URBAN AREA MPO | AV-5806 | REGION B | O, T |  |  |  |  | 2025 | 12880000 |  |  | 12880000 | OTHER FUNDS ARE AIRPORT FUNDS
ONSLOW | DOWNTOWN GREENWAY | CHANEY AVENUE TO WARDOLA DRIVE IN JACKSONVILLE. CONSTRUCT MULTI-USE PATH. | BIKE/PED | 3 | JACKSONVILLE URBAN AREA MPO | EB-6012 | DIVISION 3 | L, TA5200 |  |  |  |  | 2022 | 1367000 |  |  | 1367000
ONSLOW | JACKSONVILLE | LEJEUNE BOULEVARD GREENWAY, SOUTH SIDE OF NC 24 (LEJEUNE BOULEVARD), MONTFORD POINT ROAD TO U-5132 GREENWAY TERMINI. | BIKE/PED | 3 | JACKSONVILLE URBAN AREA MPO | EB-4705 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
ONSLOW | COMMERCE DRIVE EXTENSION | COMMERCE DRIVE TO SR 1406 (PINEY GREEN ROAD). CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5878 | DIVISION 3 | T |  |  |  |  | 2022 | 3849000 |  |  | 3849000 | UNDER CONSTRUCTION
ONSLOW | JACKSONVILLE PARKWAY | COUNTRY CLUB ROAD TO SR 1470 (WESTERN BOULEVARD). | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-4007B | [11 empty] | COMPLETE
ONSLOW | NC 172 | CAMP LEJEUNE GATE TO NC 210. CONVERT TWO LANE ROADWAY TO THREE LANE ROADWAY WITH A TWO WAY LEFT TURN LANE. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | W-5602 | REGION B | T |  |  |  |  | 2019 | 11418000 |  |  | 11418000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $5,500,000 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE).
ONSLOW | NC 210 | US 17 TO SOUTH OF SR 1518 (OLD FOLKSTONE ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5949 | REGION B | T | 2028 | 8344000 | 2028 | 17594000 | 2030 | 69901000 |  |  | 95839000
ONSLOW | NC 24 | US 258 (RICHLANDS HIGHWAY) INTERSECTION. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5716 | STATEWIDE MOBILITY | T | 2027 | 26700000 | 2027 | 2700000 | 2029 | 40700000 |  |  | 70100000 | PROJECT BEING LET WITH U-5739
ONSLOW | NC 24 | NC 24 (WEST CORBETT AVENUE) AND SR 1512 (OLD HAMMOCKS ROAD). UPGRADE PEDESTRIAN SIGNALS. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | W-5803D | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2022 | 17000 |  |  | 17000 | UNDER CONSTRUCTION.
ONSLOW | NC 24 (LEJEUNE BOULEVARD) | NC 53 (WESTERN BOULEVARD) IN JACKSONVILLE. UPGRADE INTERSECTION AND DRAINAGE. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5508 | STATEWIDE MOBILITY | T | 2027 | 799000 | 2027 | 150000 | 2029 | 1650000 |  |  | 2599000 | COMBINE WITH U-5736 AND U-4007E.
ONSLOW | NC 24 (LEJEUNE BOULEVARD) | NC 24 BUSINESS (JOHNSON BOULEVARD) TO NC 172. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5741 | REGION B | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7367000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3664000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 49600000 |  |  | 60631000 | PROJECT INCLUDES B-5650
ONSLOW | NC 24 (WEST CORBETT AVENUE) | BELGRADE-SWANSBORO ROAD TO FRONT STREET. CONSTRUCT SUPERSTREET. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | R-5885 | NOT FUNDED | NHP | NOT FUNDED | 15304000 | NOT FUNDED | 802000 | NOT FUNDED | 28699000 |  |  | 44805000
ONSLOW | NC 24 (WEST CORBETT AVENUE) | REPLACE CULVERT EAST OF WEST SHORE DRIVE. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | R-5885A | REGION B | NHP | 2025 | 115000 | 2025 | 84000 | 2027 | 1500000 |  |  | 1699000
ONSLOW | NC 53 | SR 1109 (HOLLY SHELTER ROAD). REALIGNMENT AND LANE CONSTRUCTION. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | SF-4903F | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION - COMBINED FOR LETTING WITH R-5023B AND C.
ONSLOW | NC 53 | NC 53: FROM US 17 (MARINE BOULEVARD) TO SR 2716 (EXCHANGE DRIVE). | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-4007E | STATEWIDE MOBILITY | T | 2027 | 8100000 | 2027 | 400000 | 2029 | 7200000 |  |  | 15700000 | COMBINED WITH U-5736 AND U-5508.
ONSLOW | NC 53 | NC 53 (WESTERN BOULEVARD) AND CENTER STREET / LIBERTY DRIVE. UPGRADE TRAFFIC SIGNAL AND ADD ADDITIONAL SPEED LIMIT SIGNS. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | W-5803E | REGION B | HSIP |  |  |  |  | 2022 | 57000 |  |  | 57000 | UNDER CONSTRUCTION.
ONSLOW | NC 53 (WESTERN BOULEVARD) | US 17 (MARINE BOULEVARD) TO NC 24 (LEJEUNE BOULEVARD) IN JACKSONVILLE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5736 | REGION B | T | 2027 | 10500000 | 2027 | 2440000 | 2029 | 31300000 |  |  | 44240000 | COMBINED WITH U-4007E AND U-5508.
ONSLOW | NC 53 (WESTERN BOULEVARD) | SR 2714 (JACKSONVILLE PARKWAY). IMPROVE INTERSECTION. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5789 | REGION B | T |  |  |  |  | 2025 | 4550000 |  |  | 4550000 | RIGHT-OF-WAY IN PROGRESS
ONSLOW | NC 53 (WESTERN BOULEVARD) | SR 1308 (GUM BRANCH ROAD) TO US 17 (MARINE BOULEVARD). UPGRADE TO SUPERSTREET. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-6081 | NOT FUNDED | T | NOT FUNDED | 2400000 | NOT FUNDED | 1000000 | NOT FUNDED | 50800000 |  |  | 54200000
ONSLOW | NC 53 (WESTERN BOULEVARD) | NC 53 (WESTERN BOULEVARD) AT SR 1336 (HENDERSON DRIVE). INTERSECTION IMPROVEMENTS. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | W-5203U | REGION B | HSIP |  |  | 2023 | 23000 | 2023 | 1550000 |  |  | 1573000
ONSLOW | SR 1308 (BELL FORK ROAD) | SR 1403 (COUNTRY CLUB ROAD/HARGETT STREET). IMPROVE INTERSECTION. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-6082 | DIVISION 3 | T | 2025 | 1300000 | 2025 | 900000 | 2027 | 4300000 |  |  | 6500000
ONSLOW | SR 1308 (GUM BRANCH ROAD) | WEST OF SR 1313 (MILLS FIELDS ROAD) TO EAST OF SR 1324 (RAMSEY ROAD) IN JACKSONVILLE. WIDENING. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-4906 | PRE-STI (TRANSITION) | BGANY |  |  |  |  | 2021 | 15945000 |  |  | 15945000 | RIGHT-OF-WAY IN PROGRESS
ONSLOW | SR 1308 (GUM BRANCH ROAD) | SR 1470 (WESTERN BOULEVARD) IN JACKSONVILLE. IMPROVE INTERSECTION. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5319 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
ONSLOW | SR 1308 (GUM BRANCH ROAD) | SR 1322 (SUMMERSILL SCHOOL ROAD) TO SR 1390 (COUNTRY CLUB BOULEVARD). UPGRADE TO SUPERSTREET. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5793
ONSLOW | SR 1308 (GUM BRANCH ROAD) | SR 1322 (SUMMERSILL SCHOOL ROAD) TO SR 1324 (RAMSEY ROAD). | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5793A | DIVISION 3 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9200000 |  |  | 17000000
ONSLOW | SR 1308 (GUM BRANCH ROAD) | SR 1324 (RAMSEY ROAD) TO SR 1390 (COUNTRY CLUB BOULEVARD). | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5793B | DIVISION 3 | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 12600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 27900000 |  |  | 44500000
ONSLOW | SR 1308 (GUM BRANCH ROAD) | WILLIAMSBURG PARKWAY TO INDIAN DRIVE. UPGRADE TO SUPERSTREET. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-6200 | NOT FUNDED | T | NOT FUNDED | 2127000 | NOT FUNDED | 1137000 | NOT FUNDED | 8800000 |  |  | 12064000
ONSLOW | SR 1336 (HENDERSON ROAD) | SR 1308 (GUM BRANCH ROAD) TO NC 53 (WESTERN BOULEVARD). UPGRADE TO SUPERSTREET. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5903 | DIVISION 3 | T | 2028 | 7400000 | 2028 | 4400000 | 2030 | 43600000 |  |  | 55400000
ONSLOW | SR 1509 (QUEENS CREEK ROAD) | REPLACE BRIDGE 660077 OVER QUEEN'S CREEK. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | B-5944 | DIVISION 3 | BFP | 2024 | 500000 |  |  | 2025 | 10099000 |  |  | 10599000
ONSLOW | SR 1509 (QUEENS CREEK ROAD) | JONES ROAD TO SR 1565 (SMALLWOOD ROAD). WIDEN ROADWAY. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | R-5948 | NOT FUNDED | T | NOT FUNDED | 4600000 | NOT FUNDED | 10300000 | NOT FUNDED | 12600000 |  |  | 27500000
ONSLOW | SR 1702 (WEST HUFF DRIVE) | SR 1308 (BELL FORK ROAD) TO EAST OF SR 1470 (WESTERN BOULEVARD). | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-4007A | [11 empty] | COMPLETE
ONSLOW | SR 2714 | NC 53 (WESTERN BOULEVARD) TO SR 1324 (RAMSEY ROAD). | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5791A | DIVISION 3 | T | 2024 | 6708000 | 2024 | 1964000 | 2026 | 43295000 |  |  | 51967000 | PLANNING/DESIGN IN PROGRESS. BUILD NC BOND FUNDING: $16,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE).
ONSLOW | SR 2714 | SR 1324 (RAMSEY ROAD) TO US 17 (NEW BERN HIGHWAY). | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5791B | NOT FUNDED | T | NOT FUNDED | 7900000 | NOT FUNDED | 2300000 | NOT FUNDED | 22600000 |  |  | 32800000
ONSLOW | SR 2714 (JACKSONVILLE PARKWAY EXTENSION) | NC 53 (WESTERN BOULEVARD) TO US 17 (NEW BERN HIGHWAY). WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5791 | DIVISION 3
ONSLOW | SR 2715 (TRADE STREET) | NC 53 (WESTERN BOULEVARD) TO MCDANIEL DRIVE IN JACKSONVILLE. CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5787 | DIVISION 3 | T | 2023 | 13600000 | 2023 | 2208000 | 2025 | 5200000 |  |  | 21008000
ONSLOW | US 17 | MULTI-LANE SECTION NORTH OF JACKSONVILLE TO SOUTH OF BELGRADE. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | R-2514A | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
ONSLOW | US 17 | US 17 BUSINESS TO SR 1326 (DRUMMER KELLUM ROAD) IN JACKSONVILLE. ADD ADDITIONAL LANES AND CONSTRUCT ROUTES ON NEW LOCATION. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-4007
ONSLOW | US 17 | WESTERN BOULEVARD TO FAIRWAY DRIVE. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-4007C | NOT FUNDED | NHP | NOT FUNDED | 34775000 |  |  | NOT FUNDED | 26300000 |  |  | 61075000
ONSLOW | US 17 | FAIRWAY DRIVE TO DRUMMER KELLUM ROAD. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-4007D | NOT FUNDED | NHP | NOT FUNDED | 32345000 |  |  | NOT FUNDED | 16600000 |  |  | 48945000
ONSLOW | US 17 | US 17 BUSINESS (MARINE BOULEVARD). UPGRADE AT-GRADE INTERSECTION TO PARTIAL INTERCHANGE. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5951 | REGION B | T | 2028 | 400000 | 2028 | 69000 | 2030 | 14200000 |  |  | 14669000
ONSLOW | US 17 | NC 172 (SNEADS FERRY ROAD/SR 1518 (OLD FOLKSTONE ROAD). INSTALL SUPER-STREET WITH INTERSECTION IMPROVEMENTS. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-6065 | STATEWIDE MOBILITY | HSIP, T | 2024 | 1000000 | 2024 | 1178000 | 2026 | 8701000 |  |  | 10879000
ONSLOW | US 17 | MCDANIEL DRIVE /WORKSHOP LANE. UPGRADE INTERSECTION. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-6107 | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3000000 |  |  | 4100000
ONSLOW | US 17 (WILMINGTON HIGHWAY) | SR 1130 (OLD MAPLEHURST ROAD) IN JACKSONVILLE. CONSTRUCT INTERCHANGE AND ASSOCIATED IMPROVEMENTS TO MCAS NEW RIVER MAIN GATE. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5735 | REGION B | T | 2027 | 28865000 | 2027 | 8328000 | 2029 | 51624000 |  |  | 88817000
ONSLOW | US 17 (WILMINGTON HIGHWAY) | ROADWAY IMPROVEMENTS TO DOUGLAS GATE ENTRANCE. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5735A | EXEMPT | O |  |  |  |  | 2021 | 1075000 |  |  | 1075000 | UNDER CONSTRUCION. OTHER FUNDS REPRESENT DEPARTMENT OF DEFENSE FUNDS.
ONSLOW | US 17 BUSINESS | US 17 BUSINESS (MARINE BOULEVARD) AND SR 1402 (OLD BRIDGE STREET). UPGRADE TRAFFIC SIGNAL, PAVEMENT MARKINGS, AND IMPROVE SIGHT DISTANCE. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | W-5803C | REGION B | HSIP |  |  |  |  | 2023 | 82000 |  |  | 82000
ONSLOW | US 17 BUSINESS (MARINE BOULEVARD) | SR 1308 (BELL FORK ROAD) IN JACKSONVILLE. IMPROVE INTERSECTION. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5728 | REGION B | T |  |  |  |  | 2025 | 4000000 |  |  | 4000000 | RIGHT-OF-WAY IN PROGRESS
ONSLOW | US 17 BUSINESS (MARINE BOULEVARD) | SR 1336 (HENDERSON DRIVE). IMPROVE INTERSECTION. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5950 | REGION B | T | 2025 | 75000 | 2025 | 154000 | 2027 | 825000 |  |  | 1054000
ONSLOW | US 258/NC 24 (RICHLANDS HIGHWAY) | SR 1219 (BLUE CREEK ROAD)/SR 1396 (RIDGE ROAD). REALIGN INTERSECTIONS TO FORM ONE AT-GRADE INTERSECTION. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5719 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
ONSLOW | US 258/NC 24 (RICHLANDS HIGHWAY) | SR 1212 (PONY FARM ROAD) TO SR 1213 (BLUE CREEK ROAD). CONSTRUCT SUPERSTREET. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5739 | REGION B | T | 2027 | 3500000 | 2027 | 2900000 | 2029 | 19800000 |  |  | 26200000 | PROJECT BEING LET WITH WITH U-5716.
ONSLOW | US 258/NC 24 (RICHLANDS HIGHWAY) | SR 1329 (RHODESTOWN FIRE DEPARTMENT ROAD). IMPROVE INTERSECTION. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-6148 | NOT FUNDED | NHP | NOT FUNDED | 329000 | NOT FUNDED | 140000 | NOT FUNDED | 750000 |  |  | 1219000
ONSLOW | VARIOUS | DIVISION 3 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | W-5203REG | REGION B
ONSLOW | JACKSONVILLE TRANSIT | EXPANSION BUS - FIXED ROUTE | PUBLIC TRANSIT | 3 | JACKSONVILLE URBAN AREA MPO | TA-4943 | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 1587000 | 1587000
ONSLOW | JACKSONVILLE TRANSIT | REPLACEMENT BUS - FIXED ROUTE | PUBLIC TRANSIT | 3 | JACKSONVILLE URBAN AREA MPO | TA-4944 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2516000 | 2516000
ONSLOW | JACKSONVILLE TRANSIT | FACILITY - TRANSIT CENTER - DOWNTOWN | PUBLIC TRANSIT | 3 | JACKSONVILLE URBAN AREA MPO | TD-4904 | DIVISION 3 | 5307, 5309, L, T |  |  |  |  | 2020 | 11055000 |  |  | 11055000
ONSLOW | JACKSONVILLE TRANSIT | NON-FIXED ROUTE ADA PARATRANSIT | PUBLIC TRANSIT | 3 | JACKSONVILLE URBAN AREA MPO | TG-4952 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 761000 | 761000
ONSLOW | JACKSONVILLE TRANSIT | PREVENTIVE MAINTENANCE - FIXED ROUTE | PUBLIC TRANSIT | 3 | JACKSONVILLE URBAN AREA MPO | TG-5109 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2076000 | 2076000
ONSLOW | JACKSONVILLE TRANSIT | JACKSONVILLE TRANSIT - MOBILITY MANAGEMENT | PUBLIC TRANSIT | 3 | JACKSONVILLE URBAN AREA MPO | TG-5220 | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 312000 | 312000
ONSLOW | JACKSONVILLE TRANSIT | ROUTINE CAPITAL-BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, SERVICE VEHICLES, ETC. | PUBLIC TRANSIT | 3 | JACKSONVILLE URBAN AREA MPO | TG-5225 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 149000 | 149000
ONSLOW | JACKSONVILLE TRANSIT | MOBILITY MANAGEMENT | PUBLIC TRANSIT | 3 | JACKSONVILLE URBAN AREA MPO | TG-5225C | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 653000 | 653000
ONSLOW | JACKSONVILLE TRANSIT | CONSTRUCT AN URBAN FIXED-ROUTE SATELLITE TRANSFER FACILITY FOR JACKSONVILLE TRANSIT TO INCLUDE PUBLIC PARKING, SHELTERS, RESTROOMS AND PESSENGER TERMINAL | PUBLIC TRANSIT | 3 | JACKSONVILLE URBAN AREA MPO | TL-0001 | PUBLIC TRANSIT | 5307 |  |  |  |  | 2020 | 1000000 |  |  | 1000000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
ONSLOW | JACKSONVILLE TRANSIT | CONSTRUCT PEDESTRIAN ACCESS AND SAFETY IMPROVEMENTS FOR JACKSONVILLE TRANSIT WITHIN 1/2 MILE OF HIGH VOLUME URBAN FIXED ROUTE BUS STOPS. IMPROVEMENTS WILL INCLUDE NEW SIDE WALK CONNECTIONS, ADA RETROFIT OF EXISTING SIDE WALKS AND CONSTRUCTION OF HIGH VISI | PUBLIC TRANSIT | 3 | JACKSONVILLE URBAN AREA MPO | TL-0002 | PUBLIC TRANSIT | 5307 |  |  |  |  | 2020 | 900000 |  |  | 900000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
ONSLOW | JACKSONVILLE TRANSIT | OPERATING ASSISTANCE | PUBLIC TRANSIT | 3 | JACKSONVILLE URBAN AREA MPO | TO-4923 | PUBLIC TRANSIT | 5307, L, SMAP | [6 empty] | 2020 | 7990000 | 7990000
ONSLOW | JACKSONVILLE TRANSIT | PLANNING ASSISTANCE - 5307 | PUBLIC TRANSIT | 3 | JACKSONVILLE URBAN AREA MPO | TP-4908 | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 745000 | 745000
ONSLOW | JACKSONVILLE TRANSIT | PLANNING ASSISTANCE - 5303 | PUBLIC TRANSIT | 3 | JACKSONVILLE URBAN AREA MPO | TP-5102 | PUBLIC TRANSIT | 5303, L, S | [6 empty] | 2020 | 335000 | 335000
ONSLOW | JACKSONVILLE TRANSIT | SAFETY & SECURITY - MIN. 1% SET ASIDE | PUBLIC TRANSIT | 3 | JACKSONVILLE URBAN AREA MPO | TS-5114 | PUBLIC TRANSIT | 5307 | [6 empty] | 2020 | 116000 | 116000 | FUNDS AUTHORIZED IN PROGRESS
ONSLOW | JACKSONVILLE TRANSIT | TECHNOLOGY - VEHICLE TRACKING, FARE COLLECTION, PASSENGER INFORMATION, DATA COMMUNICATIONS, TRAFFIC SIGNAL PRIORITY | PUBLIC TRANSIT | 3 | JACKSONVILLE URBAN AREA MPO | TT-4907 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 1140000 | 1140000
ONSLOW, BRUNSWICK, NEW HANOVER | VARIOUS | DIVISION 3 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO, GRAND STRAND AREA TRANSPORTATION STUDY, WILMINGTON URBAN AREA MPO | W-5203DIV | DIVISION 3
ONSLOW, JONES | US 17 | SOUTH OF BELGRADE TO NORTH OF MAYSVILLE. | HIGHWAY | 2, 3 | JACKSONVILLE URBAN AREA MPO, DOWN EAST RPO | R-2514B | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
ONSLOW, PENDER | US 17 | US 17 BETWEEN NEW HANOVER / PENDER COUNTY LINE AND MILE POST 19.3 IN ONSLOW COUNTY. INSTALL SHOULDER RUMBLE STRIPS. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO, WILMINGTON URBAN AREA MPO, CAPE FEAR RPO | W-5803B | REGION B | HSIP |  |  |  |  | 2023 | 425000 |  |  | 425000
ORANGE | BARNES STREET | KING STREET TO SR 1005 (JONES FERRY ROAD) IN CARRBORO. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5890 | DIVISION 7 | L, TAANY | 2024 | 16000 |  |  | 2025 | 230000 | 2023 | 46000 | 292000
ORANGE | MORGAN CREEK GREENWAY | WESTERN SECTION, SR 1919 (SMITH LEVEL ROAD) TO UNIVERSITY LAKE IN CARRBORO. CONSTRUCT GREENWAY AND CONNECTIONS. | BIKE/PED | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EL-4828 | PRE-STI (TRANSITION) | [10 empty] | PLANNING, DESIGN, RIGHT-OF-WAY AND CONSTRUCTION BY TOWN OF CARRBORO
ORANGE | MORGAN CREEK GREENWAY | PHASE 1 - ABBEY LANE TO SR 1919 (SMITH LEVEL ROAD) IN CARRBORO AND PIEDMONT EMC UTILITY EASEMENT TO SR 1919 (SMITH LEVEL ROAD) IN CARRBORO. CONSTRUCT GREENWAY AND CONNECTIONS. | BIKE/PED | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EL-4828A | PRE-STI (TRANSITION) | BGDA, L |  |  |  |  | 2023 | 372000 |  |  | 372000
ORANGE | MORGAN CREEK GREENWAY | PHASE 2 - WEST OF MORGAN CREEK TO PIEDMONT EMC UTILITY EASEMENT IN CARRBORO. CONSTRUCT GREENWAY AND CONNECTIONS. | BIKE/PED | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EL-4828B | PRE-STI (TRANSITION) | [10 empty] | PROJECT DELETED
ORANGE | NC 54 | WESTBROOK DRIVE IN CARRBORO TO WEST OF US 15 / US 501 / NC 86 (SOUTH COLUMBIA STREET) INTERCHANGE IN CHAPEL HILL. CONSTRUCT SIDEWALK AND INSTALL PEDESTRIAN SIGNALS, CROSSWALKS, AND REFUGE ISLANDS AT SELECTED LOCATIONS. | BIKE/PED | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | BL-0044 | DIVISION 7 | BGDA, L, S |  |  |  |  | 2023 | 1311000 | 2022 | 175000 | 1486000 | “S” FUNDING REFLECTS SPOT SAFETY ALLOCATION.
ORANGE | NC 54 | ANDERSON PARK TO JAMES STREET IN CARRBORO. CONSTRUCT MULTIUSE PATH ON NORTH SIDE OF NC 54. | BIKE/PED | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5994 | DIVISION 7 | L, TAANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 43000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1188000 | 2027 | 238000 | 1469000
ORANGE | ORANGE COUNTY BICYCLE ROUTE 1 | CLELAND DRIVE TO WILLOW DRIVE IN CHAPEL HILL. UPGRADE EXISTING OFF-ROAD PATH AND CONSTRUCT NEW SECTION OF PATH. | BIKE/PED | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5721 | DIVISION 7 | BGDA, L, TAANY |  |  |  |  | 2022 | 1282000 |  |  | 1282000
ORANGE | SR 1005 (JONES FERRY ROAD) | DAVIE ROAD TO SR 1010 (WEST MAIN STREET) IN CARRBORO. CONSTRUCT SIDEWALK ON NORTH SIDE. | BIKE/PED | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5880 | DIVISION 7 | L, TAANY | 2024 | 31000 |  |  | 2025 | 441000 | 2023 | 89000 | 561000
ORANGE | SR 1780 (ESTES DRIVE) | SR 1772 (NORTH GREENSBORO STREET) IN CARRBORO TO NC 86 (MARTIN LUTHER KING, JR. BOULEVARD) IN CHAPEL HILL. BICYCLE AND PEDESTRIAN IMPROVEMENTS. | BIKE/PED | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5886 | DIVISION 7
ORANGE | SR 1780 (ESTES DRIVE) | SR 1772 (NORTH GREENSBORO STREET) TO SOUTH OF NORFOLK-SOUTHERN RR TRACKS IN CARRBORO | BIKE/PED | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5886A | DIVISION 7 | L, TAANY | 2024 | 46000 |  |  | 2026 | 848000 | 2022 | 170000 | 1064000 | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CARRBORO. CONSTRUCTION ADMINISTRATION BY DIV. 7.
ORANGE | SR 1780 (ESTES DRIVE) | SOUTH OF NORFOLK-SOUTHERN RR TRACKS TO NC 86 (MARTIN LUTHER KING, JR. BLVD) IN CHAPEL HILL | BIKE/PED | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5886B | DIVISION 7 | L, TAANY | 2023 | 864000 |  |  | 2025 | 3104000 | 2022 | 534000 | 4502000 | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CHAPEL HILL. CONSTRUCTION ADMINISTRATION BY DIV. 7.
ORANGE | US 15 / US 501 | WILLOW DRIVE TO SR 1741 / SR 1838 (OLD DURHAM-CHAPEL HILL ROAD) IN CHAPEL HILL. CONSTRUCT MULTIUSE PATHS. | BIKE/PED | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5998 | DIVISION 7 | L, TAANY |  |  |  |  | 2026 | 2044000 | 2023 | 204000 | 2248000 | COORDINATE WITH U-5304
ORANGE | EXCHANGE PARK LANE | SOUTH CHURTON STREET TO FARIBAULT LANE IN HILLSBOROGH. REPAIR BRIDGE 670241 OVER ENO RIVER. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | HL-0045 | DIVISION 7 | BGDACV, L |  |  |  |  | 2023 | 153000 | 2021 | 20000 | 173000
ORANGE | I-40 | I-85 IN ORANGE COUNTY TO DURHAM COUNTY. WIDEN TO SIX LANES, IMPROVE NC 86 INTERCHANGE, AND INSTALL ITS. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-3306A | STATEWIDE MOBILITY | NHP, S(M) | 2021 | 10724000 | 2021 | 628000 | 2021 | 303565000 |  |  | 314917000 | UNDER CONSTRUCTION; DESIGN-BUILD PROJECT; $51 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035
ORANGE | I-40 | NC 86 UPGRADE TO SUPERSTREET FROM NORTHWOOD DRIVE TO RAMP C/D AT I-40 INTERCHANGE. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-3306AC | REGION D | NHP | 2024 | 550000 | 2024 | 450000 | 2026 | 4350000 |  |  | 5350000
ORANGE | I-40 / I-85 | WEST OF SR 1114 (BUCKHORN ROAD) TO WEST OF SR 1006 (ORANGE GROVE ROAD). PAVEMENT REHABILITATION. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO, BURLINGTON-GRAHAM MPO | I-5958 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2027 | 9500000 |  |  | 9500000
ORANGE | I-85 | SR 1009 (SOUTH CHURTON STREET) IN HILLSBOROUGH. INTERCHANGE IMPROVEMENTS. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-5967 | STATEWIDE MOBILITY | NHP | 2028 | 52800000 | 2028 | 1200000 | 2031 | 57200000 |  |  | 111200000
ORANGE | I-85 | NC 86 IN HILLSBOROUGH. UPGRADE INTERCHANGE. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-5984 | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 58200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 44100000 |  |  | 104400000 | COORDINATE WITH I-305
ORANGE | JONES CREEK GREENWAY | CONSTRUCT A 100 FOOT BRIDGE AND 650 FOOT PAVED TRAIL IN CARRBORO TO FILL GAP BETWEEN THE UPPER BOLIN TRAIL AND TWIN CREEKS GREENWAY AND IMPLEMENT PROGRAM TO SUPPORT NON-VEHICLE TRIPS TO MORRIS GROVE ELEMENTARY SCHOOL. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | C-5181 | EXEMPT | CMAQ, L |  |  |  |  | 2023 | 654000 | 2023 | 12000 | 666000
ORANGE | NC 54 | SR 1006 (ORANGE GROVE ROAD) TO SR 1107 / SR 1937 (OLD FAYETTEVILLE ROAD). CONSTRUCT OPERATIONAL IMPROVEMENTS, INCLUDING BICYCLE/PEDESTRIAN ACCOMMODATIONS, AND IMPROVE SR 1006 INTERSECTION. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO, TRIANGLE AREA RPO | R-5821
ORANGE | NC 54 | SR 1006 (ORANGE GROVE ROAD) TO SR 1107 / SR 1937 (OLD FAYETTEVILLE ROAD). CONSTRUCT OPERATIONAL IMPROVEMENTS, INCLUDING BICYCLE/PEDESTRIAN ACCOMMODATIONS | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | R-5821A | REGION D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7000000 |  |  | 17100000
ORANGE | NC 54 | SR 1006 (ORANGE GROVE ROAD). INTERSECTION IMPROVEMENTS. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | R-5821B | DIVISION 7 | [10 empty] | UNDER CONSTRUCTION
ORANGE | NC 54 | US 15 / US 501. UPGRADE INTERCHANGE. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5774A | NOT FUNDED | T | NOT FUNDED | 2800000 | NOT FUNDED | 140000 | NOT FUNDED | 16100000 |  |  | 19040000
ORANGE | NC 86 | REPLACE BRIDGE 670049 OVER NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN RAILROAD. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | B-6037 | REGION D | BFP | 2024 | 250000 |  |  | 2025 | 2500000 |  |  | 2750000
ORANGE | RIVERWALK TRAIL | RIVERWALK TRAIL, PHASE III IN HILLSBOROUGH. CONSTRUCT A PAVED OFF-ROAD TAIL ALONG ENO RIVER CONNECTING RIVER PARK, GOLD PARK AND THE OCCONEECHEE MOUNTAIN STATE NATURAL AREA, AND CONSTRUCT SIDEWALK TO PROVIDE PEDESTRIAN AND BICYCLE CONNECTIONS TO THE GREE | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | C-5184 | EXEMPT | [10 empty] | UNDER CONSTRUCTION BY TOWN OF HILLSBOROUGH
ORANGE | SR 1004 (EFLAND-CEDAR GROVE ROAD) | NORTH OF INTERSECTION WITH SR 1332 (HIGHLAND FARM ROAD). IMPROVE HORIZONTAL ALIGNMENT OF CURVE TO PROVIDE A MINIMUM OF 60 MPH DESIGN SPEED. | HIGHWAY | 7 | TRIANGLE AREA RPO | W-5143 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
ORANGE | SR 1005 (OLD GREENSBORO ROAD) | REPLACE BRIDGE 670085 OVER PHIL'S CREEK. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | B-5348 | HIGHWAY FUND | [10 empty] | UNDER CONSTRUCTION
ORANGE | SR 1008 (MT. CARMEL CHURCH ROAD) | SR 1913 (BENNETT ROAD) IN CHAPEL HILL. CONSTRUCT ROUNDABOUT AND RELATED SAFETY IMPROVEMENTS. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5854 | DIVISION 7 | [10 empty] | UNDER CONSTRUCTION
ORANGE | SR 1009 (SOUTH CHURTON STREET) | I-40 TO ENO RIVER IN HILLSBOROUGH. WIDEN TO MULTILANES. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5845 | DIVISION 7 | T | 2028 | 10200000 | 2028 | 1200000 | 2031 | 24000000 |  |  | 35400000
ORANGE | SR 1146 (WEST TEN ROAD) | SR 1114 (BUCKHORN ROAD) TO WEST OF SR 1137 (BUSHY COOK ROAD). CONSTRUCT OVERLAY, PAVED SHOULDERS AND TURN LANES. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-6245 | DIVISION 7 | T |  |  |  |  | 2021 | 829000 | 2020 | 109000 | 938000 | UNDER CONSTRUCTION; ECONOMIC DEVELOPMENT PROJECT
ORANGE | SR 1750 (NORTH ESTES DRIVE) | NC 86 (MARTIN LUTHER KING, JR. BOULEVARD) TO CASWELL DRIVE IN CHAPEL HILL. CONSTRUCT FIVE FOOT SIDEWALKS AND FIVE FOOT BIKE LANES. NC 86 (MARTIN LUTHER KING, JR. BOULEVARD) TO ELLIOTT ROAD IN CHAPEL HILL. CONSTRUCT TEN FOOT MULTIUSE PATH. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | C-5179 | EXEMPT | BGDA, BGDACV, CMAQ, L |  |  |  |  | 2020 | 5058000 |  |  | 5058000 | UNDER CONSTRUCTION BY TOWN OF CHAPEL HILL
ORANGE | SR 1772 (GREENSBORO STREET) | SR 1780 (ESTES DRIVE) IN CARRBORO. CONSTRUCT ROUNDABOUT. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5846 | DIVISION 7 | [10 empty] | UNDER CONSTRUCTION
ORANGE | SR 1919 (SMITH LEVEL ROAD / SOUTH GREENSBORO STRE | PUBLIC WORKS DRIVE TO NORTH END OF OLD PITTSBORO ROAD IN CARRBORO. CONSTRUCT SIDEWALK ON ONE SIDE. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | C-5650 | DIVISION 7 | BGANY, BGDACV, CMAQ, L | 2023 | 125000 |  |  | 2024 | 2624000 |  |  | 2749000
ORANGE | US 15 / US 501 | NC 86 (SOUTH COLUMBIA STREET). INTERCHANGE IMPROVEMENTS. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5304A | NOT FUNDED | T | NOT FUNDED | 10000000 | NOT FUNDED | 1040000 | NOT FUNDED | 22001000 |  |  | 33041000
ORANGE | US 15 / US 501 | NC 86 (SOUTH COLUMBIA STREET) TO NC 54 (RALEIGH ROAD). CAPACITY IMPROVEMENTS , WITH SIDEWALKS, WIDE OUTSIDE LANES AND TRANSIT ACCOMMODATIONS. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5304B | NOT FUNDED | T | NOT FUNDED | 6000000 | NOT FUNDED | 285000 | NOT FUNDED | 22001000 |  |  | 28286000
ORANGE | US 15 / US 501 | SR 1742 (EPHESUS CHURCH ROAD). INTERSECTION IMPROVEMENTS. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5304C | [11 empty] | WORK COMPLETED UNDER U-5550.
ORANGE | US 15 / US 501 | NC 54 (RALEIGH ROAD). TO SR 1742 (EPHESUS CHURCH ROAD). CAPACITY IMPROVEMENTS , WITH SIDEWALKS, WIDE OUTSIDE LANES AND TRANSIT ACCOMMODATIONS. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5304D | NOT FUNDED | T | NOT FUNDED | 5000000 | NOT FUNDED | 344000 | NOT FUNDED | 30001000 |  |  | 35345000
ORANGE | US 15 / US 501 | SR 1902 (MANNING DRIVE). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5304E | NOT FUNDED | T | NOT FUNDED | 12000000 | NOT FUNDED | 446000 | NOT FUNDED | 25000000 |  |  | 37446000
ORANGE | US 15 / US 501 (FORDHAM BOULEVARD) | SR 1742 (EPHESUS CHURCH ROAD) IN CHAPEL HILL. INTERSECTION IMPROVEMENTS. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5550 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION BY TOWN OF CHAPEL HILL
ORANGE | BURLINGTON -GRAHAM | 5307 OPERATING FUNDS NC-2019-060-01-P10 | PUBLIC TRANSIT | 7 | BURLINGTON-GRAHAM MPO | TO-5220 | PUBLIC TRANSIT | 5307 | [6 empty] | 2020 | 282000 | 282000 | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY 2020 GRANTS
ORANGE | CHAPEL HILL TRANSIT | REPLACEMENT BUSES | PUBLIC TRANSIT | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TA-4726 | PUBLIC TRANSIT | 5307, 5339, L, S | [6 empty] | 2020 | 9692000 | 9692000 | FUNDS AUTHORIZED IN PROGRESS
ORANGE | CHAPEL HILL TRANSIT | 3 REPLACEMENT BUSES. | PUBLIC TRANSIT | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TA-4726A | DIVISION 7 | [10 empty] | IN PROGRESS BY CHAPEL HILL TRANSIT
ORANGE | CHAPEL HILL TRANSIT | REPLACEMENT - PARATRANSIT VEHICLE | PUBLIC TRANSIT | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TA-4748 | PUBLIC TRANSIT | 5307 | [6 empty] | 2020 | 788000 | 788000 | FUNDS AUTHORIZED IN PROGRESS
ORANGE | CHAPEL HILL TRANSIT | REPLACEMENT VAN | PUBLIC TRANSIT | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TA-4979 | PUBLIC TRANSIT | 5307 | [6 empty] | 2023 | 792000 | 792000 | FUNDS AUTHORIZED IN PROGRESS
ORANGE | CHAPEL HILL TRANSIT | PREVENTIVE MAINTENANCE | PUBLIC TRANSIT | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TG-4731B | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 5372000 | 5372000 | FUNDS AUTHORIZED IN PROGRESS
ORANGE | CHAPEL HILL TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC | PUBLIC TRANSIT | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TG-4732A | PUBLIC TRANSIT | 5307, S | [6 empty] | 2020 | 1080000 | 1080000 | FUNDS AUTHORIZED IN PROGRESS
ORANGE | CHAPEL HILL TRANSIT | ROUTINE CAPITAL - SERVICE VEHICLE | PUBLIC TRANSIT | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TG-4732B | PUBLIC TRANSIT | 5307, L | [6 empty] | 2023 | 196000 | 196000 | FUNDS AUTHORIZED IN PROGRESS
ORANGE | CHAPEL HILL TRANSIT | OPERATING ASSISTANCE | PUBLIC TRANSIT | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TO-5133 | PUBLIC TRANSIT | SMAP | [6 empty] | 2020 | 14280000 | 14280000 | FUNDS AUTHORIZED IN PROGRESS
ORANGE | CHAPEL HILL TRANSIT | ALTERNATIVE ANALYSIS - ENVIRONMENTAL ASSESSMENT, DESIGN, AND ENGINEERING | PUBLIC TRANSIT | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5119A | PUBLIC TRANSIT | FED, L | [6 empty] | 2020 | 200000 | 200000 | FUNDS AUTHORIZED IN PROGRESS
ORANGE | DURHAM | 5307 OPERATING FUNDS NC 2019-060-01-P11 | PUBLIC TRANSIT | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TO-5206 | PUBLIC TRANSIT | 5307 | [6 empty] | 2020 | 311000 | 311000 | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
ORANGE | GO TRIANGLE | UNC HOSPITALS AREA IN CHAPEL HILL. CONSTRUCT NEIGHBORHOOD TRANSIT CENTER TRANSFER STATION. 400; 405; 420; 800; 805; CRX; FCX | PUBLIC TRANSIT | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TD-5284 | REGION D | 5307, L, T |  |  |  |  | 2024 | 360000 |  |  | 360000
ORANGE | GO TRIANGLE | TOWN OF HILLSBOROUGH. CONSTRUCT PARK-AND-RIDE LOT. | PUBLIC TRANSIT | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TD-5295 | REGION D | [10 empty] | UNDER CONSTRUCTION BY GO TRIANGLE
ORANGE | GOTRIANGLE | GO TRIANGLE ACCESS IMPROVEMENTS AT THE INTERSEACTION OF US 15 -501 AND EASTOWNEDRIVE | PUBLIC TRANSIT | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TL-0018 | PUBLIC TRANSIT | CMAQ, L |  |  |  |  | 2022 | 500000 |  |  | 500000
ORANGE | ORANGE PUBLIC TRANSIT | PURCHASE TWO (2) LIGHT TRANSIT VEHICLES | PUBLIC TRANSIT | 7 | TRIANGLE AREA RPO, DURHAM-CHAPEL HILL-CARRBORO MPO | TA-6721 | DIVISION 7 | L, T | [6 empty] | 2022 | 109000 | 109000
ORANGE | ORANGE PUBLIC TRANSIT | PURCHASE NEW BUS < 30'. | PUBLIC TRANSIT | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TA-6731 | PUBLIC TRANSIT | FED, L | [6 empty] | 2020 | 56000 | 56000
ORANGE | ORANGE PUBLIC TRANSIT | 1 REPLACEMENT LTV (25') AND RADIO, VEHICLE LETTERING AND LOGOS, AND ON-BOARD CAMERA. | PUBLIC TRANSIT | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TD-5155 | DIVISION 7 | BGDA, L | [6 empty] | 2022 | 77000 | 77000 | IN PROGRESS BY ORANGE PUBLIC TRANSIT
ORANGE | ORANGE PUBLIC TRANSIT | ADMINISTRATION | PUBLIC TRANSIT | 7 | TRIANGLE AREA RPO | TK-6151 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 744000 | 744000
ORANGE | NORFOLK SOUTHERN H LINE | MILEPOST 41.7 IN HILLSBOROUGH. CONSTRUCT PLATFORM, PASSENGER RAIL STATION BUILDING, SITE ACCESS, UTILITIES AND PARKING. | RAIL | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | P-5701 | DIVISION 7 | [10 empty] | UNDER CONSTRUCTION. "OTHER" FUNDING REFLECTS PARTICIPATION BY TRIANGLE TRANSIT
ORANGE | NORFOLK SOUTHERN H LINE | NORFOLK SOUTHERN H LINE, MILEPOST 41.7 IN HILLSBOROUGH. CONSTRUCT PASSENGER RAIL STATION BUILDING, SITE ACCESS, UTILITIES AND PARKING. | RAIL | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | P-5701A | DIVISION 7 | O, T |  |  |  |  | 2022 | 6860000 |  |  | 6860000
ORANGE | NORFOLK SOUTHERN H LINE | NORFOLK SOUTHERN H LINE, MILEPOST 41.7 IN HILLSBOROUGH. CONSTRUCT STATION PLATFORM AND REALIGN CURVE AT MILEPOST 41.4. | RAIL | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | P-5701B | DIVISION 7 | T |  |  |  |  | 2023 | 1000000 |  |  | 1000000
ORANGE | SR 1120 (MOUNT WILLING ROAD) | NORFOLK SOUTHERN RAILROAD CROSSING 735145T NEAR EFLAND. INSTALL ACTIVE WARNING DEVICES. | RAIL | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | RX-2007B | DIVISION 7 | RR |  |  |  |  | 2023 | 800000 |  |  | 800000
ORANGE, DURHAM | I-40 | I-85 IN ORANGE COUNTY TO NC 147 (DURHAM FREEWAY / TRIANGLE EXPRESSWAY) IN DURHAM COUNTY. WIDEN TO SIX LANES AND INSTALL ITS. | HIGHWAY | 5, 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-3306
ORANGE, DURHAM | I-85 | WEST OF SR 1006 (ORANGE GROVE ROAD) IN ORANGE COUNTY TO WEST OF SR 1400 (SPARGER ROAD) IN DURHAM COUNTY. ADD LANES. | HIGHWAY | 5, 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-0305 | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 17900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 120898000 |  |  | 139998000 | COORDINATE WITH I-5967, I-5984 AND U-5845
ORANGE, DURHAM | NC 54 | WEST OF US 15 / US 501 IN ORANGE COUNTY TO EAST OF SR 1110 (BARBEE CHAPEL ROAD) IN DURHAM COUNTY. UPGRADE ROADWAY CORRIDOR. | HIGHWAY | 5, 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5774B | REGION C, D | T | 2027 | 43000000 | 2027 | 74000 | 2030 | 23300000 |  |  | 66374000
ORANGE, DURHAM | SR 1838 / SR 2220 | US 15 / US 501 IN ORANGE COUNTY TO SR 1113 (POPE ROAD) IN DURHAM COUNTY | HIGHWAY | 5, 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-4707A | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
ORANGE, DURHAM | US 15 / US 501 | SR 1742 (EPHESUS CHURCH ROAD) TO I-40. CORRIDOR CAPACITY IMPROVEMENTS. | HIGHWAY | 5, 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5304F | NOT FUNDED | T | NOT FUNDED | 6000000 | NOT FUNDED | 726000 | NOT FUNDED | 26999000 |  |  | 33725000
ORANGE, DURHAM | US 15 / US 501 (FORDHAM BOULEVARD) | NC 86 (SOUTH COLUMBIA STREET) TO I-40 IN CHAPEL HILL. UPGRADE CORRIDOR. | HIGHWAY | 5, 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5304 | [11 empty] | COORDINATE WITH EB-5998 AND U-5774
ORANGE, DURHAM | VARIOUS | VARIABLE MESSAGE SIGNS FOR TRAFFIC MANAGEMENT ON MAJOR CORRIDORS IN CHAPEL HILL. | HIGHWAY | 5, 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5543 | EXEMPT | [10 empty] | UNDER CONSTRUCTION BY TOWN OF CHAPEL HILL
PAMLICO | NC 55 | BRIDGE 38 OVER THE TRENT CREEK ON NC 55. | HIGHWAY | 2 | DOWN EAST RPO | B-4593 | REGION B | NHPB |  |  |  |  | 2022 | 4200000 |  |  | 4200000
PAMLICO | SR 1302 (JANIERO ROAD) | REPLACE BRIDGE 680057 OVER DAWSON CREEK. | HIGHWAY | 2 | DOWN EAST RPO | B-5995 | DIVISION 2 | BGOFF | 2022 | 600000 |  |  | 2023 | 3850000 |  |  | 4450000 | RIGHT-OF-WAY IN PROGRESS.
PAMLICO, CARTERET, CRAVEN | US 70, NC 55 | US 70 BETWEEN NUNN STREET AND SR 1605 (FRIENDLY ROAD) IN MOREHEAD CITY, AND NC 55 BETWEEN US 17 IN BRIDGETON AND SR 1210 (1ST STREET) IN BAYBORO. INSTALL 6 INCH LONG LIFE PAVEMENT MARKINGS. | HIGHWAY | 2 | DOWN EAST RPO | W-5802E | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2021 | 865000 |  |  | 865000 | UNDER CONSTRUCTION.
PASQUOTANK | ELIZABETH CITY | ELIZABETH CITY SIGNAL SYSTEM. | HIGHWAY | 1 | ALBEMARLE RPO | U-5942 | REGION A | BG5200, HP |  |  |  |  | 2021 | 5059000 |  |  | 5059000 | UNDER CONSTRUCTION. HP FUNDS REPRESENT REPURPOSED EARMARK NC 088 IN THE AMOUNT OF $62,368
PASQUOTANK | PROVIDENCE ROAD | REPLACE BRIDGE 690034 OVER KNOBBS CREEK TRIBUTARY IN ELIZABETH CITY. | HIGHWAY | 1 | ALBEMARLE RPO | B-6053 | DIVISION 1 | BGOFF, L |  |  | 2021 | 135000 | 2022 | 1725000 |  |  | 1860000 | UNDER CONSTRUCTION. MUNICIPAL BRIDGE.
PASQUOTANK | US 17 (FUTURE I-87) | PERQUIMANS COUNTY LINE TO NORTH END OF US 17 (ELIZABETH CITY) BYPASS. PAVEMENT REHABILITATION. | HIGHWAY | 1 | ALBEMARLE RPO | I-6029 | STATEWIDE MOBILITY | NHP, NHPIM, S(M) |  |  |  |  | 2020 | 11886000 |  |  | 11886000 | UNDER CONSTRUCTION. GARVEE BOND FUNDING $3,203,797 FOR CONSTRUCTION, PAYBACK FY 2020 - 2034.
PASQUOTANK | US 17 (HUGHES BOULEVARD) | SR 1308 (CHURCH STREET) TO US 17 BUSINESS (NORTH ROAD STREET). ACCESS MANAGEMENT. | HIGHWAY | 1 | ALBEMARLE RPO | U-5940 | REGION A | T | 2025 | 15988000 | 2025 | 476000 | 2027 | 12899000 |  |  | 29363000
PASQUOTANK | US 17 BUSINESS | SR 1145 (OAK STUMP ROAD). IMPROVE INTERSECTION. | HIGHWAY | 1 | ALBEMARLE RPO | U-5939 | REGION A | T | 2024 | 2807000 | 2024 | 299000 | 2025 | 7000000 |  |  | 10106000
PASQUOTANK, CAMDEN | US 158 | US 17 BUSINESS (NORTH ROAD STREET) TO EAST OF PASQUOTANK RIVER IN ELIZABETH CITY. RECONSTRUCT ROADWAY AND REPLACE BRIDGE 690019. | HIGHWAY | 1 | ALBEMARLE RPO | U-4438 | [11 empty] | UNDER CONSTRUCTION
PENDER | HENDERSON FIELD (ACZ) | EXTEND RUNWAY TO 5500 FEET. | AVIATION | 3 | CAPE FEAR RPO | AV-5744 | DIVISION 3 | T | 2022 | 1978000 |  |  | 2023 | 13105000 |  |  | 15083000 | RIGHT-OF-WAY IN PROGRESS.
PENDER | HENDERSON FIELD (ACZ) | APRON EXPANSION. | AVIATION | 3 | CAPE FEAR RPO | AV-5815 | DIVISION 3 | T |  |  |  |  | 2024 | 5239000 |  |  | 5239000
PENDER | DAN OWEN DRIVE EXTENSION | SR 1570 (FACTORY ROAD) TO DAN OWEN DRIVE. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5732A | REGION B | [10 empty] | COMPLETE
PENDER | I-40 | WEST OF US 117 (MILE MARKER 388) TO NC 210 (MILE MARKER 408). PAVEMENT REHABILITATION. | HIGHWAY | 3 | CAPE FEAR RPO | I-6040 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2022 | 19768000 |  |  | 19768000
PENDER | NC 210 | SR 1560 (WATTS LANDING ROAD). CONSTRUCT ROUNDABOUT. | HIGHWAY | 3 | CAPE FEAR RPO | R-5899 | NOT FUNDED | T | NOT FUNDED | 1044000 | NOT FUNDED | 117000 | NOT FUNDED | 2600000 |  |  | 3761000
PENDER | NC 50/NC 210 | SR 1534 (BELT ROAD). CONSTRUCT ROUNDABOUT. | HIGHWAY | 3 | CAPE FEAR RPO | R-5900 | NOT FUNDED | T | NOT FUNDED | 5000000 | NOT FUNDED | 800000 | NOT FUNDED | 1300000 |  |  | 7100000
PENDER | NC 53 | US 117 BUSINESS (WALKER STREET/WILMINGTON STREET). IMPROVE INTERSECTION. | HIGHWAY | 3 | CAPE FEAR RPO | R-5701 | REGION B | L, T | 2025 | 55000 | 2025 | 172000 | 2027 | 1450000 |  |  | 1677000
PENDER | NC 53 | US 117 BYPASS TO STAG PARK ROAD. WIDEN TO THREE LANES. | HIGHWAY | 3 | CAPE FEAR RPO | R-5850 | DIVISION 3 | T | 2023 | 5900000 | 2023 | 1908000 | 2025 | 6300000 |  |  | 14108000
PENDER | US 17 | US 17 AND NC 210 WEST OF SNEADS FERRY. REVISE TRAFFIC SIGNAL AND INSTALL BE PREPARED TO STOP SIGNS. | HIGHWAY | 3 | CAPE FEAR RPO | HS-2003F | REGION B | HSIP |  |  |  |  | 2026 | 194000 |  |  | 194000
PENDER | US 17 | NC 210 TO US 17 NORTH OF HAMPSTEAD. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | R-3300B | REGION B | T |  |  |  |  | 2022 | 229554000 |  |  | 229554000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $55.8M FOR CON PAYBACK 2022 – 2036 (FY 2022 / YR 4 SALE).
PENDER | US 17 | NC 210 (SURF CITY). INTERSECTION IMPROVEMENT AT US 17 AND NC 210 NEAR SURF CITY. | HIGHWAY | 3 | CAPE FEAR RPO | R-5877 | NOT FUNDED | NHP | NOT FUNDED | 6000000 | NOT FUNDED | 2100000 | NOT FUNDED | 11900000 |  |  | 20000000
PENDER | US 17 | US 17 FROM SR 1582 (WASHINGTON ACRES ROAD) TO VISTA LANE. CONVERT TO SUPERSTREET. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5732 | REGION B | T |  |  |  |  | 2026 | 35900000 |  |  | 35900000 | RIGHT OF WAY IN PROGRESS
PENDER | PENDER ADULT SERVICES, INC. | ADMINISTRATION | PUBLIC TRANSIT | 3 | CAPE FEAR RPO | TK-6152 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 480000 | 480000 | FUNDS AUTHORIZED IN PROGRESS
PENDER, NEW HANOVER | US 17 | US 17 BYPASS SOUTH OF HAMPSTEAD TO NC 210. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | R-3300A | REGION B | T |  |  |  |  | 2027 | 146860000 |  |  | 146860000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $11,000,000 FOR CONSTRUCTION PAYBACK 2027 - 2040 (FY 2026 / YR 8 SALE).
PERQUIMANS | SR 1300 (NEW HOPE ROAD) | SR 1302 (UNION HALL ROAD) TO SR 1303 (WOODLAND CHURCH ROAD). WIDEN AND RESURFACE. | HIGHWAY | 1 | ALBEMARLE RPO | R-5716 | DIVISION 1 | [10 empty] | UNDER CONSTRUCTION
PERQUIMANS | SR 1300 (NEW HOPE ROAD) | WOODLAND CHURCH ROAD TO WOODVILLE ROAD (SR 1329). MODERNIZE ROADWAY. | HIGHWAY | 1 | ALBEMARLE RPO | R-5939 | DIVISION 1 | T | 2028 | 5400000 | 2028 | 1400000 | 2030 | 14100000 |  |  | 20900000
PERQUIMANS | SR 1329 (WOODVILLE ROAD) | SR 1331 (RED BANK ROAD) TO SR 1300 (NEW HOPE ROAD). UPGRADE ROADWAY. | HIGHWAY | 1 | ALBEMARLE RPO | R-5740 | DIVISION 1 | T | 2019 | 765000 |  |  | 2021 | 5841000 | 2020 | 1035000 | 7641000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $599,445.15 FOR ROW PAYBACK 2019 - 2033, $801,972 FOR PE PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE)
PERQUIMANS | SR 1336 (HARVEY POINT ROAD) | US 17 TO SR 1350 (CHURCHES LANE). MODERNIZE ROADWAY. | HIGHWAY | 1 | ALBEMARLE RPO | R-5806 | DIVISION 1 | BGLT5 |  |  |  |  | 2022 | 3900000 |  |  | 3900000 | UNDER CONSTRUCTION.
PERQUIMANS | SR 1338 (WYNNE FORK ROAD) | REPLACE BRIDGE 710011 OVER RACOON CREEK. | HIGHWAY | 1 | ALBEMARLE RPO | B-5606 | DIVISION 1 | T |  |  |  |  | 2021 | 1545000 |  |  | 1545000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $1,200,000 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YRS 2&3 SALE).
PERQUIMANS | US 17 | SOUTH OF US 17 BUSINESS (EDENTON ROAD) TO NORTH OF SR 1220 (WIGGINS ROAD). UPGRADE ROADWAY AND CONVERT INTERSECTIONS TO INTERCHANGES. | HIGHWAY | 1 | ALBEMARLE RPO | R-5869
PERQUIMANS | US 17 | SR 1336 (HARVEY POINT ROAD) AND SR 1338 (WAYNE FORK ROAD). CONVERT AT-GRADE INTERSECTION TO AN INTERCHANGE. | HIGHWAY | 1 | ALBEMARLE RPO | R-5869A | DIVISION 1 | NHP | 2028 | 6000000 | 2028 | 900000 | 2030 | 30000000 |  |  | 36900000 | FORMERLY IDENTIFIED AS R-4459
PERQUIMANS | US 17 | SR 1300 (NEW HOPE ROAD). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 1 | ALBEMARLE RPO | R-5869B | DIVISION 1 | NHP | 2028 | 3400000 | 2028 | 500000 | 2030 | 19800000 |  |  | 23700000 | FORMERLY IDENTIFIED AS R-4458
PERQUIMANS | US 17 | SOUTH OF US 17 BUSINESS (EDENTON ROAD) TO NORTH OF SR 1220 (WIGGINS ROAD). UPGRADE ROADWAY. | HIGHWAY | 1 | ALBEMARLE RPO | R-5869C | NOT FUNDED | NHP | NOT FUNDED | 3500000 | NOT FUNDED | 1000000 | NOT FUNDED | 135000000 |  |  | 139500000 | PROGRAMMED FOR PLANNING & ENVIRONMENTAL STUDY ONLY.
PERQUIMANS | US 17 (FUTURE I-87) | SR 1101 (EAST BEAR SWAMP ROAD) TO US 17 BUSINESS NORTH OF HERTFORD. PAVEMENT REHABILITATION. | HIGHWAY | 1 | ALBEMARLE RPO | I-6030 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2025 | 5000000 |  |  | 5000000
PERQUIMANS | US 17 BUSINESS/ NC 37 | FROM SOUTH OF PERQUIMANS RIVER BRIDGE TO NORTH OF NC 37. REPLACE BRIDGE 710008. | HIGHWAY | 1 | ALBEMARLE RPO | R-4467 | REGION A | T |  |  |  |  | 2019 | 65512000 | 2021 | 2415000 | 67927000 | UNDER CONSTRUCTION. DESIGN BUILD PROJECT. BUILD NC BOND FUNDING: $2,778,143 FOR CON PAYBACK 2019 - 2033 (FY 2019 / YR 1 SALE); $1,880,164 FOR PE, $38,098,100 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE)
PERSON | PERSON COUNTY EXECUTIVE AIRPORT (TDF) | EXTEND RUNWAY TO TOTAL LENGTH OF 7000 FT, CONSTRUCT TAXIWAY EXTENSION AND RELOCATE SR 1311 (CATES MILL ROAD). | AVIATION | 5 | KERR-TAR RPO | AV-5818 | DIVISION 5 | T |  |  |  |  | 2028 | 15160000 |  |  | 15160000
PERSON | NC 157 (HURDLE MILLS ROAD); SOUTHERN MIDDLE SCHOOL | SOUTHERN MIDDLE SCHOOL ROAD FROM NC 157 (HURDLE MILLS ROAD) TO DELTA DRIVE, AND NC 157 (HURDLE MILLS ROAD) FROM SANDSTONE WAY TO CLEVELAND LANE IN ROXBORO. CONSTRUCT SIDEWALK. NC 157 AT SOUTHERN MIDDLE SCHOOL ROAD INTERSECTION. INTERSECTION MPROVEMENTS | HIGHWAY | 5 | KERR-TAR RPO | BL-0061 | EXEMPT | CMAQ, L | 2024 | 65000 |  |  | 2024 | 450000 | 2023 | 130000 | 645000
PERSON | US 501 | SOUTH OF US 158 TO SR 1601 (NORTH MAIN STREET) IN ROXBORO. CONVERT TO 4-LANE MEDIAN DIVIDED FACILITY, IMPROVE VARIOUS INTERSECTIONS WITH SOME CONSOLIDATION OF INTERSECTIONS, AND FILL IN SIDEWALK GAPS. | HIGHWAY | 5 | KERR-TAR RPO | U-5969
PERSON | US 501 | SOUTH OF US 158 TO NC 157. | HIGHWAY | 5 | KERR-TAR RPO | U-5969A | DIVISION 5 | T | 2027 | 7200000 | 2027 | 1288000 | 2029 | 4400000 |  |  | 12888000
PERSON | US 501 | NC 157 TO SR 1596 (WEST MOREHEAD STREET) | HIGHWAY | 5 | KERR-TAR RPO | U-5969B | REGION C | T | 2023 | 6700000 | 2023 | 917000 | 2025 | 9200000 |  |  | 16817000
PERSON | US 501 / NC 49 | SR 1596 (WEST MOREHEAD STREET) TO SR 1601 (NORTH MAIN STREET) | HIGHWAY | 5 | KERR-TAR RPO | U-5969C | REGION C | T | 2023 | 6300000 | 2023 | 1346000 | 2025 | 6600000 |  |  | 14246000
PERSON | PERSON COUNTY | ADMINISTRATION | PUBLIC TRANSIT | 5 | KERR-TAR RPO | TK-6153 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 664000 | 664000 | FUNDS AUTHORIZED IN PROGRESS
PITT | GREENVILLE | SOUTH TAR RIVER GREENWAY. PHASE 3: PITT STREET TO NASH STREET. CONSTRUCT GREENWAY USING EXISTING SIDEWALKS, ROADS AND ON NEW LOCATION ALONG THE RIVER. | BIKE/PED | 2 | GREENVILLE URBAN AREA MPO | EB-5539 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
PITT | GREENVILLE | CONSTRUCT MULTI-USE PATH AT VARIOUS LOCATIONS INCLUDING ALONG THE TAR RIVER, MOYE BOULEVARD, THE NORFOLK SOUTHERN RAIL CORRIDOR, AND TOWN CREEK IN GREENVILLE. | BIKE/PED | 2 | GREENVILLE URBAN AREA MPO | EB-6042 | DIVISION 2 | DP, L |  |  |  |  | 2022 | 7069000 |  |  | 7069000 | 'DP' FUNDS REPRESENT BUILD GRANT FUNDS.
PITT | GREENVILLE | TOWN COMMON CONNECTOR. CONSTRUCT A MULTI-USE PATH FROM TOWN COMMON TO EAST 5TH STREET. | BIKE/PED | 2 | GREENVILLE URBAN AREA MPO | EB-6043 | DIVISION 2 | DP, L | 2021 | 8000 |  |  | 2022 | 1696000 | 2020 | 557000 | 2261000 | 'DP' FUNDS REPRESENT BUILD GRANT FUNDS.
PITT | GREENVILLE | MILLENNIAL CONNECTOR PATH. CONSTRUCT A 0.3 MILE MULTI-USE PATH FROM DICKINSON AVENUE TO 10TH STREET AND A 0.1 MILE MULTI-USE PATH FROM DICKINSON AVENUE TO FICKLEN STREET. | BIKE/PED | 2 | GREENVILLE URBAN AREA MPO | EB-6044 | DIVISION 2 | DP, L | 2021 | 500000 |  |  | 2022 | 280000 | 2020 | 526000 | 1306000 | 'DP' FUNDS REPRESENT BUILD GRANT FUNDS.
PITT | GREENVILLE | MOYE BOULEVARD SIDEWALK EXTENSION. CONSTRUCT A MULTI-USE PATH TO REPLACE THE EXISTING SIDEWALK ALONG MOYE BOULEVARD IN GREENVILLE. | BIKE/PED | 2 | GREENVILLE URBAN AREA MPO | EB-6045 | DIVISION 2 | DP, L | 2021 | 256000 |  |  | 2022 | 371000 | 2020 | 476000 | 1103000 | 'DP' FUNDS REPRESENT BUILD GRANT FUNDS.
PITT | NC 11 (MEMORIAL DRIVE) | NC 43 (WEST FIFTH STREET) TO SR 1128 (DAVENPORT FARM ROAD) IN GREENVILLE. CONSTRUCT SIDEWALK. | BIKE/PED | 2 | GREENVILLE URBAN AREA MPO | EB-5981 | NOT FUNDED | L, TA5200 | NOT FUNDED | 40000 |  |  | NOT FUNDED | 2044000 | NOT FUNDED | 83000 | 2167000
PITT | US 264-A (GREENVILLE BOULEVARD) | US 264-A TO US 13 (DICKINSON AVENUE) IN GREENVILLE. CONSTRUCT SIDEWALK AND CURB AND GUTTER. | BIKE/PED | 2 | GREENVILLE URBAN AREA MPO | EB-5980 | NOT FUNDED | L, TA5200 | NOT FUNDED | 50000 |  |  | NOT FUNDED | 787000 | NOT FUNDED | 34000 | 871000
PITT | GREENVILLE | GREENVILLE SIGNAL SYSTEM. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-5952 | REGION B | BG5200 |  |  | 2026 | 750000 | 2028 | 12000000 |  |  | 12750000
PITT | NC 11/NC 903 (GREENVILLE SOUTHWEST BYPASS) | NC 11 TO US 264 (GREENVILLE BYPASS). CONSTRUCT FOUR LANE DIVIDED FACILITY ON NEW LOCATION WITH BYPASS OF WINTERVILLE. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | R-2250 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
PITT | NC 222 | REPLACE BRIDGE 730024 OVER TAR RIVER. | HIGHWAY | 2 | MID-EAST RPO | B-5612 | REGION B | T | 2019 | 950000 |  |  | 2025 | 10599000 |  |  | 11549000 | RIGHT-OF-WAY IN PROGRESS
PITT | NC 33 | REPLACE BRIDGE 730050 OVER JOHNSON MILL RUN. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | B-5418 | REGION B | [10 empty] | BRIDGE PURCHASE ORDER CONTRACT (DPOC): UNDER CONSTRUCTION
PITT | NC 33 | NC 33 FROM US 13/NC 11 (MEMORIAL DRIVE) TO DAUGHTRIDGE DRIVE IN GREENVILLE. INSTALL MEDIAN ISLAND AND REVISE PAVEMENT MARKINGS. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | HS-2002J | DIVISION 2 | HSIP |  |  |  |  | 2023 | 120000 |  |  | 120000
PITT | NC 33 | SR 1755 (BLACKJACK-SIMPSON ROAD) TO SR 1760 (MOBLEYS BRIDGE ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO, MID-EAST RPO | U-6215 | NOT FUNDED | T | NOT FUNDED | 30100000 | NOT FUNDED | 2900000 | NOT FUNDED | 70099000 |  |  | 103099000
PITT | NC 33 (10TH STREET) | OXFORD ROAD TO SR 1702 (EVANS STREET). ACCESS MANAGEMENT. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-6125 | NOT FUNDED | T | NOT FUNDED | 6800000 | NOT FUNDED | 3500000 | NOT FUNDED | 14199000 |  |  | 24499000
PITT | NC 43 | SR 1708 (FIRETOWER ROAD) TO SR 1711 (WORTHINGTON ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-5991 | DIVISION 2 | T | 2027 | 14000000 | 2027 | 7500000 | 2029 | 30200000 |  |  | 51700000
PITT | NC 43 (CHARLES BOULEVARD) | US 264A (GREENVILLE BOULEVARD) TO SR 1726 (BELLS FORK ROAD). ACCESS MANAGEMENT. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-6147 | NOT FUNDED | T | NOT FUNDED | 5900000 | NOT FUNDED | 800000 | NOT FUNDED | 12001000 |  |  | 18701000
PITT | OXFORD ROAD | REPLACE BRIDGE 730419 OVER MEETING HOUSE BRANCH IN GREENVILLE. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | HB-0021 | DIVISION 2 | BGOFF | 2023 | 50000 | 2024 | 143000 | 2024 | 1668000 | 2023 | 363000 | 2224000
PITT | ROCK SPRINGS ROAD | REPLACE BRIDGE 730096 OVER GREENS MILL RUN IN GREENVILLE. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | HB-0022 | DIVISION 2 | BGOFF | 2024 | 100000 | 2025 | 126000 | 2025 | 2277000 | 2024 | 495000 | 2998000
PITT | SR 1126 (BOYD STREET) | NC 11 TO RAILROAD STREET. UPGRADE ROADWAY. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-5919 | DIVISION 2 | [10 empty] | UNDER CONSTRUCTION
PITT | SR 1203 (ALLEN ROAD) | SR 1467 (STANTONSBURG ROAD) TO US 13 (DICKINSON AVENUE EXTENSION). WIDEN TO MULTI-LANES. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-5875 | DIVISION 2 | T |  |  |  |  | 2024 | 27800000 |  |  | 27800000 | RIGHT-OF-WAY IN PROGRESS.
PITT | SR 1418 (STATON HOUSE ROAD) | REPLACE BRIDGE 730171 OVER JOHNSON MILL RUN CREEK. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | BR-0238 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 1000000 |  |  | 1000000 | PROJECT REPRESENTS HFB 2.R.92 PROJECT.
PITT | SR 1467 (STANTONSBURG ROAD) | SR 1204 (B'S BARBEQUE ROAD) TO NC 11 (MEMORIAL DRIVE). ACCESS MANAGEMENT. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-6195 | NOT FUNDED | T | NOT FUNDED | 2800000 | NOT FUNDED | 1200000 | NOT FUNDED | 17200000 |  |  | 21200000
PITT | SR 1514 (STANTON MILL ROAD) | REPLACE BRIDGE NO. 730109 OVER GRINDLE CREEK ON SR 1514 (STANTON MILL ROAD). | HIGHWAY | 2 | MID-EAST RPO | BR-0119 | DIVISION 2 | DP |  |  |  |  | 2021 | 1075000 |  |  | 1075000 | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING.
PITT | SR 1551 | REPLACE BRIDGE NO. 730123 OVER MEADOW BRANCH ON SR 1552. | HIGHWAY | 2 | MID-EAST RPO | BR-0120 | DIVISION 2 | DP, HFB | 2019 | 60000 |  |  | 2021 | 875000 |  |  | 935000 | HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. UNDER CONSTRUCTION.
PITT | SR 1571 (WEST 5TH STREET) | REHABILITATION AND REALIGNMENT OF SR 1571 (WEST 5TH STREET) FROM CADILLAC STREET TO READE CIRCLE IN GREENVILLE. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-6240 | DIVISION 2 | DP, L |  |  |  |  | 2022 | 18480000 |  |  | 18480000 | 'DP' FUNDS REPRESENT BUILD GRANT FUNDS.
PITT | SR 1598 (DICKINSON AVENUE) | NC 11 TO READE CIRCLE. IMPROVE ROADWAY. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-5606 | DIVISION 2 | BG5200 |  |  |  |  | 2022 | 11701000 |  |  | 11701000 | RIGHT OF WAY IN PROGRESS
PITT | SR 1700 (EVANS STREET/ OLD TAR ROAD) | SR 1711 (WORTHINGTON ROAD) IN WINTERVILLE TO US 264 ALTERNATE (GREENVILLE BOULEVARD) IN GREENVILLE. WIDEN TO MULTI-LANES. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-2817 | DIVISION 2 | BG5200 | 2019 | 22800000 | 2019 | 3972000 | 2025 | 67545000 |  |  | 94317000 | RIGHT-OF-WAY IN PROGRESS.
PITT | SR 1702 (EVANS STREET) | SR 1155 (RED BANKS ROAD) TO WEST 5TH STREET. ACCESS MANAGEMENT. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-6196 | NOT FUNDED | T | NOT FUNDED | 9500000 | NOT FUNDED | 2900000 | NOT FUNDED | 9300000 |  |  | 21700000
PITT | SR 1703 (14TH STREET) | INSTALL CROSSWALK, WHEELCHAIR RAMPS, SIDEWALK, AND FENCING ALONG SR 1703 (14TH STREET) FROM HASKETT WAY AND BERKLEY ROAD. REMOVE TWO EXISTING OBSOLETE CROSSWALKS. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | HS-2002A | DIVISION 2 | HSIP |  |  |  |  | 2021 | 50000 |  |  | 50000 | UNDER CONSTRUCTION.
PITT | SR 1704 (FOURTEENTH STREET) | RED BANKS ROAD TO SR 1708 (FIRETOWER ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-5917 | DIVISION 2 | T | 2019 | 952000 | 2024 | 2772000 | 2026 | 14901000 | 2020 | 1740000 | 20365000 | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH U-5785. BUILD NC BOND FUNDING: $793,508.60 FOR ROW PAYBACK 2019 - 2033, $1,349,849 FOR PE PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE).
PITT | SR 1708 (FIRETOWER ROAD) | WEST OF EAST ARLINGTON BOULEVARD TO SR 1704 (FOURTEENTH STREET) IN GREENVILLE. WIDEN TO MULTI-LANES. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-5785 | DIVISION 2 | T | 2024 | 17620000 | 2024 | 1000000 | 2026 | 20500000 |  |  | 39120000 | TO BE LET WITH U-5917.
PITT | SR 1708 (FIRETOWER ROAD) | SR 1704 (FOURTEENTH STREET) TO NC 33 (EAST 10TH STREET) IN GREENVILLE. WIDEN TO MULTI-LANES. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-5870 | DIVISION 2 | T | 2024 | 12616000 | 2024 | 1600000 | 2026 | 28200000 |  |  | 42416000
PITT | SR 1711 (WORTHINGTON ROAD) | SR 1725 (COUNTY HOME ROAD). UPGRADE INTERSECTION. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-6197 | DIVISION 2 | T | 2027 | 900000 | 2027 | 500000 | 2029 | 1600000 |  |  | 3000000
PITT | SR 1777 (BLACK JACK / GRIMESLAND ROAD) | REPLACE BRIDGE 730005 OVER CHICOD CREEK. | HIGHWAY | 2 | MID-EAST RPO | B-4605 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 1100000 |  |  | 1100000
PITT | SR 1923 (GARDENVILLE ROAD) | REPLACE BRIDGE 730043 OVER SWIFT CREEK. | HIGHWAY | 2 | DOWN EAST RPO, MID-EAST RPO | B-4607 | DIVISION 2 | BGOFF | 2022 | 260000 |  |  | 2022 | 1783000 |  |  | 2043000 | UNDER CONSTRUCTION.
PITT | US 13 | BRIDGE 38 OVER THE TAR RIVER ON US 13 IN GREENVILLE. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | B-4786 | REGION B | NHPB |  |  |  |  | 2022 | 8200000 |  |  | 8200000
PITT | US 13 (MEMORIAL DRIVE) | NC 43 (5TH STREET). UPGRADE INTERSECTION. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-5730 | REGION B | T |  |  |  |  | 2025 | 825000 |  |  | 825000 | RIGHT-OF-WAY IN PROGRESS
PITT | US 264 ALTERNATE | US 264 ALTERNATE (GREENVILLE BOULEVARD) AT SR 1534 (OLD PACTOLUS ROAD). CONSTRUCT A RESTRICTED-CROSSING INTERSECTION. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | HS-2002E | REGION B | HSIP |  |  |  |  | 2023 | 705000 |  |  | 705000
PITT | US 264/US 258 (FUTURE I-587) | GREENE COUNTY LINE TO SR 1467 (STANTONSBURG ROAD) INTERCHANGE (GREENVILLE SOUTHWEST BYPASS). PAVEMENT REHABILITATION. | HIGHWAY | 2 | MID-EAST RPO, GREENVILLE URBAN AREA MPO | I-6035 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2019 | 14420000 |  |  | 14420000 | TO BE LET WITH I-6032. GARVEE BOND FUNDING $12.0 M; PAYBACK FY 2019-2033. UNDER CONSTRUCTION.
PITT | GREENVILLE AREA TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC | PUBLIC TRANSIT | 2 | GREENVILLE URBAN AREA MPO | TG-4767 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2404000 | 2404000 | FUNDS AUTHORIZED IN PROGRESS
PITT | GREENVILLE AREA TRANSIT | PREVENTIVE MAINTENANCE | PUBLIC TRANSIT | 2 | GREENVILLE URBAN AREA MPO | TG-5107B | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 2700000 | 2700000 | FUNDS AUTHORIZED IN PROGRESS
PITT | GREENVILLE AREA TRANSIT | OPERATING ASSISTANCE - ADA PARATRANSIT SERVICE | PUBLIC TRANSIT | 2 | GREENVILLE URBAN AREA MPO | TG-5107C | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 600000 | 600000 | FUNDS AUTHORIZED IN PROGRESS
PITT | GREENVILLE AREA TRANSIT | FLEET SERVICE BUILDING EXPANSION. | PUBLIC TRANSIT | 2 | GREENVILLE URBAN AREA MPO | TL-0009 | PUBLIC TRANSIT | CARES, L |  |  |  |  | 2021 | 976000 |  |  | 976000
PITT | GREENVILLE AREA TRANSIT | OPERATING ASSISTANCE | PUBLIC TRANSIT | 2 | GREENVILLE URBAN AREA MPO | TO-4726 | PUBLIC TRANSIT | 5307, L, SMAP | [6 empty] | 2020 | 5420000 | 5420000 | FUNDS AUTHORIZED IN PROGRESS
PITT | GREENVILLE AREA TRANSIT | PLANNING ASSISTANCE - 5303 | PUBLIC TRANSIT | 2 | GREENVILLE URBAN AREA MPO | TP-5107 | PUBLIC TRANSIT | 5303, L, S | [6 empty] | 2020 | 132000 | 132000 | FUNDS AUTHORIZED IN PROGRESS
PITT | GREENVILLE AREA TRANSIT | SAFETY & SECURITY | PUBLIC TRANSIT | 2 | GREENVILLE URBAN AREA MPO | TS-5112 | PUBLIC TRANSIT | 5307 | [6 empty] | 2020 | 15000 | 15000 | FUNDS AUTHORIZED IN PROGRESS
PITT | PITT COUNTY | ADMINISTRATION | PUBLIC TRANSIT | 2 | MID-EAST RPO | TK-6154 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 720000 | 720000 | FUNDS AUTHORIZED IN PROGRESS
POLK | I-26 | US 74/NC 108 INTERCHANGE (EXIT 67). REVISE INTERCHANGE AND CONSTRUCT IMPROVEMENTS TO NC 108. | HIGHWAY | 14 | FOOTHILLS RPO | I-4729
POLK | I-26 | REVISE THE I-26/US 74/NC 108 INTERCHANGE. CONSTRUCT RAMPS FROM I-26 WESTBOUND TO US 74 EASTBOUND, AND FROM US 74 WESTBOUND TO I-26 EASTBOUND. | HIGHWAY | 14 | FOOTHILLS RPO | I-4729A | REGION G | [10 empty] | COMPLETE
POLK | I-26 | CONSTRUCT IMPROVEMENTS ON NC 108 AT EXIT 67. | HIGHWAY | 14 | FOOTHILLS RPO | I-4729B | REGION G | T | 2019 | 10200000 | 2027 | 2000000 | 2029 | 22599000 |  |  | 34799000 | RIGHT-OF-WAY IN PROGRESS
POLK | I-26 | HENDERSON COUNTY LINE TO MILE MARKER 65. PAVEMENT REHABILITATION. | HIGHWAY | 14 | FOOTHILLS RPO | I-5926 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2025 | 14000000 |  |  | 14000000
POLK | I-26 | MILE MARKER 65 TO SOUTH CAROLINA STATE LINE. PAVEMENT REHABILITATION. | HIGHWAY | 14 | FOOTHILLS RPO | I-5927 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2023 | 19600000 |  |  | 19600000
POLK | NC 9 | US 74 TO NC 108. ADD PAVED SHOULDERS. | HIGHWAY | 14 | FOOTHILLS RPO | R-5840 | DIVISION 14 | T | 2022 | 2200000 | 2022 | 1400000 | 2025 | 8600000 |  |  | 12200000
POLK | SR 1004 (POORS FORD ROAD) | REPLACE BRIDGE 740087 OVER BROAD RIVER. | HIGHWAY | 14 | FOOTHILLS RPO | HB-0025 | DIVISION 14 | BGOFF | 2024 | 260000 | 2024 | 260000 | 2025 | 5200000 |  |  | 5720000
POLK | US 74 | NC 108 INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | 14 | FOOTHILLS RPO | R-5873 | STATEWIDE MOBILITY | NHP |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3200000 |  |  | 3400000
POLK | US 74 EB | I-26 TO THE RUTHERFORD COUNTY LINE. UPGRADE END TERMINALS TO CURRENT STANDARDS. | HIGHWAY | 14 | FOOTHILLS RPO | W-5814C | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2021 | 179000 |  |  | 179000 | COMPLETE
POLK | US 74 WB | I-26 TO THE RUTHERFORD COUNTY LINE. UPGRADE END TERMINALS TO CURRENT STANDARDS. | HIGHWAY | 14 | FOOTHILLS RPO | W-5814B | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2021 | 199000 |  |  | 199000 | COMPLETE
POLK | POLK COUNTY TRANSPORTATION | ADMINISTRATION | PUBLIC TRANSIT | 14 | FOOTHILLS RPO | TK-6155 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 736000 | 736000 | FUNDS AUTHORIZED IN PROGRESS
RANDOLPH | REGIONAL AIRPORT (HBI) ASHEBORO | CONSTRUCT TAXILANE EXTENSION, EXTEND ACCESS ROAD, AND CONSTRUCT NEW ACCESS ROAD. | AVIATION | 8 | PIEDMONT TRIAD RPO | AV-5858 | DIVISION 8 | T |  |  |  |  | 2025 | 3455000 |  |  | 3455000
RANDOLPH | INDUSTRIAL PARK AVENUE | RANDOLPH COMMUNITY COLLEGE ENTRANCE TO CONTINUING EDUCATION AND INDUSTRIAL CENTER IN ASHEBORO. CONSTRUCT SIDEWALK ON SOUTH SIDE. | BIKE/PED | 8 | PIEDMONT TRIAD RPO | EB-5862 | DIVISION 8 | L, TA5200 |  |  |  |  | 2022 | 147000 |  |  | 147000
RANDOLPH | SR 1950 (WEST ACADEMY STREET) | SR 1952 (HIGH POINT STREET) TO HILLARY STREET IN RANDLEMAN. CONSTRUCT SIDEWALK ON NORTH SIDE. | BIKE/PED | 8 | PIEDMONT TRIAD RPO | EB-5744 | DIVISION 8 | L, TA5200 |  |  |  |  | 2023 | 411000 |  |  | 411000
RANDOLPH | SR 1950 (WEST NAOMI STREET) | WEST ACADEMY STREET TO US 220 BUSINESS (SOUTH MAIN STREET) IN RANDLEMAN. CONSTRUCT SIDEWALK, IMPLEMENT ROAD DIET, AND INSTALL RAISED CROSSWALK AND MEDIAN. | BIKE/PED | 8 | PIEDMONT TRIAD RPO | EB-5898 | DIVISION 8 | L, TA5200 | 2024 | 25000 |  |  | 2024 | 258000 |  |  | 283000
RANDOLPH | US 64 / NC 49 (EAST DIXIE DRIVE) | EXECUTIVE WAY TO CENTERPOINT PLAZA SHOPPING CENTER IN ASHEBORO. CONSTRUCT SIDEWALK. | BIKE/PED | 8 | PIEDMONT TRIAD RPO | EB-6004 | DIVISION 8 | L, TA5200 |  |  |  |  | 2024 | 130000 |  |  | 130000
RANDOLPH | I-73 | SOUTH OF SR 2269 (VISION DRIVE) TO NORTH OF SR 1712 (PINEVIEW STREET). PAVEMENT REHABILITATION. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | I-5737 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
RANDOLPH | I-73 | US 311 TO 0.6 MILE NORTH OF SR 1938 (HOCKETT DAIRY ROAD). PAVEMENT REHABILITATION. | HIGHWAY | 8 | PIEDMONT TRIAD RPO, HIGH POINT URBAN AREA MPO | I-5763 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
RANDOLPH | I-73 / I-74 / US 220 | MONTGOMERY COUNTY LINE TO NORTH OF SR 1462 (PARK DRIVE) IN ASHEBORO. PAVEMENT REHABILITATION. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | I-5948 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2026 | 17001000 |  |  | 17001000
RANDOLPH | I-73 / US 220 | SR 1009 (OLD US HIGHWAY 311) TO GUILFORD COUNTY LINE. PAVEMENT REHABILITATION. | HIGHWAY | 8 | PIEDMONT TRIAD RPO, HIGH POINT URBAN AREA MPO | HI-0003 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2028 | 8120000 |  |  | 8120000
RANDOLPH | I-74 | SR 1928 (CEDAR SQUARE ROAD) TO I-73 / US 220. PAVEMENT REHABILITATION. | HIGHWAY | 8 | HIGH POINT URBAN AREA MPO, PIEDMONT TRIAD RPO | HI-0004 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2028 | 8140000 |  |  | 8140000
RANDOLPH | I-85 | SOUTH OF SR 1009 (MAIN STREET) TO NORTH OF SR 1912 (LUNAR DRIVE) IN ARCHDALE. PAVEMENT REHABILITATION. | HIGHWAY | 8 | HIGH POINT URBAN AREA MPO | I-5738 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION - CONSTRUCTION COST INCLUDED UNDER I-5789
RANDOLPH | I-85 | SR 1009 (SOUTH MAIN STREET) IN ARCHDALE. INTERCHANGE IMPROVEMENTS. | HIGHWAY | 8 | HIGH POINT URBAN AREA MPO | U-5770 | REGION E | T | 2022 | 5833000 | 2022 | 2200000 |  |  |  |  | 8033000
RANDOLPH | NC 159 (ZOO PARKWAY) | RIDGE STREET IN ASHEBORO. IMPROVE INTERSECTION. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-5958 | DIVISION 8 | T | 2023 | 320000 | 2023 | 265000 | 2025 | 1450000 |  |  | 2035000
RANDOLPH | NC 42 | SR 2237 (EAST SALISBURY STREET) TO NORTH OF US 64 / NC 49 (DIXIE DRIVE) IN ASHEBORO. WIDEN TO THREE LANES. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | U-5743 | REGION E | T | 2022 | 1083000 | 2022 | 900000 | 2024 | 8099000 |  |  | 10082000
RANDOLPH | NC 42 (EAST SALISBURY STREET) | SR 2189 (MARTIN LUTHER KING, JR. DRIVE) / NORTH RANDOLPH AVENUE TO SR 2237 (EAST SALISBURY STREET) IN ASHEBORO. IMPROVE CORRIDOR. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-5957 | NOT FUNDED | T | NOT FUNDED | 2100000 | NOT FUNDED | 700000 | NOT FUNDED | 3400000 |  |  | 6200000
RANDOLPH | NC 49 | SR 1174 (WAYNICK MEADOW ROAD) TO SOUTH OF SR 1193 (OLD NC 49). WIDEN TO MULTILANES. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-5931 | NOT FUNDED | T | NOT FUNDED | 2964000 | NOT FUNDED | 5766000 | NOT FUNDED | 79999000 |  |  | 88729000
RANDOLPH | NC 62 | SR 3252 (SURRETT DRIVE) IN TRINITY TO SR 1009 (NORTH MAIN STREET) IN ARCHDALE. MODERNIZE ROADWAY. | HIGHWAY | 8 | HIGH POINT URBAN AREA MPO | U-6191 | DIVISION 8 | T | 2027 | 5700000 | 2027 | 4700000 | 2029 | 12400000 |  |  | 22800000
RANDOLPH | SR 1009 (SOUTH MAIN STREET) | WEST OF COLUMBUS AVENUE TO SR 3182 (COMANCHE ROAD/TARHEEL ROAD). MILLING AND RESURFACING. | HIGHWAY | 8 | HIGH POINT URBAN AREA MPO | U-5770A | REGION E | S, T |  |  |  |  | 2023 | 1693000 |  |  | 1693000 | “S” FUNDING REFLECTS CONTRACT RESURFACING FUNDS.
RANDOLPH | SR 1009 (SOUTH MAIN STREET) | WEST OF COLUMBUS AVENUE TO SR 3182 (COMANCHE ROAD/TARHEEL ROAD). CONSTRUCT DDI AND RCI IMPROVEMENTS. | HIGHWAY | 8 | HIGH POINT URBAN AREA MPO | U-5770B | REGION E | T |  |  |  |  | 2025 | 17500000 |  |  | 17500000
RANDOLPH | SR 1547 (FINCH FARM ROAD) | SR 3106 (KENNEDY ROAD) TO I-85 IN TRINITY. WIDEN TO MULTILANES. | HIGHWAY | 8 | HIGH POINT URBAN AREA MPO | U-5308 | DIVISION 8 | T | 2019 | 2459000 | 2019 | 3500000 | 2025 | 26800000 | 2020 | 2703000 | 35462000 | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $2.1 MILLION FOR PE AND $190,000 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE)
RANDOLPH | SR 1712 (PINEVIEW STREET) | WEST OF SYLVAN STREET TO US 220 BUSINESS IN ASHEBORO. WIDEN TO MULTILANES. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | U-5711 | DIVISION 8 | T |  |  |  |  | 2024 | 4950000 |  |  | 4950000 | RIGHT-OF-WAY IN PROGRESS
RANDOLPH | SR 2407 (STARMOUNT ROAD) | REPLACE BRIDGE 750129 OVER BRANCH OF SANDY CREEK. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | B-5763 | DIVISION 8 | [10 empty] | UNDER CONSTRUCTION
RANDOLPH | SR 2481 (LOW BRIDGE ROAD) | REPLACE BRIDGE 750374 OVER SANDY CREEK. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | B-5360 | HIGHWAY FUND | [10 empty] | UNDER CONSTRUCTION - LET WITH B-5546; PRIOR YEARS COST INCLUDES B-5546 CONSTRUCTION
RANDOLPH | SR 2481 (LOW BRIDGE ROAD) | REPLACE BRIDGE 750307 OVER MOUNT PLEASANT CREEK. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | B-5546 | HIGHWAY FUND | [10 empty] | UNDER CONSTRUCTION - LET WITH B-5360; CONSTRUCTION COST IS INCLUDED IN THAT PROJECT
RANDOLPH | SR 2621 (FOUSHEE ROAD) | REPLACE BRIDGE 750170 OVER REED CREEK. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | B-5739 | DIVISION 8 | [10 empty] | UNDER CONSTRUCTION
RANDOLPH | US 220 BUSINESS | SR 2123 (CAUDLE ROAD) TO SR 2270 (US 311 EXTENSION) IN RANDLEMAN. WIDEN TO 4-LANE DIVIDED FACILITY. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | U-6006 | DIVISION 8 | T | 2023 | 1000000 | 2023 | 2748000 | 2026 | 8500000 |  |  | 12248000 | COORDINATE WITH R-5956
RANDOLPH | US 220 BUSINESS (FAYETTEVILLE STREET) | INTERSECTION OF US 220 BUSINESS (FAYETTEVILLE STREET) AND PRESNELL STREET IN ASHEBORO. INTERSECTION IMPROVEMENTS. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | U-5758 | REGION E | [10 empty] | UNDER CONSTRUCTION
RANDOLPH | US 220 BUSINESS (NORTH FAYETTEVILLE STREET) | SR 2269 (VISION DRIVE) ITO SR 2123 (CAUDLE ROAD) IN ASHEBORO. WIDEN TO MULTILANES. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-5956 | DIVISION 8 | [10 empty] | COORDINATE WITH U-6006
RANDOLPH | US 220 BUSINESS (NORTH FAYETTEVILLE STREET) | SR 2269 (VISION DRIVE) TO SR 2149 (HUB MORRIS ROAD). WIDEN TO MULTILANES. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-5956A | NOT FUNDED | T | NOT FUNDED | 6200000 | NOT FUNDED | 5300000 | NOT FUNDED | 18200000 |  |  | 29700000
RANDOLPH | US 220 BUSINESS (NORTH FAYETTEVILLE STREET) | SR 2149 (HUB MORRIS ROAD) TO SR 2123 (CAUDLE ROAD). WIDEN TO MULTILANES. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-5956B | NOT FUNDED | T | NOT FUNDED | 3200000 | NOT FUNDED | 6005000 | NOT FUNDED | 9399000 |  |  | 18604000
RANDOLPH | US 220 BUSINESS (SOUTH FAYETTEVILLE STREET) | SOUTH OF SR 2915 (RIDGE STREET) TO SOUTH OF SR 1453 (WALKER AVENUE) IN ASHEBORO. CONSTRUCT RIGHT TURN LANE ON SR 2915, CONSTRUCT LEFT-OVERS AT SR 1154 (COUNTRY CLUB DRIVE) / SR 2800 (ATLANTIC AVENUE), AND REDUCE NUMBER OF LANES FROM SR 2800 TO SOUTH OF S | HIGHWAY | 8 | PIEDMONT TRIAD RPO | U-6007 | DIVISION 8 | T |  |  | 2022 | 300000 | 2023 | 750000 |  |  | 1050000 | RIGHT-OF-WAY IN PROGRESS
RANDOLPH | US 421 | CHATHAM COUNTY LINE TO THE GUILFORD COUNTY LINE. INSTALL 1 MILE AND .5 MILE MARKERS AND REVISE EXIT NUMBER SIGNS. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | HS-2008D | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2023 | 50000 |  |  | 50000
RANDOLPH | US 64 | SR 1409 (LAKE PARK ROAD) TO ASHEBORO BYPASS | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-2220DA | REGION E | T | 2027 | 6796000 | 2027 | 7554000 | 2029 | 52800000 |  |  | 67150000
RANDOLPH | US 64 | ASHEBORO SOUTHERN BYPASS, US 64 WEST TO US 64 EAST. FOUR-LANE FREEWAY ON NEW LOCATION WITH INTERCHANGES AT US 220, NC 49 AND ZOO ACCESS AT NC 159. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-2536 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION - DESIGN-BUILD PROJECT
RANDOLPH | US 64 | ASHEBORO BYPASS TO EAST OF I-73 / I-74 / US 220 IN ASHEBORO. WIDEN TO MULTILANES, RECONSTRUCT INTERCHANGE AT NC 49, MODIFY INTERCHANGE AT I-73 / I-74 / US 220 AND REPLACE BRIDGE 750171 OVER US 64 AND NC 49. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | U-5813 | REGION E | NHP | 2021 | 15934000 | 2021 | 399000 | 2023 | 31900000 |  |  | 48233000
RANDOLPH | VARIOUS | RANDOLPH COUNTY MEGASITE NEAR LIBERTY. ROADWORK AND WETLANDS MITIGATION. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | HE-0004 | DIVISION 8 | S, T | 2022 | 5000000 | 2022 | 2000000 | 2023 | 37000000 | 2023 | 1000000 | 45000000 | ECONOMIC DEVELOPMENT PROJECT. "S" FUNDS REFLECT STATE LEGISLATIVE ALLOCATION.
RANDOLPH | RANDOLPH- MONTGOMERY RESTORE | PURCHASE ADDITIONAL 20-FOOT LIGHT TRANSIT VEHICLES. | PUBLIC TRANSIT | 8 | PIEDMONT TRIAD RPO | TA-6670 | REGION E | [10 empty] | IN ACQUISITION
RANDOLPH, DAVIDSON | I-85 | NC 109 IN THOMASVILLE TO SR 1009 (SOUTH MAIN STREET) IN ARCHDALE. PAVEMENT REHABILITATION. | HIGHWAY | 8, 9 | HIGH POINT URBAN AREA MPO | HI-0002 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2022 | 15392000 |  |  | 15392000
RANDOLPH, DAVIDSON | US 64 | NC 109 TO SR 1409 (LAKE PARK ROAD) | HIGHWAY | 8, 9 |  | R-2220C | NOT FUNDED | T | NOT FUNDED | 13746000 | NOT FUNDED | 1650000 | NOT FUNDED | 56452000 |  |  | 71848000
RANDOLPH, DAVIDSON, GUILFORD | HIGH POINT TRANSIT SYSTEM / HI-TRAN | OPERATING ASSISTANCE | PUBLIC TRANSIT | 7, 8, 9 | HIGH POINT URBAN AREA MPO | TO-4790 | PUBLIC TRANSIT | 5307, L, SMAP | [6 empty] | 2020 | 11516000 | 11516000 | FUNDS AUTHORIZED IN PROGRESS
RANDOLPH, GUILFORD | SR 1577 / SR 1004 (ARCHDALE ROAD) | US 311 (MAIN STREET) TO EAST OF SPRINGWOOD LANE IN ARCHDALE. WIDEN TO MULTILANES. | HIGHWAY | 7, 8 | HIGH POINT URBAN AREA MPO | U-3400 | DIVISION 7, 8 | T | 2023 | 7900000 | 2023 | 12126000 | 2026 | 18600000 |  |  | 38626000
RANDOLPH, GUILFORD | SR 1595 / SR 4053 (SURRETT DRIVE) | I-85 IN TRINITY TO SR 1300 (WEST FAIRFIELD ROAD) IN HIGH POINT. WIDEN TO MULTILANES. | HIGHWAY | 7, 8 | HIGH POINT URBAN AREA MPO | U-5864 | DIVISION 7, 8 | T | 2026 | 5064000 | 2026 | 5100000 | 2029 | 23700000 |  |  | 33864000
RICHMOND | RICHMOND COUNTY AIRPORT (RCZ) | CLEAR OBSTRUCTIONS IN RUNWAY 14 APPROACH. | AVIATION | 8 | LUMBER RIVER RPO | AV-5761 | DIVISION 8 | T |  |  |  |  | 2023 | 550000 |  |  | 550000
RICHMOND | RICHMOND COUNTY AIRPORT (RCZ) | EXTEND RUNWAY 14-32 TO 5500 FEET. | AVIATION | 8 | LUMBER RIVER RPO | AV-5763 | DIVISION 8 | T |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5065000 |  |  | 5065000
RICHMOND | RICHMOND COUNTY AIRPORT (RCZ) | CONSTRUCT EAST RAMP EXPANSION. | AVIATION | 8 | LUMBER RIVER RPO | AV-5853 | DIVISION 8 | T |  |  |  |  | 2023 | 3658000 |  |  | 3658000
RICHMOND | SR 1639 (SPRING STREET); SR 1615 (SOUTH MAIN STREE | SPRING STREET FROM SR 1640 (WIREGRASS ROAD) TO NC 177 AND MAIN STREET FROM BRIDGES STREET TO NC 38 IN HAMLET. CONSTRUCT SIDEWALKS. | BIKE/PED | 8 | LUMBER RIVER RPO | EB-6018 | DIVISION 8 | L, TA5200 | 2024 | 72000 | 2024 | 55000 | 2025 | 720000 | 2023 | 28000 | 875000
RICHMOND | I-73 / I-74 | SOUTH OF US 220 / SR 1446 (HAYWOOD CEMETERY ROAD) TO MONTGOMERY COUNTY LINE. PAVEMENT REHABILITATION. | HIGHWAY | 8 | LUMBER RIVER RPO | I-5946
RICHMOND | I-73/I-74 | SOUTH OF US 220 / SR 1446 (HAYWOOD CEMETERY ROAD) TO SR 1455 (FIRE TOWER ROAD). PAVEMENT REHABILITATION. | HIGHWAY | 8 | LUMBER RIVER RPO | I-5946A | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION - LET WITH I-5947B
RICHMOND | I-73/I-74 | SR 1455 (FIRE TOWER ROAD) TO MONTGOMERY COUNTY LINE. PAVEMENT REHABILITATION. | HIGHWAY | 8 | LUMBER RIVER RPO | I-5946B | STATEWIDE MOBILITY | BGIM |  |  |  |  | 2022 | 6812000 |  |  | 6812000 | UNDER CONSTRUCTION
RICHMOND | US 1 | SOUTH CAROLINA STATE LINE TO SR 1001 (MARSTON ROAD). WIDEN TO FOUR LANES WITH VARIABLE WIDTH MEDIAN WITH BYPASS OF ROCKINGHAM ON NEW LOCATION. | HIGHWAY | 8 | LUMBER RIVER RPO | R-2501
RICHMOND | US 1 | SOUTH CAROLINA STATE LINE TO SR 1104 (OSBORNE ROAD) | HIGHWAY | 8 | LUMBER RIVER RPO | R-2501A | NOT FUNDED | T | NOT FUNDED | 4500000 |  |  | NOT FUNDED | 25700000 |  |  | 30200000 | SCHEDULED FOR REPRIORITIZATION
RICHMOND | US 1 | SR 1104 (OSBORNE ROAD) TO US 74 BYPASS | HIGHWAY | 8 | LUMBER RIVER RPO | R-2501BA | NOT FUNDED | T | NOT FUNDED | 5519000 | NOT FUNDED | 908000 | NOT FUNDED | 40500000 |  |  | 46927000 | SCHEDULED FOR REPRIORITIZATION
RICHMOND | US 1 | US 74 BYPASS TO US 74 BUSINESS | HIGHWAY | 8 | LUMBER RIVER RPO | R-2501BB | NOT FUNDED | T | NOT FUNDED | 13300000 | NOT FUNDED | 2523000 | NOT FUNDED | 67700000 |  |  | 83523000 | SCHEDULED FOR REPRIORITIZATION
RICHMOND | US 1 | US 74 BUSINESS TO NORTH OF SR 1606 (FOX ROAD) | HIGHWAY | 8 | LUMBER RIVER RPO | R-2501BC | NOT FUNDED | T | NOT FUNDED | 24248000 | NOT FUNDED | 6950000 | NOT FUNDED | 101101000 |  |  | 132299000 | COORDINATE WITH R-5928
RICHMOND | US 1 | NORTH OF SR 1606 (FOX ROAD) TO SOUTH OF SR 1001 (MARSTON ROAD) | HIGHWAY | 8 | LUMBER RIVER RPO | R-2501C | DIVISION 8 | T |  |  |  |  | 2019 | 12975000 | 2021 | 217000 | 13192000 | UNDER CONSTRUCTION; BUILD NC BONDS: $7.007 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $169,000 FOR PRELIMINARY ENGINEERING AND $3.551 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
RICHMOND | US 1 | SR 1640 (WIREGRASS ROAD) TO LOCH LAURIN LANE. WIDEN TO MULTILANES. | HIGHWAY | 8 | LUMBER RIVER RPO | R-5928 | DIVISION 8 | T | 2027 | 5000000 | 2027 | 2900000 | 2029 | 28901000 |  |  | 36801000 | COORDINATE WITH R-2501BC
RICHMOND | US 1 (PROPOSED) /SR 1516 (GREENE STREET) | US 220 TO US 1 IN ROCKINGHAM. WIDEN TO 3-LANE FACILITY AND RE-ROUTE US 1 ALONG PROJECT. | HIGHWAY | 8 | LUMBER RIVER RPO | U-6027 | DIVISION 8 | T | 2023 | 1200000 | 2023 | 500000 | 2025 | 5700000 |  |  | 7400000
RICHMOND | US 220 / FUTURE I-73 / FUTURE I-74 | ROCKINGHAM BYPASS. FOUR LANES DIVIDED ON NEW LOCATION. | HIGHWAY | 8 | LUMBER RIVER RPO | R-3421
RICHMOND | US 220 BYPASS / FUTURE I-73 / FUTURE I-74 | ROCKINGHAM BYPASS, US 74 BYPASS WEST OF ROCKINGHAM AT SR 1109 (ZION CHURCH ROAD) INTERCHANGE TO SOUTH OF SR 1140 (OLD CHARLOTTE HIGHWAY) | HIGHWAY | 8 | LUMBER RIVER RPO | R-3421A | REGION E | T | 2020 | 5495000 |  |  | 2020 | 106857000 |  |  | 112352000 | UNDER CONSTRUCTION; BUILD NC BONDS: $4.27 MILLION FOR RIGHT-OF-WAY AND $6.531 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE), $51.269 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
RICHMOND | US 220 BYPASS / FUTURE I-73 / FUTURE I-74 | ROCKINGHAM BYPASS, SOUTH OF SR 1140 (OLD CHARLOTTE HIGHWAY) TO SOUTHWEST OF SR 1304 (HARRINGTON ROAD) | HIGHWAY | 8 | LUMBER RIVER RPO | R-3421B | REGION E | T |  |  |  |  | 2020 | 98972000 |  |  | 98972000 | UNDER CONSTRUCTION; BUILD NC BONDS: $46.324 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
RICHMOND | US 220 BYPASS / FUTURE I-73 / FUTURE I-74 | ROCKINGHAM BYPASS, 0.2 MILES SOUTHWEST OF SR 1304 (HARRINGTON ROAD) TO I-73 / I-74 INTERCHANGE SOUTH OF ELLERBE | HIGHWAY | 8 | LUMBER RIVER RPO | R-3421C | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
RICHMOND | US 74 / FUTURE I-74 | US 1 (EXIT 311). INTERCHANGE IMPROVEMENTS. | HIGHWAY | 8 | LUMBER RIVER RPO | I-5979 | DIVISION 8 | NHP | 2022 | 500000 | 2022 | 420000 | 2024 | 5500000 |  |  | 6420000
RICHMOND | VARIOUS | US 74 BUSINESS TO SR 1426 (ABERDEEN ROAD). CONSTRUCT TWO LANE FACILITY UTILIZING SECTIONS OF SR 1641 (CLEMMER ROAD) AND SR 1645 (MT. OLIVE CHURCH ROAD), REMAINDER ON NEW LOCATION. | HIGHWAY | 8 | LUMBER RIVER RPO | U-5706 | DIVISION 8 | T | 2023 | 8600000 | 2023 | 1800000 | 2026 | 31070000 |  |  | 41470000 | BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE)
ROBESON | LUMBERTON REGIONAL AIRPORT (LBT) | PARTIAL PARALLEL TAXIWAY RUNWAY 5. | AVIATION | 6 | LUMBER RIVER RPO | AV-5747 | DIVISION 6 | T |  |  |  |  | 2022 | 2600000 |  |  | 2600000
ROBESON | LUMBERTON REGIONAL AIRPORT (LBT) | RUNWAY 13-31. CONSTRUCT TAXIWAYS. | AVIATION | 6 | LUMBER RIVER RPO | AV-5901 | DIVISION 6 | T |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3100000 |  |  | 3100000
ROBESON | NC 711 (THIRD STREET) | SR 1563 (UNION CHAPEL ROAD) TO WALMART SHOPPING CENTER/JOHNES ROAD IN PEMBROKE. CONSTRUCT SIDEWALKS. | BIKE/PED | 6 | LUMBER RIVER RPO | EB-6013 | DIVISION 6 | L, TA5200 | 2028 | 168000 |  |  | 2029 | 848000 | 2027 | 170000 | 1186000
ROBESON | CHURCH ROAD) SR 1529 (MOUNT OLIVE | REPLACE BRIDGES 770299 AND 770300 OVER SADDLE TREE SWAMP. | HIGHWAY | 6 | LUMBER RIVER RPO | HB-0007 | DIVISION 6 | BGOFF | 2023 | 170000 |  |  | 2024 | 1700000 |  |  | 1870000
ROBESON | I-74 | NC 710 TO NC 41. PAVEMENT AND BRIDGE REHABILITATION. | HIGHWAY | 6 | LUMBER RIVER RPO | I-5938 | STATEWIDE MOBILITY
ROBESON | I-74 | BRIDGE REHABILITATION | HIGHWAY | 6 | LUMBER RIVER RPO | I-5938A | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
ROBESON | I-74 | PAVEMENT REHABILITATION | HIGHWAY | 6 | LUMBER RIVER RPO | I-5938B | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
ROBESON | I-95 | NORTH OF US 301 (MILE MARKER 22) TO CUMBERLAND COUNTY LINE (MILE MARKER 40). PAVEMENT REHABILITATION. | HIGHWAY | 6 | LUMBER RIVER RPO, FAYETTEVILLE AREA MPO | I-5850 | STATEWIDE MOBILITY
ROBESON | I-95 | BRIDGE REHABILITATION, MEDIAN DRAINAGE, AND CONTROL OF ACCESS FENCE. | HIGHWAY | 6 | LUMBER RIVER RPO, FAYETTEVILLE AREA MPO | I-5850A | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
ROBESON | I-95 | PAVEMENT REHABILITATION. | HIGHWAY | 6 | LUMBER RIVER RPO, FAYETTEVILLE AREA MPO | I-5850B | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
ROBESON | I-95 | SR 1536 (CARTHAGE ROAD/WEST CARTHAGE ROAD) (EXIT 19). IMPROVE INTERCHANGE. | HIGHWAY | 6 | LUMBER RIVER RPO | I-5879 | DIVISION 6 | NHP |  |  |  |  | 2021 | 15028000 |  |  | 15028000 | UNDER CONSTRUCTION. PROJECT LET WITH I-6064 A, B AND C.
ROBESON | I-95 | SOUTH CAROLINA STATE LINE (MILE MARKER 0.0) TO I-74 (MILE MARKER 13). PAVEMENT REHABILITATION. | HIGHWAY | 6 | LUMBER RIVER RPO | I-5939 | STATEWIDE MOBILITY | BGIM |  |  |  |  | 2022 | 20184000 |  |  | 20184000
ROBESON | I-95 | SOUTH OF US 301 TO SOUTH OF PROPOSED I-295. WIDEN TO EIGHT LANES. | HIGHWAY | 6 | LUMBER RIVER RPO, FAYETTEVILLE AREA MPO | I-5987 | REGION C | [10 empty] | DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING.
ROBESON | I-95 | SOUTH OF US 301 TO SOUTH OF NC 20. WIDEN TO EIGHT LANES. | HIGHWAY | 6 | LUMBER RIVER RPO | I-5987A | REGION C | T | 2021 | 3395000 | 2021 | 875000 | 2023 | 271025000 |  |  | 275295000 | BUILD NC BOND FUNDING: $43,000,000 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $32,000,000 FOR CONSTRUCTION PAYBACK 2024 - 2038 (FY 2024 / YR 6 SALE). RIGHT-OF-WAY IN PROGRESS.
ROBESON | I-95 | CONSTRUCT WEIGH IN MOTION STATION. | HIGHWAY | 6 | LUMBER RIVER RPO | I-5987AA | REGION C | T |  |  |  |  | 2025 | 2400000 |  |  | 2400000
ROBESON | I-95 | SOUTH OF NC 20 TO SOUTH OF PROPOSED I-295. WIDEN TO EIGHT LANES. | HIGHWAY | 6 | LUMBER RIVER RPO, FAYETTEVILLE AREA MPO | I-5987B | REGION C | T | 2021 | 3581000 | 2021 | 2300000 | 2023 | 346893000 |  |  | 352774000 | BUILD NC BOND FUNDING: $43,000,000 FOR CONSTRUCTION PAYBACK 2023 - 2036 (FY 2022 / YR 4 SALE); $32,000,000 FOR CONSTRUCTION PAYBACK 2024 - 2038 (FY 2024 / YR 6 SALE). RIGHT-OF-WAY IN PROGRESS.
ROBESON | I-95 | GAUGE INSTALLATION, MODELING / HYDRAULIC STUDIES, AND STRESS TESTING ALONG CORRIDOR. | HIGHWAY | 6 | LUMBER RIVER RPO, FAYETTEVILLE AREA MPO | I-5987C | REGION C | DP, T | [6 empty] | 2022 | 315000 | 315000
ROBESON | I-95 | MILE MARKER 13 TO MILE MARKER 22. WIDENING AND PAVEMENT REHABILITATION. | HIGHWAY | 6 | LUMBER RIVER RPO | I-6064 | [11 empty] | DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING. PROJECT LET WITH I-5879.
ROBESON | I-95 | I-74 (EXIT 13) TO CARTHAGE ROAD (EXIT 19). WIDEN ROADWAY. | HIGHWAY | 6 | LUMBER RIVER RPO | I-6064A | REGION C | DP, T | 2021 | 3087000 | 2021 | 3250000 | 2021 | 164551000 |  |  | 170888000 | UNDER CONSTRUCTION
ROBESON | I-95 | CARTHAGE ROAD (EXIT 19) TO US 301 (FAYETTEVILLE ROAD, EXIT 22). WIDEN ROADWAY. | HIGHWAY | 6 | LUMBER RIVER RPO | I-6064B | STATEWIDE MOBILITY | T | 2022 | 7429000 | 2022 | 2025000 | 2022 | 64620000 |  |  | 74074000 | UNDER CONSTRUCTION
ROBESON | I-95 | MILE MARKER 13 TO MILE MARKER 22. PAVEMENT REHABILITATION. | HIGHWAY | 6 | LUMBER RIVER RPO | I-6064C | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2021 | 131492000 |  |  | 131492000 | UNDER CONSTRUCTION
ROBESON | I-95 | GAUGE INSTALLATION, MODELING / HYDRAULIC STUDIES, AND STRESS TESTING ALONG CORRIDOR. | HIGHWAY | 6 | LUMBER RIVER RPO | I-6064D | STATEWIDE MOBILITY | DP, T | [6 empty] | 2022 | 315000 | 315000
ROBESON | NC 20 | SR 1743 (COVINGTON FARM ROAD) TO I-95. WIDEN TO MULTI-LANES. | HIGHWAY | 6 | LUMBER RIVER RPO | R-5904 | NOT FUNDED | T | NOT FUNDED | 5400000 | NOT FUNDED | 3400000 | NOT FUNDED | 18800000 |  |  | 27600000
ROBESON | NC 41 (EAST ELIZABETHTOWN ROAD) | SR 2110 (SNAKE ROAD) TO SYCAMORE LANE. WIDEN EXISTING ROADWAY. | HIGHWAY | 6 | LUMBER RIVER RPO | R-5888 | REGION C | T | 2028 | 900000 | 2028 | 300000 | 2030 | 5800000 |  |  | 7000000
ROBESON | NC 41 (MARTIN LUTHER KING DRIVE) | US 74 TO MARION ROAD. WIDEN ROADWAY. | HIGHWAY | 6 | LUMBER RIVER RPO | R-5951 | NOT FUNDED | T | NOT FUNDED | 10500000 | NOT FUNDED | 3200000 | NOT FUNDED | 18600000 |  |  | 32300000
ROBESON | NC 41 (MARTIN LUTHER KING JR DRIVE) | NC 41 (MARTIN LUTHER KING JR DRIVE) AT NC 72 (WEST SECOND STREET) AND SR 1599 (MARTIN LUTHER KING JR DRIVE). CONSTRUCT SIGNALIZED PEDESTRIAN CROSSINGS. | HIGHWAY | 6 | LUMBER RIVER RPO | W-5806E | REGION C | HSIP |  |  |  |  | 2022 | 115000 |  |  | 115000
ROBESON | NC 41/NC 72/SR 1600 | REPLACE BRIDGE 770125 AND 770175 OVER LUMBER RIVER. | HIGHWAY | 6 | LUMBER RIVER RPO | B-5985 | REGION C | BFP, NHPB | 2022 | 395000 | 2022 | 485000 | 2023 | 16675000 |  |  | 17555000 | RIGHT-OF-WAY IN PROGRESS.
ROBESON | NC 711 | SR 1340 (ODOM STREET-PHILADELPHUS ROAD) IN PEMBROKE TO SR 1557 (REDMOND ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 6 | LUMBER RIVER RPO | R-4428 | REGION C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9263000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1220000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 11600000 |  |  | 22083000
ROBESON | PEMBROKE | CONSTRUCT IMPROVEMENTS TO CONNECT THE DOWNTOWN TO THE UNIVERSITY OF NORTH CAROLINA AT PEMBROKE TO THE WEST AND THE HEADQUARTERS OF THE LUMBEE TRIBE TO THE EAST IN PEMBROKE. | HIGHWAY | 6 | LUMBER RIVER RPO | HL-0009 | EXEMPT | DP, L, S | 2022 | 100000 | 2022 | 930000 | 2023 | 5310000 | 2021 | 350000 | 6690000 | 'DP' FUNDS REPRESENT FEDERAL BUILD GRANT FUNDS. 'S' FUNDS REPRESENT STATE HIGHWAY FUNDS.
ROBESON | SR 1340 (PROSPECT STREET/ NORTH ODUM ROAD) | SR 1566 (CORINTH ROAD) TO NC 711 (THIRD STREET). UPGRADE TO SUPERSTREET. | HIGHWAY | 6 | LUMBER RIVER RPO | U-5925 | DIVISION 6 | [10 empty] | UNDER CONSTRUCTION
ROBESON | SR 1924 (CURRIE ROAD) | REPLACE BRIDGE 770059 OVER BIG MARSH SWAMP. | HIGHWAY | 6 | LUMBER RIVER RPO | B-5693 | DIVISION 6 | [10 empty] | UNDER CONSTRUCTION
ROBESON | SR 1935 (HOWELL ROAD) | CONVERT INTERSECTION OF SR 1924 (BARKER TEN MILE ROAD) AND SR 1935 (HOWELL ROAD) TO AN ALL WAY STOP. REALIGN NORTH LEG OF SR 1005 (TOLARSVILLE ROAD) AT SR 1935 (HOWELL ROAD) AND REMOVE SOUTH LEG. | HIGHWAY | 6 | LUMBER RIVER RPO | HS-2006D | DIVISION 6 | HSIP | 2022 | 20000 |  |  | 2023 | 428000 |  |  | 448000
ROBESON | SR 1945 (MEADOW ROAD) | SR 1984 (LINKHAW ROAD). IMPROVE INTERSECTION. | HIGHWAY | 6 | LUMBER RIVER RPO | R-5954 | NOT FUNDED | T | NOT FUNDED | 100000 | NOT FUNDED | 300000 | NOT FUNDED | 2000000 |  |  | 2400000
ROBESON | SR 1997 (FAYETTEVILLE ROAD) | I-95 TO FARRINGTON STREET. WIDEN ROADWAY. | HIGHWAY | 6 | LUMBER RIVER RPO | R-5955 | NOT FUNDED | T | NOT FUNDED | 16000000 | NOT FUNDED | 6900000 | NOT FUNDED | 16300000 |  |  | 39200000
ROBESON | SR 1997 (FAYETTEVILLE ROAD) | FARRINGTON STREET TO EAST 22ND STREET. WIDEN TO MULTI-LANES. | HIGHWAY | 6 | LUMBER RIVER RPO | U-5797 | DIVISION 6 | T | 2023 | 7100000 | 2023 | 2208000 | 2024 | 22100000 |  |  | 31408000
ROBESON | SR 2269 (BLOOMINGDALE ROAD) | REPLACE BRIDGE 770108 OVER INDIAN SWAMP. | HIGHWAY | 6 | LUMBER RIVER RPO | B-6007 | DIVISION 6 | [10 empty] | UNDER CONSTRUCTION
ROBESON | SR 2519 (SOUTH ROBESON ROAD) | REPLACE BRIDGE 770135 OVER AARON SWAMP. | HIGHWAY | 6 | LUMBER RIVER RPO | B-5706 | HIGHWAY FUND | [10 empty] | DIVISION PURCHASE ORDER CONTRACT (DPOC) - UNDER CONSTRUCTION
ROBESON | US 74 | CONVERT AT-GRADE INTERSECTION OF US 74 AND SR 2225 (CREEK ROAD) TO GRADE SEPARATION. | HIGHWAY | 6 | LUMBER RIVER RPO | I-6011A | DIVISION 6 | T | 2025 | 55000 | 2025 | 352000 | 2027 | 7400000 |  |  | 7807000
ROBESON | US 74 | NC 72/NC 130. UPGRADE AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 6 | LUMBER RIVER RPO | R-5751 | REGION C | T | 2021 | 325000 |  |  | 2023 | 26600000 |  |  | 26925000 | RIGHT-OF-WAY IN PROGRESS
ROBESON | US 74 | SR 2220 (BROADBRIDGE ROAD). UPGRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 6 | LUMBER RIVER RPO | R-5752 | DIVISION 6 | [10 empty] | UNDER CONSTRUCTION - NATIONAL HIGHWAY FREIGHT PROGRAM PROJECT
ROBESON | US 74 (FUTURE I-74) | US 74 (FUTURE I-74) FROM EAST OF NC 41 TO THE COLUMBUS COUNTY LINE. PAVEMENT REHABILITATION. | HIGHWAY | 6 | LUMBER RIVER RPO | HI-0016 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2023 | 9200000 |  |  | 9200000
ROBESON | US 74 (FUTURE I-74) | US 74 (FUTURE I-74) FROM THE SCOTLAND COUNTY LINE TO I-74/US 74 BUSINESS. PAVEMENT REHABILITATION. | HIGHWAY | 6 | LUMBER RIVER RPO | HI-0017 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2023 | 3000000 |  |  | 3000000
ROBESON | ROBESON COUNTY | ADMINISTRATION | PUBLIC TRANSIT | 6 | LUMBER RIVER RPO | TK-6158 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 800000 | 800000 | FUNDS AUTHORIZED IN PROGRESS
ROBESON | SR 1154 (UNION SCHOOL ROAD) | INSTALLATION OF ACTIVE WARNING DEVICES AT CSX CROSSING 629606K NEAR PEMBROKE. | RAIL | 6 | LUMBER RIVER RPO | RX-2006B | DIVISION 6 | RR |  |  |  |  | 2023 | 800000 |  |  | 800000
ROBESON, CUMBERLAND | I-295 | I-95 IN ROBESON COUNTY TO SOUTH OF SR 1118 (PARKTON ROAD) IN CUMBERLAND COUNTY. | HIGHWAY | 6 | LUMBER RIVER RPO | U-2519AA | REGION C | NHP, S(M) |  |  |  |  | 2018 | 134842000 |  |  | 134842000 | DESIGN BUILD PROJECT. UNDER CONSTRUCTION. GARVEE BOND FUNDING $111 M; PAYBACK FY 2018 - 2032 FOR CONSTRUCTION.
ROBESON, CUMBERLAND, JOHNSTON, NASH, HALIFAX, WILSON, HARNETT, NORTHAMPTON | I-95 | INSTALL BROADBAND FIBER ALONG I-95 FROM SOUTH CAROLINA LINE TO VIRGINIA STATE LINE. | HIGHWAY | 1, 4, 6 | UPPER COASTAL PLAIN RPO, LUMBER RIVER RPO, PEANUT BELT RPO, FAYETTEVILLE AREA MPO, MID-CAROLINA RPO, ROCKY MOUNT URBAN AREA MPO | I-5986C | STATEWIDE MOBILITY | DP, T |  |  |  |  | 2021 | 27667000 |  |  | 27667000 | UNDER CONSTRUCTION. LETTING COMBINED WITH R-5777D, HO-0002A, HO-0002B, AND HO-0002C. DP FUNDS REPRESENT FEDERAL INFRA GRANT FUNDS.
ROBESON, HARNETT | VARIOUS | DIVISION 6 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | 6 | LUMBER RIVER RPO, MID-CAROLINA RPO | W-5206REG | REGION C
ROCKINGHAM | ROCKINGHAM COUNTY / NC SHILOH AIRPORT (SIF) | CONSTRUCT T-HANGAR TAXILANES FOR ADDITION OF T-HANGARS. | AVIATION | 7 | PIEDMONT TRIAD RPO | AV-5898 | DIVISION 7 | T |  |  |  |  | 2025 | 770000 |  |  | 770000
ROCKINGHAM | ROCKINGHAM COUNTY AIRPORT (SIF) | EXTEND RUNWAY TO 5500 FT. | AVIATION | 7 | PIEDMONT TRIAD RPO | AV-5852 | DIVISION 7 | T |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2000000 |  |  | 2000000
ROCKINGHAM | SR 1747 (EAST STADIUM DRIVE) | SR 1962 (NORTH PIERCE STREET) TO FREEDOM PARK IN EDEN. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | PIEDMONT TRIAD RPO | EB-5888 | DIVISION 7 | L, TA5200 |  |  |  |  | 2023 | 443000 |  |  | 443000
ROCKINGHAM | US 220 BUSINESS | EAST JACKSON STREET IN MAYODAN TO MAYO RIVER STATE PARK. CONSTRUCT MULTIUSE PATH. | BIKE/PED | 7 | PIEDMONT TRIAD RPO | EB-5891 | DIVISION 7 | L, TALT5 |  |  |  |  | 2023 | 652000 |  |  | 652000
ROCKINGHAM | FUTURE I-73 / US 220 | US 311 / NC 135 INTERCHANGE. REPLACE BRIDGE 780074 AND UPGRADE INTERCHANGE. | HIGHWAY | 7 | PIEDMONT TRIAD RPO | I-5898 | REGION D | T | 2022 | 1500000 | 2022 | 1600000 | 2025 | 14000000 |  |  | 17100000 | IN PROGRESS
ROCKINGHAM | NC 14 / NC 87 | REPLACE BRIDGE 780155 OVER NORFOLK SOUTHERN RAILROAD. | HIGHWAY | 7 | PIEDMONT TRIAD RPO | B-6038 | REGION D | BFP, NHPB | 2023 | 390000 | 2023 | 163000 | 2023 | 3900000 |  |  | 4453000
ROCKINGHAM | NC 65 / NC 87 | WEST OF SR 2371 (OLD COUNTY HOME ROAD) IN WENTWORTH TO US 158 / US 29 BUSINESS (FREEWAY DRIVE) IN REIDSVILLE. UPGRADE ROADWAY. | HIGHWAY | 7 | PIEDMONT TRIAD RPO | R-5766
ROCKINGHAM | NC 65 / NC 87 | WEST OF SR 2371 (OLD COUNTY HOME ROAD) IN WENTWORTH TO SR 1001 (SANDY CROSS ROAD) / SR 1998 (WENTWORTH STREET) | HIGHWAY | 7 | PIEDMONT TRIAD RPO | R-5766A | DIVISION 7 | T | 2024 | 8700000 | 2024 | 2200000 | 2026 | 13100000 |  |  | 24000000
ROCKINGHAM | NC 65 / NC 87 | SR 1001 (SANDY CROSS ROAD) / SR 1998 (WENTWORTH STREET) TO SR 2413 (VANCE STREET EXTENSION) | HIGHWAY | 7 | PIEDMONT TRIAD RPO | R-5766B | DIVISION 7 | T | 2024 | 4000000 | 2024 | 900000 | 2026 | 8800000 |  |  | 13700000
ROCKINGHAM | NC 65 / NC 87 | SR 2413 (VANCE STREET EXTENSION) TO US 158 / US 29 BUSINESS IN REIDSVILLE | HIGHWAY | 7 | PIEDMONT TRIAD RPO | R-5766C | DIVISION 7 | T | 2024 | 5900000 | 2024 | 1700000 | 2026 | 14900000 |  |  | 22500000
ROCKINGHAM | NC 87 | SR 1998 (WENTWORTH STREET) / SR 1001 (SANDY CROSS ROAD). INTERSECTION REALIGNMENT. | HIGHWAY | 7 | PIEDMONT TRIAD RPO | R-5704 | REGION D | [10 empty] | UNDER CONSTRUCTION
ROCKINGHAM | SR 1138 (LINDSEY BRIDGE ROAD) | REPLACE BRIDGE 780140 OVER DAN RIVER | HIGHWAY | 7 | PIEDMONT TRIAD RPO | B-5716 | DIVISION 7 | BGOFF | 2022 | 610000 |  |  | 2023 | 6101000 |  |  | 6711000
ROCKINGHAM | SR 1169 (ISLAND DRIVE) | REPLACE BRIDGE 780277 OVER BEAVER CREEK | HIGHWAY | 7 | PIEDMONT TRIAD RPO | B-5722 | DIVISION 7 | BGOFF | 2023 | 200000 |  |  | 2023 | 2000000 |  |  | 2200000
ROCKINGHAM | SR 1535 (PRICE ROAD) | REPLACE BRIDGE 780177 OVER MATRIMONY CREEK IN EDEN. | HIGHWAY | 7 | PIEDMONT TRIAD RPO | HB-0035 | DIVISION 7 | BGOFF | 2025 | 180000 | 2025 | 180000 | 2026 | 3600000 |  |  | 3960000
ROCKINGHAM | SR 1925 (WORSHAM MILL ROAD) | REPLACE BRIDGE 780097 OVER WOLF ISLAND CREEK. | HIGHWAY | 7 | PIEDMONT TRIAD RPO | B-4803 | DIVISION 7 | [10 empty] | UNDER CONSTRUCTION
ROCKINGHAM | SR 2177 (DAN VALLEY ROAD) | REPLACE BRIDGE 780124 OVER MAYO RIVER IN MADISON. | HIGHWAY | 7 | PIEDMONT TRIAD RPO | B-5721 | DIVISION 7 | BGLT5 | 2022 | 188000 | 2022 | 336000 | 2023 | 3500000 |  |  | 4024000 | IN PROGRESS
ROCKINGHAM | SR 2351 (WITTY ROAD) | REPLACE BRIDGE 780017 OVER HAW RIVER. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO, PIEDMONT TRIAD RPO | B-5715 | DIVISION 7 | [10 empty] | UNDER CONSTRUCTION
ROCKINGHAM | SR 2600 (MIZPAH CHURCH ROAD) | REPLACE BRIDGE 780085 OVER SOUTHERN RAILROAD. | HIGHWAY | 7 | PIEDMONT TRIAD RPO | B-4964 | DIVISION 7 | [10 empty] | UNDER CONSTRUCTION
ROCKINGHAM | US 220 (NORTHBOUND) | REPLACE BRIDGE 780131 OVER NORFOLK SOUTHERN RAILROAD. | HIGHWAY | 7 | PIEDMONT TRIAD RPO | B-5352 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
ROCKINGHAM | US 220 / FUTURE I-73 | NC 68 INTERSECTION - CONVERT AT-GRADE INTERSECTION TO INTERCHANGE | HIGHWAY | 7 | PIEDMONT TRIAD RPO | R-2413CA | PRE-STI (TRANSITION) | [10 empty] | IN PROGRESS
ROCKINGHAM | US 29 BUSINESS (FREEWAY DRIVE) | SOUTH SCALES STREET TO SR 2686 (RICHARDSON DRIVE) | HIGHWAY | 7 | PIEDMONT TRIAD RPO | U-3326A | [11 empty] | UNDER CONSTRUCTION
ROCKINGHAM | US 29 BUSINESS / US 158 (FREEWAY DRIVE) | SR 2686 (RICHARDSON DRIVE) TO NC 14 | HIGHWAY | 7 | PIEDMONT TRIAD RPO | U-3326B | [11 empty] | UNDER CONSTRUCTION
ROCKINGHAM | US 29 BUSINESS/US 158 (FREEWAY DRIVE) | SOUTH SCALES STREET TO NC 14 IN REIDSVILLE. WIDEN TO MULTILANES. | HIGHWAY | 7 | PIEDMONT TRIAD RPO | U-3326
ROCKINGHAM | US 311 / NC 14 (SOUTH VAN BUREN ROAD) | SR 2066 (KINGS HIGHWAY) IN EDEN. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 7 | PIEDMONT TRIAD RPO | U-5893 | REGION D | T | 2024 | 1644000 | 2024 | 717000 | 2026 | 12199000 |  |  | 14560000
ROCKINGHAM | ROCKINGHAM COUNTY COUNCIL ON AGING, INC. | ADMINISTRATION | PUBLIC TRANSIT | 7 | PIEDMONT TRIAD RPO | TK-6159 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 708000 | 708000 | FUNDS AUTHORIZED IN PROGRESS
ROCKINGHAM, GUILFORD | NC 65 / NC 68 | NC 65 IN STOKESDALE (SOUTHERNMOST INTERSECTION) TO US 220 / FUTURE I-73. WIDEN TO MULTILANES. | HIGHWAY | 7 | PIEDMONT TRIAD RPO, GREENSBORO URBAN AREA MPO | R-5823 | DIVISION 7 | T | 2024 | 10500000 | 2024 | 424000 | 2026 | 28200000 |  |  | 39124000
ROCKINGHAM, GUILFORD | US 220 / FUTURE I-73 | HAW RIVER TO NC 68-US 220 INTERSECTION | HIGHWAY | 7 | PIEDMONT TRIAD RPO, GREENSBORO URBAN AREA MPO | R-2413C | [11 empty] | UNDER CONSTRUCTION
ROCKINGHAM, GUILFORD | US 29 (FUTURE I-785) | SR 2565 (HICONE ROAD) IN GREENSBORO TO US 158 / NC 14 IN REIDSVILLE. UPGRADE CORRIDOR TO INTERSTATE STANDARDS. | HIGHWAY | 7 | PIEDMONT TRIAD RPO, GREENSBORO URBAN AREA MPO | R-5889 | REGION D | T | 2028 | 26500000 | 2028 | 7300000 | 2031 | 186200000 |  |  | 220000000
ROWAN | GRANTS CREEK GREENWAY | KELSEY SCOTT PARK TO CATAWBA COLLEGE IN SALISBURY. CONSTRUCT MULTIUSE PATH. | BIKE/PED | 9 | CABARRUS-ROWAN MPO | EB-5619 | DIVISION 9 | [10 empty] | PLANNING / DESIGN / RIGHT OF WAY / CONSTRUCTION BY CITY OF SALISBURY
ROWAN | GRANTS CREEK GREENWAY | VICINITY OF FORESTDALE DRIVE TO CATAWBA COLLEGE IN SALISBURY. CONSTRUCT LOW-WATER BRIDGE GREENWAY CONNECTION. | BIKE/PED | 9 | CABARRUS-ROWAN MPO | EB-5619A | DIVISION 9 | [10 empty] | UNDER CONSTRUCTION
ROWAN | GRANTS CREEK GREENWAY | CATAWBA COLLEGE AND MEADOWBROOK NEIGHBORHOOD TO WILTSHIRE VILLAGE. CONSTRUCT MULTIUSE PATH. | BIKE/PED | 9 | CABARRUS-ROWAN MPO | EB-5619B | DIVISION 9 | BGDA, L | 2020 | 825000 |  |  | 2023 | 1439000 |  |  | 2264000 | RIGHT OF WAY IN PROGRESS
ROWAN | GRANTS CREEK GREENWAY | WILTSHIRE VILLAGE TO KELSEY SCOTT PARK. CONSTRUCT MULTIUSE PATH. | BIKE/PED | 9 | CABARRUS-ROWAN MPO | EB-5619C | DIVISION 9 | BGDA, L |  |  |  |  | 2023 | 2352000 | 2021 | 368000 | 2720000
ROWAN | SR 2739 (NORTH MAIN STREET) | 12TH STREET TO 22ND STREET IN KANNAPOLIS. CONSTRUCT SIDEWALK. | BIKE/PED | 9 | CABARRUS-ROWAN MPO | EB-5921 | DIVISION 9 | L, TAANY | 2024 | 450000 |  |  | 2025 | 1900000 | 2023 | 450000 | 2800000 | COORDINATE WITH U-6062
ROWAN | THIRD STREET GREENWAY | 3RD STREET TO YADKIN RIVER IN SPENCER. CONSTRUCT ALTERNATE ROUTE, INCLUDING SPUR FROM GRANTS CREEK. | BIKE/PED | 9 | CABARRUS-ROWAN MPO | EB-5861 | DIVISION 9 | L, TAANY |  |  |  |  | 2024 | 4472000 |  |  | 4472000
ROWAN | US 70 / US 601 (JAKE ALEXANDER BOULEVARD) | WEST OF KELSEY SCOTT PARK GREENWAY TO END OF SALISBURY MALL GREENWAY/CAROLINA THREAD TRAIL. CONSTRUCT SIDEWALK. | BIKE/PED | 9 | CABARRUS-ROWAN MPO | BL-0034 | EXEMPT | CMAQ, L | 2023 | 90000 |  |  | 2025 | 604000 | 2022 | 151000 | 845000
ROWAN | ARLINGTON AVENUE | ARLINGTON AVENUE TO WALMART PARKING LOT | HIGHWAY | 9 | CABARRUS-ROWAN MPO | C-4908D | EXEMPT | [10 empty] | COMPLETE
ROWAN | BRENNER AVENUE | US 70 / US 601 (JAKE ALEXANDER BOULEVARD) TO MILFORD HILLS ROAD IN SALISBURY. CONSTRUCT MEDIAN; CONSTRUCT ROUNDABOUT AT MILFORD HILLS ROAD. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | HL-0049 | DIVISION 9 | BGDACV, L | 2023 | 14000 |  |  | 2023 | 830000 | 2022 | 181000 | 1025000
ROWAN | HORAH STREET | BRENNER AVENUE TO PARTEE STREET | HIGHWAY | 9 | CABARRUS-ROWAN MPO | C-4908A | EXEMPT | [10 empty] | PROJECT DELETED AT MPO REQUEST
ROWAN | I-85 | SR 2180 (LANE STREET) IN CABARRUS COUNTY TO US 29 / US 601 CONNECTOR IN ROWAN COUNTY | HIGHWAY | 9 | CABARRUS-ROWAN MPO | I-3802B | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION - DESIGN-BUILD PROJECT
ROWAN | I-85 | SR 1221 (OLD BEATTY FORD ROAD) NEAR LANDIS. CONVERT GRADE SEPARATION TO INTERCHANGE. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | I-3804 | DIVISION 9 | [10 empty] | INCLUDED IN I-3802B - DESIGN-BUILD PROJECT
ROWAN | I-85 | US 52 (INNES STREET) AND US 601 (JAKE ALEXANDER BOULEVARD) INTERCHANGES. STABILIZE SLOPES, REPLACE EMERGENCY LANE / SHOULDER , AND RESEAL JOINTS. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | I-5505 | [11 empty] | CONSTRUCTION INCLUDED WITH I-5741
ROWAN | I-85 | US 29 / US 601 IN CHINA GROVE TO US 601 (JAKE ALEXANDER BOULEVARD) IN SALISBURY AND FROM SOUTH OF US 52 IN SALISBURY TO NORTH OF SR 2120 (LONG FERRY ROAD) IN SPENCER. PAVEMENT REHABILITATION. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | I-5858 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2019 | 12012000 |  |  | 12012000 | UNDER CONSTRUCTION; GARVEE BOND FUNDING: $10 MILLION FOR CONSTRUCTION - PAYBACK 2019-2033
ROWAN | MAIN STREET | "D" AVENUE TO SUNSET DRIVE | HIGHWAY | 9 | CABARRUS-ROWAN MPO | C-4908H | EXEMPT | [10 empty] | UNDER CONSTRUCTION
ROWAN | NC 152 | INTERSECTION WITH PROPOSED ACCESS ROAD EAST OF I-85 / US 601 IN CHINA GROVE. WIDEN PAVEMENT AND CONSTRUCT ROUNDABOUT. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | HE-0009 | DIVISION 9 | T |  |  |  |  | 2023 | 3900000 | 2022 | 600000 | 4500000 | ECONOMIC DEVELOPMENT PROJECT
ROWAN | NC 152 | NC 152, INTERSECTION WITH PROPOSED ACCESS ROAD EAST OF I-85 / US 601 IN CHINA GROVE. INTERMEDIATE INTERSECTION IMPROVEMENTS. WIDEN PAVEMENT AND CONSTRUCT TURN LANES FOR PHASE I OF ROADWAY IMPROVEMENTS. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | HE-0009A | DIVISION 9 | T |  |  |  |  | 2023 | 1000000 |  |  | 1000000 | CONSTRUCTION BY STATE FORCES.
ROWAN | NC 152 | WEST OF US 29 / US 601 TO EAST OF I-85 IN CHINA GROVE. REVISE INTERCHANGES WITH US 29 / US 601 AND WITH I-85, AND IMPROVE CORRIDOR. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | I-3610 | [11 empty] | INCLUDED IN I-3802 - UNDER CONSTRUCTION
ROWAN | NC 801 | REPLACE BRIDGE 790061 OVER FOURTH CREEK. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | B-5778 | HIGHWAY FUND | [10 empty] | UNDER CONSTRUCTION
ROWAN | NC 801; SR 1951 (PARKS ROAD) | NC 801 AT SR 2048 (COOL SPRINGS ROAD / WOODLEAF ROAD), SR 1951 (PARKS ROAD) AT SR 2048 (WOODLEAF ROAD) AND NC 801 AT SR 2004 (WOODLEAF BARBER ROAD / QUARRY ROAD). WIDENING, INTERSECTION REALIGNMENT, TURN LANES AND GEOMETRIC IMPROVEMENTS. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | W-5314 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
ROWAN | NEW ROUTE | SR 1211 (KIMBALL ROAD) EXTENSION, NORTH CHAPEL STREET TO SR 1221 (BOSTIAN ROAD) IN LANDIS. CONSTRUCT TWO-LANE CONNECTOR ON NEW LOCATION. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | U-5608 | DIVISION 9 | [10 empty] | UNDER CONSTRUCTION
ROWAN | NEW ROUTE | SR 2576 (BENDIX DRIVE) TO US 52 (EAST INNES STREET) AT NEWSOME ROAD IN SALISBURY. CONSTRUCT A NEW MULTILANE ROADWAY. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | U-5820 | [11 empty] | FUNDING FOR PART B REFLECTS REIMBURSEMENT TO CITY OF SALISBURY
ROWAN | NEW ROUTE | SR 2576 (BENDIX DRIVE) TO SR 1006 (FAITH ROAD) IN SALISBURY. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | U-5820A | DIVISION 9 | T |  |  |  |  | 2019 | 2609000 |  |  | 2609000 | UNDER CONSTRUCTION; BUILD NC BONDS: $2.023 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE)
ROWAN | NEW ROUTE | SR 1006 (FAITH ROAD) TO US 52 (EAST INNES STREET) IN SALISBURY. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | U-5820B | DIVISION 9 | T |  |  |  |  | 2020 | 1100000 |  |  | 1100000
ROWAN | NEW ROUTE | AIRPORT PARKWAY, SR 1710 (HARRISON ROAD) NEAR US 70 / US 601 (JAKE ALEXANDER BOULEVARD) TO SR 2539 (PEACH ORCHARD ROAD) AT US 29 IN SALISBURY. CONSTRUCT 2-LANE ROADWAY ON MULTILANE RIGHT OF WAY. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | U-5901 | DIVISION 9 | T | 2027 | 8900000 | 2027 | 6900000 | 2030 | 39502000 |  |  | 55302000
ROWAN | NEWSOME ROAD | SR 1002 (BRINGLE FERRY ROAD) TO SR 1004 (STOKES FERRY ROAD) | HIGHWAY | 9 | CABARRUS-ROWAN MPO | C-4908F | EXEMPT | [10 empty] | PROJECT DELETED AT MPO REQUEST
ROWAN | NEWSOME ROAD | CITY OF SALISBURY - CONSTRUCT BIKE LANES. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | C-5160 | EXEMPT | [10 empty] | UNDER CONSTRUCTION BY CITY OF SALISBURY
ROWAN | SR 1002 (BRINGLE FERRY ROAD) | LONG STREET TO NEWSOME ROAD | HIGHWAY | 9 | CABARRUS-ROWAN MPO | C-4908E | EXEMPT | [10 empty] | COMPLETE
ROWAN | SR 1002 (OLD CONCORD ROAD) | SR 1002 (OLD CONCORD ROAD) FROM JAKE ALEXANDER BOULEVARD IN SALISBURY TO THE CABARRUS COUNTY LINE. INSTALL PAVEMENT MARKINGS. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | HS-2009E | DIVISION 9 | HSIP |  |  |  |  | 2023 | 396000 |  |  | 396000
ROWAN | SR 1004 (STOKES FERRY ROAD) | SR 2380 (ODDIE ROAD). INTERSECTION IMPROVEMENTS. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | W-5303 | [11 empty] | UNDER CONSTRUCTION - LET WITH B-4257
ROWAN | SR 1007 (JAKE ALEXANDER BOULEVARD) | SR 1007 (JAKE ALEXANDER BOULEVARD) AT MORLAN PARK ROAD. INSTALL CONCRETE CHANNELIZATION AND LEFT-OVER WITH U-TURN BULB EAST OF MORLAN PARK ROAD. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | HS-2009D | DIVISION 9 | HSIP | 2022 | 50000 | 2022 | 20000 | 2023 | 350000 |  |  | 420000 | IN PROGRESS
ROWAN | SR 1221 (OLD BEATTY FORD ROAD) | SR 1210 (OLD BEATTY FORD ROAD) / SR 1221 (BOSTIAN ROAD) TO SR 1337 (LENTZ ROAD). RELOCATE EXISTING ROAD WITH GRADE SEPARATION OVER I-85. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | W-5516 | DIVISION 9 | [10 empty] | UNDER CONSTRUCTION
ROWAN | SR 1724 (HURLEY SCHOOL ROAD) | REPLACE BRIDGE 790066 OVER NORFOLK SOUTHERN RAILROAD. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | B-5772 | DIVISION 9 | BGOFF | 2021 | 77000 | 2021 | 31000 | 2022 | 1950000 |  |  | 2058000 | UNDER CONSTRUCTION
ROWAN | SR 1986 (MT. VERNON ROAD) | REPLACE BRIDGE 790050 OVER NAILS BRANCH. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | B-5160 | DIVISION 9 | [10 empty] | UNDER CONSTRUCTION
ROWAN | SR 2120 (LONG FERRY ROAD) | SR 2182 (I-85 SERVICE ROAD) NEAR SPENCER. CONSTRUCT RIGHT-TURN LANE ON SR 2120, AND CONSTRUCT CUL-DE-SAC, REMOVE RESIDUAL PAVEMENT AND STRENGTHEN REMAINING PAVEMENT ON SR 2182. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | U-6237 | DIVISION 9 | T |  |  | 2021 | 50000 | 2021 | 365000 |  |  | 415000 | UNDER CONSTRUCTION; ECONOMIC DEVELOPMENT PROJECT
ROWAN | SR 2528 (JULIAN ROAD) | US 601 (JAKE ALEXANDER BOULEVARD) TO SR 2667 (SUMMIT PARK DRIVE) IN SALISBURY. WIDEN TO MULTILANES. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | U-5738 | DIVISION 9 | T |  |  |  |  | 2022 | 14995000 |  |  | 14995000 | UNDER CONSTRUCTION
ROWAN | SR 2539 (PEACH ORCHARD ROAD) | REPLACE BRIDGE 790200 OVER TOWN CREEK. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | B-5769 | DIVISION 9 | [10 empty] | UNDER CONSTRUCTION
ROWAN | US 29 | NC 152 IN CHINA GROVE. RAMP AND INTERSECTION IMPROVEMENTS. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | U-6130 | REGION D | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2000000 |  |  | 4800000
ROWAN | US 29; NC 152 | REPLACE BRIDGE 790021 AND BRIDGE 790034 OVER NORFOLK SOUTHERN RAILROAD AND US 29 IN CHINA GROVE. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | B-5365 | [11 empty] | INCLUDED IN I-3802
ROWAN | US 52 | PROPOSED MISENHEIMER BYPASS TO PROPOSED ROCKWELL BYPASS. WIDEN TO MULTILANES. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | R-5860 | DIVISION 9 | T | 2027 | 7047000 | 2027 | 846000 | 2029 | 39321000 |  |  | 47214000
ROWAN | US 70 (STATESVILLE BOULEVARD) | US 601 (JAKE ALEXANDER BOULEVARD) | HIGHWAY | 9 | CABARRUS-ROWAN MPO | C-4908G | EXEMPT | [10 empty] | UNDER CONSTRUCTION
ROWAN | VARIOUS | CONSTRUCT SIDEWALKS AT SELECTED LOCATIONS IN SALISBURY. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | C-4908 | EXEMPT
ROWAN | VARIOUS | SPORTS COMPLEX, RYAN STREET TO CELEBRATION DRIVE AND SOUTH BOUNDARY STREET, HILLBORO STREET TO HILLS STREET | HIGHWAY | 9 | CABARRUS-ROWAN MPO | C-4908B | EXEMPT | [10 empty] | COMPLETE
ROWAN | VARIOUS | SALISBURY HIGH SCHOOL, ON VARIOUS STREETS AROUND HIGH SCHOOL | HIGHWAY | 9 | CABARRUS-ROWAN MPO | C-4908C | EXEMPT | [10 empty] | COMPLETE
ROWAN | VARIOUS | CITY OF SALISBURY SIGNAL SYSTEM UPGRADE. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | HL-0005 | DIVISION 9 | BGDA, L |  |  |  |  | 2022 | 429000 |  |  | 429000
ROWAN | CITY OF SALISBURY | REPLACMENT BUSES | PUBLIC TRANSIT | 9 | CABARRUS-ROWAN MPO | TA-5181 | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 8235000 | 8235000 | FUNDS AUTHORIZED IN PROGRESS
ROWAN | CITY OF SALISBURY | EXPANSION VEHICLE (ADA PARATRANSIT, ADMINISTRATION) | PUBLIC TRANSIT | 9 |  | TA-5182 | PUBLIC TRANSIT | 5339, L | [6 empty] | 2020 | 2000000 | 2000000 | FUNDS AUTHORIZED IN PROGRESS
ROWAN | CITY OF SALISBURY | PREVENTIVE MAINTENANCE FOR BUS AND BUS FACILITY, FACILITY IMPROVEMENTS AND REPAIRS, AUTOMATIC BUS WASHER, SHOP EQUIPMENT, FUELING SYSTEM, SECURITY GATE UPGRADE, | PUBLIC TRANSIT | 9 |  | TD-5302 | PUBLIC TRANSIT | 5339, L | [6 empty] | 2020 | 2025000 | 2025000
ROWAN | CITY OF SALISBURY | PREVENTIVE MAINTENANCE - BUS, FACILITIES | PUBLIC TRANSIT | 9 | CABARRUS-ROWAN MPO | TG-5232 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 3336000 | 3336000 | FUNDS AUTHORIZED IN PROGRESS
ROWAN | CITY OF SALISBURY | BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC. | PUBLIC TRANSIT | 9 | CABARRUS-ROWAN MPO | TG-5233 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 1120000 | 1120000 | FUNDS AUTHORIZED IN PROGRESS
ROWAN | CITY OF SALISBURY | ROUTINE CAPITAL - ADA SERVICES | PUBLIC TRANSIT | 9 | CABARRUS-ROWAN MPO | TG-5260 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 704000 | 704000 | FUNDS AUTHORIZED IN PROGRESS
ROWAN | CITY OF SALISBURY | AVL SYSTEM | PUBLIC TRANSIT | 9 | CABARRUS-ROWAN MPO | TG-6179 | PUBLIC TRANSIT | 5339, L | [6 empty] | 2020 | 1400000 | 1400000 | FUNDS AUTHORIZED IN PROGRESS
ROWAN | CITY OF SALISBURY | OPERATING | PUBLIC TRANSIT | 9 | CABARRUS-ROWAN MPO | TO-5135 | PUBLIC TRANSIT | 5307, L, SMAP | [6 empty] | 2020 | 3560000 | 3560000 | FUNDS AUTHORIZED IN PROGRESS
ROWAN | CITY OF SALISBURY | OPERATING - FREE FARE | PUBLIC TRANSIT | 9 | CABARRUS-ROWAN MPO | TO-5139 | PUBLIC TRANSIT | CMAQ, L | [6 empty] | 2020 | 336000 | 336000 | FUNDS AUTHORIZED IN PROGRESS
ROWAN | CITY OF SALISBURY | OPERATING ASSISTANCE | PUBLIC TRANSIT | 9 | CABARRUS-ROWAN MPO | TO-5201 | PUBLIC TRANSIT | CMAQ, SMAP | [6 empty] | 2020 | 904000 | 904000 | FUNDS AUTHORIZED IN PROGRESS
ROWAN | CITY OF SALISBURY | PLANNING ASSISTANCE - 5303 | PUBLIC TRANSIT | 9 | CABARRUS-ROWAN MPO | TP-5150 | PUBLIC TRANSIT | 5303, L, S | [6 empty] | 2020 | 170000 | 170000 | FUNDS AUTHORIZED IN PROGRESS
ROWAN | CITY OF SALISBURY | SAFETY & SECURITY MIN. 1% SET ASIDE | PUBLIC TRANSIT | 9 | CABARRUS-ROWAN MPO | TS-5133 | PUBLIC TRANSIT | 5307 | [6 empty] | 2020 | 28000 | 28000 | FUNDS AUTHORIZED IN PROGRESS
ROWAN | ROWAN COUNTY | ADMINISTRATION | PUBLIC TRANSIT | 9 | CABARRUS-ROWAN MPO | TK-6160 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 728000 | 728000 | FUNDS AUTHORIZED IN PROGRESS
ROWAN | SALISBURY TRANSIT ( CITY OF SALISBURY) | REPLACE FOUR TRANSIT BUSES THAT HAVE EXCEEDED THEIR USEFUL LIFE, AND REPLACE VEHICLE RELATED EQUIPMENT SUCH AS FARE BOXES, DESTINATION SIGNS, CAMERA SYSTEMS, AND AUTOMATED VOICE ANNUNCIATION SYSTEMS. | PUBLIC TRANSIT | 9 | CABARRUS-ROWAN MPO | TC-0023 | PUBLIC TRANSIT | 5339(b), L | [6 empty] | 2021 | 4560000 | 4560000
ROWAN | NORFOLK SOUTHERN | SALISBURY TRAIN STATION SECOND PLATFORM AND PEDESTRIAN UNDERPASS. | RAIL | 9 | CABARRUS-ROWAN MPO | P-5726A | REGION D | T |  |  |  |  | 2023 | 2500000 |  |  | 2500000 | UNDER CONSTRUCTION
ROWAN | NORFOLK SOUTHERN | SALISBURY NORFOLK SOUTHERN CROSSOVER RELOCATION. | RAIL | 9 | CABARRUS-ROWAN MPO | P-5726B | REGION D | T |  |  |  |  | 2023 | 4000000 |  |  | 4000000 | UNDER CONSTRUCTION
ROWAN | NORFOLK SOUTHERN | CITY OF SALISBURY. UPGRADE STATION BUILDING, EXPAND WAITING SPACE AND SURFACE PARKING. | RAIL | 9 | CABARRUS-ROWAN MPO | P-5733 | DIVISION 9 | L, T | 2025 | 600000 |  |  | 2026 | 2600000 |  |  | 3200000
ROWAN | RAILROAD NORFOLK SOUTHERN | NS MAINLINE IN ROWAN COUNTY. CONSTRUCT TRACK IMPROVEMENTS, SECOND PLATFORM, PEDESTRIAN UNDERPASS, SITEWORK, RETAINING WALL AND SIGNAL EQUIPMENT. | RAIL | 9 | CABARRUS-ROWAN MPO | P-5726 | REGION D | O, T |  |  |  |  | 2024 | 8599000 |  |  | 8599000 | "O" FUNDING REFLECTS PARTICIPATION BY CITY OF SALISBURY
ROWAN, CABARRUS | SR 2739 (NORTH MAIN STREET / SOUTH MAIN STREET) | SR 2000 (JACKSON PARK ROAD) / NORTH LOOP ROAD IN KANNAPOLIS TO SR 1211 (KIMBALL ROAD) IN CHINA GROVE. UPGRADE ROADWAY INCORPORATING BICYCLE LANES AND SIDEWALKS. | HIGHWAY | 9, 10 | CABARRUS-ROWAN MPO | U-6062 | DIVISION 9, 10 | T | 2028 | 28900000 | 2028 | 3900000 | 2031 | 28400000 |  |  | 61200000 | COORDINATE WITH EB-5921
RUTHERFORD | THERMAL BELT RAIL TRAIL | US 64/74A IN RUTHERFORDTON TO FORREST HUNT DRIVE. CONSTRUCT INTERSECTION IMPROVEMENTS AT SELECTED LOCATIONS ALONG RAIL CORRIDOR. | BIKE/PED | 13 | FOOTHILLS RPO | EB-5915 | DIVISION 13 | L, TA5200 |  |  |  |  | 2022 | 455000 |  |  | 455000
RUTHERFORD | THERMAL BELT RAIL TRAIL IN RUTHERFORDTON. | CONSTRUCT SIDEWALK CONNECTIONS TO THERMAL BELT RAIL TRAIL ALONG VICTORY DRIVE, ALLEN STREET/RAILROAD STREET, PINE STREET, BROADWAY, EAST LIBERTY STREET/BEAVER STREET, MAIN STREET, AND WESTVIEW STREET | BIKE/PED | 13 | FOOTHILLS RPO | EB-5966 | DIVISION 13 | L, TA5200 | 2025 | 300000 |  |  | 2026 | 750000 | 2024 | 150000 | 1200000
RUTHERFORD | NC 108 (CHARLOTTE STREET) | NC 108 (MAPLE STREET), SOUTH WASHINGTON STREET, MONFREDO STREET INTERSECTION IN RUTHERFORDTON. IMPROVE INTERSECTION. | HIGHWAY | 13 | FOOTHILLS RPO | R-5916 | NOT FUNDED | BG5200 | NOT FUNDED | 2100000 | NOT FUNDED | 200000 | NOT FUNDED | 1200000 |  |  | 3500000
RUTHERFORD | NEW ROUTE | CONSTRUCT NEW ACCESS ROAD AT RUTHERFORDTON INDUSTRIAL PARK. | HIGHWAY | 13 | FOOTHILLS RPO | HA-0005 | EXEMPT | ADHSL | 2023 | 10000 |  |  | 2023 | 265000 | 2022 | 25000 | 300000 | ARC PROJECT NO. 20187, AWARD AMOUNT = $299,843
RUTHERFORD | SR 1306 (BILLS CREEK ROAD) | REPLACE BRIDGE 800628 OVER LAKE LURE DAM AND BROAD RIVER. | HIGHWAY | 13 | FOOTHILLS RPO | B-5871 | DIVISION 13 | BGOFF | 2023 | 250000 |  |  | 2024 | 5000000 |  |  | 5250000 | TO BE LET WITH B-5876
RUTHERFORD | SR 1510 (HUDLOW ROAD) | US 221A TO NC 64. UPGRADE GUARDRAIL. | HIGHWAY | 13 | FOOTHILLS RPO | HS-2013G | DIVISION 13 | HSIP |  |  |  |  | 2022 | 497000 |  |  | 497000
RUTHERFORD | SR 2125 (HARRIS HENRIETTA ROAD) | REPLACE BRIDGE 800145 OVER FLOYDS CREEK. | HIGHWAY | 13 | FOOTHILLS RPO | B-6047 | DIVISION 13 | BGOFF | 2023 | 210000 |  |  | 2024 | 2100000 |  |  | 2310000
RUTHERFORD | SR 2241 (OAK STREET) | SR 2159 (PINE RIDGE ROAD) TO US 74. WIDEN EXISTING ROADWAY. | HIGHWAY | 13 | FOOTHILLS RPO | U-5833 | DIVISION 13 | T | 2020 | 435000 |  |  | 2020 | 7530000 | 2020 | 1050000 | 9015000 | UNDER CON. BUILD NC BOND FUNDING: $749,752 FOR PE, $338,782 FOR ROW, $2.176 M FOR CON - PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $52,371 FOR PE, PAYBACK 2021-2035 (YR 2&3 SALE); $3.666 M FOR CON, PAYBACK 2021-2035 (YR 2&3 SALE).
RUTHERFORD | US 221 | SOUTH CAROLINA STATE LINE TO NORTH OF SR 1366 (ROPER LOOP ROAD). WIDEN TO MULTI-LANES WITH BYPASS OF RUTHERFORDTON ON NEW LOCATION. | HIGHWAY | 13 | FOOTHILLS RPO | R-2233
RUTHERFORD | US 221 | SOUTH CAROLINA STATE LINE TO SOUTH OF FLOYD'S CREEK | HIGHWAY | 13 | FOOTHILLS RPO | R-2233AA | DIVISION 13 | [10 empty] | COMPLETE
RUTHERFORD | US 221 | SOUTH OF FLOYD'S CREEK TO NORTH OF US 74 BYPASS | HIGHWAY | 13 | FOOTHILLS RPO | R-2233AB | [11 empty] | COMPLETE
RUTHERFORD | US 221 | NORTH OF US 74 BYPASS TO SOUTH OF US 74 BUSINESS | HIGHWAY | 13 | FOOTHILLS RPO | R-2233BA | DIVISION 13 | T | 2024 | 12000000 | 2024 | 3200000 | 2027 | 85100000 |  |  | 100300000
RUTHERFORD | US 221 | SOUTH OF US 74 BUSINESS TO NORTH OF SR 1366 (ROPER LOOP ROAD) | HIGHWAY | 13 | FOOTHILLS RPO | R-2233BB | DIVISION 13 | T | 2021 | 20000000 |  |  | 2022 | 91412000 |  |  | 111412000 | UNDER CONSTRUCTION. ADDITIONAL FUNDING FOR RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. BUILD NC BOND FUNDING: $25M FOR CONSTRUCTION, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE)
RUTHERFORD | US 221 | NORTH OF SR 1366 (ROPER LOOP ROAD) IN RUTHERFORD COUNTY TO SR 1153 (GOOSE CREEK ROAD) IN MCDOWELL COUNTY. WIDEN TO MULTI-LANES. | HIGHWAY | 13 | FOOTHILLS RPO | R-2597
RUTHERFORD | US 221 | NORTH OF SR 1366 (ROPER LOOP ROAD) TO SR 1325 (NANNEY TOWN ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 13 | FOOTHILLS RPO | R-2597A | NOT FUNDED | NHP | NOT FUNDED | 12600000 | NOT FUNDED | 3400000 | NOT FUNDED | 69201000 |  |  | 85201000
RUTHERFORD | US 221 | SR 2201 (THUNDER ROAD) / SR 1005 (COXE ROAD) INTERSECTION. IMPROVE INTERSECTION. | HIGHWAY | 13 | FOOTHILLS RPO | R-5880 | NOT FUNDED | NHP | NOT FUNDED | 500000 | NOT FUNDED | 400000 | NOT FUNDED | 2500000 |  |  | 3400000
RUTHERFORD | US 221A (EAST MAIN STREET) | KENTUCKY STREET/OAKLAND ROAD INTERSECTION IN RUTHERFORDTON. IMPROVE INTERSECTION | HIGHWAY | 13 | FOOTHILLS RPO | R-5918 | NOT FUNDED | BG5200 | NOT FUNDED | 3100000 | NOT FUNDED | 400000 | NOT FUNDED | 3100000 |  |  | 6600000
RUTHERFORD | US 64 (EAST MOUNTAIN STREET) | NORTH WASHINGTON STREET INTERSECTION IN RUTHERFORDTON. IMPROVE INTERSECTION. | HIGHWAY | 13 | FOOTHILLS RPO | R-5917 | NOT FUNDED | BG5200 | NOT FUNDED | 1400000 | NOT FUNDED | 300000 | NOT FUNDED | 900000 |  |  | 2600000
RUTHERFORD | US 74 | REPLACE BRIDGE 800083 AND BRIDGE 800084 OVER SECOND BROAD RIVER. | HIGHWAY | 13 | FOOTHILLS RPO | B-5876 | STATEWIDE MOBILITY | HFB |  |  |  |  | 2023 | 9799000 |  |  | 9799000 | TO BE LET WITH B-5871. RIGHT-OF-WAY IN PROGRESS
RUTHERFORD | RUTHERFORD COUNTY | ADMINISTRATION | PUBLIC TRANSIT | 13 | FOOTHILLS RPO | TK-6161 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 788000 | 788000 | FUNDS AUTHORIZED IN PROGRESS
RUTHERFORD, BURKE, MITCHELL, YANCEY | VARIOUS | VARIOUS SR LOCATIONS. INSTALL LONG LIFE PAVEMENT MARKINGS. | HIGHWAY | 13 | FOOTHILLS RPO, GREATER HICKORY MPO, HIGH COUNTRY RPO | W-5813B | DIVISION 13 | HSIP |  |  |  |  | 2022 | 1600000 |  |  | 1600000
RUTHERFORD, McDOWELL | US 221 | SR 1325 (NANNEY TOWN ROAD) TO SR 1781 (POLLY SPROUT ROAD) NORTHERN INTERSECTION. | HIGHWAY | 13 | FOOTHILLS RPO | R-2597B | NOT FUNDED | NHP | NOT FUNDED | 7700000 | NOT FUNDED | 1800000 | NOT FUNDED | 42400000 |  |  | 51900000
SAMPSON | CLINTON SAMPSON COUNTY AIRPORT (CTZ) | OVERLAY RUNWAY TO ACCOMMODATE LARGER AIRCRAFT. | AVIATION | 3 | MID-CAROLINA RPO | AV-5823 | DIVISION 3 | T |  |  |  |  | 2025 | 1904000 |  |  | 1904000
SAMPSON | BEAMAN STREET | NORTH BOULEVARD TO SAMPSON REGIONAL MEDICAL CENTER IN CLINTON. CONSTRUCT SIDEWALK. | BIKE/PED | 3 | MID-CAROLINA RPO | EB-6011 | NOT FUNDED | L, TA5200 | NOT FUNDED | 10000 |  |  | NOT FUNDED | 105000 | NOT FUNDED | 18000 | 133000
SAMPSON | I-40 | I-40 FROM THE JOHNSTON COUNTY LINE (MILE MARKER 340) TO THE DUPLIN COUNTY LINE (MILE MARKER 360). PAVEMENT REHABILITATION. | HIGHWAY | 3 | MID-CAROLINA RPO | HI-0011 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2028 | 22400000 |  |  | 22400000
SAMPSON | I-40 | JOHNSTON COUNTY LINE (MILE MARKER 340) TO DUPLIN COUNTY LINE (MILE MARKER 360). PAVEMENT REHABILITATION. | HIGHWAY | 3 | MID-CAROLINA RPO | I-5780 | STATEWIDE MOBILITY | NHFP, NHPIM |  |  |  |  | 2019 | 10166000 |  |  | 10166000
SAMPSON | NC 24 | REPLACE BRIDGE 810056 OVER SIX RUNS CREEK. | HIGHWAY | 3 | MID-CAROLINA RPO | B-4636 | STATEWIDE MOBILITY | BFP, HFB | 2020 | 390000 |  |  | 2023 | 5900000 |  |  | 6290000 | RIGHT-OF-WAY IN PROGRESS.
SAMPSON | NC 24 | SR 1404 (DOWDY ROAD) TO SR 1303 (MITCHELL LOOP ROAD). | HIGHWAY | 3 | MID-CAROLINA RPO | R-2303C | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
SAMPSON | NC 24 | SR 1303 (MITCHELL LOOP ROAD) TO US 421/US 701/SR 1296 (SUNSET AVENUE). | HIGHWAY | 3 | MID-CAROLINA RPO | R-2303D | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
SAMPSON | NC 24 | WEST OF SR 1262 (AIRPORT ROAD) TO EAST OF US 421. | HIGHWAY | 3 | MID-CAROLINA RPO | R-2303DA | [11 empty] | COMPLETE
SAMPSON | NC 24 | US 421/US 701/SR 1296 (SUNSET AVENUE) TO SR 1935 (CECIL ODIE ROAD). | HIGHWAY | 3 | MID-CAROLINA RPO | R-2303E | DIVISION 3 | T | 2020 | 4395000 |  |  | 2020 | 37896000 | 2020 | 5055000 | 47346000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,416,253 FOR PE, $3,411,206.30 FOR ROW, $4,631,935.65 FOR CON PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $518,490 FOR PE, $19,782,317 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE)
SAMPSON | NC 24 (SOUTHWEST BOULEVARD/MLK JR BOULEVARD) | BUTLER ROAD/TRAM ROAD. IMPROVE INTERSECTION. | HIGHWAY | 3 | MID-CAROLINA RPO | U-6126 | NOT FUNDED | NHP | NOT FUNDED | 302000 | NOT FUNDED | 126000 | NOT FUNDED | 2500000 |  |  | 2928000
SAMPSON | SR 1002 (DUNN ROAD) | REPLACE BRIDGE 810133 OVER CAESAR SWAMP. | HIGHWAY | 3 | MID-CAROLINA RPO | BR-0235 | HIGHWAY FUND | [10 empty] | UNDER CONSTRUCTION. PROJECT REPRESENTS HFB 3.R.64 PROJECT.
SAMPSON | SR 1004 (EDMOND MATTHIS ROAD) | REPLACE BRIDGE 810018 OVER CRANE CREEK. | HIGHWAY | 3 | MID-CAROLINA RPO | BR-0230 | DIVISION 3 | [10 empty] | UNDER CONSTRUCTION. PROJECT REPRESENTS HFB 3.R.78 PROJECT.
SAMPSON | SR 1206 (WRIGHT BRIDGE ROAD) | REPLACE BRIDGE 810072 OVER GREAT COHARIE CREEK. | HIGHWAY | 3 | MID-CAROLINA RPO | B-6049 | DIVISION 3 | BGOFF | 2023 | 340000 |  |  | 2023 | 3400000 |  |  | 3740000
SAMPSON | SR 1409 (OLD SALEMBURG ROAD) | REPLACE BRIDGE 810326 AND BRIDGE 810327 OVER LITTLE COHARIE CREEK AND BRIDGE 810325 OVER LITTLE COHARIE CREEK OVERFLOW. | HIGHWAY | 3 | MID-CAROLINA RPO | B-4637 | DIVISION 3 | [10 empty] | UNDER CONSTRUCTION
SAMPSON | SR 1455 (PAYTON DANIELS ROAD) | REPLACE BRIDGE 810152 OVER CAESAR SWAMP. | HIGHWAY | 3 | MID-CAROLINA RPO | BR-0236 | DIVISION 3 | [10 empty] | UNDER CONSTRUCTION. PROJECT REPRESENTS HFB 3.R.79 PROJECT.
SAMPSON | SR 1620 (TIMOTHY ROAD) | REPLACE BRIDGE 810169 OVER BIG JUNIPER RUN. | HIGHWAY | 3 | MID-CAROLINA RPO | B-5631 | DIVISION 3 | BGOFF |  |  |  |  | 2022 | 875000 |  |  | 875000
SAMPSON | SR 1703 (CHURCH ROAD) | REPLACE BRIDGE 810195 OVER MERKLE SWAMP. | HIGHWAY | 3 | MID-CAROLINA RPO | BR-0231 | HIGHWAY FUND | [10 empty] | UNDER CONSTRUCTION. PROJECT REPRESENTS HFB 3.R.77 PROJECT.
SAMPSON | SR 1703 (OLD GOLDSBORO ROAD) | REPLACE BRIDGE NO. 810348 OVER BEAVERDAM CREEK ON SR 1703 (OLD GOLDSBORO ROAD). | HIGHWAY | 3 | MID-CAROLINA RPO | BR-0122 | DIVISION 3 | DP |  |  |  |  | 2021 | 727000 |  |  | 727000 | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING.
SAMPSON | SR 1706 (KORNEGAY TOWN ROAD) | REPLACE BRIDGE 810214 OVER KILL SWAMP. | HIGHWAY | 3 | MID-CAROLINA RPO | B-5651 | DIVISION 3 | [10 empty] | UNDER CONSTRUCTION
SAMPSON | SR 1804 (HOUSES MILL ROAD) | REPLACE BRIDGE NO. 810178 OVER SEVENMILE SWAMP ON SR 1804 (HOUSES MILL ROAD). | HIGHWAY | 3 | MID-CAROLINA RPO | BR-0121 | DIVISION 3 | DP |  |  |  |  | 2021 | 1400000 |  |  | 1400000 | UNDER CONSTRUCTION. DP FUNDS REPRESENT FEDERAL BUILD GRANT FUNDING.
SAMPSON | SR 1817 (BRADSHAW ROAD) | REPLACE BRIDGE 810188 OVER WARD SWAMP. | HIGHWAY | 3 | MID-CAROLINA RPO | B-5310 | DIVISION 3 | BGOFF | 2023 | 150000 |  |  | 2024 | 1500000 |  |  | 1650000
SAMPSON | SR 1904 (PINE RIDGE ROAD) | REPLACE BRIDGE 810248 OVER SIX RUNS CREEK. | HIGHWAY | 3 | MID-CAROLINA RPO | B-5621 | DIVISION 3 | BGOFF | 2021 | 154000 |  |  | 2022 | 2500000 |  |  | 2654000
SAMPSON | US 13 | REPLACE BRIDGE 810009 OVER SOUTH RIVER OVERFLOW. | HIGHWAY | 3 | MID-CAROLINA RPO | B-4635 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 2250000 |  |  | 2250000
SAMPSON | SAMPSON COUNTY | ADMINISTRATION | PUBLIC TRANSIT | 3 | MID-CAROLINA RPO | TK-6162 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 632000 | 632000 | FUNDS AUTHORIZED IN PROGRESS
SAMPSON, CUMBERLAND | NC 24 | SR 1853 (JOHN NUNNERY ROAD) IN CUMBERLAND COUNTY TO SR 1404 (DOWDY ROAD) IN SAMPSON COUNTY. | HIGHWAY | 3, 6 | MID-CAROLINA RPO | R-2303B | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
SAMPSON, CUMBERLAND, DUPLIN | NC 24 | WEST OF SR 1006 (MAXWELL ROAD/CLINTON ROAD) IN CUMBERLAND COUNTY TO I-40 IN DUPLIN COUNTY AT WARSAW. FOUR LANES DIVIDED, PART ON NEW LOCATION. | HIGHWAY | 3, 6 | MID-CAROLINA RPO, FAYETTEVILLE AREA MPO, EASTERN CAROLINA RPO | R-2303
SAMPSON, DUPLIN | NC 24 | SR 1935 (CECIL ODIE ROAD) IN SAMPSON COUNTY TO I-40 IN DUPLIN COUNTY. | HIGHWAY | 3 | MID-CAROLINA RPO, EASTERN CAROLINA RPO | R-2303F | NOT FUNDED | T | NOT FUNDED | 16800000 | NOT FUNDED | 1960000 | NOT FUNDED | 276700000 |  |  | 295460000 | PLANNING/DESIGN IN PROGRESS.
SCOTLAND | LAURINBURG- MAXTON AIRPORT (MEB) | CONSTRUCT 1500 FT RUNWAY EXTENSION. | AVIATION | 8 | LUMBER RIVER RPO | AV-5854 | DIVISION 8 | T |  |  |  |  | 2024 | 6390000 |  |  | 6390000
SCOTLAND | SR 1107 (ATKINSON STREET) | US 401 BUSINESS (SOUTH MAIN STREET) TO WEST VANCE STREET IN LAURINBURG. CONSTRUCT SIDEWALKS. | BIKE/PED | 8 | LUMBER RIVER RPO | EB-5865 | DIVISION 8 | L, TA5200 | 2023 | 193000 |  |  | 2024 | 379000 | 2022 | 76000 | 648000
SCOTLAND | SR 1108 (WEST BOULEVARD) | SR 1105 (TURNPIKE ROAD) TO SUNSET DRIVE IN LAURINBURG. CONSTRUCT SIDEWALK ON WEST SIDE, AND PROVIDE PEDESTRIAN ACCOMMODATIONS AT US 15 / US 401 / US 501 INTERSECTION AND ACROSS US 74. | BIKE/PED | 8 | LUMBER RIVER RPO | EB-5872 | DIVISION 8 | [10 empty] | PROJECT LENGTH REFLECTS PARTS A ONLY- PART B IS NON-STI PROJECT; EB 5872C PROJECT BREAK DELETED WORK TO BE ACCOMPLISHED UNDER EB-5872A.
SCOTLAND | SR 1108 (WEST BOULEVARD) | SR 1105 (TURNPIKE ROAD) TO GLASGOW DRIVE AND EAST OF US 15 / US 401 / US 501 TO SUNSET DRIVE IN LAURINBURG. | BIKE/PED | 8 | LUMBER RIVER RPO | EB-5872A | DIVISION 8 | L, TA5200 | 2024 | 166000 |  |  | 2024 | 436000 |  |  | 602000
SCOTLAND | SR 1108 (WEST BOULEVARD) | GLASGOW DRIVE TO EAST OF US 15 / US 401 / US 501 (MCCOLL ROAD) IN LAURINBURG. | BIKE/PED | 8 | LUMBER RIVER RPO | EB-5872B | EXEMPT
SCOTLAND | US 401 BUSINESS (SOUTH MAIN STREET | PLAZA ROAD TO CREPE MYRTLE AVENUE IN LAURINBURG. CONSTRUCT SIDEWALKS | BIKE/PED | 8 | LUMBER RIVER RPO | EB-6015B | DIVISION 8 | L, TA5200 | 2024 | 52000 |  |  | 2025 | 273000 | 2023 | 55000 | 380000
SCOTLAND | US 401 BUSINESS (SOUTH MAIN STREET) | SR 1674 (LAUCHWOOD DRIVE) TO CREPE MYRTLE AVENUE IN LAURINBURG. CONSTRUCT SIDEWALKS. | BIKE/PED | 8 | LUMBER RIVER RPO | EB-6015
SCOTLAND | US 401 BUSINESS (SOUTH MAIN STREET) | SR 1674 (LAUCHWOOD DRIVE) TO PLAZA ROAD IN LAURINBURG. CONSTRUCT SIDEWALKS | BIKE/PED | 8 | LUMBER RIVER RPO | EB-6015A | DIVISION 8 | L, TA5200 | 2023 | 76000 |  |  | 2024 | 330000 | 2022 | 66000 | 472000
SCOTLAND | COMMONWEALTH AVENUE | REPLACE BRIDGE 820081 OVER LEITH CREEK WITH CULVERT IN LAURINBURG. | HIGHWAY | 8 | LUMBER RIVER RPO | B-5003 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION BY CITY OF LAURINBURG - MUNICIPAL BRIDGE
SCOTLAND | US 15 / US 401 | SOUTH CAROLINA STATE LINE TO SOUTH OF SR 1105 (TURNPIKE ROAD) IN LAURINBURG. WIDEN TO MULTILANES. | HIGHWAY | 8 | LUMBER RIVER RPO | U-5977 | REGION E | T | 2028 | 4800000 | 2028 | 2900000 | 2030 | 19400000 |  |  | 27100000
SCOTLAND | US 15 / US 501 | NC 144 INTERSECTION. CONSTRUCT ROUNDABOUT | HIGHWAY | 8 | LUMBER RIVER RPO | W-5208MA | REGION E | [10 empty] | UNDER CONSTRUCTION
SCOTLAND | US 74 | RICHMOND COUNTY LINE TO SR 1363. UPGRADE GUARDRAIL. | HIGHWAY | 8 | LUMBER RIVER RPO | HS-2008A | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2021 | 360000 |  |  | 360000 | UNDER CONSTRUCTION
SCOTLAND | US 74 / FUTURE I-74 WESTBOUND | EXITS 183 AND 184 IN LAURINBURG. UPGRADE SIGNING AND PAVEMENT MARKINGS. | HIGHWAY | 8 | LUMBER RIVER RPO | W-5808A | STATEWIDE MOBILITY | [10 empty] | PROJECT DELETED AT REQUEST OF TRANSPORTATION MOBILITY AND SAFETY DIVISION. PROJECT WILL UTILZE NON-STIP FUNDS.
SCOTLAND | SCOTLAND COUNTY | ADMINISTRATION | PUBLIC TRANSIT | 8 | LUMBER RIVER RPO | TK-6163 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 460000 | 460000 | FUNDS AUTHORIZED IN PROGRESS
SCOTLAND | CSX | RAIL SPUR FOR INDUSTRIAL ACCESS. CONSTRUCT SPINE TRACK AND TURNOUTS, AND REHABILITATE EXISTING TRACK SECTIONS. | RAIL | 8 | LUMBER RIVER RPO | P-5724 | DIVISION 8 | [10 empty] | UNDER CONSTRUCTION; ECONOMIC DEVELOPMENT PROJECT; "O" FUNDING INCLUDES PARTICIPATION BY NORTH CAROLINA RAILROAD, LAURINBURG-MAXTON AIRPORT, RAIL INDUSTRIIAL ACCESS PROGRAM, AND COMMUNITY DEVELOPMENT BLOCK GRANT PROGRAM
SCOTLAND, RICHMOND | US 74 / FUTURE I-74 | US 74 BUSINESS EAST OF HAMLET TO US 74 BUSINESS WEST OF LAURINBURG. UPGRADE CORRIDOR TO INTERSTATE STANDARDS. | HIGHWAY | 8 | LUMBER RIVER RPO | I-6055 | REGION E | T | 2027 | 27600000 | 2027 | 8584000 | 2030 | 187500000 |  |  | 223684000
STANLY | STANLY COUNTY AIRPORT (VUJ) | ACQUIRE LAND FOR EXPANSION AND PERFORM ESA TO DETERMINE STATUS OF STRUCTURES ON PROPERTY. CLEAR AND GRUBB LAND REQUIRED FOR EXPANSION AND DEMOLISH HOUSES ON PROPERTY ACQUIRED. | AVIATION | 10 | ROCKY RIVER RPO | AV-5817 | DIVISION 10 | T | 2025 | 2860000 |  |  | 2027 | 1776000 |  |  | 4636000
STANLY | ALBEMARLE | US 52, WEST MAIN STREET TO SNUGGES STREET. CONSTRUCT SIDEWALK ON EAST SIDE OF ROAD | BIKE/PED | 10 | ROCKY RIVER RPO | EB-5841 | DIVISION 10 | L, TA5200 | 2025 | 250000 |  |  | 2026 | 250000 | 2024 | 50000 | 550000
STANLY | NORTH SECOND AVENUE | PARK RIDGE TO SALISBURY AVENUE. CONSTRUCT SIDEWALKS, ADA RAMPS, AND CROSSWALKS. | BIKE/PED | 10 | ROCKY RIVER RPO | EB-5972 | DIVISION 10 | L, TA5200 | 2026 | 130000 |  |  | 2027 | 450000 | 2024 | 10000 | 590000
STANLY | SALISBURY AVENUE | US 52 TO NORTH SECOND STREET. CONSTRUCT BIKE LANES. | BIKE/PED | 10 | ROCKY RIVER RPO | EB-5973 | DIVISION 10 | L, TA5200 |  |  |  |  | 2025 | 120000 | 2024 | 12000 | 132000
STANLY | STANFIELD | NC 200, NORTH LOVE CHAPEL TO CARMEL ROAD. CONSTRUCT SIDEWALKS AND ADA RAMPS ON WEST SIDE OF STREET. | BIKE/PED | 10 | ROCKY RIVER RPO | EB-5857 | DIVISION 10 | L, TALT5 | 2022 | 80000 |  |  | 2023 | 475000 | 2021 | 95000 | 650000
STANLY | US 52 BUSINESS RAMP | NC 24/27 TO SECOND STREET. CONSTRUCT SIDEWALK ALONG US 52 BUSINESS RAMP | BIKE/PED | 10 | ROCKY RIVER RPO | EB-5974 | NOT FUNDED | L, TA5200 | NOT FUNDED | 30000 |  |  | NOT FUNDED | 200000 | NOT FUNDED | 30000 | 260000
STANLY | NC 24/NC 27 | SR 1963 (ST. MARTIN ROAD) IN ALBEMARLE TO NC 73. WIDEN TO MULTI- LANES. (COORDINATE WITH B-4974). | HIGHWAY | 10 | ROCKY RIVER RPO | R-2530
STANLY | NC 24-27 | SR 1963 (ST. MARTIN ROAD) TO BIRD ROAD IN ALBEMARLE | HIGHWAY | 10 | ROCKY RIVER RPO | R-2530A | [11 empty] | COMPLETE
STANLY | NC 24-27 | BIRD ROAD IN ALBEMARLE TO WEST OF THE PEE DEE RIVER | HIGHWAY | 10 | ROCKY RIVER RPO | R-2530B | REGION E | T | 2020 | 5700000 | 2020 | 3600000 | 2020 | 91695000 | 2020 | 7800000 | 108795000 | BUILD NC BOND: $5.911 M FOR PE, $4.431 M FOR ROW, $2.788 M FOR UTL, $11.666 M FOR CON, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $137,639 FOR PE, $40.927 M FOR CON, PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
STANLY | SR 1434 (ROGERS ROAD) | REPLACE BRIDGE 830042 OVER BIG BEAR CREEK. | HIGHWAY | 10 | ROCKY RIVER RPO | B-5811 | DIVISION 10 | BGOFF | 2025 | 15000 |  |  | 2026 | 600000 |  |  | 615000
STANLY | SR 1917 (BETHLEHEM CHURCH ROAD) | REPLACE BRIDGE 830102 OVER LONG CREEK. | HIGHWAY | 10 | ROCKY RIVER RPO | B-6046 | DIVISION 10 | BGOFF | 2022 | 145000 |  |  | 2023 | 1700000 |  |  | 1845000
STANLY | VARIOUS | VARIOUS IMPROVEMENTS AROUND TOWN OF OAKBORO. | HIGHWAY | 10 | ROCKY RIVER RPO | R-5965 | [11 empty] | ECONOMIC DEVELOPMENT PROJECT
STANLY | VARIOUS | NC 205/SR 1108 (LIGHTHOUSE ROAD)/SR 1109 (BUSTER ROAD) INTERSECTION AND SR 1110 (SWIFT ROAD) AT CHARLOTTE PIPE FACILITY. IMPROVE INTERSECTIONS. | HIGHWAY | 10 | ROCKY RIVER RPO | R-5965A | DIVISION 10 | T | 2021 | 75000 |  |  | 2021 | 2405000 |  |  | 2480000
STANLY | VARIOUS | SR 1107 (SILVER ROAD)/SR 1108 (LIGHTHOUSE ROAD) AND SR 1107 (SILVER ROAD)/SR 1110 (SWIFT ROAD) INTERSECTIONS. IMPROVE INTERSECTIONS. SR 1107 (SILVER ROAD), SR 1108 (LIGHTHOUSE ROAD) AND SR 1110 (SWIFT ROAD). VARIOUS ROADWAY IMPROVEMENTS INCLUDING FULL D | HIGHWAY | 10 | ROCKY RIVER RPO | R-5965B | DIVISION 10 | T | 2021 | 250000 |  |  | 2023 | 1586000 |  |  | 1836000
STANLY | SCUSA TRANSPORTATION | ADMINISTRATION | PUBLIC TRANSIT | 10 | ROCKY RIVER RPO | TK-6164 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 904000 | 904000 | FUNDS AUTHORIZED IN PROGRESS
STATEWIDE | VARIOUS | NATIONAL RECREATIONAL TRAILS. | BIKE/PED | STATEWIDE | STATEWIDE PROJECT | E-4018 | DIVISION SW | TA |  |  |  |  | 2020 | 19200000 |  |  | 19200000 | IN PROGRESS
STATEWIDE | VARIOUS | STATEWIDE PEDESTRIAN FACILITIES PROGRAM. | BIKE/PED | STATEWIDE | STATEWIDE PROJECT | EB-3314 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
STATEWIDE | VARIOUS | ROADWAY IMPROVEMENTS FOR BICYCLE SAFETY ON STATE AND LOCAL DESIGNATED BIKE ROUTES. | BIKE/PED | STATEWIDE | STATEWIDE PROJECT | EB-4411 | [11 empty] | IN PROGRESS
STATEWIDE | VARIOUS | SAFE ROUTES TO SCHOOL EDUCATION. | BIKE/PED | STATEWIDE | STATEWIDE PROJECT | EB-6033 | DIVISION SW | [10 empty] | IN PROGRESS
STATEWIDE | VARIOUS | RAILS TO TRAILS PROGRAM | BIKE/PED | STATEWIDE | STATEWIDE PROJECT | EB-6037 | DIVISION SW | [10 empty] | LOCAL FUNDS REPRESENT LOCAL MATCH FOR RIGHT-OF-WAY AND CONSTRUCTION OF TRAILS BY LOCAL GOVERNMENTS.
STATEWIDE | VARIOUS | SIDEWALK PROGRAM IN ALL FOURTEEN HIGHWAY DIVISIONS. | BIKE/PED | STATEWIDE | STATEWIDE PROJECT | ER-2971 | PRE-STI (TRANSITION) | [10 empty] | IN PROGRESS - $182,000 IN STPDA FUNDS ALLOCATED TO ER-2971E
STATEWIDE | NORTH CAROLINA STATE UNIVERSITY | NORTH CAROLINA STATE UNIVERSITY SOLAR CENTER CLEAN TRANSPORTATION PROGRAM. DEVELOP AND ADMINISTER A SEVEN YEAR CLEAN FUEL-ADVANCED TECHNOLOGY REBATE PROGRAM IN ALL CMAQ ELIGIBLE COUNTIES TO REDUCE EMISSIONS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | C-4902 | EXEMPT | [10 empty] | IN PROGRESS BY NORTH CAROLINA STATE UNIVERSITY
STATEWIDE | NORTH CAROLINA STATE UNIVERSITY | PHASE 2 OF IMPLEMENTATION | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | C-4902A | EXEMPT
STATEWIDE | VARIOUS | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | B-8888 | DIVISION SW | BGOFF |  |  |  |  | 2022 | 0
STATEWIDE | VARIOUS | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | B-8888DIV | DIVISION SW | BFP |  |  |  |  | 2022 | 0
STATEWIDE | VARIOUS | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | B-8888REG | REGION SW | BFP |  |  |  |  | 2022 | 0
STATEWIDE | VARIOUS | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | B-8888SW | STATEWIDE MOBILITY | BFP |  |  |  |  | 2022 | 0
STATEWIDE | VARIOUS | BRIDGE INSPECTION PROGRAM. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | B-9999 | [11 empty] | IN PROGRESS
STATEWIDE | VARIOUS | BRIDGE INSPECTION PROGRAM. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | B-9999DIV | DIVISION SW | BG | [6 empty] | 2020 | 7200000 | 7200000
STATEWIDE | VARIOUS | BRIDGE INSPECTION PROGRAM. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | B-9999REG | REGION SW | BG | [6 empty] | 2020 | 7200000 | 7200000
STATEWIDE | VARIOUS | BRIDGE INSPECTION PROGRAM. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | B-9999SW | STATEWIDE MOBILITY | BG | [6 empty] | 2020 | 9600000 | 9600000
STATEWIDE | VARIOUS | ESTABLISH BRIDGE MANAGEMENT SYSTEM. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | BK-5100 | DIVISION SW | [10 empty] | IN PROGRESS
STATEWIDE | VARIOUS | DECK PRESERVATION AT 15 SELECTED LOCATIONS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | BK-5101 | DIVISION SW | [10 empty] | UNDER CONSTRUCTION
STATEWIDE | VARIOUS | BRIDGE PAINTING AT 19 SELECTED LOCATIONS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | BK-5102 | DIVISION SW | [10 empty] | IN PROGRESS
STATEWIDE | VARIOUS | BRIDGE PRESERVATION ISSUES AT SELECTED SITES. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | BP-5500
STATEWIDE | VARIOUS | BRIDGE PRESERVATION ISSUES AT SELECTED SITES. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | BP-5500DIV | DIVISION SW
STATEWIDE | VARIOUS | BRIDGE PRESERVATION ISSUES AT SELECTED SITES. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | BP-5500REG | REGION SW
STATEWIDE | VARIOUS | BRIDGE PRESERVATION ISSUES AT SELECTED SITES. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | BP-5500SW | STATEWIDE MOBILITY
STATEWIDE | VARIOUS | DEPARTMENT OF MOTOR VEHICLES (DMV), VEHICLE EMISSION COMPLIANCE SYSTEM. UPGRADE NORTH CAROLINA'S MOTOR VEHICLE EMISSIONS INSPECTION AND MAINTENANCE (I/M) PROGRAM. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | C-3600 | EXEMPT | [10 empty] | IN PROGRESS BY DEPARTMENT OF MOTOR VEHICLES
STATEWIDE | VARIOUS | STATEWIDE CMAQ PROJECTS TO IMPROVE AIR QUALITY WITHIN NONATTAINMENT AND MAINTENANCE AREAS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | C-5600 | EXEMPT | CMAQ, S(M) |  |  |  |  | 2023 | 1648000 |  |  | 1648000
STATEWIDE | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. CONDUCT A CLEAN-FUEL ADVANCED TECHNOLOGY OUTREACH AND AWARENESS PROGRAM, INCLUDING EMISSIONS-REDUCING SUB-AWARDS, IN ALL CMAQ-ELIGIBLE COUNTIES. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | C-5702 | EXEMPT
STATEWIDE | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. CONDUCT A CLEAN-FUEL ADVANCED TECHNOLOGY OUTREACH AND AWARENESS PROGRAM IN ALL CMAQ-ELIGIBLE COUNTIES. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | C-5702A | EXEMPT | [10 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. EMISSIONS-REDUCING SUB-AWARDS IN ALL CMAQ-ELIGIBLE COUNTIES. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | C-5702B | EXEMPT | [10 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. EMISSIONS-REDUCING SUB-AWARDS IN ALL CMAQ-ELIGIBLE COUNTIES. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | C-5702C | EXEMPT
STATEWIDE | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. CONDUCT A CLEAN-FUEL ADVANCED TECHNOLOGY OUTREACH AND AWARENESS PROGRAM IN ALL CMAQ-ELIGIBLE COUNTIES. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | C-5702D | EXEMPT | CMAQ, L | [6 empty] | 2022 | 3258000 | 3258000
STATEWIDE | VARIOUS | NORTH CAROLINA CLEAN ENERGY TECHNOLOGY CENTER. EMISSIONS-REDUCING SUB-AWARDS IN ALL CMAQ-ELIGIBLE COUNTIES. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | C-5702E | EXEMPT | CMAQ, L | [6 empty] | 2022 | 5584000 | 5584000
STATEWIDE | VARIOUS | VEGETATION MANAGEMENT - CLEAR ZONE IMPROVEMENT AND MANAGEMENT STATEWIDE. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | ER-5600 | DIVISION SW | STPE |  |  |  |  | 2022 | 4000000 |  |  | 4000000 | IN PROGRESS
STATEWIDE | VARIOUS | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | HB-8888 | DIVISION SW | BGOFF |  |  |  |  | 2024 | 405732000 |  |  | 405732000
STATEWIDE | VARIOUS | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | HB-8888DIV | DIVISION SW | BFP |  |  |  |  | 2024 | 200242000 |  |  | 200242000
STATEWIDE | VARIOUS | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | HB-8888REG | REGION SW | BFP |  |  |  |  | 2024 | 200242000 |  |  | 200242000
STATEWIDE | VARIOUS | BRIDGE REPLACEMENT PROGRAM - UNPROGRAMMED BALANCE | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | HB-8888SW | STATEWIDE MOBILITY | BFP |  |  |  |  | 2024 | 266989000 |  |  | 266989000
STATEWIDE | VARIOUS | BRIDGE INSPECTION PROGRAM INSPECTIONS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | HB-9999A
STATEWIDE | VARIOUS | BRIDGE INSPECTION PROGRAM INSPECTIONS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | HB-9999ADIV | DIVISION SW | T | [6 empty] | 2021 | 117000000 | 117000000
STATEWIDE | VARIOUS | BRIDGE INSPECTION PROGRAM INSPECTIONS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | HB-9999AREG | REGION SW | T | [6 empty] | 2021 | 117000000 | 117000000
STATEWIDE | VARIOUS | BRIDGE INSPECTION PROGRAM INSPECTIONS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | HB-9999ASW | STATEWIDE MOBILITY | T | [6 empty] | 2021 | 156000000 | 156000000
STATEWIDE | VARIOUS | BRIDGE INSPECTION PROGRAM STRUCTURE INVENTORY AND APPRAISAL. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | HB-9999B
STATEWIDE | VARIOUS | BRIDGE INSPECTION PROGRAM STRUCTURE INVENTORY AND APPRAISAL. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | HB-9999BDIV | DIVISION SW | T | [6 empty] | 2021 | 9000000 | 9000000
STATEWIDE | VARIOUS | BRIDGE INSPECTION PROGRAM ANALYSIS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | HB-9999C
STATEWIDE | VARIOUS | BRIDGE INSPECTION PROGRAM ANALYSIS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | HB-9999CDIV | DIVISION SW | T | [6 empty] | 2021 | 11700000 | 11700000
STATEWIDE | VARIOUS | BRIDGE INSPECTION PROGRAM ANALYSIS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | HB-9999CREG | REGION SW | T | [6 empty] | 2021 | 11700000 | 11700000
STATEWIDE | VARIOUS | BRIDGE INSPECTION PROGRAM ANALYSIS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | HB-9999CSW | STATEWIDE MOBILITY | T | [6 empty] | 2021 | 15600000 | 15600000
STATEWIDE | VARIOUS | INTERSTATE MAINTENANCE PROGRAM - UNPROGRAMMED BALANCE | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | HI-9999 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 807412000 |  |  | 807412000
STATEWIDE | VARIOUS | NATIONAL ELECTRIC VEHICLE INFRASTRUCTURE PROGRAM - UNPROGRAMMED BALANCE | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | HO-9999 | DIVISION SW | NEVI |  |  |  |  | 2022 | 244800000 |  |  | 244800000
STATEWIDE | VARIOUS | HIGHWAY SAFETY IMPROVEMENT PROGRAM - UNPROGRAMMED BALANCE | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | HS-9999
STATEWIDE | VARIOUS | HIGHWAY SAFETY IMPROVEMENT PROGRAM - UNPROGRAMMED BALANCE | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | HS-9999DIV | DIVISION SW | HSIP |  |  |  |  | 2024 | 282185000 |  |  | 282185000
STATEWIDE | VARIOUS | HIGHWAY SAFETY IMPROVEMENT PROGRAM - UNPROGRAMMED BALANCE | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | HS-9999REG | REGION SW | HSIP |  |  |  |  | 2024 | 282185000 |  |  | 282185000
STATEWIDE | VARIOUS | HIGHWAY SAFETY IMPROVEMENT PROGRAM - UNPROGRAMMED BALANCE | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | HS-9999SW | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2024 | 376246000 |  |  | 376246000
STATEWIDE | VARIOUS | PHOTOGRAMMETRY, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0219 | STATEWIDE MOBILITY
STATEWIDE | VARIOUS | PHOTOGRAMMETRY, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0219DIV | DIVISION SW | T | [6 empty] | 2020 | 1200000 | 1200000
STATEWIDE | VARIOUS | PHOTOGRAMMETRY, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0219REG | REGION SW | T | [6 empty] | 2020 | 1200000 | 1200000
STATEWIDE | VARIOUS | PHOTOGRAMMETRY, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0219SW | STATEWIDE MOBILITY | T | [6 empty] | 2020 | 1600000 | 1600000
STATEWIDE | VARIOUS | TECHNICAL SERVICES, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0360 | [11 empty] | IN PROGRESS
STATEWIDE | VARIOUS | TECHNICAL SERVICES, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0360DIV | DIVISION SW | T | [6 empty] | 2020 | 4800000 | 4800000
STATEWIDE | VARIOUS | TECHNICAL SERVICES, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0360REG | REGION SW | T | [6 empty] | 2020 | 4800000 | 4800000
STATEWIDE | VARIOUS | TECHNICAL SERVICES, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0360SW | STATEWIDE MOBILITY | T | [6 empty] | 2020 | 6400000 | 6400000
STATEWIDE | VARIOUS | STATEWIDE GEOTECHNICAL STUDIES AND INVESTIGATIONS PROJECT TO COVER NON-PROJECT SPECIFIC WORK. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0376 | [11 empty] | IN PROGRESS
STATEWIDE | VARIOUS | STATEWIDE GEOTECHNICAL STUDIES AND INVESTIGATIONS PROJECT TO COVER NON-PROJECT SPECIFIC WORK. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0376DIV | DIVISION SW | T | [6 empty] | 2020 | 4320000 | 4320000
STATEWIDE | VARIOUS | STATEWIDE GEOTECHNICAL STUDIES AND INVESTIGATIONS PROJECT TO COVER NON-PROJECT SPECIFIC WORK. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0376REG | REGION SW | T | [6 empty] | 2020 | 4320000 | 4320000
STATEWIDE | VARIOUS | STATEWIDE GEOTECHNICAL STUDIES AND INVESTIGATIONS PROJECT TO COVER NON-PROJECT SPECIFIC WORK. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0376SW | STATEWIDE MOBILITY | T | [6 empty] | 2020 | 5670000 | 5670000
STATEWIDE | VARIOUS | SCOUR EVALUATION PROGRAM OF EXISTING BRIDGES. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0379 | DIVISION SW | [10 empty] | IN PROGRESS
STATEWIDE | VARIOUS | STRUCTURE DESIGN, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0391 | [11 empty] | IN PROGRESS
STATEWIDE | VARIOUS | STRUCTURE DESIGN, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0391DIV | DIVISION SW | T | [6 empty] | 2020 | 1920000 | 1920000
STATEWIDE | VARIOUS | STRUCTURE DESIGN, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0391REG | REGION SW | T | [6 empty] | 2020 | 1920000 | 1920000
STATEWIDE | VARIOUS | STRUCTURE DESIGN, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0391SW | STATEWIDE MOBILITY | T | [6 empty] | 2020 | 2560000 | 2560000
STATEWIDE | VARIOUS | HYDRAULICS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0392 | [11 empty] | IN PROGRESS
STATEWIDE | VARIOUS | HYDRAULICS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0392DIV | DIVISION SW | T | [6 empty] | 2020 | 768000 | 768000
STATEWIDE | VARIOUS | HYDRAULICS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0392REG | REGION SW | T | [6 empty] | 2020 | 768000 | 768000
STATEWIDE | VARIOUS | HYDRAULICS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0392SW | STATEWIDE MOBILITY | T | [6 empty] | 2020 | 1024000 | 1024000
STATEWIDE | VARIOUS | MUNICIPAL BRIDGE INSPECTION PROGRAM | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0414 |  | BGOFF, L | [6 empty] | 2020 | 16000000 | 16000000
STATEWIDE | VARIOUS | STORM WATER RUNOFF. RESEARCH, DESIGN, CONSTRUCT, MAINTAIN AND MONITOR STORM WATER DRAINAGE FROM 50 BRIDGES OVER WATERWAYS. (HB 2346, SECTION 25.18) | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0418 | DIVISION SW | [10 empty] | UNDER CONSTRUCTION
STATEWIDE | VARIOUS | STATEWIDE LANDSCAPE PLANS FOR STIP CONSTRUCTION PROJECTS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0451
STATEWIDE | VARIOUS | STATEWIDE LANDSCAPE PLANS FOR STIP CONSTRUCTION PROJECTS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0451DIV | DIVISION SW | T | [6 empty] | 2020 | 336000 | 336000
STATEWIDE | VARIOUS | STATEWIDE LANDSCAPE PLANS FOR STIP CONSTRUCTION PROJECTS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0451REG | REGION SW | T | [6 empty] | 2020 | 336000 | 336000
STATEWIDE | VARIOUS | STATEWIDE LANDSCAPE PLANS FOR STIP CONSTRUCTION PROJECTS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0451SW | STATEWIDE MOBILITY | T | [6 empty] | 2020 | 448000 | 448000
STATEWIDE | VARIOUS | TOLLING/FINANCIAL FEASIBILITY STUDIES. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0452 | STATEWIDE MOBILITY | T | [6 empty] | 2020 | 3200000 | 3200000
STATEWIDE | VARIOUS | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0479
STATEWIDE | VARIOUS | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS SAP INTEGRATION PROJECT. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0479A
STATEWIDE | VARIOUS | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS SAP INTEGRATION PROJECT. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0479ADIV | DIVISION SW | T | [6 empty] | 2020 | 7200000 | 7200000
STATEWIDE | VARIOUS | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS SAP INTEGRATION PROJECT. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0479AREG | REGION SW | T | [6 empty] | 2020 | 7200000 | 7200000
STATEWIDE | VARIOUS | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS SAP INTEGRATION PROJECT. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0479ASW | STATEWIDE MOBILITY | T | [6 empty] | 2020 | 9600000 | 9600000
STATEWIDE | VARIOUS | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS ENVIRONMENTAL ANALYSIS UNIT GROUPS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0479B
STATEWIDE | VARIOUS | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS ENVIRONMENTAL ANALYSIS UNIT GROUPS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0479BDIV | DIVISION SW | T | [6 empty] | 2020 | 2400000 | 2400000
STATEWIDE | VARIOUS | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS ENVIRONMENTAL ANALYSIS UNIT GROUPS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0479BREG | REGION SW | T | [6 empty] | 2020 | 2400000 | 2400000
STATEWIDE | VARIOUS | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR ATLAS ENVIRONMENTAL ANALYSIS UNIT GROUPS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0479BSW | STATEWIDE MOBILITY | T | [6 empty] | 2020 | 3200000 | 3200000
STATEWIDE | VARIOUS | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0479DIV | DIVISION SW | T | [6 empty] | 2020 | 24000000 | 24000000
STATEWIDE | VARIOUS | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0479REG | REGION SW | T | [6 empty] | 2020 | 24000000 | 24000000
STATEWIDE | VARIOUS | STATEWIDE PROJECT DEVELOPMENT AND ENVIRONMENTAL ANALYSIS, PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0479SW | STATEWIDE MOBILITY | T | [6 empty] | 2020 | 32000000 | 32000000
STATEWIDE | VARIOUS | TRANSPORTATION PROGRAM MANAGEMENT UNIT (TPMU) OVERSIGHT FOR LOCALLY-ADMINISTERED PROJECTS INCLUDING PREPARATION OF AGREEMENTS AND FUNDING AUTHORIZATION REQUESTS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0505 | DIVISION SW | T | [6 empty] | 2020 | 4800000 | 4800000
STATEWIDE | VARIOUS | RIGHT-OF-WAY BRANCH, REVIEW OF LOCAL PUBLIC AGENCY (LPA) PROJECTS BY THE APPRAISAL SECTION. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0515 | DIVISION SW | T | 2020 | 4000000 | [6 empty] | 4000000
STATEWIDE | VARIOUS | TRANSPORTATION PLANNING BRANCH, TRAFFIC FORECASTING FOR MISCELLANEOUS PROJECTS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0521 | [11 empty] | IN PROGRESS
STATEWIDE | VARIOUS | TRANSPORTATION PLANNING BRANCH, TRAFFIC FORECASTING FOR MISCELLANEOUS PROJECTS ON THE DIVISION TIER. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0521DIV | DIVISION SW | T | [6 empty] | 2020 | 100000 | 100000
STATEWIDE | VARIOUS | TRANSPORTATION PLANNING BRANCH, TRAFFIC FORECASTING FOR MISCELLANEOUS PROJECTS ON THE REGIONAL TIER. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0521REG | REGION SW | T | [6 empty] | 2020 | 100000 | 100000
STATEWIDE | VARIOUS | TRANSPORTATION PLANNING BRANCH, TRAFFIC FORECASTING FOR MISCELLANEOUS PROJECTS ON THE STATEWIDE TIER. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0521SW | STATEWIDE MOBILITY | T | [6 empty] | 2020 | 100000 | 100000
STATEWIDE | VARIOUS | HYDRAULICS, PRELIMINARY ENGINEERING FOR THE HIGHWAY FLOODPLAIN PROGRAM (HFP) TO FACILITATE FEDERAL EMERGENCY MANAGEMENT AGENCY (FEMA) AND NATIONAL FLOOD INSURANCE PROGRAM (NFIP) COMPLIANCE AND FLOOD RESILIENCE. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0534 | [11 empty] | IN PROGRESS
STATEWIDE | VARIOUS | PRELIMINARY ENGINEERING FOR THE HIGHWAY FLOODPLAIN PROGRAM (HFP) TO FACILITATE FEDERAL EMERGENCY MANAGEMENT AGENCY (FEMA) AND NATIONAL FLOOD INSURANCE PROGRAM (NFIP) COMPLIANCE AND FLOOD RESILIENCE. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0534DIV | DIVISION SW | T | [6 empty] | 2020 | 9600000 | 9600000
STATEWIDE | VARIOUS | PRELIMINARY ENGINEERING FOR THE HIGHWAY FLOODPLAIN PROGRAM (HFP) TO FACILITATE FEDERAL EMERGENCY MANAGEMENT AGENCY (FEMA) AND NATIONAL FLOOD INSURANCE PROGRAM (NFIP) COMPLIANCE AND FLOOD RESILIENCE. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0534REG | REGION SW | T | [6 empty] | 2020 | 9600000 | 9600000
STATEWIDE | VARIOUS | PRELIMINARY ENGINEERING FOR THE HIGHWAY FLOODPLAIN PROGRAM (HFP) TO FACILITATE FEDERAL EMERGENCY MANAGEMENT AGENCY (FEMA) AND NATIONAL FLOOD INSURANCE PROGRAM (NFIP) COMPLIANCE AND FLOOD RESILIENCE. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0534SW | STATEWIDE MOBILITY | T | [6 empty] | 2020 | 12800000 | 12800000
STATEWIDE | VARIOUS | ENVIRONMENTAL MITIGATION AND MINIMIZATION. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0539
STATEWIDE | VARIOUS | ENVIRONMENTAL MITIGATION AND MINIMIZATION. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0539DIV | DIVISION SW | T | [6 empty] | 2020 | 43200000 | 43200000
STATEWIDE | VARIOUS | ENVIRONMENTAL MITIGATION AND MINIMIZATION. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0539REG | REGION SW | T | [6 empty] | 2020 | 43200000 | 43200000
STATEWIDE | VARIOUS | ENVIRONMENTAL MITIGATION AND MINIMIZATION. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0539SW | STATEWIDE MOBILITY | T | [6 empty] | 2020 | 57600000 | 57600000
STATEWIDE | VARIOUS | ROADWAY DESIGN - OPEN ROADS DESIGNER (ORD) TRANING AND DEVELOPMENT. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0552A
STATEWIDE | VARIOUS | ROADWAY DESIGN - OPEN ROADS DESIGNER (ORD) TRANING AND DEVELOPMENT. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0552ADIV | DIVISION SW | T | [6 empty] | 2022 | 150000 | 150000
STATEWIDE | VARIOUS | ROADWAY DESIGN - OPEN ROADS DESIGNER (ORD) TRANING AND DEVELOPMENT. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0552AREG | REGION SW | T | [6 empty] | 2022 | 150000 | 150000
STATEWIDE | VARIOUS | ROADWAY DESIGN - OPEN ROADS DESIGNER (ORD) TRANING AND DEVELOPMENT. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0552ASW | STATEWIDE MOBILITY | T | [6 empty] | 2022 | 200000 | 200000
STATEWIDE | VARIOUS | ROADWAY DESIGN - TRAINING AND DEVELOPMENT FOR MISCELLANEOUS PROJECTS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0552B
STATEWIDE | VARIOUS | ROADWAY DESIGN - TRAINING AND DEVELOPMENT FOR MISCELLANEOUS PROJECTS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0552BDIV | DIVISION SW | T | [6 empty] | 2022 | 324000 | 324000
STATEWIDE | VARIOUS | ROADWAY DESIGN - TRAINING AND DEVELOPMENT FOR MISCELLANEOUS PROJECTS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0552BREG | REGION SW | T | [6 empty] | 2022 | 324000 | 324000
STATEWIDE | VARIOUS | ROADWAY DESIGN - TRAINING AND DEVELOPMENT FOR MISCELLANEOUS PROJECTS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0552BSW | STATEWIDE MOBILITY | T | [6 empty] | 2022 | 432000 | 432000
STATEWIDE | VARIOUS | TECHNICAL SERVICES. PRELIMINARY ENGINEERING FOR MISCELLANEOUS PROJECTS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0553 | EXEMPT
STATEWIDE | VARIOUS | INTEGRATED PROJECT DELIVERY | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0553A | EXEMPT | T | [6 empty] | 2022 | 10500000 | 10500000
STATEWIDE | VARIOUS | TRAINING AND SPECIAL PROJECTS | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0553B | EXEMPT | T | [6 empty] | 2022 | 2000000 | 2000000
STATEWIDE | VARIOUS | NCDOT MITIGATION ORDER TO DIVISION OF MITIGATION SERVICES (DMS). | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0554
STATEWIDE | VARIOUS | NCDOT MITIGATION ORDER TO DIVISION OF MITIGATION SERVICES (DMS). | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0554DIV | DIVISION SW | T | [6 empty] | 2022 | 105000000 | 105000000
STATEWIDE | VARIOUS | NCDOT MITIGATION ORDER TO DIVISION OF MITIGATION SERVICES (DMS). | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0554REG | REGION SW | T | [6 empty] | 2022 | 105000000 | 105000000
STATEWIDE | VARIOUS | NCDOT MITIGATION ORDER TO DIVISION OF MITIGATION SERVICES (DMS). | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | M-0554SW | STATEWIDE MOBILITY | T | [6 empty] | 2022 | 140000000 | 140000000
STATEWIDE | VARIOUS | ASPHALT MATERIALS TESTING LABORATORIES CORRECTIVE ACTION PLAN FOR GROUNDWATER CLEAN-UP AT 54 SITES. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | R-4073 | [11 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NPDES PERMIT, RETROFIT FOURTEEN SITES PER YEAR TO PROTECT WATER QUALITY. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | R-4436 | [11 empty] | IN PROGRESS
STATEWIDE | VARIOUS | NPDES PERMIT, RETROFIT FOURTEEN SITES PER YEAR TO PROTECT WATER QUALITY - DIVISION CATEGORY. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | R-4436DIV | DIVISION SW | BG |  |  |  |  | 2020 | 900000 |  |  | 900000 | IN PROGRESS
STATEWIDE | VARIOUS | NPDES PERMIT, RETROFIT FOURTEEN SITES PER YEAR TO PROTECT WATER QUALITY - REGIONAL CATEGORY. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | R-4436REG | REGION SW | BG |  |  |  |  | 2020 | 900000 |  |  | 900000 | IN PROGRESS
STATEWIDE | VARIOUS | NPDES PERMIT, RETROFIT FOURTEEN SITES PER YEAR TO PROTECT WATER QUALITY - STATEWIDE CATEGORY. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | R-4436SW | STATEWIDE MOBILITY | BG |  |  |  |  | 2020 | 1200000 |  |  | 1200000 | IN PROGRESS
STATEWIDE | VARIOUS | FEDERAL LANDS TRANSPORTATION PROGRAM (FLTP) AND EMERGENCY RELIEF FOR FEDERALLY OWNED ROADS (ERFO). ROAD AND BRIDGE IMPROVEMENTS TO BE CONSTRUCTED ON TRANSPORTATION FACILITIES THAT ARE OWNED BY THE FEDERAL GOVERNMENT THAT PROVIDE ACCESS TO FEDERAL LANDS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | R-5753 | EXEMPT | ERFO, FLTP |  |  |  |  | 2020 | 63244000 |  |  | 63244000 | PROGRAM IN PROGRESS
STATEWIDE | VARIOUS | FEDERAL TRIBAL TRANSPORTATION PROGRAM (FTTP). ROAD AND BRIDGE IMPROVEMENTS TO BE CONSTRUCTED ON TRANSPORTATION FACILITIES THAT ARE OWNED BY THE FEDERAL GOVERNMENT THAT PROVIDE ACCESS TO TRIBAL LANDS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | R-5966 | EXEMPT | FTTP |  |  |  |  | 2020 | 12981000 |  |  | 12981000 | PROGRAM IN PROGRESS
STATEWIDE | VARIOUS | NPDES PERMIT, RETROFIT FOURTEEN SITES PER YEAR TO PROTECT WATER QUALITY. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | R-5968
STATEWIDE | VARIOUS | NPDES PERMIT, RETROFIT FOURTEEN SITES PER YEAR TO PROTECT WATER QUALITY - DIVISION CATEGORY. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | R-5968DIV | DIVISION SW | BGANY |  |  |  |  | 2020 | 14400000 |  |  | 14400000 | IN PROGRESS
STATEWIDE | VARIOUS | NPDES PERMIT, RETROFIT FOURTEEN SITES PER YEAR TO PROTECT WATER QUALITY - REGIONAL CATEGORY. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | R-5968REG | REGION SW | BGANY |  |  |  |  | 2020 | 14400000 |  |  | 14400000 | IN PROGRESS
STATEWIDE | VARIOUS | NPDES PERMIT, RETROFIT FOURTEEN SITES PER YEAR TO PROTECT WATER QUALITY - STATEWIDE CATEGORY. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | R-5968SW | STATEWIDE MOBILITY | BGANY |  |  |  |  | 2020 | 19200000 |  |  | 19200000 | IN PROGRESS
STATEWIDE | VARIOUS | ENVIRONMENTAL MITIGATION AND MINIMIZATION. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | R-9999WM | [11 empty] | IN PROGRESS
STATEWIDE | VARIOUS | ENVIRONMENTAL MITIGATION AND MINIMIZATION. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | R-9999WMDIV | DIVISION SW | NHP, T | [6 empty] | 2020 | 300000 | 300000
STATEWIDE | VARIOUS | ENVIRONMENTAL MITIGATION AND MINIMIZATION. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | R-9999WMREG | REGION SW | NHP, T | [6 empty] | 2020 | 300000 | 300000
STATEWIDE | VARIOUS | ENVIRONMENTAL MITIGATION AND MINIMIZATION. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | R-9999WMSW | STATEWIDE MOBILITY | NHP, T | [6 empty] | 2020 | 400000 | 400000
STATEWIDE | VARIOUS | SAFE ROUTES TO SCHOOL PROGRAM. EDUCATIONAL,TRAINING AND OTHER NON-INFRASTRUCTURE NEEDS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | SR-5000 | DIVISION SW | [10 empty] | IN PROGRESS
STATEWIDE | VARIOUS | SAFE ROUTES TO SCHOOL PROGRAM. PROJECTS TO IMPROVE SAFETY, REDUCE TRAFFIC, FUEL CONSUMPTION AND AIR POLLUTION IN VICINITY OF SCHOOLS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | SR-5001 | DIVISION SW | [10 empty] | IN PROGRESS - $200,800 IN STPDA FUNDS ALLOCATED TO SR-5001C
STATEWIDE | VARIOUS | HIGHWAY SYSTEM DATA COLLECTION. TRAFFIC ENGINEERING BRANCH TO PARTICIPATE IN A THREE YEAR DATA COLLECTION PROGRAM. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | W-5508
STATEWIDE | VARIOUS | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | W-5517
STATEWIDE | VARIOUS | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | W-5517DIV | DIVISION SW
STATEWIDE | VARIOUS | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | W-5517REG | REGION SW
STATEWIDE | VARIOUS | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | W-5517SW | STATEWIDE MOBILITY
STATEWIDE | VARIOUS | RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | W-5601 | [11 empty] | IN PROGRESS
STATEWIDE | VARIOUS | RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS ON DIVISION CATEGORY. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | W-5601DIV | DIVISION SW | HSIP | 2021 | 68000 |  |  | 2020 | 3670000 |  |  | 3738000
STATEWIDE | VARIOUS | RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS ON REGIONAL CATEGORY. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | W-5601REG | REGION SW | HSIP | 2021 | 68000 |  |  | 2021 | 6170000 |  |  | 6238000
STATEWIDE | VARIOUS | RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS ON STATWIDE CATEGORY. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | W-5601SW | STATEWIDE MOBILITY | HSIP | 2021 | 90000 |  |  | 2021 | 3360000 |  |  | 3450000
STATEWIDE | VARIOUS | SIGNAL RETIMING TO IMPROVE SAFETY. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | W-5700 | [11 empty] | IN PROGRESS
STATEWIDE | VARIOUS | SIGNAL RETIMING TO IMPROVE SAFETY. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | W-5700DIV | DIVISION SW
STATEWIDE | VARIOUS | SIGNAL RETIMING TO IMPROVE SAFETY. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | W-5700REG | REGION SW
STATEWIDE | VARIOUS | SIGNAL RETIMING TO IMPROVE SAFETY. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | W-5700SW | STATEWIDE MOBILITY
STATEWIDE | VARIOUS | SIGNAL RETIMING AND SIGNAL OPERATIONS SOFTWARE TO IMPROVE SAFETY. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | W-5715
STATEWIDE | VARIOUS | SIGNAL RETIMING AND SIGNAL OPERATIONS SOFTWARE TO IMPROVE SAFETY. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | W-5715DIV | DIVISION SW | HSIP | [6 empty] | 2020 | 8400000 | 8400000
STATEWIDE | VARIOUS | SIGNAL RETIMING AND SIGNAL OPERATIONS SOFTWARE TO IMPROVE SAFETY. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | W-5715REG | REGION SW | HSIP | [6 empty] | 2020 | 8400000 | 8400000
STATEWIDE | VARIOUS | SIGNAL RETIMING AND SIGNAL OPERATIONS SOFTWARE TO IMPROVE SAFETY. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | W-5715SW | STATEWIDE MOBILITY | HSIP | [6 empty] | 2020 | 11200000 | 11200000
STATEWIDE | VARIOUS | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | W-5716
STATEWIDE | VARIOUS | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | W-5716DIV | DIVISION SW | HSIP | [6 empty] | 2020 | 26400000 | 26400000
STATEWIDE | VARIOUS | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | W-5716REG | REGION SW | HSIP | [6 empty] | 2020 | 26400000 | 26400000
STATEWIDE | VARIOUS | SAFETY MANAGEMENT PROGRAM, PROJECT IDENTIFICATION, ANALYSIS AND PRELIMINARY ENGINEERING. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | W-5716SW | STATEWIDE MOBILITY | HSIP | [6 empty] | 2020 | 35200000 | 35200000
STATEWIDE | VARIOUS | HIGHWAY SYSTEM DATA COLLECTION. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | W-5717
STATEWIDE | VARIOUS | HIGHWAY SYSTEM DATA COLLECTION. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | W-5717DIV | DIVISION SW | HSIP | [6 empty] | 2020 | 2400000 | 2400000
STATEWIDE | VARIOUS | HIGHWAY SYSTEM DATA COLLECTION. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | W-5717REG | REGION SW | HSIP | [6 empty] | 2020 | 2400000 | 2400000
STATEWIDE | VARIOUS | HIGHWAY SYSTEM DATA COLLECTION. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | W-5717SW | STATEWIDE MOBILITY | HSIP | [6 empty] | 2020 | 3200000 | 3200000
STATEWIDE | VARIOUS | HIGHWAY SAFETY IMPROVEMENT PROGRAM BALANCE. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | W-9999
STATEWIDE | VARIOUS | HIGHWAY SAFETY IMPROVEMENT PROGRAM BALANCE. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | W-9999DIV | DIVISION SW | HSIP |  |  |  |  | 2020 | 45163000 |  |  | 45163000
STATEWIDE | VARIOUS | HIGHWAY SAFETY IMPROVEMENT PROGRAM BALANCE. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | W-9999REG | REGION SW | HSIP |  |  |  |  | 2020 | 55935000 |  |  | 55935000
STATEWIDE | VARIOUS | HIGHWAY SAFETY IMPROVEMENT PROGRAM BALANCE. | HIGHWAY | STATEWIDE | STATEWIDE PROJECT | W-9999SW | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2020 | 74580000 |  |  | 74580000
STATEWIDE | NCDOT | 5311 ADTAP CAPITAL FUNDING FOR RURAL TRANSIT | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TC-0003 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2023 | 1371000 | 1371000
STATEWIDE | NCDOT | 5339(b) DISCRETIONARY GRANT FOR FACILITY CONSTRUCTION | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TC-0011 | PUBLIC TRANSIT | 5339, L |  |  |  |  | 2023 | 719000 | 2021 | 8689000 | 9408000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | NCDOT | 5310 CAPITAL PROJECTS FOR RURAL | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TC-0018 | PUBLIC TRANSIT | 5310, L, S | [6 empty] | 2022 | 4673000 | 4673000
STATEWIDE | NCDOT | 5311 CAPITAL FUNDS FOR FTA GRANTS | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TC-0019 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2022 | 17147000 | 17147000
STATEWIDE | NCDOT | 5339 SMALL URBAN | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TC-0020 | PUBLIC TRANSIT | 5339, L, S, STBG | [6 empty] | 2022 | 3057000 | 3057000
STATEWIDE | NCDOT | 5339 STATEWIDE RURAL | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TC-0021 | PUBLIC TRANSIT | 5339, L, S | [6 empty] | 2022 | 7774000 | 7774000
STATEWIDE | NCDOT | 5311 ADTAP CAPITAL FUND FOR FTA GRANTS | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TC-0022 | PUBLIC TRANSIT | ADTAP, L, S | [6 empty] | 2022 | 1880000 | 1880000
STATEWIDE | NCDOT | FEDERAL AMERICAN RESCUE PLAN (ARP) FUNDS FOR CAPITAL | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TC-0026 | PUBLIC TRANSIT | ARP | [6 empty] | 2023 | 500000 | 500000
STATEWIDE | NCDOT | INTEGRATED MOBILITY DIVISION STATE ADMINISTRATION FUNDS TO SUPPORT THE IMD WITH PROVIDING SUBRECIPIENT MONITORING AND OVERSIGHT AND PROVIDE TECHNICAL ASSISTANCE IN THE DEVELOPMENT OF PROJECTS AND PLANS FOR SMALL URBAN AND RURAL AREAS(5311 ADMIN/OPERATING/ | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TM-0002 | PUBLIC TRANSIT | 5311 | [6 empty] | 2023 | 3950000 | 3950000
STATEWIDE | NCDOT | INTEGRATED MOBILITY DIVISION STATE ADMINISTRATION FUNDS TO SUPPORT THE IMD WITH PROVIDING SUBRECIPIENT MONITORING AND OVERSIGHT AND PROVIDE TECHNICAL ASSISTANCE IN THE DEVELOPMENT OF PROJECTS AND PLANS FOR SMALL URBAN AND RURAL AREAS(5311CAPITAL-ADTAP) | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TM-0004 | PUBLIC TRANSIT | 5311 | [6 empty] | 2023 | 150000 | 150000
STATEWIDE | NCDOT | INTEGRATED MOBILITY DIVISION STATE ADMINISTRATION FUNDS TO SUPPORT THE IMD WITH PROVIDING SUBRECIPIENT MONITORING AND OVERSIGHT AND PROVIDE TECHNICAL ASSISTANCE IN THE DEVELOPMENT OF PROJECTS AND PLANS FOR SMALL URBAN AND RURAL AREAS(5310 ADMIN/OPERATING/ | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TM-0023 | PUBLIC TRANSIT | 5310 | [6 empty] | 2023 | 522000 | 522000
STATEWIDE | NCDOT | 5310 OPERATING PROJECTS | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TM-0025 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2022 | 4212000 | 4212000
STATEWIDE | NCDOT | 5311 ADMINISTRATIVE FUNDS FOR FTA GRANTS | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TM-0027 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2022 | 42190000 | 42190000
STATEWIDE | NCDOT | 5311 OPERATING FUNDS FOR FTA GRANTS | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TM-0028 | PUBLIC TRANSIT | 5311, L | [6 empty] | 2022 | 2928000 | 2928000
STATEWIDE | NCDOT | 5311 STATE ADMINISTRATIVE FUNDS FOR FTA GRANTS | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TM-0029 | PUBLIC TRANSIT | 5311 | [6 empty] | 2022 | 3361000 | 3361000
STATEWIDE | NCDOT | 5311 ADTAP STATE ADMINISTRATIVE FUNDS | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TM-0030 | PUBLIC TRANSIT | ADTAP | [6 empty] | 2022 | 177000 | 177000
STATEWIDE | NCDOT | RTAP STATEWIDE FUNDS FOR FTA GRANTS | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TM-0031 | PUBLIC TRANSIT | RTAP | [6 empty] | 2022 | 978000 | 978000
STATEWIDE | NCDOT | 5311(F) INTERCITY BUS FUNDS FOR FTA GRANTS | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TM-0032 | PUBLIC TRANSIT | 5311, S | [6 empty] | 2022 | 29441000 | 29441000
STATEWIDE | NCDOT | 5311(F) INTERCITY BUS - STATE ADMIN | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TM-0033 | PUBLIC TRANSIT | 5311 | [6 empty] | 2022 | 494000 | 494000
STATEWIDE | NCDOT | IMD STATE ADMINISTRATION - AMERICAN RESCUE PLAN AND CORONAVIRUS RESPONSE AND RELIEF SUPPLEMENTAL APPROPRIATION ACT FUNDS TO SUPPORT THE INTEGRATED MOBILITY DIVISION WITH PROVIDING SUBRECIPIENT MONITORING AND OVERSIGHT AND PROVIDE TECHNICAL ASSISTANCE IN | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TM-0038 | PUBLIC TRANSIT | FEDT, S | [6 empty] | 2023 | 1501000 | 1501000
STATEWIDE | NCDOT | H.O.P.E GRANT OPPORTUNITY FROM THE FTA. DISCRETIONARY GRANT AWARDED BY FTA. PLANNING AND DESIGN IN PREPARATION FOR ELECTRIC VEHICLE DEPLOYMENT. | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TU-0003 | PUBLIC TRANSIT | 5303, 5312, S | [6 empty] | 2021 | 222000 | 222000 | ADD PROJECT TU-0003 TO STIP FOR FFY 2021. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD. PROJECT ADDED AT THE REQUEST OF IMD.
STATEWIDE | NCDOT | 5303 METROPOLITAN TRANSPORTATION PLANNING FUNDS FOR FTA GRANTS | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TU-0005 | PUBLIC TRANSIT | 5303, L, S | [6 empty] | 2022 | 10809000 | 10809000
STATEWIDE | NCDOT | NCSU (ITRE) WILL PROVIDE TECHNICAL ASSISTANCE TO THE INTEGRATED MOBILITY DIVISION AND SUBRECIPIENTS. | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TU-0008 | PUBLIC TRANSIT | 5311, S | [6 empty] | 2022 | 588000 | 588000
STATEWIDE | NCDOT | NCSU (ITRE) WILL USE THE FUNDS TO PROVIDE TRAINING/PROFESSIONAL DEVELOPMENT RELATED TO DELIVERY OF ADA TRAINING TO TRANSIT PROFESSIONALS. | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TU-0009 | PUBLIC TRANSIT | RTAP | [6 empty] | 2022 | 765000 | 765000
STATEWIDE | NCDOT | NCDOT-IMD SECTION 5304 PROGRAM FUNDS TO SUPPORT THE INTEGRATED MOBILITY DIVISION URBAN TRANSIT TECHNICAL ASSISTANCE ACTIVITIES. | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TU-0011 | PUBLIC TRANSIT | 5303, L | [6 empty] | 2022 | 1731000 | 1731000
STATEWIDE | NCDOT | CAPE FEAR PUBLIC TRANSPORTATION AUTHORITY. PLANNING STUDY ON THE TRANSITION TO ZERO EMISSIONS LIGHT AND HEAVY DUTY PASSENGER VEHICLES. THE TRANSITION PLAN IS AREQUIREMENT BY FTA TO APPLY FOR GRANT FUNDS SUPPORTING ANY ZEV PROJECTS, INCLUDING VEHICLES AND | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TU-0012 | PUBLIC TRANSIT | 5303, L | [6 empty] | 2023 | 100000 | 100000
STATEWIDE | NCDOT | NCSU (ITRE) WILL PROVIDE TECHNICAL ASSISTANCE TO THE INTEGRATED MOBILITY DIVISION AND SUBRECIPIENTS. | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TU-0014 | PUBLIC TRANSIT | 5311, L | [6 empty] | 2023 | 634000 | 634000
STATEWIDE | NCDOT | NCSU (ITRE) WILL USE THE FUNDS TO PROVIDE TRAINING/PROFESSIONAL DEVELOPMENT RELATED TO THE DELIVERY OF ADA TRAINING TO TRANSIT PROFESSIONALS. | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TU-0015 | PUBLIC TRANSIT | RTAP | [6 empty] | 2023 | 73000 | 73000
STATEWIDE | REGIONAL COORDINATED AREA TRANSPORTION | PLANNING ASSISTANCE - RESEARCH SUPPORT ACTIVITIES | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TP-4901 | PUBLIC TRANSIT | FSPR, S | [6 empty] | 2020 | 720000 | 720000 | FUNDS AUTHORIZED IN PROGRESS
STATEWIDE | STATEWIDE | 5311 CAPITAL PROJECTS FOR RURAL AREAS | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TA-6665 | PUBLIC TRANSIT | 5311 | [6 empty] | 2021 | 4749000 | 4749000 | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
STATEWIDE | STATEWIDE | 5339 BUS AND BUS FACILITIES | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TA-6666 | PUBLIC TRANSIT | 5339 | [6 empty] | 2021 | 6750000 | 6750000 | FUNDS AUTHORIZED IN PROGRESS
STATEWIDE | STATEWIDE | 5339(b) DISCRETIONARY GRANT FOR FACILITY CONSTRUCTION | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TC-0005 | PUBLIC TRANSIT | 5339, L |  |  |  |  | 2022 | 2650000 |  |  | 2650000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | 5339(b) DISCRETIONARY GRANT FOR FOR FACILITY CONSTRUCTION | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TC-0006 | PUBLIC TRANSIT | 5339, L |  |  |  |  | 2021 | 1819000 |  |  | 1819000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | 5339(b) DISCRETIONARY GRANT FOR CONSTRUCTION PROJECT | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TC-0007 | PUBLIC TRANSIT | 5339, L | [6 empty] | 2021 | 3976000 | 3976000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | 5339(b) DISCRETIONARY GRANT FOR FACILITY CONSTRUCTION | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TC-0008 | PUBLIC TRANSIT | 5339, L | [6 empty] | 2021 | 10900000 | 10900000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | 5339(b) DISCRETIONARY GRANT FOR FOR FACILITY CONSTRUCTION | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TC-0010 | PUBLIC TRANSIT | 5339, L |  |  |  |  | 2021 | 4069000 |  |  | 4069000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | 5339(b) DISCRETIONARY GRANT TO PURCHASE ELECTRIC BUSES AND CHARGING STATIONS. | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TC-0012 | PUBLIC TRANSIT | 5339, L | [6 empty] | 2021 | 3767000 | 3767000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | MOBILITY FROM ALL GRANT OPPORTUNITY FROM THE FTA.5310 DISCRETIONARY GRANT AWARDED BY FTA. | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TC-0013 | PUBLIC TRANSIT | 5310, S | [6 empty] | 2021 | 350000 | 350000
STATEWIDE | STATEWIDE | 5311 ADTAP | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TC-5004 | PUBLIC TRANSIT | ADTAP | [6 empty] | 2021 | 3392000 | 3392000 | FUMODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
STATEWIDE | STATEWIDE | FY21 5307 SBUS CAPITAL | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TG-0002 | PUBLIC TRANSIT | 5307 | [6 empty] | 2021 | 21000 | 21000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | FY21 5307 SBUS CAPITAL | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TG-0004 | PUBLIC TRANSIT | 5307 | [6 empty] | 2021 | 168000 | 168000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | FY21 5307 SBUS CAPITAL | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TG-0005 | PUBLIC TRANSIT | 5307 | [6 empty] | 2021 | 168000 | 168000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | FY21 5307 SBUS CAPITAL | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TG-0006 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2021 | 381000 | 381000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | 5311(F) INTERCITY BUS FUNDS FOR FTA GANTS | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TI-6109 | PUBLIC TRANSIT | 5311 | [6 empty] | 2021 | 2698000 | 2698000 | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
STATEWIDE | STATEWIDE | 5311 STATE ADMINISTRATION AND 5311 STATE ADMINISTRATION | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TK-4900Z | PUBLIC TRANSIT | 5311 | [6 empty] | 2021 | 3080000 | 3080000 | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
STATEWIDE | STATEWIDE | STATE ADMINISTRATION OF APPALACHIAN DEVELOPMENT TRANSPORTATION ASSISTANCE PROGRAM | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TK-4902 | PUBLIC TRANSIT | ADTAP | [6 empty] | 2021 | 235000 | 235000 | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
STATEWIDE | STATEWIDE | 5311 ADMINISTRATIVE | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TK-6181 | PUBLIC TRANSIT | 5311 | [6 empty] | 2021 | 15025000 | 15025000 | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
STATEWIDE | STATEWIDE | 5307 OPERATING FUNDS | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TM-0010 | PUBLIC TRANSIT | 5307 | [6 empty] | 2021 | 142000 | 142000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | 5307 OPERATING FUNDS | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TM-0012 | PUBLIC TRANSIT | 5307 | [6 empty] | 2021 | 129000 | 129000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | 5307 OPERATING FUNDS | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TM-0014 | PUBLIC TRANSIT | 5307 | [6 empty] | 2021 | 75000 | 75000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | 5307 OPERATING FUNDS | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TM-0015 | PUBLIC TRANSIT | 5307 | [6 empty] | 2021 | 145000 | 145000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | 5307 OPERATING FUNDS | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TM-0020 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2021 | 2191000 | 2191000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | 5307 OPERATING FUNDS | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TM-0022 | PUBLIC TRANSIT | 5307 | [6 empty] | 2021 | 18000 | 18000 | NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD.
STATEWIDE | STATEWIDE | AIM GRANT OPPORTUNITY FROM THE FTA. DISCRETIONARY GRANT AWARDED BY FTA. THIS WILL ALLOW THE CITY TO EXPAND SERVICE AND HOURS. | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TM-0024 | PUBLIC TRANSIT | 5312, L | [6 empty] | 2021 | 313000 | 313000
STATEWIDE | STATEWIDE | 5310 STATE ADMINISTRATIVE FUNDS. | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TM-0036 | PUBLIC TRANSIT | 5310 | [6 empty] | 2022 | 567000 | 567000
STATEWIDE | STATEWIDE | 5317 NEW FREEDOM | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TN-6125 | PUBLIC TRANSIT | FEP, L | [6 empty] | 2020 | 4272000 | 4272000
STATEWIDE | STATEWIDE | HUMAN TRAFFICKING AWARENESS AND PUBLIC SAFETY INITIATIVE DISCRETIONARY GRANT AWARDED BY FTA. GRANT WILL ALLOW FOR STATEWIDE TRAINING AND IMPLEMENTATION OF A TRAINING PROGRAM FOR TRANSIT EMPLOYEES ACROSS THE STATE ON HOW TO RECOGNIZE AND RESPOND TO THE SIG | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TO-0003 | PUBLIC TRANSIT | 5307, 5312 | [6 empty] | 2021 | 150000 | 150000
STATEWIDE | STATEWIDE | SYSTEM SAFETY OVERSIGHT GRANT FOR NCDOT RAIL DIVISION. | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TO-0004 | PUBLIC TRANSIT | S, SSO | [6 empty] | 2021 | 880000 | 880000 | ADD PROJECT TO TO-0004 TO STIP FOR FFY 2021. NEW PROJECT DEVELOPED FOR FEDERAL FUNDING AWARD FOR SYSTEM SAFETY OVERSIGHT FOR THE NCDOT RAIL DIVISION. PROJECT ADDED AT THE REQUEST OF IMD.
STATEWIDE | STATEWIDE | 5311 OPERATING FUNDS FOR FTA GRANTS | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TO-6135 | PUBLIC TRANSIT | 5311 | [6 empty] | 2021 | 947000 | 947000 | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
STATEWIDE | STATEWIDE | URBANIZED FORMULA PROGRAM FUNDS MANAGED BY NCDOT FOR ORANGE, ALAMANCE, DAVIDSON, GUILFORD, CABARRUS, IREDELL, HOKE, CUMBERLAND, HARNETT, UNION, MECKLENBURG TRANSPORTATION SYSTEMS - OPERATING | PUBLIC TRANSIT | STATEWIDE | BURLINGTON-GRAHAM MPO, CHARLOTTE REGIONAL TPO, FAYETTEVILLE AREA MPO, HIGH POINT URBAN AREA MPO, WINSTON-SALEM URBAN AREA MPO | TO-6142 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 11230000 | 11230000
STATEWIDE | STATEWIDE | 5311 OPERATING AND 5311 OPERATING F | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TO-6155 | PUBLIC TRANSIT | 5311, L | [6 empty] | 2020 | 154320000 | 154320000
STATEWIDE | STATEWIDE | 5304 PLANNING | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TP-5154 | PUBLIC TRANSIT | 5303, L | [6 empty] | 2020 | 5136000 | 5136000
STATEWIDE | STATEWIDE | 5310 OPERATING PROJECTS FOR RURAL AREAS | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TQ-6954 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2021 | 6235000 | 6235000 | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
STATEWIDE | STATEWIDE | 5310 CAPITAL PROJECTS FOR RURAL AREAS AND SMALL URBAN AREAS | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TQ-9038 | PUBLIC TRANSIT | 5310 | [6 empty] | 2021 | 2850000 | 2850000 | MODIFYING THE FEDERAL FUND S RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
STATEWIDE | STATEWIDE | STATEWIDE RTAP | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TS-4900Z | PUBLIC TRANSIT | RTAP | [6 empty] | 2021 | 480000 | 480000 | MODIFYING THE FEDERAL FUNDS RECEIVED FROM FTA ADMINISTERED BY PTD BASED ON SFY21 GRANTS
STATEWIDE | STATEWIDE | 5329 STATE SAFETY AND OVERSIGHT | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TS-7001 | PUBLIC TRANSIT | FED, L, S | [6 empty] | 2020 | 4676000 | 4676000
STATEWIDE | SUB REGIONAL | STATE ADMINISTRATION - JOB ACCESS NON-URBAN | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TM-5301 | PUBLIC TRANSIT | 5316 | [6 empty] | 2020 | 500000 | 500000 | FUNDS AUTHORIZED IN PROGRESS
STATEWIDE | SUB REGIONAL | STATE ADMINISTRATION - NEW FREEDOM - 5317 | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TN-5112 | PUBLIC TRANSIT | 5317 | [6 empty] | 2020 | 350000 | 350000 | FUNDS AUTHORIZED IN PROGRESS
STATEWIDE | SUB REGIONAL | 5310 STATE ADMIN | PUBLIC TRANSIT | STATEWIDE | STATEWIDE PROJECT | TV-4903 | PUBLIC TRANSIT | 5310 | [6 empty] | 2021 | 450000 | 450000 | FUNDS AUTHORIZED IN PROGRESS
STATEWIDE | VARIOUS | STATEWIDE RAIL PRELIMINARY ENGINEERING | RAIL | STATEWIDE | STATEWIDE PROJECT | P-5602 | [11 empty] | IN PROGRESS
STATEWIDE | VARIOUS | STATEWIDE RAIL PRELIMINARY ENGINEERING | RAIL | STATEWIDE | STATEWIDE PROJECT | P-5602DIV | DIVISION SW | T | [6 empty] | 2020 | 4800000 | 4800000
STATEWIDE | VARIOUS | STATEWIDE RAIL PRELIMINARY ENGINEERING | RAIL | STATEWIDE | STATEWIDE PROJECT | P-5602REG | REGION SW | T | [6 empty] | 2020 | 4800000 | 4800000
STATEWIDE | VARIOUS | STATEWIDE RAIL PRELIMINARY ENGINEERING | RAIL | STATEWIDE | STATEWIDE PROJECT | P-5602SW | STATEWIDE MOBILITY | T | [6 empty] | 2020 | 6400000 | 6400000
STATEWIDE | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES PROGRAM ADMINISTRATION | RAIL | STATEWIDE | STATEWIDE PROJECT | RC-2000 | STATEWIDE MOBILITY | [10 empty] | PROGRAMMED FOR PLANNING ONLY.
STATEWIDE | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES - UNPROGRAMMED BALANCE | RAIL | STATEWIDE | STATEWIDE PROJECT | RC-9999 | DIVISION SW | RR |  |  |  |  | 2024 | 36000000 |  |  | 36000000
STATEWIDE | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS PROGRAM ADMINISTRATION. | RAIL | STATEWIDE | STATEWIDE PROJECT | RX-2000 | STATEWIDE MOBILITY | [10 empty] | PROGRAMMED FOR PLANNING ONLY.
STATEWIDE | VARIOUS | PASSENGER RAIL CROSSING SAFETY IMPROVEMENT INVENTORY PROGRAM | RAIL | STATEWIDE | STATEWIDE PROJECT | RX-2100 | DIVISION SW | RR | [6 empty] | 2021 | 2500000 | 2500000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDIES ONLY
STATEWIDE | VARIOUS |  | RAIL | STATEWIDE | STATEWIDE PROJECT | RX-9999 | DIVISION SW | RR |  |  |  |  | 2024 | 42000000 |  |  | 42000000
STATEWIDE | VARIOUS | TRAFFIC SEPARATION STUDY IMPLEMENTATION AND CLOSURES - UNPROGRAMMED BALANCE | RAIL | STATEWIDE | STATEWIDE PROJECT | Y-5500 | DIVISION SW | RR | 2021 | 1500000 |  |  | 2020 | 7560000 |  |  | 9060000 | IN PROGRESS
STATEWIDE | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS. | RAIL | STATEWIDE | STATEWIDE PROJECT | Z-5400 | DIVISION SW | [10 empty] | IN PROGRESS
STATEWIDE | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS. | RAIL | STATEWIDE | STATEWIDE PROJECT | Z-5700 | DIVISION SW | [10 empty] | IN PROGRESS
STATEWIDE | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS. | RAIL | STATEWIDE | STATEWIDE PROJECT | Z-5800 | DIVISION SW | RR | 2021 | 500000 |  |  | 2020 | 3280000 |  |  | 3780000
STATEWIDE | VARIOUS | HIGHWAY-RAIL GRADE CROSSING SAFETY IMPROVEMENTS - UNPROGRAMMED BALANCE. | RAIL | STATEWIDE | STATEWIDE PROJECT | Z-9999 | DIVISION SW | RR | 2023 | 500000 |  |  | 2023 | 3000000 |  |  | 3500000
STOKES | US 311 | NC 65 IN WALNUT COVE. UPGRADE INTERSECTION AND IMPROVE RAILROAD CROSSING. | HIGHWAY | 9 | NORTHWEST PIEDMONT RPO | R-5768 | DIVISION 9 | BGLT5 |  |  |  |  | 2023 | 3800000 |  |  | 3800000 | IN PROGRESS
STOKES | US 311 (NORTH MAIN STREET) | SR 1918 (FIRST STREET) IN WALNUT COVE. CONSTRUCT ROUNDABOUT. | HIGHWAY | 9 | NORTHWEST PIEDMONT RPO | R-5828 | DIVISION 9 | T |  |  |  |  | 2022 | 3050000 |  |  | 3050000 | UNDER CONSTRUCTION
SURRY | MOUNT AIRY - SURRY COUNTY AIRPORT (MWK) | CONSTRUCT GENERAL AVIATION APRON AND AIRCRAFT STORAGE HANGARS. | AVIATION | 11 | NORTHWEST PIEDMONT RPO | AV-5859 | DIVISION 11 | T |  |  |  |  | 2020 | 4000000 |  |  | 4000000 | Under construction
SURRY | MOUNT AIRY | S. SOUTH STREET, WORTH STREET TO ROCKFORD STREET. ROCKFORD STREET, PENN STREET TO US 52. WORTH STREET, SOUTH STREET TO US 52. CONSTRUCT SIDEWALK. | BIKE/PED | 11 | NORTHWEST PIEDMONT RPO | EB-5845 | DIVISION 11 | L, TA5200 | 2023 | 161000 |  |  | 2024 | 430000 | 2022 | 192000 | 783000
SURRY | US 21 BUSINESS (NORTH BRIDGE STREET) | NC 268 (CC CAMP ROAD) TO HIGHLAND AVENUE. CONSTRUCT SIDEWALK ON WEST SIDE OF ROADWAY. | BIKE/PED | 11 | NORTHWEST PIEDMONT RPO | EB-5961 | DIVISION 11 | L, TA5200 | 2023 | 53000 |  |  | 2024 | 175000 | 2022 | 63000 | 291000
SURRY | I-74 | I-77 TO US 601. PAVEMENT REHABILITATION. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | I-5907 | STATEWIDE MOBILITY | BGLT5 |  |  |  |  | 2022 | 5543000 |  |  | 5543000
SURRY | I-77 | MILE MARKER 91 TO MILE MARKER 95. PAVEMENT REHABILITATION. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | I-5829 | [11 empty] | UNDER CONSTRUCTION
SURRY | I-77 | MILE MARKER 91 TO MILE MARKER 95. DIAMOND GRINDING | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | I-5829A | STATEWIDE MOBILITY | T |  |  |  |  | 2022 | 2505000 |  |  | 2505000
SURRY | I-77 NORTHBOUND | REPLACE BRIDGE 850006 OVER NC 268, NORFOLK SOUTHERN RAILROAD, AND THE YADKIN RIVER. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | B-5831 | STATEWIDE MOBILITY | BFP | 2024 | 667000 | 2024 | 67000 | 2026 | 10700000 |  |  | 11434000
SURRY | NC 103 (EAST PINE STREET) | SR 1742 (QUAKER ROAD) INTERSECTION. IMPROVE INTERSECTION. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5895 | NOT FUNDED | T | NOT FUNDED | 2700000 | NOT FUNDED | 390000 | NOT FUNDED | 1600000 |  |  | 4690000
SURRY | NC 268 | BRIDGE 850103 ON NC 268 OVER MITCHELL RIVER | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | BR-0048 | REGION F | HFB |  |  |  |  | 2022 | 4252000 |  |  | 4252000 | RIGHT OF WAY IN PROGRESS.
SURRY | NC 89 (WEST PINE STREET) | SR 1397 (ROUND PEAK CHURCH ROAD) INTERSECTION. IMPROVE INTERSECTION. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5901 | NOT FUNDED | T | NOT FUNDED | 500000 | NOT FUNDED | 100000 | NOT FUNDED | 3900000 |  |  | 4500000
SURRY | NC 89 (WEST PINE STREET) | SR 1387 (TOAST ROAD) TO SR 1396 (PINE RIDGE ROAD). MODERNIZE ROADWAY AND IMPROVE INTERSECTION AT SR 1396 (PINE RIDGE ROAD). | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5905 | DIVISION 11 | BG5200 | 2026 | 5900000 | 2026 | 5800000 | 2028 | 38501000 |  |  | 50201000
SURRY | SR 1149 (ELK SPUR STREET) | REPLACE BRIDGE 850387 OVER ELKIN CREEK. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | B-5971 | DIVISION 11 | BGOFF | 2026 | 300000 |  |  | 2027 | 6400000 |  |  | 6700000
SURRY | SR 2080 (QUAKER CHURCH ROAD) | REPLACE BRIDGE 850152 OVER ARARAT RIVER. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | B-5832 | DIVISION 11 | BGOFF | 2024 | 200000 |  |  | 2025 | 3600000 |  |  | 3800000
SURRY | SR 2081 | REPLACE BRIDGE 850153 OVER HOGAN CREEK. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | BR-0210 | HIGHWAY FUND | DP |  |  |  |  | 2020 | 875000 |  |  | 875000 | THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.132. DP REPRESENT FEDERAL BUILD GRANT FUNDING
SURRY | US 21 BUSINESS (NORTH BRIDGE STREET) | NC 268 (CC CAMP ROAD) INTERSECTION. IMPROVE US 21 BUSINESS NORTHBOUND TO NC 268 EASTBOUND MOVEMENT. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5910 | DIVISION 11 | BG5200 | 2022 | 400000 | 2022 | 400000 | 2023 | 1800000 |  |  | 2600000
SURRY | US 52 (NORTHBOUND LANE) | REPLACE BRIDGE 850122 OVER TOMS CREEK AND REPLACE BRIDGE 850342 OVER OLD US 52 SOUTHBOUND EXIT RAMP. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | B-5527 | STATEWIDE MOBILITY | HFB | 2023 | 400000 |  |  | 2024 | 4000000 |  |  | 4400000
SURRY | US 601 | US 52 TO SR 1365 (FORREST DRIVE). UPGRADE ROADWAY. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5714 | REGION F | T | 2019 | 1615000 |  |  | 2023 | 11700000 |  |  | 13315000 | RIGHT-OF-WAY IN PROGRESS
SURRY | US 601 | I-74 TO SR 1104 (CODY TRAIL). WIDEN TO 4-LANES. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5836 | DIVISION 11 | T | 2024 | 3100000 | 2024 | 1700000 | 2026 | 76000000 |  |  | 80800000
SURRY, YADKIN | US 21 BUSINESS | BRIDGE #850021 OVER YADKIN RIVER. REHABILITATE STRUCTURE AND WIDEN SIDEWALKS. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5913B | HIGHWAY FUND | HFB |  |  |  |  | 2025 | 1400000 |  |  | 1400000
SWAIN | FUTURE US 74 | SR 1121 (WATTIA ROAD) AT ALMONDS TO EXISTING US 19/NC 28 | HIGHWAY | 14 | SOUTHWESTERN RPO | A-0009DA | [11 empty] | COMPLETE
SWAIN | GREAT SMOKY MOUNTAINS NATIONAL PARK | SUSTAINABLE TRANSPORTATION PRACTICES TO REDUCE AIR POLLUTION. | HIGHWAY | 14 | SOUTHWESTERN RPO | HO-0004 | EXEMPT | CMAQ, L | [6 empty] | 2022 | 250000 | 250000
SWAIN | NC 28 | US 129 TO SWAIN/GRAHAM COUNTY LINE AT LITTLE TENNESSEE RIVER. UPGRADE ROADWAY. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5839A | NOT FUNDED | T | NOT FUNDED | 1520000 | NOT FUNDED | 200000 | NOT FUNDED | 312700000 |  |  | 314420000
SWAIN | SR 1321 (BRYSON WALK), SR 1336 (DEPOT STREET) | SR 1323 (SLOPE STREET) TO SR 1336 (DEEP CREEK ROAD). IMPROVE INTERSECTIONS. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5843 | DIVISION 14 | T |  |  |  |  | 2022 | 2983000 |  |  | 2983000 | RIGHT-OF-WAY IN PROGRESS
SWAIN | US 19 | SR 1152 (HUGHES BRANCH ROAD) IN BRYSON CITY TO SR 1195 (US 19A). MODERNIZE ROADWAY. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-4751 | NOT FUNDED | T | NOT FUNDED | 25000000 | NOT FUNDED | 4900000 | NOT FUNDED | 75000000 |  |  | 104900000
SWAIN | SWAIN COUNTY FOCAL POINT ON AGING, INC. | ADMINISTRATION | PUBLIC TRANSIT | 14 | SOUTHWESTERN RPO | TK-6165 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 508000 | 508000 | FUNDS AUTHORIZED IN PROGRESS
SWAIN, GRAHAM | FUTURE US 74 | EAST OF CALFPEN GAP IN GRAHAM COUNTY TO SR 1121 (WATTIA ROAD) AT ALMONDS IN SWAIN COUNTY | HIGHWAY | 14 | SOUTHWESTERN RPO | A-0009DB | [11 empty] | COMPLETE
TRANSYLVANIA | BREVARD | CONSTRUCT BICYCLE AND PEDESTRIAN BRIDGE FROM CITY OF BREVARD EXISTING SHARED USE PATH ACROSS DAVIDSON RIVER. | BIKE/PED | 14 | LAND-OF-SKY RPO | EB-5858 | DIVISION 14 | L, TA5200 | 2022 | 97000 |  |  | 2024 | 515000 | 2022 | 788000 | 1400000
TRANSYLVANIA | (FISH HATCHERY ROAD) SR 1408 | 1.5 MILES WEST OF US 276 TO END OF PAVEMENT. INSTALL GUARDRAIL AT VARIOUS LOCATIONS. | HIGHWAY | 14 | LAND-OF-SKY RPO | HF-0002 | EXEMPT | FLAP, S(M) |  |  |  |  | 2023 | 230000 | 2022 | 10000 | 240000 | FLAP PROJECT ID: NC 44. AWARD AMOUNT = $240,000. STATE MATCH ARE HIGHWAY FUNDS.
TRANSYLVANIA | BREVARD | REPLACE BRIDGE 870102 ON RAILROAD AVENUE OVER KINGS CREEK. | HIGHWAY | 14 | LAND-OF-SKY RPO | B-5550 | DIVISION 14 | BFPOFF |  |  |  |  | 2023 | 1824000 |  |  | 1824000 | RIGHT-OF-WAY IN PROGRESS. PLANNING/DESIGN BY CITY OF BREVARD
TRANSYLVANIA | DAVIDSON RIVER VILLAGE CONNECTOR | US 64 TO US 276/US 64 IN PISGAH FOREST. | HIGHWAY | 14 | LAND-OF-SKY RPO | R-5605 | DIVISION 14 | T |  |  |  |  | 2020 | 3345000 |  |  | 3345000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $2.592M FOR CON, PAYBACK FY 2020-2034 (FY 2019/ YR 1 SALE)
TRANSYLVANIA | MOUNTAIN INDUSTRIAL DRIVE EXTENSION | CONSTRUCT ROAD EXTENSION IN JENNINGS INDUSTRIAL PARK. | HIGHWAY | 14 | LAND-OF-SKY RPO | HA-0002 | EXEMPT | ADHSL | 2022 | 10000 |  |  | 2023 | 826000 | 2021 | 60000 | 896000 | ARC PROJECT NO. 20191, AWARD AMOUNT = $895,610
TRANSYLVANIA | SR 1532 (ISLAND COVE ROAD) | REPLACE BRIDGE 870196 OVER CRAB CREEK. | HIGHWAY | 14 | LAND-OF-SKY RPO | B-5403 | DIVISION 14 | [10 empty] | COMPLETE
TRANSYLVANIA | SR 1533 (EVERETT ROAD) | REPLACE BRIDGE 870030 OVER FRENCH BROAD RIVER. | HIGHWAY | 14 | LAND-OF-SKY RPO | HB-0026 | DIVISION 14 | BGOFF | 2024 | 200000 | 2024 | 200000 | 2025 | 4000000 |  |  | 4400000
TRANSYLVANIA | SR 1540 (WILSON ROAD) | SR 1504 (OLD US 64) TO US 276. UPGRADE ROADWAY. | HIGHWAY | 14 | LAND-OF-SKY RPO | R-5763 | DIVISION 14 | T | 2022 | 17400000 | 2022 | 2400000 | 2024 | 40200000 |  |  | 60000000
TRANSYLVANIA | US 178 | SR 1156 (MAIN STREET) IN ROSMAN TO SR 1133 (MIDDLEFORK ROAD) MODERNIZE ROADWAY. | HIGHWAY | 14 | LAND-OF-SKY RPO | R-5919 | DIVISION 14 | BGLT5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10100000 |  |  | 12700000
TRANSYLVANIA | US 276 | US 64 TO AVERY CREEK TRAILHEAD. INSTALL GUARDRAIL AND CONSTRUCT SIDEWALK AND INSTALL GUARDRAIL FROM SLIDING ROCK TO PROPOSED OFF-SITE PARKING. | HIGHWAY | 14 | LAND-OF-SKY RPO | HF-0004 | EXEMPT | FLAP, S(M) |  |  |  |  | 2024 | 495000 | 2022 | 30000 | 525000 | FLAP PROJECT ID: NC 40; AWARD AMOUNT = $420,000. STATE MATCH ARE HIGHWAY FUNDS.
TRANSYLVANIA | US 276 | US 64 TO AVERY CREEK TRAILHEAD. INSTALL GUARDRAIL AND CONSTRUCT SIDEWALK AND INSTALL GUARDRAIL FROM SLIDING ROCK TO PROPOSED OFF-SITE PARKING. | HIGHWAY | 14 | LAND-OF-SKY RPO | HO-0007 | EXEMPT | FLAP, S(M) |  |  |  |  | 2022 | 495000 | 2021 | 30000 | 525000 | FLAP PROJECT ID: NC 40; AWARD AMOUNT = $420,000. STATE MATCH ARE HIGHWAY FUNDS.
TRANSYLVANIA | US 276 | US 64 TO AVERY CREEK TRAIL HEAD. WIDEN TO 3-LANES WITH BICYCLE LANES. NC FLAP DOT 276(1). | HIGHWAY | 14 | LAND-OF-SKY RPO | R-5865 | EXEMPT | FLAP, S(M) |  |  |  |  | 2023 | 3148000 |  |  | 3148000 | STATE MATCHING FUNDS FROM DIVISION 14 MAINTENANCE FUNDING
TRANSYLVANIA | US 64 | WEST OF NC 281 N NEAR LAKE TOXAWAY TO INDIAN CREEK. WIDENING AND REALIGNMENT. | HIGHWAY | 14 | LAND-OF-SKY RPO | R-2409C | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
TRANSYLVANIA | US 64 | INDIAN CREEK TO FLAT CREEK VALLEY ROAD. WIDENING AND REALIGNMENT | HIGHWAY | 14 | LAND-OF-SKY RPO | R-2409D | NOT FUNDED | BGLT5 | NOT FUNDED | 1000000 |  |  | NOT FUNDED | 5000000 |  |  | 6000000
TRANSYLVANIA | US 64 | US 276, NC 280 INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 14 | LAND-OF-SKY RPO | R-5799 | REGION G | T | 2022 | 5890000 | 2022 | 600000 | 2024 | 16000000 |  |  | 22490000 | BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE)
TRANSYLVANIA | US 64 (SOUTH BROAD STREET) | US 64 BUSINESS (SOUTH CALDWELL STREET), SR 1116 (NORTH COUNTRY CLUB ROAD) INTERSECTION. IMPROVE INTERSECTION ALIGNMENT. | HIGHWAY | 14 | LAND-OF-SKY RPO | R-5882 | NOT FUNDED | T | NOT FUNDED | 4400000 | NOT FUNDED | 1200000 | NOT FUNDED | 1900000 |  |  | 7500000
TRANSYLVANIA | US 64, US 276 | FORTUNE COVE ROAD TO US 64 BUSINESS (NORTH CALDWELL STREET). CONSTRUCT MEDIAN AND ACCESS CONTROL MEASURES. | HIGHWAY | 14 | LAND-OF-SKY RPO | R-5800 | REGION G | T | 2023 | 14800000 | 2023 | 3900000 | 2025 | 17801000 |  |  | 36501000 | RIGHT-OF-WAY IN PROGRESS
TRANSYLVANIA | TRANSYLVANIA COUNTY | ADMINISTRATION | PUBLIC TRANSIT | 14 |  | TK-6167 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 644000 | 644000 | FUNDS AUTHORIZED IN PROGRESS
TRANSYLVANIA, JACKSON | US 64 | NC 107 AT CASHIERS TO US 178 AT ROSMAN. SAFETY IMPROVEMENTS AND CLIMBING LANES AT SELECTED LOCATIONS. | HIGHWAY | 14 | LAND-OF-SKY RPO, SOUTHWESTERN RPO | R-2409 | [11 empty] | DIVISION PROJECT
TYRRELL | US 64 | EAST OF COLUMBIA TO WEST OF SR 1229 (OLD US 64) AT ALLIGATOR RIVER. | HIGHWAY | 1 | ALBEMARLE RPO | R-2545AA | NOT FUNDED | T | NOT FUNDED | 1825000 | NOT FUNDED | 1395000 | NOT FUNDED | 24800000 |  |  | 28020000
TYRRELL | US 64 | WEST OF SR 1229 (OLD US 64) AT ALLIGATOR RIVER TO WEST OF ALLIGATOR RIVER. | HIGHWAY | 1 | ALBEMARLE RPO | R-2545AB | NOT FUNDED | T | NOT FUNDED | 2025000 | NOT FUNDED | 1611000 | NOT FUNDED | 72500000 |  |  | 76136000
TYRRELL | US 64 | COLUMBIA TO ALLIGATOR RIVER BRIDGE. MODERNIZE ROADWAY. | HIGHWAY | 1 | ALBEMARLE RPO | R-5940 | DIVISION 1 | NHP | 2028 | 900000 | 2028 | 9100000 | 2030 | 47100000 |  |  | 57100000
TYRRELL | TYRELL COUNTY | ADMINISTRATION | PUBLIC TRANSIT | 1 | ALBEMARLE RPO | TK-6168 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 88000 | 88000 | FUNDS AUTHORIZED IN PROGRESS
TYRRELL, DARE | US 64 | EAST OF COLUMBIA TO EAST OF THE ALLIGATOR RIVER. WIDEN TO MULTI-LANES. | HIGHWAY | 1 | ALBEMARLE RPO | R-2545 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY
UNION | CHARLOTTE-MONROE EXECUTIVE AIRPORT (EQY) | RELOCATE AND WIDEN THE EXISTING PARALLEL TAXIWAY SECTION BETWEEN THE EXISTING RAMP AND THE RUNWAY 5 TAXIWAY EXTENSION. | AVIATION | 10 | CHARLOTTE REGIONAL TPO | AV-5814 | DIVISION 10 | T |  |  |  |  | 2028 | 8800000 |  |  | 8800000
UNION | INDIAN TRAIL | NORTH INDIAN TRAIL ROAD. SOUTH FORK ROAD TO LIBERTY LANE. CONSTRUCT COMPLETE STREET. INCLUDES INTERSECTION IMPROVEMENTS AT SR 1008 (INDIAN TRAIL ROAD) AND SR 1367 (UNIONVILLE-INDIAN TRAIL ROAD (FORMERLY U-6250). | BIKE/PED | 10 | CHARLOTTE REGIONAL TPO | EB-5931 | DIVISION 10 | BGANY, BGDA, L | 2022 | 260000 |  |  | 2023 | 6622000 | 2020 | 391000 | 7273000 | $723,000 IN ADDITIONAL LOCAL FUNDS ARE NON-PARTICIPATORY FROM THE TOWN OF INDIAN TRAIL; $4.719M IN BGANY USED AS PART OF FUND SWAP.
UNION | MARVIN LOOP TRAIL | SR 3635 (MARVIN ROAD) AT SADDLE AVENUE TO SR 1316 (MARVIN SCHOOL ROAD) AT YELLOW JASMINE LANE. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | BIKE/PED | 10 | CHARLOTTE REGIONAL TPO | BL-0012 | DIVISION 10 | BGDA, L | 2024 | 157000 |  |  | 2025 | 1309000 | 2023 | 244000 | 1710000
UNION | SR 1735 (EAST UNION STREET) | SR 1719 (OLIVE BRANCH ROAD) TO PARK DRIVE. CONSTRUCT PEDESTRIAN IMPROVEMENTS AND INSTALL PAVEMENT MARKINGS. | BIKE/PED | 10 | CHARLOTTE REGIONAL TPO | BL-0011 | DIVISION 10 | BGDA, L |  |  |  |  | 2024 | 335000 | 2023 | 63000 | 398000
UNION | US 74 | SR 1520 (INDIAN TRAIL FAIRVIEW ROAD) TO SR 1367 (UNIONVILLE INDIAN TRAIL ROAD). CONSTRUCT A MULTI-USE PATH. SR 1367 (UNIONVILLE INDIAN TRAIL ROAD) TO OAKWOOD LANE. CONSTRUCT A MULTI-USE PATH. | BIKE/PED | 10 | CHARLOTTE REGIONAL TPO | EB-5723 | DIVISION 10 | CMAQ, L, TAANY | 2022 | 125000 |  |  | 2023 | 3930000 |  |  | 4055000 | $2.042M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
UNION | WAXHAW | DOWNTOWN WAXHAW PEDESTRIAN AND BICYCLE FACILITY ENHANCEMENTS. | BIKE/PED | 10 | CHARLOTTE REGIONAL TPO | EB-5819 | DIVISION 10 | BGDA, L |  |  |  |  | 2023 | 1230000 |  |  | 1230000
UNION | INDIAN TRAIL | UNIONVILLE-INDIAN TRAIL ROAD AND SARDIS ROAD. CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5987 | DIVISION 10 | BGDA, CMAQ, L | 2020 | 25000 |  |  | 2020 | 3796000 |  |  | 3821000 | UNDER CONSTRUCTION. $1.68M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP. ADDITIONAL FUNDING FOR PE AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES.
UNION | MARVIN | NEW TOWN ROAD AT MARVIN ROAD. CONSTRUCT ROUNDABOUT. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6088 | DIVISION 10 | BGDA, CMAQ, L, S(M) |  |  |  |  | 2023 | 1943000 |  |  | 1943000 | RIGHT-OF-WAY IN PROGRESS. STATE MATCH FOR CONSTRUCTION IS A COMBINATION OF SPOT SAFETY FUNDS ($121,000), SMALL CONSTRUCTION ($66,610), AND CONTINGENCY FUNDS ($105,000). PROJECT PART OF I-77 PPSL FUND SWAP.
UNION | NC 16 (PROVIDENCE ROAD SOUTH) | SR 1316 (REA ROAD EXTENSION) TO SR 3530 (WAXHAW PARKWAY) IN WAXHAW. WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5769
UNION | NC 16 (PROVIDENCE ROAD SOUTH) | SR 1316 (REA ROAD EXTENSION) TO SR 1307 (BONDS GROVE CHURCH RD). WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5769A | REGION E | T | 2024 | 10700000 | 2024 | 4400000 | 2027 | 26401000 |  |  | 41501000
UNION | NC 16 (PROVIDENCE ROAD SOUTH) | SR 1307 (BONDS GROVE CHURCH RD) TO SR 3530 (WAXHAW PARKWAY) IN WAXHAW. WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5769B | REGION E | T | 2024 | 15500000 | 2024 | 2800000 | 2027 | 31400000 |  |  | 49700000
UNION | NC 200 | REPLACE BRIDGE 890053 OVER STEWARTS CREEK. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | B-5949 | REGION E | BFP | 2024 | 120000 |  |  | 2025 | 2500000 |  |  | 2620000
UNION | NC 75 | SR 1111 (OLD PROVIDENCE ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6248 | EXEMPT | BGDA, L | 2023 | 1598000 |  |  | 2025 | 3543000 | 2021 | 200000 | 5341000 | STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT.
UNION | NC 84 | NC 16 TO SR 1008 (WAXHAW-INDIAN TRAIL ROAD) IN WESLEY CHAPEL. CONSTRUCT FOUR LANE ROADWAY, PART ON NEW LOCATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-3467 | REGION E | BGANY | 2024 | 70000000 | 2024 | 3000000 | 2027 | 44900000 |  |  | 117900000
UNION | NC 84 | SR 1007 (ROCKY RIVER ROAD) INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6246 | EXEMPT | BGDA, L, S(M) | 2023 | 350000 |  |  | 2025 | 2080000 | 2022 | 200000 | 2630000 | STBG-DA FUNDS ARE EXEMPT SINCE THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT. LOCAL MATCH IS $50K FROM THE CITY OF MONOROE AND $50K FROM UNION COUNTY. STATE MATCH IS SPOT MOBILITY FUNDS.
UNION | NC 84 | SR 1162 (POTTER ROAD) INTERSECTION. IMPROVE INTERSECTON. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6247 | EXEMPT | BGDA, L, S(M) | 2023 | 270000 |  |  | 2025 | 2555000 | 2021 | 363000 | 3188000 | "S(M)" FUNDS REPRESENT SPOT MOBILITY FUNDS, STBG-DA FUNDS ARE EXEMPT AS THEY ARE BEING USED ON AN ELIGIBLE REGIONAL IMPACT PROJECT.
UNION | NORTH CHARLOTTE AVENUE AND NEW TOWN ROAD | NORTH CHARLOTTE AVENUE FROM WALNUT STREET TO NC 200 AND NEW TOWN ROAD FROM CUTHBERTSON ROAD TO ENNIS ROAD. RESURFACE ROADWAYS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | HL-0039A | DIVISION 10 | BGDACV |  |  |  |  | 2022 | 963000 |  |  | 963000
UNION | SR 1004 (LAWYERS ROAD) | I-485 TO SR 1524 (STEVENS MILL ROAD). WIDEN ROADWAY TO FOUR LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6170 | NOT FUNDED | BGANY | NOT FUNDED | 3000000 | NOT FUNDED | 1400000 | NOT FUNDED | 8800000 |  |  | 13200000
UNION | SR 1009 (CHARLOTTE AVENUE) | SEYMOUR STREET TO NC 200 (DICKERSON BOULEVARD). WIDEN TO FOUR-LANES DIVIDED. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6031 | DIVISION 10 | T | 2028 | 7700000 | 2028 | 4500000 | 2030 | 10100000 |  |  | 22300000
UNION | SR 1009 (JOHN STREET-OLD MONROE ROAD) | WEST OF MORNINGSIDE MEADOW LANE TO EAST OF SR 1377 (WESLEY CHAPEL-STOUTS ROAD) | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-4714B | DIVISION 10 | BGANY, BGDA, O, S(M), T | 2021 | 46000000 | 2021 | 2300000 | 2024 | 51674000 |  |  | 99974000 | TO BE LET WITH U-4714AC. BUILD NC BOND FUNDING: $20M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE); $8.5M FOR CONSTRUCTION, PAYBACK FY 2026-2040 (FY 2026 / YR 8 SALE).
UNION | SR 1009 (OLD MONROE ROAD) | SR 1377 (WESLEY CHAPEL-STOUTS ROAD) TO SR 1349 (AIRPORT ROAD). | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6169 | NOT FUNDED | BGANY | NOT FUNDED | 3000000 | NOT FUNDED | 2800000 | NOT FUNDED | 26100000 |  |  | 31900000
UNION | SR 1357 (POTTER ROAD) | SR 1357 (POTTER ROAD) AND SR 1358 (FOREST LAWN DRIVE). IMPROVE INTERSECTION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | HL-0055 | DIVISION 10 | L, T(DA) | 2024 | 643000 |  |  | 2025 | 1373000 | 2023 | 475000 | 2491000 | $380K IN STBG-DA FUNDS SWITCHED WITH $380K IN T(DA) FOR PE, $466K IN STBG-DA FUNDS SWITCHED WITH $466K IN T(DA) FOR ROW, AND $1.098M IN STBG-DA FUNDS SWITCHED WITH $1.098M IN T(DA) FOR CON AS PART OF FUND SWAP.
UNION | SR 1362 (CHESTNUT LANE CONNECTOR) | SR 1367 (MATTHEWS INDIAN TRAIL ROAD) TO SR 1368 (GRIBBLE ROAD). CONSTRUCT ROAD ON NEW LOCATION. INTERSECTION OF US 74 AND EXISTING SR 1362 (CHESTNUT LANE CONNECTOR). CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5808 | DIVISION 10 | T | 2019 | 1615000 |  |  | 2023 | 13501000 |  |  | 15116000 | RIGHT-OF-WAY IN PROGRESS
UNION | SR 1681 (OLD CAMDEN ROAD) | REPLACE BRIDGE 890021 OVER STEWART'S CREEK. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | B-5376 | DIVISION 10 | BGOFF | 2023 | 210000 |  |  | 2024 | 2100000 |  |  | 2310000
UNION | SR 2111 (BELK MILL ROAD) | REPLACE BRIDGE 890129 OVER LANES CREEK. | HIGHWAY | 10 | ROCKY RIVER RPO | B-5806 | DIVISION 10 | BGOFF |  |  |  |  | 2022 | 1225000 |  |  | 1225000 | RIGHT-OF-WAY IN PROGRESS.
UNION | STALLINGS | SR 1364 (PLEASANT PLAINS ROAD) AT SR 1357 (POTTERS ROAD) IN STALLINGS. CONSTRUCT INTERSECTION IMPROVEMENTS INCLUDING LEFT TURN LANES AND MODIFICATION OF TRAFFIC SIGNAL. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5112 | PRE-STI (TRANSITION) | BGDA, CMAQ, HSIP, L | 2021 | 676000 |  |  | 2023 | 4571000 |  |  | 5247000 | RIGHT-OF-WAY IN PROGRESS - PROJECT TO BE ADMINISTERED BY THE TOWN OF STALLINGS. $1.6M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
UNION | STALLINGS | WEDDINGTON-MATTHEWS ROAD AT CHESTNUT LANE. CONSTRUCT ROUNDABOUT. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6091 | DIVISION 10 | CMAQ, L, O, S(M) | 2020 | 450000 |  |  | 2022 | 2425000 | 2020 | 375000 | 3250000 | UNDER CONSTRUCTION. STATE MATCH IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND ROW TO COVER ANTICIPATED EXPENDITURES. OTHER FUNDS PROVIDED BY DEVELOPER. LOCAL FUNDS PROVIDED BY STALLINGS AND UNION COUNTY PER AGREEMENT.
UNION | UNION COUNTY | CONSTRUCT IMPROVEMENTS AT SR 1315 (NEW TOWN ROAD) AND SR 1008 (WAXHAW-INDIAN TRAIL ROAD) INTERSECTION | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | W-5710Y | DIVISION 10 | BGANY, HSIP, S(M) |  |  |  |  | 2021 | 2581000 |  |  | 2581000 | $1.385M IN BGANY USED AS PART OF FUND SWAP.
UNION | UNION COUNTY | INTERSECTION OF NC 200, NC 522, SR 1007 (SOUTH ROCKY RIVER ROAD), AND SR 1146 (PARKWOOD SCHOOL ROAD). CONSTRUCT 5-APPROACH ROUNDABOUT. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | W-5710Z | REGION E | BGANY, BGDA, HSIP, L, S(M) | 2020 | 35000 |  |  | 2022 | 2571000 | 2020 | 195000 | 2801000 | $1.486M IN BGANY USED AS PART OF FUND SWAP.
UNION | US 601 | EXISTING US 74 TO THE MONROE BYPASS. WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-4024 | REGION E | T | 2028 | 3300000 | 2028 | 400000 | 2030 | 13700000 |  |  | 17400000 | COORDINATE WITH U-5723
UNION | US 74 | US 601 INTERCHANGE. CONSTRUCT IMPROVEMENTS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5723 | STATEWIDE MOBILITY | T |  |  |  |  | 2025 | 15001000 |  |  | 15001000 | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-4024
UNION | US 74 | NC 200 (DICKERSON BOULEVARD) TO SR 1007 (ROCKY RIVER ROAD). WIDEN EXISTING ROADWAY. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5764 | REGION E | T | 2025 | 24500000 | 2025 | 2700000 | 2028 | 43399000 |  |  | 70599000 | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5931
UNION | US 74 | INTERSECTION OF US 74 AND SECREST SHORTCUT ROAD. CONSTRUCT IMPROVEMENTS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5931 | STATEWIDE MOBILITY | T | 2025 | 1100000 | 2025 | 1000000 | 2028 | 4600000 |  |  | 6700000 | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5764.
UNION | US 74 (ROOSEVELT BLVD) | SR 1514 (ROCKY RIVER ROAD) INTERSECTION. RECONFIGURE TO SUPERSTREET. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5703A | STATEWIDE MOBILITY | [10 empty] | COMPLETE
UNION | US 74 (ROOSEVELT BLVD) | REALIGN JAMES HAMILTON ROAD TO INTERSECT WITH SR 1514 (ROCKY RIVER ROAD) AT MYERS ROAD. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5703B | STATEWIDE MOBILITY | O, T | 2023 | 900000 |  |  | 2025 | 1600000 |  |  | 2500000
UNION | US 74 (ROOSEVELT BOULEVARD) | SR 1514 (ROCKY RIVER ROAD) INTERSECTION. RECONFIGURE TO SUPERSTREET. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5703 | [11 empty] | OTHER FUNDS PROVIDED BY THE CITY OF MONROE
UNION | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE ROCKY RIVER RPO. | HIGHWAY | 10 | ROCKY RIVER RPO | C-5617 | EXEMPT | CMAQ, L | 2020 | 6000 |  |  | 2020 | 38000 | 2020 | 18000 | 62000
UNION | VARIOUS | VARIOUS MAINTENANCE ACTIVITIES INCLUDING RESURFACING, TRAFFIC SIGNAL LOOP REPLACEMENT, AND PAVEMENT RESTRIPING. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | HL-0039
UNION | VARIOUS | REPLACE PAVEMENT MARKINGS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | HL-0039B | EXEMPT | BGDACV |  |  |  |  | 2022 | 126000 |  |  | 126000
UNION | VARIOUS | REPLACE TRAFFIC SIGNAL LOOPS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | HL-0039C | EXEMPT | BGDACV |  |  |  |  | 2022 | 164000 |  |  | 164000
UNION | VARIOUS | DIVISION 10 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS IN STATEWIDE CATEGORY. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | W-5210SW | STATEWIDE MOBILITY
UNION | WAXHAW | NC 16 TO SUNSET HILL ROAD. KENSINGTON DRIVE CORRIDOR IMPROVEMENT PROJECT. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | EB-5950 | DIVISION 10 | BGDA, L | 2022 | 591000 |  |  | 2024 | 3818000 |  |  | 4409000
UNION | WEDDINGTON | WEDDINGTON-MATTHEWS ROAD AT TILLEY MORRIS ROAD. CONSTRUCT ROUNDABOUT. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6090 | DIVISION 10 | CMAQ, L, S(M) | 2020 | 261000 |  |  | 2022 | 2443000 | 2020 | 391000 | 3095000 | RIGHT-OF-WAY IN PROGRESS. STATE MATCH IS SPOT SAFETY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PRELIMINARY ENGINEERING AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. $1.988M IN STBG-DA SWITCHED FOR CMAQ AS PART OF I-77 PPSL FUND SWAP.
UNION | WESLEY CHAPEL | POTTER ROAD AT WESLEY CHAPEL ROAD. CONSTRUCT ROUNDABOUT. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6087 | DIVISION 10 | BGDA, CMAQ, L, S(M) |  |  |  |  | 2023 | 1880000 |  |  | 1880000 | RIGHT-OF-WAY IN PROGRESS. STATE MATCH IS SPOT MOBILITY FUNDS FROM THE HIGHWAY FUND. ADDITIONAL FUNDING FOR PE AND RIGHT-OF-WAY TO COVER ANTICIPATED EXPENDITURES. CURRENT MATCH FOR PE EXCEEDS FEDERAL AGREEMENT. PROJECT PART OF I-77 FUND SWAP.
UNION | UNION COUNTY | 5307 FUNDS TO REH/REN EQUIPMENT FFY20-21 (20-SU-089) | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO | TA-6149 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 17000 | 17000 | ADD FUNDING TO FY20
UNION | UNION COUNTY | ADMINISTRATION | PUBLIC TRANSIT | 10 | ROCKY RIVER RPO | TK-6169 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 732000 | 732000 | FUNDS AUTHORIZED IN PROGRESS
UNION | UNION COUNTY | 5307 OPERATIONS FOR FFY20-21 (20-LU-089) | PUBLIC TRANSIT | 10 | CHARLOTTE REGIONAL TPO | TO-6156 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 1566000 | 1566000 | ADDING FUNDS FOR FFY20-21
UNION | CSX SF LINE | MILEPOST 311.8 TO MILEPOST 316.9. 10,000 FEET SIDING EXTENSION AT STOUTS IN UNION COUNTY. | RAIL | 10 | CHARLOTTE REGIONAL TPO | P-5704 | REGION E | O, T |  |  |  |  | 2019 | 4000000 |  |  | 4000000 | UNDER CONSTRUCTION. OTHER FUNDING PROVIDED BY CSX CORPORATION
UNION | CSX SF LINE | SR 1377 (WESLEY CHAPEL STOUTS ROAD). CONSTRUCT GRADE SEPERATION. | RAIL | 10 | CHARLOTTE REGIONAL TPO | P-5744 | STATEWIDE MOBILITY | DP, O, T | 2025 | 5851000 | 2025 | 826000 | 2027 | 9126000 |  |  | 15803000 | DP REPRESENTS FEDERAL CRISI GRANT. OTHER FUNDING PROVIDED BY CSX.
UNION | CSX SG LINE | CONSTRUCT RAIL SIDING AND GRADE SEPARATION IN VICINITY OF SR 1300 (HELMS ROAD) AND CLOSE AT-GRADE CROSSINGS AT SR 1300 (HELMS ROAD) AND SR 1432 (TORY PATH). | RAIL | 10 | CHARLOTTE REGIONAL TPO | P-5748 | REGION E | [10 empty] | DP REPRESENTS FEDERAL INFRA GRANT FUNDS; OTHER FUNDING PROVIDED BY CSX.
UNION | CSX SG LINE | CONSTRUCT RAIL SIDING IN WAXHAW | RAIL | 10 | CHARLOTTE REGIONAL TPO | P-5748A | REGION E | T |  |  |  |  | 2022 | 5894000 |  |  | 5894000
UNION | CSX SG LINE | SR 1300 (HELMS ROAD) INTERSECTION. CONSTRUCT GRADE SEPARATION AND CLOSE AT-GRADE CROSSING AT SR 1432 (TORY PATH). | RAIL | 10 | CHARLOTTE REGIONAL TPO | P-5748B | REGION E | DP, O, T | 2023 | 5000000 | 2023 | 378000 | 2024 | 18178000 |  |  | 23556000
UNION | SR 3522 (WEDDINGTON ROAD) | CSX CROSSING 631587H NEAR MONROE. CONSTRUCT SAFETY IMPROVEMENTS. | RAIL | 10 | CHARLOTTE REGIONAL TPO | RX-2010A | DIVISION 10 | RR |  |  |  |  | 2023 | 800000 |  |  | 800000
UNION, ANSON, MECKLENBURG | NC 218 | US 74 IN ANSON COUNTY TO US 601 IN UNION COUNTY, AND FROM MILL GROVE ROAD IN UNION COUNTY TO I-485 IN MECKLENBURG COUNTY. INSTALL MILLED RUMBLE STRIPS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | HS-2010C | REGION E | HSIP |  |  |  |  | 2022 | 616000 |  |  | 616000
UNION, MECKLENBURG | IDLEWILD ROAD | SR 3175 (STALLINGS ROAD) TO SR 1524 (STEVENS MILL ROAD). WIDEN EXISTING ROADWAY. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-4913 | DIVISION 10 | T | 2026 | 8000000 | 2026 | 3900000 | 2028 | 28000000 |  |  | 39900000
UNION, MECKLENBURG | SR 1009 (JOHN STREET-OLD MONROE ROAD) | SR 3448-SR 3474 (TRADE STREET) TO SR 1377 (WESLEY CHAPEL-STOUTS ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-4714 | [11 empty] | OTHER FUNDS PROVIDED BY TOWN OF INDIAN TRAIL.
UNION, MECKLENBURG | SR 1009 (JOHN STREET-OLD MONROE ROAD) | EAST OF I-485 TO WEST OF MORNINGSIDE MEADOW LANE | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-4714AC | DIVISION 10 | BGANY, BGDA, S(M), T, T(DA) | 2019 | 11780000 | 2019 | 2200000 | 2024 | 20439000 |  |  | 34419000 | TO BE LET WITH U-4714B. BUILD NC BOND FUNDING: $8.4M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE). $7.7M IN STBG-DA FUNDS SWITCHED WITH $7.7M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP.
UNION, MECKLENBURG | VARIOUS | DIVISION 10 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS IN DIVISION CATEGORY. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | W-5210DIV | DIVISION 10
VANCE | SR 1162 (DABNEY DRIVE) | COBLE BOULEVARD TO US 158 BUSINESS IN HENDERSON. CORRIDOR UPGRADE. | HIGHWAY | 5 | KERR-TAR RPO | U-5890 | DIVISION 5 | T | 2026 | 41300000 | 2026 | 7300000 | 2028 | 16800000 |  |  | 65400000
VANCE | SR 1165 (BECKFORD DRIVE) | HARRISON STREET TO NORTH PARK DRIVE IN HENDERSON. WIDEN TO THREE LANES WITH CURB AND GUTTER, STORM DRAINAGE, AND SIDEWALKS. | HIGHWAY | 5 | KERR-TAR RPO | U-4916 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION BY CITY OF HENDERSON
VANCE | US 1 | SR 1113 (LAKE LODGE ROAD) INTERSECTION. CONVERT FULL-MOVEMENT INTERSECTION TO UNSIGNALIZED SUPERSTREET. | HIGHWAY | 5 | KERR-TAR RPO | W-5805G | STATEWIDE MOBILITY | HSIP | 2023 | 45000 |  |  | 2023 | 955000 |  |  | 1000000
VANCE | KERR AREA TRANSPORTATION AUTHORITY | PURCHASE ONE (1) EXPANSION VEHICLE. | PUBLIC TRANSIT | 5 | KERR-TAR RPO | TA-6711 | REGION C | FEDT, L, T | [6 empty] | 2020 | 56000 | 56000
VANCE, WARREN | I-85 | SOUTH OF US 158 IN VANCE COUNTY TO NORTH OF SR 1237 (MANSON DREWRY ROAD) IN WARREN COUNTY | HIGHWAY | 5 | KERR-TAR RPO | I-0914BA | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
VANCE, WARREN, FRANKLIN, HALIFAX, WAKE | CSX S-LINE CSX SA-LINE | CSX S-LINE FROM RALEIGH TO VIRGINIA STATE LINE AND CSX SA-LINE FROM RALEIGH TO WELDON. AQUIRE RIGHT OF WAY, UPGRADE EXISTING TRACK AND CONSTRUCT NEW TRACK. | RAIL | 4, 5 | KERR-TAR RPO, CAPITAL AREA MPO, PEANUT BELT RPO | P-5753 | [11 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY
WAKE | RALEIGH DURHAM INTERNATIONAL AIRPORT (RDU) | RECONSTRUCT RUNWAY 5L-23R. | AVIATION | 5 | CAPITAL AREA MPO | AV-5700 | STATEWIDE MOBILITY | O, T |  |  |  |  | 2023 | 101000000 |  |  | 101000000
WAKE | (SR 1307) WEST CHATHAM STREET | HUNTER STREET TO SAUNDER STREET IN APEX. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. | BIKE/PED | 5 | CAPITAL AREA MPO | EB-6046 | DIVISION 5 | BGDA, L |  |  |  |  | 2022 | 953000 |  |  | 953000
WAKE | AVENT FERRY ROAD | COTTEN LANE TO WEST BALLANTINE STREET AND CONNECTING FROM THE SOUTH / EAST SIDE OF AVENT FERRY ROAD TO STINSON AVENUE VIA PINE AVENUE IN HOLLY SPRINGS. CONSTRUCT SIDEWALK EXTENSIONS. | BIKE/PED | 5 | CAPITAL AREA MPO | EB-6049 | DIVISION 5 | BGDA, L |  |  |  |  | 2022 | 1250000 |  |  | 1250000
WAKE | BEAVER CREEK GREENWAY EXTENSION | KELLY ROAD PARK TO APEX NATURE PARK IN APEX. GREENWAY EXTENSION. REALIGN ADJACENT SEGMENT OF EXISTING BEAVER CREEK GREENWAY. | BIKE/PED | 5 | CAPITAL AREA MPO | EB-6021 | DIVISION 5 | L, TADA |  |  |  |  | 2023 | 6565000 |  |  | 6565000
WAKE | BLACK CREEK GREENWAY | PHASES I, II AND V, WEST DYNASTY DRIVE TO OLD REEDY CREEK ROAD IN CARY. CONSTRUCT GREENWAY. | BIKE/PED | 5 | CAPITAL AREA MPO | EB-5894 | DIVISION 5 | CMAQ, L, TAANY |  |  |  |  | 2022 | 6231000 |  |  | 6231000
WAKE | CRABTREE CREEK GREENWAY | LASSITER MILL ROAD TO HERTFORD STREET IN RALEIGH. CONSTRUCT GREENWAY TRAIL. | BIKE/PED | 5 | CAPITAL AREA MPO | BL-0027 | DIVISION 5 | BGDA, L |  |  |  |  | 2023 | 1689000 |  |  | 1689000
WAKE | CRABTREE CREEK GREENWAY | BOND PARK TO SR 1615 (HIGH HOUSE ROAD) IN CARY. CONSTRUCT GREENWAY BETWEEN BLACK CREEK AND WHITE OAK CREEK GREENWAYS AND BETWEEN BOND PARK AND PRESTON FIELDS PARK. | BIKE/PED | 5 | CAPITAL AREA MPO | BL-0036 | EXEMPT | CMAQ, L |  |  |  |  | 2024 | 1402000 | 2024 | 248000 | 1650000
WAKE | CRABTREE CREEK GREENWAY CONNECTOR | CRABTREE CREEK GREENWAY TO WESTON GREENWAY IN CARY. CONSTRUCT 10-FOOT GREENWAY INCLUDING GRADE SEPARATION UNDER WESTON PARKWAY. | BIKE/PED | 5 | CAPITAL AREA MPO | BL-0037 | EXEMPT | CMAQ, L |  |  |  |  | 2023 | 2825000 |  |  | 2825000
WAKE | EAST JONES STREET | US 401 / NC 42 TO NORTH WOODROW STREET IN FUQUAY-VARINA. CONSTRUCT SIDEWALKS. | BIKE/PED | 5 | CAPITAL AREA MPO | BL-0038 | EXEMPT | CMAQ, L | 2022 | 480000 |  |  | 2023 | 353000 | 2022 | 74000 | 907000
WAKE | LITTLE DRIVE | SR 2153 (LOUIS STEPHENS DRIVE) TO CSX RAILROAD IN RESEARCH TRIANGLE PARK. CONSTRUCT GREENWAY TRAIL. | BIKE/PED | 5 | CAPITAL AREA MPO | BL-0026 | DIVISION 5 | BGDA, L |  |  |  |  | 2023 | 1063000 | 2022 | 219000 | 1282000
WAKE | NC 55 (EAST WILLIAMS STREET) | SR 1301 (SUNSET LAKE ROAD) TO NC 55 IN HOLLY SPRINGS. CONSTRUCT SIDEWALK. | BIKE/PED | 5 | CAPITAL AREA MPO | EB-5895 | DIVISION 5 | L, TAANY |  |  |  |  | 2021 | 500000 |  |  | 500000 | UNDER CONSTRUCTION
WAKE | NOTTINGHAM DRIVE; JOHNSON STREET NORWELL BOULEVARD | NORWELL BOULEVARD FROM BEXLEY BLUFF LANE TO WESTON PKWY, NOTTINGHAM DRIVE FROM DONALDSON DRIVE TO BUCK JONES ROAD, AND JOHNSON STREET FROM SR 1652 (NORTH HARRISON AVENUE) TO NORTH ACADEMY STREET IN CARY. CONSTRUCT SIDEWALK IMPROVEMENTS. | BIKE/PED | 5 | CAPITAL AREA MPO | BL-0039 | EXEMPT | CMAQ, L | 2022 | 167000 |  |  | 2023 | 1144000 | 2022 | 50000 | 1361000
WAKE | SR 1012 (WESTERN BOULEVARD) | CONSTRUCT BICYCLE / PEDESTRIAN TUNNEL IMMEDIATELY WEST OF SR 1321 (AVENT FERRY ROAD) IN RALEIGH. | BIKE/PED | 5 | CAPITAL AREA MPO | EB-5718 | DIVISION 5 | L, TAANY |  |  |  |  | 2025 | 4000000 |  |  | 4000000 | COORDINATE WITH B-5675 (NON-STIP PROJECT) AND TO-6166
WAKE | SR 1152 (HOLLY SPRINGS ROAD) | FLINT POINT LANE TO MIDDLECREST WAY IN HOLLY SPRINGS. ENHANCE PEDESTRIAN SAFETY. | BIKE/PED | 5 | CAPITAL AREA MPO | BL-0023 | DIVISION 5 | BGDA, L |  |  |  |  | 2022 | 1115000 |  |  | 1115000
WAKE | SR 1306 (LAURA DUNCAN ROAD) | APEX COMMUNITY PARK AND NORTH SALEM STREET IN APEX. IMPROVE SAFETY OF PEDESTRIAN CROSSING. | BIKE/PED | 5 | CAPITAL AREA MPO | EB-6019 | DIVISION 5 | BGDA, L |  |  |  |  | 2021 | 544000 |  |  | 544000 | PLANNING / DESIGN / RIGHT OF WAY / CONSTRUCTION BY TOWN OF APEX. UNDER CONSTRUCTION.
WAKE | SR 1616 / NON-SYSTEM (OLD APEX ROAD) | WEST CHATHAM STREET TO MURPHY DRIVE IN CARY, INCLUDING CSX RAILROAD CROSSING. COMPLETE SIDEWALK GAPS. | BIKE/PED | 5 | CAPITAL AREA MPO | BL-0048 | DIVISION 5 | BGDA, L |  |  |  |  | 2023 | 2000000 |  |  | 2000000
WAKE | SR 1637 (CHURCH STREET) | SR 3014 (MORRISVILLE-CARPENTER ROAD) TO DURHAM COUNTY LINE IN MORRISVILLE. CONSTRUCT SIDEWALKS TO FILL IN GAPS. | BIKE/PED | 5 | CAPITAL AREA MPO | EB-5838 | DIVISION 5 | L, TAANY | 2023 | 250000 |  |  | 2024 | 1450000 | 2022 | 300000 | 2000000
WAKE | SR 2000 (WAKE FOREST ROAD) | FOREST RIDGE ROAD TO RONALD DRIVE IN RALEIGH. EXTEND EXISTING SIDEWALKS. | BIKE/PED | 5 | CAPITAL AREA MPO | BL-0025 | DIVISION 5 | BGDA, L | 2023 | 200000 |  |  | 2023 | 1339000 | 2022 | 150000 | 1689000
WAKE | SR 2768 (SOUTHEAST JUDD PARKWAY) | SOUTH OF LOGAN MEADOW COURT TO NORTH OF OLDWYCK DRIVE IN FUQUAY-VARINA. COMPLETE SIDEWALK GAPS. | BIKE/PED | 5 | CAPITAL AREA MPO | BL-0054 | DIVISION 5 | BGDA, L | 2023 | 50000 |  |  | 2023 | 615000 | 2023 | 60000 | 725000
WAKE | SR 3015 (AIRPORT BOULEVARD) | MCCRIMMON PARKWAY TO FACTORY SHOPPES ROAD IN MORRISVILLE. CONSTRUCT SIDEWALK. | BIKE/PED | 5 | CAPITAL AREA MPO | EB-5814 | DIVISION 5 | L, TAANY |  |  |  |  | 2022 | 800000 |  |  | 800000
WAKE | SR 3112 (NW CARY PARKWAY) | VICINITY OF BLACK CREEK IN CARY. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. | BIKE/PED | 5 | CAPITAL AREA MPO | BL-0024 | DIVISION 5 | BGDA, L | 2022 | 54000 |  |  | 2023 | 4911000 | 2022 | 960000 | 5925000
WAKE | US 64 BUSINESS WENDELL BOULEVARD (WENDELL BOULEVA | NORTH OF SR 2346 (HANOR LANE) TO EAST OF SR 2353 (OLD WILSON ROAD) IN WENDELL. CONSTRUCT GEOMETRIC IMPROVEMENTS, SIDEWALK EXTENSION AND INSTALL PEDESTRIAN CROSSING AT SR 2329 (MARSHBURN ROAD). | BIKE/PED | 5 | CAPITAL AREA MPO | EB-6048 | DIVISION 5 | BGDA, L | 2022 | 75000 |  |  | 2022 | 384000 |  |  | 459000 | RIGHT OF WAY IN PROGRESS.
WAKE | VARIOUS | DOWNTOWN FUQUAY-VARINA TO FUQUAY VARINA HIGH SCHOOL IN FUQUAY-VARINA. CONSTRUCT SIDEWALK EXTENSIONS AND IMPROVE SAFETY OF PEDESTRIAN CROSSING. | BIKE/PED | 5 | CAPITAL AREA MPO | BL-0022 | DIVISION 5 | BGDA, L | 2023 | 150000 |  |  | 2023 | 1220000 | 2022 | 87000 | 1457000
WAKE | VARIOUS | COMPLETE SIDEWALKS GAPS IN DOWNTOWN APEX ON HILLCREST ROAD, PATE STREET, HUNTER STREET, CASH STREET, APEX PEAKWAY, AND AMBERGATE STATION. INCLUDE CROSSING IMPROVEMENTS AT INTERSECTION OF NORTH SALEM STREET AND HUNTER STREET. | BIKE/PED | 5 | CAPITAL AREA MPO | BL-0047 | DIVISION 5 | L, TADA | 2023 | 221000 |  |  | 2023 | 1524000 |  |  | 1745000
WAKE | (JUDD PARKWAY) SR 1110 / SR 5056 | NC 55 (BROAD STREET) INTERSECTION IN FUQUAY-VARINA. CONSTRUCT DEDICATED TURN LANES ON SR 5056 LEG OF JUDD PARKWAY. | HIGHWAY | 5 | CAPITAL AREA MPO | HL-0042 | EXEMPT | CMAQ, L | 2023 | 125000 |  |  | 2023 | 1494000 | 2022 | 253000 | 1872000
WAKE | (SIX FORKS ROAD) SR 1005 | SR 2006 (DURANT ROAD) INTERSECTION IN RALEIGH. ADD NORTHBOUND AND WESTBOUND RIGHT TURN LANES. | HIGHWAY | 5 | CAPITAL AREA MPO | HL-0043 | EXEMPT | CMAQ, S | 2024 | 275000 |  |  | 2025 | 1040000 | 2022 | 190000 | 1505000 | "S" FUNDING REFLECTS SPOT MOBILITY FUNDS
WAKE | (SR 3126) AIRPORT BOULEVARD | GARDEN SQUARE LANE TO SR 1637 (CHURCH STREET) IN MORRISVILLE. CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | 5 | CAPITAL AREA MPO | HL-0033 | DIVISION 5 | BGDA, L | 2022 | 600000 |  |  | 2023 | 6474000 |  |  | 7074000
WAKE | APEX PEAKWAY | JAMES STREET TO TOWHEE DRIVE. CONSTRUCT GRADE SEPARATED INTERCHANGE FOR APEX PEAKWAY AT SOUTH SALEM STREET AND CSX RR. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5928 | DIVISION 5 | BGANY, BGDA, L |  |  |  |  | 2023 | 25000000 |  |  | 25000000 | IN PROGRESS
WAKE | BLUE RIDGE ROAD | HOMEWOOD BANKS DRIVE TO CRABTREE VALLEY AVENUE IN RALEIGH. ADD CENTER TURN LANE, RAISED MEDIAN, COMPLETE STREETS IMPROVEMENTS, AND GRADE SEPARATION WITH HOUSE CREEK GREENWAY CONNECTION. | HIGHWAY | 5 | CAPITAL AREA MPO | HL-0052 | DIVISION 5 | BGDA, S |  |  |  |  | 2023 | 7997000 |  |  | 7997000
WAKE | CRABTREE CREEK GREENWAY | CONSTRUCT GREENWAY CONNECTING EXISTING GREENWAY IN CARY THROUGH MORRISVILLE, INCLUDING REPLACEMENT OF TRAIN TRESTLE. | HIGHWAY | 5 | CAPITAL AREA MPO | C-5168 | EXEMPT | [10 empty] | UNDER CONSTRUCTION BY TOWN OF MORRISVILLE
WAKE | I-40 | SR 1728 (WADE AVENUE) TO I-440 / US 1 / US 64. WIDEN TO SIX LANES. | HIGHWAY | 5 | CAPITAL AREA MPO | I-4744 | PRE-STI (TRANSITION) | NHP |  |  |  |  | 2009 | 4635000 |  |  | 4635000 | PROJECT COMPLETE - GARVEE BOND FUNDING $42.2 MILLION; PAYBACK FY 2009 - FY 2020
WAKE | I-40 | I-440 / US 64 (EXIT 301) TO JOHNSTON COUNTY LINE. | HIGHWAY | 5 | CAPITAL AREA MPO | I-5111SW | STATEWIDE MOBILITY | NHP | 2019 | 15826000 |  |  | 2018 | 108398000 |  |  | 124224000 | UNDER CONSTRUCTION - DESIGN-BUILD PROJECT; GARVEE BONDS: $15 MILLION FOR RIGHT OF WAY - PAYBACK 2019-2033
WAKE | I-40 | SR 1002 (AVIATION PARKWAY) INTERCHANGE. IMPROVE INTERCHANGE AND CONSTRUCT AUXILIARY LANE ON I-40 WESTBOUND FROM SR 1002 TO SR 3015 (AIRPORT BOULEVARD). | HIGHWAY | 5 | CAPITAL AREA MPO | I-5506 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
WAKE | I-40 | SR 3015 (AIRPORT BOULEVARD). REVISE INTERCHANGE; CONSTRUCT AUXILIARY LANES ON I-40 EASTBOUND FROM I-540 TO SR 3015 (AIRPORT BOULEVARD) AND FROM SR 3015 TO SR 1002 (AVIATION PARKWAY), AND CONSTRUCT AUXILIARY LANE ON I-40 WESTBOUND FROM SR 3015 (AIRPORT BO | HIGHWAY | 5 | CAPITAL AREA MPO | I-5700 | STATEWIDE MOBILITY | NHP, S(M) |  |  |  |  | 2020 | 51733000 |  |  | 51733000 | UNDER CONSTRUCTION; GARVEE BOND FUNDING: $10 MILLION FOR CONSTRUCTION - PAYBACK 2020-2034
WAKE | I-40 | I-440 / US 1 / US 64 INTERCHANGE IN RALEIGH. RECONSTRUCT INTERCHANGE. | HIGHWAY | 5 | CAPITAL AREA MPO | I-5703 | STATEWIDE MOBILITY | NHP | 2026 | 29600000 | 2026 | 3600000 | 2026 | 119100000 |  |  | 152300000 | DESIGN-BUILD PROJECT - TO BE LET WITH I-5701
WAKE | I-40 | NC 54 IN RALEIGH. INTERCHANGE IMPROVEMENTS. | HIGHWAY | 5 | CAPITAL AREA MPO | I-5873 | REGION C | [10 empty] | UNDER CONSTRUCTION
WAKE | I-40 | SR 1728 (WADE AVENUE) TO I-440 / US 1 IN RALEIGH. PAVEMENT AND BRIDGE REHABILITATION. | HIGHWAY | 5 | CAPITAL AREA MPO | I-5943 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2022 | 18419000 |  |  | 18419000
WAKE | I-40 | SR 1002 (AVIATION PARKWAY) TO SR 1652 (HARRISON AVENUE) IN CARY. CONSTRUCT AUXILIARY LANES IN BOTH DIRECTIONS. | HIGHWAY | 5 | CAPITAL AREA MPO | I-5966 | STATEWIDE MOBILITY | NHP | 2027 | 700000 | 2027 | 138000 | 2030 | 47701000 |  |  | 48539000
WAKE | I-40 / US 64 | I-440 / US 1 / US 64 TO SR 1370 (LAKE WHEELER ROAD) IN RALEIGH. ADD LANES. | HIGHWAY | 5 | CAPITAL AREA MPO | I-5701 | STATEWIDE MOBILITY | NHP | 2026 | 0 | 2026 | 1100000 | 2026 | 62800000 |  |  | 63900000 | DESIGN-BUILD PROJECT - TO BE LET WITH I-5703
WAKE | I-40; SR 1728 (WADE AVENUE) | EAST OF I-540 TO WADE AVENUE (EXIT 289) INCLUDING RAMPS, AND SR 1728 (WADE AVENUE) FROM I-40 TO SR 3009 (EDWARDS MILL ROAD). MILL AND RESURFACE ROADWAY, SHOULDERS AND RAMPS. | HIGHWAY | 5 | CAPITAL AREA MPO | I-5112 | PRE-STI (TRANSITION) | BGANY, NHP |  |  |  |  | 2009 | 637000 |  |  | 637000 | PROJECT COMPLETE - GARVEE BOND FUNDING $5.8 MILLION; CONSTRUCTION - PAYBACK FY 2009-2020
WAKE | I-440 / US 1 | SR 2000 (WAKE FOREST ROAD) IN RALEIGH. INTERCHANGE IMPROVEMENTS. | HIGHWAY | 5 | CAPITAL AREA MPO | I-5708 | STATEWIDE MOBILITY | NHP | 2019 | 1736000 |  |  | 2025 | 9100000 |  |  | 10836000 | RIGHT-OF-WAY IN PROGRESS; GARVEE BONDS: $1.445 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019 - 2033
WAKE | I-440 / US 1 | US 70 (GLENWOOD AVENUE) IN RALEIGH. CONSTRUCT INTERCHANGE IMPROVEMENTS, REVISE US 70 INTERSECTION WITH SR 1670 (BLUE RIDGE ROAD) / SR 1820 (LEAD MINE ROAD), AND REPLACE BRIDGE 910494 ON SR 1670. | HIGHWAY | 5 | CAPITAL AREA MPO | I-5870 | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 193100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 213701000 |  |  | 411801000
WAKE | I-440 / US 1 | US 401 (CAPITAL BOULEVARD) IN RALEIGH. INTERCHANGE IMPROVEMENTS. | HIGHWAY | 5 | CAPITAL AREA MPO | I-5970 | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 48400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 89899000 |  |  | 141599000
WAKE | I-440 / US 1 | SR 1728 (WADE AVENUE) TO SR 2000 (WAKE FOREST ROAD) IN RALEIGH. PAVEMENT REHABILITATION. | HIGHWAY | 5 | CAPITAL AREA MPO | I-5997 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2022 | 23100000 |  |  | 23100000
WAKE | I-440/US-1 | SOUTH OF SR 1313 (WALNUT STREET) TO NORTH OF SR 1728 (WADE AVENUE) IN RALEIGH. WIDEN FROM FOUR TO SIX LANES, IMPROVE STORAGE AT LAKE BOONE TRAIL INTERCHANGE AND INSTALL RAMP METERS. | HIGHWAY | 5 | CAPITAL AREA MPO | U-2719 | STATEWIDE MOBILITY | NHP | 2019 | 34749000 |  |  | 2019 | 158558000 |  |  | 193307000 | UNDER CONSTRUCTION; GARVEE BONDS: $27 MILLION FOR RIGHT OF WAY AND $125 MILLION FOR CONSTRUCTION - PAYBACK 2019-2033
WAKE | I-540 | TRIANGLE TOWNE CENTER BOULEVARD IN RALEIGH TO I-495 / US 64 / US 264 IN KNIGHTDALE. PAVEMENT REHABILITATION. | HIGHWAY | 5 | CAPITAL AREA MPO | I-5945 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2026 | 27900000 |  |  | 27900000
WAKE | I-540 | US 70 TO SR 1829 (LEESVILLE ROAD) IN RALEIGH. CONSTRUCT EASTBOUND AUXILIARY LANE. | HIGHWAY | 5 | CAPITAL AREA MPO | I-5968 | STATEWIDE MOBILITY | NHP | 2028 | 3200000 | 2028 | 10000 | 2030 | 20501000 |  |  | 23711000
WAKE | I-540 | US 70 (GLENWOOD AVENUE) TO EAST OF TRIANGLE TOWN BOULEVARD IN RALEIGH. PAVEMENT REHABILITATION. | HIGHWAY | 5 | CAPITAL AREA MPO | I-5999 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2023 | 33400000 |  |  | 33400000 | COORDINATE WITH I-5998 AND I-6000;
WAKE | I-87 / US 64 / US 264 | I-440 IN RALEIGH TO SR 1003 (ROLESVILLE ROAD). PAVEMENT REHABILITATION. | HIGHWAY | 5 | CAPITAL AREA MPO | I-5944 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2026 | 28600000 |  |  | 28600000
WAKE | I-87 / US 64 / US 264 | US 64 BUSINESS (WENDELL BOULEVARD) TO US 264. WIDEN TO 6 LANES. | HIGHWAY | 5 | CAPITAL AREA MPO | I-6005 | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 53699000 |  |  | 56499000
WAKE | I-87 / US 64 / US 264 | SR 2233 (SMITHFIELD ROAD). CONVERT INTERCHANGE TO DIVERGING DIAMOND. | HIGHWAY | 5 | CAPITAL AREA MPO | I-6007 | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 16199000 |  |  | 22099000
WAKE | LAKE BOONE TRAIL | I-440 TO RIDGE ROAD IN RALEIGH. UPGRADE ROADWAY TO COMPLETE STREET. | HIGHWAY | 5 | CAPITAL AREA MPO | HL-0032 | DIVISION 5 | BGDA, L |  |  |  |  | 2023 | 1272000 |  |  | 1272000
WAKE | MCCRIMMON PARKWAY | SR 3015 (AIRPORT BOULEVARD) TO SR 1002 (AVIATION PARKWAY) IN MORRISVILLE. WIDEN TO MULTILANES, PART ON NEW LOCATION. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5828 | DIVISION 5 | T |  |  |  |  | 2019 | 3097000 |  |  | 3097000 | UNDER CONSTRUCTION; BUILD NC BONDS: $2.406 MILLION FOR CONSTRUCTION - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE)
WAKE | MORRISVILLE PARKWAY EXTENSION | SR 1600 / SR 1625 (GREEN LEVEL CHURCH ROAD) TO EAST OF NC 55 IN CARY. MULTILANE FACILITY ON NEW LOCATION, INCLUDING INTERCHANGE AT NC 540 (TRIANGLE EXPRESSWAY / WESTERN WAKE FREEWAY). | HIGHWAY | 5 | CAPITAL AREA MPO | U-5315 | [11 empty] | PART C CONSTRUCTION BY TOWN OF CARY
WAKE | MORRISVILLE PARKWAY EXTENSION | WEST OF HIGHCROFT DRIVE TO EAST OF MILLS PARK DRIVE IN CARY. CONSTRUCT 2-LANE FACILITY ON 4-LANE RIGHT OF WAY. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5315A | DIVISION 5 | [10 empty] | UNDER CONSTRUCTION
WAKE | MORRISVILLE PARKWAY EXTENSION | NC 540 (TRIANGLE EXPRESSWAY / WESTERN WAKE FREEWAY). CONSTRUCT INTERCHANGE. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5315B | DIVISION 5 | [10 empty] | UNDER CONSTRUCTION
WAKE | MORRISVILLE PARKWAY EXTENSION | SR 1600 / SR 1625 (GREEN LEVEL CHURCH ROAD) TO EAST OF NC 55 IN CARY. WIDEN TO 4 LANES WITH LANDSCAPED MEDIAN. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5315C | NOT FUNDED | L |  |  |  |  | NOT FUNDED | 7900000 |  |  | 7900000
WAKE | NC 231 | REPLACE BRIDGE 910034 OVER NORFOLK SOUTHERN RAILROAD IN WENDELL. | HIGHWAY | 5 | CAPITAL AREA MPO | B-5986 | REGION C | BFP, NHPB | 2023 | 164000 | 2023 | 202000 | 2024 | 2948000 |  |  | 3314000
WAKE | NC 42 | SR 1101 (PINEY GROVE - WILBON ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | HIGHWAY | 5 | CAPITAL AREA MPO | W-5805A | REGION C | HSIP | 2023 | 235000 |  |  | 2024 | 725000 |  |  | 960000
WAKE | NC 42 | BRIDGE 910023 OVER MIDDLE CREEK. INSTALL GUARDRAIL. | HIGHWAY | 5 | CAPITAL AREA MPO | W-5805D | REGION C | HSIP |  |  |  |  | 2022 | 77000 |  |  | 77000
WAKE | NC 50 | REPLACE BRIDGE 910069 OVER US 70 IN GARNER. | HIGHWAY | 5 | CAPITAL AREA MPO | B-4654 | REGION C | BFP |  |  |  |  | 2023 | 9000000 |  |  | 9000000
WAKE | NC 50 (BENSON ROAD) | SR 2812 (TIMBER DRIVE) INTERSECTION IN GARNER. INTERSECTION IMPROVEMENTS. | HIGHWAY | 5 | CAPITAL AREA MPO | HL-0008C | EXEMPT | BGBA | 2022 | 50000 |  |  | 2023 | 525000 |  |  | 575000
WAKE | NC 50 (CREEDMOOR ROAD) | I-540 TO NORTH OF NC 98. WIDEN TO MULTILANE DIVIDED ROADWAY. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5891 | REGION C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 56400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 66001000 |  |  | 124101000
WAKE | NC 54 | SR 1635 (MCCRIMMON PARKWAY) IN MORRISVILLE. CONVERT AT-GRADE INTERSECTION TO GRADE SEPARATION, INCLUDING GRADE SEPARATION OF NORTH CAROLINA RAILROAD. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5747B | REGION C | T | 2019 | 72000 |  |  | 2023 | 23196000 |  |  | 23268000 | RIGHT OF WAY IN PROGRESS; BUILD NC BONDS: $60,000 FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), $4 MILLION FOR CONSTRUCTION - PAYBACK 2024-2036 (FY 2022 / YR 4 SALE).
WAKE | NC 54 | NC 540 TO PERIMETER PARK DRIVE IN MORRISVILLE. ADD LANES. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5750 | REGION C | T | 2019 | 4000 | 2022 | 1700000 | 2024 | 19164000 | 2019 | 2025000 | 22893000 | COORDINATE WITH U-5747; BUILD NC BONDS: $1.574 MILLION PE AND $3,371 FOR RIGHT OF WAY - PAYBACK 2020-2033 (FY 2019 / Y1 SALE), AND $3.359 MILLION FOR CONSTRUCTION - PAYBACK 2024-2036 (FY 2022 / YR 4 SALE)
WAKE | NC 54 (HILLSBOROUGH STREET) | SR 1664 / SR 3074 (BLUE RIDGE ROAD) IN VICINITY OF NC RAILROAD (CSX CORPORATION AND NORFOLK SOUTHERN) IN RALEIGH. CONSTRUCT GRADE SEPARATIONS AND ACCESS ROAD BETWEEN NC 54 AND SR 1664 / SR 3074. | HIGHWAY | 5 | CAPITAL AREA MPO | U-4437 | DIVISION 5 | [10 empty] | UNDER CONSTRUCTION; DESIGN-BUILD PROJECT - LET WITH U-2719; INCLUDES $19.9 MILLION FEDERAL TIGER GRANT
WAKE | NC 54; SR 1635 (MCCRIMMON PARKWAY) | SR 1635 (MCCRIMMON PARKWAY) FROM WEST OF SR 1613 (DAVIS DRIVE) TO NORTH OF SR 1637 (CHURCH STREET); NC 54 AT SR 1635 (MCCRIMMON PARKWAY) IN MORRISVILLE. WIDEN SR 1635 AND CONVERT NC 54 AT-GRADE INTERSECTION TO GRADE SEPARATION, INCLUDING GRADE SEPARATION | HIGHWAY | 5 | CAPITAL AREA MPO | U-5747 |  | T | [6 empty] | 2019 | 3001000 | 3001000 | COORDINATE WITH U-5750; BUILD NC BONDS: $2.332M FOR PE - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE)
WAKE | NC 540 | NC 55 BYPASS TO EAST OF SR 1152 (HOLLY SPRINGS ROAD). CONSTRUCT FREEWAY ON NEW LOCATION. | HIGHWAY | 5 | CAPITAL AREA MPO | R-2721A | STATEWIDE MOBILITY | NHP |  |  |  |  | 2019 | 78889000 |  |  | 78889000 | UNDER CONSTRUCTION
WAKE | NC 540 | EAST OF SR 1152 (HOLLY SPRINGS ROAD) TO EAST OF US 401. CONSTRUCT FREEWAY ON NEW LOCATION. | HIGHWAY | 5 | CAPITAL AREA MPO | R-2721B | STATEWIDE MOBILITY | NHP |  |  |  |  | 2019 | 77067000 |  |  | 77067000 | UNDER CONSTRUCTION
WAKE | NC 55 | SR 1191 (TECHNOLOGY DRIVE) / SR 6107 (EAST WILLIAMS STREET) IN APEX. CONVERT INTERSECTION TO INTERCHANGE. | HIGHWAY | 5 | CAPITAL AREA MPO | HL-0007 | EXEMPT | NHPBA | 2024 | 5600000 | 2024 | 1000000 | 2025 | 21701000 |  |  | 28301000
WAKE | NC 55 | SR 1115 (AVENT FERRY ROAD) TO SOUTH MAIN STREET IN HOLLY SPRINGS. CONSTRUCT 3RD SOUTHBOUND LANE. | HIGHWAY | 5 | CAPITAL AREA MPO | HL-0029 | EXEMPT | BGDA, L | 2023 | 102000 |  |  | 2023 | 914000 |  |  | 1016000
WAKE | NC 55 | SR 4809 (JICARILLA LANE) TO NC 42 IN FUQUAY-VARINA. | HIGHWAY | 5 | CAPITAL AREA MPO | R-5705C | NOT FUNDED | T | NOT FUNDED | 8170000 | NOT FUNDED | 1386000 | NOT FUNDED | 17900000 |  |  | 27456000
WAKE | NC 55 (WILLIAMS STREET) | US 1 TO NORTH OF SR 1160 (OLIVE CHAPEL ROAD) IN APEX. WIDEN TO A MULTILANE CURB AND GUTTER FACILITY. | HIGHWAY | 5 | CAPITAL AREA MPO | U-2901 | [11 empty] | PROJECTS U-2901AA AND AB COMPLETE
WAKE | NC 55 (WILLIAMS STREET) | US 1 TO NORTH OF SR 1160 (OLIVE CHAPEL ROAD). CONVERT EXISTING MULTILANES TO MEDIAN DIVIDED SECTION AND WIDEN REMAINING 2-LANE SECTIONS TO MULTILANES. | HIGHWAY | 5 | CAPITAL AREA MPO | U-2901B | REGION C | T | 2028 | 12000000 | 2028 | 3900000 | 2031 | 37001000 |  |  | 52901000
WAKE | NC 98 | CAMP KANATA RD AND NC 98 IN WAKE FOREST. IMPROVE INTERSECTION, ADD TURN LANES ON NC 98. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6222 | EXEMPT | BGDA, S |  |  |  |  | 2021 | 1050000 | 2020 | 150000 | 1200000 | "S" FUNDING REFLECTS SPOT SAFETY PROGRAM MATCH; UNDER CONSTRUCTION
WAKE | NC 98 | SR 2057 / SR 4465 (MOORES POND ROAD) | HIGHWAY | 5 | CAPITAL AREA MPO | W-5805E | REGION C | HSIP | 2023 | 100000 |  |  | 2024 | 1230000 |  |  | 1330000
WAKE | NC 98 BUSINESS | US 1, CLOVERLEAF DRIVE, AND RETAIL DRIVE / HAMPTON WAY IN WAKE FOREST. REVISE TRAFFIC SIGNALS. | HIGHWAY | 5 | CAPITAL AREA MPO | W-5805B | REGION C | [10 empty] | PROJECT DELETED; WORK TO BE ACCOMPLISHED UNDER U-6023.
WAKE | NC-42 | SR 2735 (JOHNSON ROAD) INTERSECTION.INTERSECTION IMPROVEMENTS. | HIGHWAY | 5 | CAPITAL AREA MPO | HL-0008O | EXEMPT | BGBA | 2023 | 175000 | 2024 | 125000 | 2025 | 1300000 |  |  | 1600000
WAKE | NCSU CAMPUS | MULTIMODAL CONNECTED VEHICLE PILOT (MMCVP) CONNECTED VEHICLE INFRASTRUCTURE, CONNECTED VEHICLE APPLICATIONS, TRAFFIC SIGNAL IMPROVEMENTS, PROJECT MANAGEMENT. | HIGHWAY | 5 | CAPITAL AREA MPO | HO-0001AA | EXEMPT | DP, S |  |  |  |  | 2022 | 2981000 | 2021 | 369000 | 3350000
WAKE | NCSU CAMPUS | FIBER OPTIC CABLE INSTALLATION. | HIGHWAY | 5 | CAPITAL AREA MPO | HO-0001AB | EXEMPT | DP, S |  |  |  |  | 2022 | 168000 | 2022 | 150000 | 318000
WAKE | NCSU CAMPUS | ECO DRIVING APPLICATION | HIGHWAY | 5 | CAPITAL AREA MPO | HO-0001AC | EXEMPT | DP, S |  |  |  |  | 2024 | 704000 | 2023 | 74000 | 778000 | PROJECT DELETED
WAKE | NCSU CAMPUS | SYSTEMS ENGINEERING, GRANT ADMINISTRATION | HIGHWAY | 5 | CAPITAL AREA MPO | HO-0001B | EXEMPT | DP, S | [6 empty] | 2021 | 200000 | 200000
WAKE | NCSU CAMPUS | BEFORE & AFTER STUDY, EXPANSION FEASIBILITY STUDY | HIGHWAY | 5 | CAPITAL AREA MPO | HO-0001C | EXEMPT | DP, S | [6 empty] | 2021 | 310000 | 310000
WAKE | NEW ROUTE | SR 1613 (MCCRIMMON PARKWAY) TO NC 540 IN MORRISVILLE. CONSTRUCT MULTILANE FACILITY ON NEW LOCATION. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5966 | REGION C | T | 2028 | 12900000 | 2028 | 2398000 | 2030 | 93701000 |  |  | 108999000 | NORTH CAROLINA TURNPIKE AUTHORITY PROJECT
WAKE | NEW ROUTE (FUTURE NC 540) | SOUTHERN WAKE FREEWAY / TRIANGLE EXPRESSWAY SOUTHEAST EXTENSION (RALEIGH OUTER LOOP), NC 55 (SOUTH) TO EAST OF US 401 SOUTH. FREEWAY ON NEW LOCATION. | HIGHWAY | 5 | CAPITAL AREA MPO | R-2721 | STATEWIDE MOBILITY | [10 empty] | COORDINATE WITH U-5746; NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT
WAKE | NEW ROUTE; SR 1152 (HOLLY SPRINGS - NEW HILL ROAD) | NEW ROUTE INTERSECTING GREEN OAKS PARKWAY BETWEEN THOMAS MILL ROAD AND NC 55, SR 1153 INTERSECTION WITH BENNET KNOLL PARKWAY, AND SR 1152 INTERSECTION WITH SR 1153 IN HOLLY SPRINGS. CONSTRUCT ACCESS ROAD AND INTERSESCTION IMPROVEMENTS. | HIGHWAY | 5 | CAPITAL AREA MPO | HE-0002 | DIVISION 5 | T | 2023 | 200000 |  |  | 2024 | 9500000 |  |  | 9700000 | ECONOMIC DEVELOPMENT PROJECT
WAKE | NORTH JUDD PARKWAY | NC 55 (NORTH BROAD STREET) TO NC 42 (WEST ACADEMY STREET) IN FUQUAY-VARINA, WAKE COUNTY. MULTILANE FACILITY ON NEW LOCATION. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5317 | DIVISION 5 | [10 empty] | UNDER CONSTRUCTION BY TOWN OF FUQUAY-VARINA
WAKE | SOUTH MAIN STREET | SR 1152 (HOLLY SPRINGS ROAD) TO EARP STREET IN HOLLY SPRINGS. UPGRADE INTERSECTION, ADD TURN LANES AND SIDEWALK ON NORTHBOUND MAIN STREET. | HIGHWAY | 5 | CAPITAL AREA MPO | HL-0030 | DIVISION 5 | BGDA, L | 2023 | 451000 |  |  | 2023 | 749000 |  |  | 1200000
WAKE | SR 1002 (AVIATION PARKWAY) | NC 54 TO I-40 IN MORRISVILLE. WIDEN TO MULTILANES WITH INTERCHANGE MODIFICATIONS AT I-40. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5811 | DIVISION 5 | T | 2026 | 8420000 | 2026 | 556000 | 2028 | 31401000 |  |  | 40377000
WAKE | SR 1004 (GARNER ROAD); TIMBER DRIVE EAST | SR 2539 (YEARGAN ROAD), SR 2564 (CREECH ROAD), AND SHENSTONE BOULEVARD INTERSECTIONS IN GARNER. UPGRADE TRAFFIC SIGNALS | HIGHWAY | 5 | CAPITAL AREA MPO | W-5805H | DIVISION 5 | HSIP |  |  |  |  | 2021 | 75000 |  |  | 75000
WAKE | SR 1006 (OLD STAGE ROAD) | REPLACE BRIDGE 910277 OVER BLACK CREEK. | HIGHWAY | 5 | CAPITAL AREA MPO | B-4655 | HIGHWAY FUND | [10 empty] | UNDER CONSTRUCTION
WAKE | SR 1007 (POOLE ROAD) | SR 2233 (SMITHFIELD ROAD). UPGRADE INTERSECTION. | HIGHWAY | 5 | CAPITAL AREA MPO | HL-0031 | DIVISION 5 | BGDA, S | 2022 | 217000 |  |  | 2023 | 1885000 |  |  | 2102000 | "S" FUNDING REFLECTS SPOT MOBILITY FUNDS
WAKE | SR 1010 (TEN-TEN ROAD) | SR 1006 (OLD STAGE ROAD) AND SR 1010 (TEN TEN ROAD) INTERSECTION IMPROVEMENTS. | HIGHWAY | 5 | CAPITAL AREA MPO | HL-0008F | EXEMPT | BGBA |  |  |  |  | 2024 | 1565000 |  |  | 1565000
WAKE | SR 1010 (TEN-TEN ROAD) | SR 1386 (BELLS LAKE ROAD) , SR 1386 (GRAHAM NEWTON ROAD) INTERSECTION. INTERSECTION IMPROVEMENTS. | HIGHWAY | 5 | CAPITAL AREA MPO | HL-0008L | EXEMPT | BGBA | 2023 | 300000 | 2024 | 225000 | 2025 | 2400000 |  |  | 2925000
WAKE | SR 1010 (TEN-TEN ROAD) | NC 50 INTERSECTION. INTERSECTION IMPROVEMENTS. | HIGHWAY | 5 | CAPITAL AREA MPO | HL-0008P | EXEMPT | BGBA | 2023 | 250000 | 2024 | 175000 | 2025 | 1750000 |  |  | 2175000
WAKE | SR 1010 (TEN-TEN ROAD) | APEX PEAKWAY IN APEX TO SR 1300 (KILDARE FARM ROAD) IN CARY. WIDEN TO MULTILANES. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5825 | DIVISION 5 | T | 2028 | 26800000 | 2028 | 4700000 | 2031 | 45701000 |  |  | 77201000 | COORDINATE WITH U-6066
WAKE | SR 1115 (AVENT FERRY ROAD) | WEST OF SR 1101 (PINEY GROVE - WILBON ROAD) TO VILLAGE WALK DRIVE IN HOLLY SPRINGS. OPERATIONAL IMPROVEMENTS. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5529 | DIVISION 5 | BGDA, L |  |  |  |  | 2020 | 1830000 |  |  | 1830000 | UNDER CONSTRUCTION BY TOWN OF HOLLY SPRINGS
WAKE | SR 1115 (AVENT FERRY ROAD) | SR 1116 (CASS HOLT ROAD) TO NC 55 BYPASS IN HOLLY SPRINGS. WIDEN TO MULTILANES, WITH INTERSECTION IMPROVEMENTS AT SR 1116 (CASS HOLT ROAD), SR 1101 (PINEY GROVE-WILBON ROAD) AND NC 55 BYPASS. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5889 | DIVISION 5 | T | 2026 | 1200000 | 2026 | 500000 | 2028 | 7300000 |  |  | 9000000
WAKE | SR 1152 (HOLLY SPRINGS ROAD) | SR 1301 (SUNSET LAKE ROAD) INTERSECTION IN HOLLY SPRINGS. INTERSECTION IMPROVEMENTS. | HIGHWAY | 5 | CAPITAL AREA MPO | HL-0008D | EXEMPT | BGBA | 2023 | 400000 | 2024 | 200000 | 2025 | 1750000 |  |  | 2350000
WAKE | SR 1152 (HOLLY SPRINGS ROAD) | EAST OF NC 55 TO FLINT POINT LANE IN HOLLY SPRINGS. WIDEN FROM 2 TO 4 LANES. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6094 | DIVISION 5 | BGDA, L | 2020 | 1480000 |  |  | 2022 | 1521000 |  |  | 3001000 | RIGHT OF WAY IN PROGRESS BY TOWN OF HOLLY SPRINGS
WAKE | SR 1152 (HOLLY SPRINGS ROAD) | SR 1010 (TEN-TEN ROAD) TO SR 3977 (CARY PARKWAY). IMPROVE INTERSECTIONS AT SR 1010, SR 1379 (PENNY ROAD), AND SR 3977. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6217 | DIVISION 5 | T | 2028 | 13400000 | 2028 | 1142000 | 2031 | 27100000 |  |  | 41642000
WAKE | SR 1152 (HOLLY SPRINGS ROAD) | FLINT POINT LANE TO SR 1301 (SUNSET LAKE ROAD) IN HOLLY SPRINGS. WIDEN TO A FOUR-LANE MEDIAN-DIVIDED FACILITY AND CONSTRUCT SIDEWALK. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6243 | DIVISION 5 | BGDA, L |  |  |  |  | 2022 | 18000000 |  |  | 18000000 | UNDER CONSTRUCTION
WAKE | SR 1162 (APEX BARBECUE ROAD) | REPLACE BRIDGE 910362 OVER BEAVER CREEK IN APEX. | HIGHWAY | 5 | CAPITAL AREA MPO | B-5161 | DIVISION 5 | [10 empty] | UNDER CONSTRUCTION
WAKE | SR 1179 (BRIDGE STREET) | REPLACE BRIDGE 910497 OVER NORFOLK SOUTHERN RAILROAD IN FUQUAY-VARINA. | HIGHWAY | 5 | CAPITAL AREA MPO | HB-0029 | DIVISION 5 | BGOFF | 2025 | 100000 | 2025 | 100000 | 2026 | 2000000 |  |  | 2200000
WAKE | SR 1301 (SUNSET LAKE ROAD) | US 401 TO SR 1431 (PRODUCTS ROAD) IN FUQUAY-VARINA. WIDEN TO MULTILANES. | HIGHWAY | 5 | CAPITAL AREA MPO | HL-0027 | DIVISION 5 | BGDA, L | 2023 | 1000000 |  |  | 2023 | 578000 | 2022 | 62000 | 1640000
WAKE | SR 1319 (JONES FRANKLIN ROAD) | ATHENS DRIVE IN RALEIGH. INSTALL LEFT TURN LANES. | HIGHWAY | 5 | CAPITAL AREA MPO | HL-0051 | DIVISION 5 | BGDA, S | 2023 | 80000 |  |  | 2024 | 400000 | 2023 | 110000 | 590000
WAKE | SR 1321 (AVENT FERRY ROAD) | REPLACE BRIDGE 910318 OVER LAKE JOHNSON IN RALEIGH. | HIGHWAY | 5 | CAPITAL AREA MPO | B-5130 | DIVISION 5 | BFP |  |  |  |  | 2026 | 3650000 |  |  | 3650000 | RIGHT-OF-WAY IN PROGRESS
WAKE | SR 1349 (DILLARD DRIVE) | VILLAGE TAVERN ROAD TO SR 1319 (JONES FRANKLIN ROAD) IN RALEIGH. INSTALL TWO WAY LEFT TURN LANE. | HIGHWAY | 5 | CAPITAL AREA MPO | HL-0050 | DIVISION 5 | BGDA, S | 2023 | 174000 |  |  | 2023 | 1098000 |  |  | 1272000
WAKE | SR 1371 / SR 1375 (LAKE WHEELER ROAD) | SR 1375 (SIMPKINS ROAD) / NON-SYSTEM (SIMPKINS FARM LANE) INTERSECTION. INTERSECTION IMPROVEMENTS. | HIGHWAY | 5 | CAPITAL AREA MPO | HL-0008H | EXEMPT | BGBA | 2022 | 150000 | 2023 | 175000 | 2023 | 1750000 |  |  | 2075000
WAKE | SR 1375 (LAKE WHEELER ROAD) | SR 1393 (HILLTOP-NEEDMORE ROAD) INTERSECTION IN FUQUAY VARINA. INTERSECTION IMPROVEMENTS. | HIGHWAY | 5 | CAPITAL AREA MPO | HL-0008G | EXEMPT | BGBA | 2023 | 180000 | 2023 | 225000 | 2024 | 2400000 |  |  | 2805000
WAKE | SR 1379 (PENNY ROAD) | SR 4720 (LOCH HIGHLANDS DRIVE) TO EAST OF ENTRANCE TO OAK GROVE ELEMENTARY SCHOOL IN RALEIGH. COMPLETE SIDEWALK GAPS. | HIGHWAY | 5 | CAPITAL AREA MPO | BL-0051 | EXEMPT | CMAQ, L | 2023 | 50000 |  |  | 2023 | 350000 | 2023 | 50000 | 450000
WAKE | SR 1379 (PENNY ROAD) | SR 1382 (OLDE SOUTH ROAD) INTERSECTION IN RALIEGH. INTERSECTION IMPROVEMENTS. | HIGHWAY | 5 | CAPITAL AREA MPO | HL-0008S | EXEMPT | BGBA | 2023 | 175000 | 2024 | 125000 | 2025 | 1100000 |  |  | 1400000
WAKE | SR 1390 (OPTIMIST FARM ROAD) | SR 1386 (BELLS LAKE ROAD) INTERSECTION IN APEX. INTERSECTION IMPROVEMENTS. | HIGHWAY | 5 | CAPITAL AREA MPO | HL-0008Q | EXEMPT | BGBA | 2023 | 300000 | 2024 | 225000 | 2025 | 2400000 |  |  | 2925000
WAKE | SR 1521 (LAKE PINE DRIVE) | WIDEN TO 3 LANES - NORTH OF MACGREGOR PINES ROAD TO NORTH OF VERSAILLES DRIVE. INCL. 10 FT MULTIUSE PATH EAST SIDE; 5 FT SIDEWALK WEST SIDE. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5537 | DIVISION 5 | BGDA, L |  |  |  |  | 2021 | 585000 |  |  | 585000 | UNDER CONSTRUCTION BY TOWN OF APEX
WAKE | SR 1624 (CARPENTER FIRE STATION ROAD) | NC 55 TO CAMERON POND DRIVE IN CARY. WIDEN TO MULTI LANES. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6227 | DIVISION 5 | BGDA, L | 2021 | 5629000 |  |  | 2022 | 8100000 |  |  | 13729000 | RIGHT OF WAY IN PROGRESS.
WAKE | SR 1630 (GREEN LEVEL CHURCH ROAD) | REPLACE BRIDGE 910061 OVER KIT CREEK IN CARY. | HIGHWAY | 5 | CAPITAL AREA MPO | B-5673 | DIVISION 5 | HFB | 2023 | 130000 |  |  | 2025 | 4550000 |  |  | 4680000
WAKE | SR 1632 (LOUIS STEPHENS DRIVE) | DELARONDE LANE IN CARY TO GRAY MARBLE ROAD IN MORRISVILLE,AND NORTHEAST CORNER OF LOUIS STEPHENS DRIVE AND SR 1635 (MCCRIMMON PARKWAY). COMPLETE SIDEWALK GAPS. | HIGHWAY | 5 | CAPITAL AREA MPO | BL-0049 | EXEMPT | CMAQ, L |  |  |  |  | 2026 | 550000 |  |  | 550000
WAKE | SR 1632 (LOUIS STEPHENS DRIVE) | POPLAR PIKE LANE IN MORRISVILLE TO SR 2153 (LITTLE DRIVE) IN RESEARCH TRIANGLE PARK. CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5827 | DIVISION 5 | T | 2020 | 1340000 |  |  | 2020 | 7699000 | 2019 | 1231000 | 10270000 | UNDER CONSTRUCTION; BUILD NC BONDS: $946,000 FOR PE, $1.041 MILLION FOR RIGHT OF WAY, AND $2.313 MILLION FOR CONSTR - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), $12,000 FOR PE AND $3.27 MILLION FOR CONSTR - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
WAKE | SR 1635 (MCCRIMMON PARKWAY) | SR 1613 (DAVIS DRIVE) TO NORTH OF SR 1637 (CHURCH STREET) IN MORRISVILLE. WIDEN TO 4-LANE DIVIDED FACILITY. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5747A | DIVISION 5 | T | 2021 | 4905000 | 2021 | 700000 | 2024 | 20413000 |  |  | 26018000 | RIGHT OF WAY IN PROGRESS; COORDINATE WITH U-5966; BUILD NC BONDS: $3 MILLION FOR CONSTRUCTION - PAYBACK 2024-2036 (FY 2022 / YR 4 SALE)
WAKE | SR 1650 (REEDY CREEK ROAD) | NC 54 (NE MAYNARD ROAD) TO SR 1652 (HARRISON AVENUE) IN CARY. WIDEN FROM 2 TO 3 LANES, TO INCLUDE ROUNDABOUTS, AS WELL AS PEDESTRIAN AND BICYCLE ENHANCEMENTS. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5501 | DIVISION 5 | BGDA, L |  |  |  |  | 2020 | 7692000 |  |  | 7692000 | UNDER CONSTRUCTION BY TOWN OF CARY
WAKE | SR 1664 (DURALEIGH ROAD) | SR 3009 (EDWARDS MILL ROAD) IN RALEIGH. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6193 | DIVISION 5 | T | 2027 | 6700000 | 2027 | 300000 | 2029 | 10200000 |  |  | 17200000
WAKE | SR 1728 (WADE AVENUE) | I-40 TO I-440 IN RALEIGH. ADD LANES. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5936 | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 74499000 |  |  | 76699000
WAKE | SR 1820 (LEAD MINE ROAD) | SR 1827 (LYNN ROAD) INTERSECTION IN RALEIGH. CONSTRUCT PEDESTRIAN REFUGE ISLANDS, AND REVISE CURB RAMPS, CROSSWALKS, AND OTHER PAVEMENT MARKINGS. | HIGHWAY | 5 | CAPITAL AREA MPO | W-5805C | DIVISION 5 | HSIP |  |  |  |  | 2021 | 135000 |  |  | 135000
WAKE | SR 1930 (STADIUM DRIVE) SR 1933 (WEST NORTH AVENUE | SR 1930 (STADIUM DRIVE), US 1 TO SR 1954 (NORTH WINGATE STREET) IN WAKE FOREST. COMPLETE STREETS IMPROVEMENTS TO INCLUDE: WIDEN TO THREE-LANE CURB AND GUTTER SECTION, CONSTRUCT SIDEWALK, MULTIUSE PATH, BICYCLE LANES, AND PEDESTRIAN / TRANSIT AMENITIES. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5515 | DIVISION 5 | [10 empty] | UNDER CONSTRUCTION BY TOWN OF WAKE FOREST
WAKE | SR 2000 (FALLS OF NEUSE ROAD) | I-540 TO SR 2006 (DURANT ROAD). ADD LANES. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5826 | DIVISION 5 | T |  |  |  |  | 2023 | 6500000 |  |  | 6500000
WAKE | SR 2015 (DIXIE FOREST ROAD) / SR 3555 (OLD WAKE FO | SR 2015 / SR 2041 (SPRING FOREST ROAD) TO US 1 (CAPITAL BOULEVARD) IN RALEIGH. UPGRADE TO A COMPLETE STREET. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6242 | DIVISION 5 | BGDA, L | 2022 | 1700000 | 2022 | 1100000 | 2023 | 11148000 |  |  | 13948000
WAKE | SR 2044 (LIGON MILL ROAD) | REPLACE BRIDGE 910126 OVER SMITHS CREEK IN WAKE FOREST. | HIGHWAY | 5 | CAPITAL AREA MPO | B-5318 | DIVISION 5 | BFP |  |  |  |  | 2023 | 6000000 |  |  | 6000000 | RIGHT OF WAY IN PROGRESS
WAKE | SR 2215 (BUFFALOE ROAD) | SR 2214 (SOUTHHALL ROAD)/BRINTONS COTTAGE STREET AND VALLEY STREAM DRIVE INTERSECTIONS IN RALEIGH. TRAFFIC SIGNALS REVISIONS, CURB RAMPS, AND PAVEMENT MARKINGS. | HIGHWAY | 5 | CAPITAL AREA MPO | HS-2005G | DIVISION 5 | HSIP |  |  |  |  | 2023 | 147000 |  |  | 147000
WAKE | SR 2542 (ROCK QUARRY ROAD) | OLDE BIRCH ROAD TO SR 2544 (SUNNYBROOK ROAD) IN RALEIGH. WIDEN TO 4-LANE DIVIDED FACILITY. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6093 | DIVISION 5 | BGDA, L | 2021 | 1891000 |  |  | 2022 | 11062000 |  |  | 12953000 | RIGHT-OF-WAY IN PROGRESS
WAKE | SR 2700 (WHITE OAK RD) | SR 2709 (ACKERMAN RD), SR 2547 (HEBRON CHURCH RD) AND SR 2700 (WHITE OAK RD) IN GARNER. IMPROVE INTERSECTION AND ADD MULTILANE ROUNDABOUT. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6225 | DIVISION 5 | BGDA, L | 2021 | 75000 |  |  | 2022 | 2080000 |  |  | 2155000 | PLANNING / DESIGN / RIGHT OF WAY / CONSTRUCTION BY TOWN OF GARNER. RIGHT-OF-WAY IN PROGRESS.
WAKE | SR 2703 (NEW BETHEL CHURCH ROAD) | REPLACE BRIDGE 910248 OVER MAHLER'S CREEK IN GARNER. | HIGHWAY | 5 | CAPITAL AREA MPO | B-5237 | DIVISION 5 | T |  |  |  |  | 2021 | 2702000 |  |  | 2702000 | BUILD NC BONDS: $2.1 MILLION FOR CONSTRUCTION - PAYBACK 2021-2035 (FY 2021 / YR 2&3 SALE)
WAKE | SR 2763 (OLD HONEYCUTT ROAD) SR 1301 (PURFOY ROAD) | INTERSECTION OF OLD HONEYCUTT ROAD (SR 2763) AND PURFOY ROAD (SR 1301) IN FUQUAY-VARINA. INTERSECTION IMPROVEMENTS. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6096 | DIVISION 5 | [10 empty] | UNDER CONSTRUCTION
WAKE | SR 2768 (JUDD PARKWAY) | US 401 (SOUTH MAIN STREET) INTERSECTION IN FUQUAY-VARINA. CONSTRUCT TURN LANES. | HIGHWAY | 5 | CAPITAL AREA MPO | HL-0041 | EXEMPT | CMAQ, L | 2022 | 63000 |  |  | 2023 | 469000 | 2022 | 86000 | 618000
WAKE | SR 3014 (MORRISVILLE- CARPENTER ROAD) | SR 1613 (DAVIS DRIVE) TO WEST OF NC 54 IN MORRISVILLE. WIDEN TO 4-LANE DIVIDED FACILITY. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5618 | DIVISION 5 | BGDA, L, S |  |  |  |  | 2020 | 7463000 |  |  | 7463000 | UNDER CONSTRUCTION BY TOWN OF MORRISVILLE; "S" FUNDS REFLECT CONTRACT RESURFACING ALLOCATION
WAKE | SR 5220 (JONES SAUSAGE ROAD) | SR 1004 (EAST GARNER ROAD) TO I-40 IN GARNER. WIDEN ROADWAY FROM SOUTH OF SR 2585 (WILMINGTON ROAD) TO I-40, INCLUDING ACCESS POINT IMPROVEMENTS, AND CONSTRUCT IMPROVEMENTS AT SR 1004 INTERSECTION AND I-40 INTERCHANGE. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6099 | DIVISION 5 | [10 empty] | UNDER CONSTRUCTION; ECONOMIC DEVELOPMENT PROJECT
WAKE | SR 6107 (NORTH MAIN STREET) | TRELLIS POINTE DRIVE TO ARBOR CREEK DRIVE IN HOLLY SPRINGS. COMPLETE SIDEWALK GAPS. | HIGHWAY | 5 | CAPITAL AREA MPO | BL-0052 | EXEMPT | CMAQ, L | 2023 | 250000 |  |  | 2023 | 500000 | 2023 | 75000 | 825000
WAKE | US 1 | I-540 IN RALEIGH TO SR 1909 (PURNELL ROAD) / SR 1931 (HARRIS ROAD) IN WAKE FOREST. UPGRADE ROADWAY TO CONTROLLED ACCESS FACILITY. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5307
WAKE | US 1 | I-540 TO NORTH OF SR 2006 (DURANT ROAD) IN RALEIGH. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5307A | STATEWIDE MOBILITY | T | 2025 | 94300000 | 2025 | 12200000 | 2025 | 184700000 |  |  | 291200000 | DESIGN-BUILD PROJECT
WAKE | US 1 | NORTH OF SR 2006 (DURANT ROAD) IN RALEIGH TO NORTH OF SR 2045 (BURLINGTON MILLS ROAD) IN WAKE FOREST. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5307B | REGION C | T | 2027 | 80053000 | 2027 | 6700000 | 2029 | 92399000 |  |  | 179152000 | BUILD NC BONDS: $19 MILLION FOR RIGHT OF WAY - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE)
WAKE | US 1 | NORTH OF SR 2045 (BURLINGTON MILLS ROAD) TO SOUTH OF NC 98 BUSINESS IN WAKE FOREST. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5307C | REGION C | T | 2027 | 28200000 | 2027 | 5100000 | 2029 | 108800000 |  |  | 142100000
WAKE | US 1 | SOUTH OF NC 98 BUSINESS TO SR1909 (PURNELL ROAD) / SR 1931 (HARRIS ROAD) IN WAKE FOREST. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5307D | REGION C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 48900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 83999000 |  |  | 141199000
WAKE | US 1 | NC 55 IN APEX TO US 64 IN CARY. ADD LANES. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6066 | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 32400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 40800000 |  |  | 74800000 | COORDINATE WITH U-5825
WAKE | US 401 | REPLACE BRIDGES 910115 AND 910117 OVER NORFOLK SOUTHERN RAILROAD AND AN UNNAMED TRIBUTARY OF SWIFT CREEK. | HIGHWAY | 5 | CAPITAL AREA MPO | B-5987 | REGION C | NHPB | 2023 | 640000 | 2023 | 640000 | 2024 | 16900000 |  |  | 18180000
WAKE | US 401 | SR 1393 (HILLTOP-NEEDMORE ROAD) / SR 2751 (HILLTOP ROAD) / SR 2752 (AIR PARK ROAD) INTERSECTION AND SR 1375 (LAKE WHEELER ROAD) INTERSECTION IN FUQUAY-VARINA. CONVERT TO REDUCED-CONFLICT INTERSECTIONS AND REALIGN SR 2751 TO INTERSECT OPPOSITE SR 1375. | HIGHWAY | 5 | CAPITAL AREA MPO | HL-0006 | EXEMPT | NHPBA | 2024 | 3000000 | 2024 | 510000 | 2025 | 22700000 |  |  | 26210000
WAKE | US 401 | SR 1404 (MILL CREEK DRIVE) / IDEAL LANE IN FUQUAY-VARINA. IMPROVE INTERSECTION. | HIGHWAY | 5 | CAPITAL AREA MPO | HL-0028 | EXEMPT | BGDA, L | 2023 | 150000 |  |  | 2023 | 1252000 | 2022 | 134000 | 1536000
WAKE | US 401 | SR 2044 (LIGON MILL ROAD) TO NORTH OF SR 2225 (LOUISBURY ROAD) | HIGHWAY | 5 | CAPITAL AREA MPO | R-2814A | [11 empty] | COMPLETE
WAKE | US 401 | ROLESVILLE BYPASS, NORTH OF SR 2225 (LOUISBURY ROAD) TO NC 96 ON NEW LOCATION | HIGHWAY | 5 | CAPITAL AREA MPO | R-2814B | PRE-STI (TRANSITION) | BGANY | 2009 | 1727000 |  |  | 2011 | 7083000 |  |  | 8810000 | COMPLETE. GARVEE BOND FUNDING: PART B $15.8 MILLION FOR RIGHT-OF-WAY - PAYBACK FY 2009 - FY 2020
WAKE | US 401 | SOUTH OF SR 1006 (OLD STAGE ROAD) TO SOUTH OF SR 2538 (MECHANICAL BOULEVARD) / GARNER STATION BOULEVARD IN GARNER. CONVERT TO SUPERSTREET. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5302 | REGION C | T | 2019 | 9931000 |  |  | 2023 | 19862000 | 2019 | 1801000 | 31594000 | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND: $1.404 MILLION FOR PE - PAYBACK 2020-2033 AND $3.207 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE), AND $3 MILLION FOR CONSTRUCTION - PAYBACK 2023-2036 (FY 2022 / YR 4 SALE)
WAKE | US 401 | SR 1467 / SR 2839 (ALLEN STREET) TO SR 1010 (TEN-TEN ROAD). ADD LANES. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5746 | REGION C | T |  |  | 2022 | 605000 | 2024 | 5400000 |  |  | 6005000 | RIGHT-OF-WAY IN PROGRESS
WAKE | US 401 | SR 2044 (LIGON MILL ROAD) / SR 2224 (MITCHELL MILL ROAD) AND SR 2006 (PERRY CREEK ROAD) IN RALEIGH. INTERSECTION IMPROVEMENTS. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5748 | REGION C | T | 2019 | 6840000 | 2021 | 212000 | 2023 | 22500000 | 2019 | 1921000 | 31473000 | BUILD NC BONDS: $1.497 MILLION FOR PE - PAYBACK 2020-2033, AND $1.556 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019-2033 (FY 2019 / YR 1 SALE)
WAKE | US 401 | NC 55 / NC 42 IN FUQUAY-VARINA. IMPROVE US 401 INTERSECTION WITH NC 55 / NC 42. PROJECT WILL INCLUDE IMPROVEMENTS TO NC 55 INTERSECTION WITH NC 42, AND CONSTRUCTION OF CONNECTOR FROM NC 55 TO SR 5056 (JUDD PARKWAY). | HIGHWAY | 5 | CAPITAL AREA MPO | U-5751 | REGION C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 39150000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2620000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 47498000 |  |  | 89268000
WAKE | US 401 | SR 1010 (TEN-TEN ROAD). CONVERT EXISTING SIGNALIZED INTERSECTION TO SQUARE-LOOP INTERCHANGE. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6112 | REGION C | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 56400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 24100000 |  |  | 82100000 | COORDINATE WITH R-2721 AND U-5746
WAKE | US 401 | SR 1375 (SIMPKINS ROAD) TO SR 2538 (MECHANICAL BOULEVARD) IN GARNER. WIDEN TO 6 LANES AND CONVERT TO SUPERSTREET. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6116 | NOT FUNDED | T | NOT FUNDED | 2200000 | NOT FUNDED | 1400000 | NOT FUNDED | 4500000 |  |  | 8100000
WAKE | US 401 (CAPITAL BOULEVARD) | REPLACE BRIDGE 910146 OVER CRABTREE CREEK IN RALEIGH. | HIGHWAY | 5 | CAPITAL AREA MPO | B-5684 | REGION C | BFP | 2023 | 430000 | 2023 | 330000 | 2024 | 8607000 |  |  | 9367000
WAKE | US 401 BUSINESS (SOUTH MAIN STREET) SR 2051 ROAD); | SR 2051 (BURLINGTON MILLS ROAD), EAST OF ROLESVILLE MIDDLE SCHOOL TO US 401 BUSINESS (SOUTH MAIN STREET) IN ROLESVILLE. REALIGN ROADWAY AND CONSTRUCT NEW INTERSECTION WITH SOUTH MAIN STREET. US 401 BUSINESS (SOUTH MAIN STREET), SR 2051 (BURLINGTON MILLS | HIGHWAY | 5 | CAPITAL AREA MPO | U-6241 | DIVISION 5 | BGDA, L |  |  |  |  | 2022 | 6048000 |  |  | 6048000
WAKE | US 64 | WEST OF SR 1308 (LAURA DUNCAN ROAD) TO US 1 IN APEX AND CARY. CORRIDOR UPGRADE AND IMPROVEMENTS. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5301 | STATEWIDE MOBILITY | T | 2026 | 100556000 | 2026 | 4012000 | 2029 | 134599000 |  |  | 239167000
WAKE | US 64 BUSINESS (WENDELL BOULEVARD) | SR 1003 (ROLESVILLE ROAD-EAGLE ROCK ROAD) IN WENDELL. CONNECTIVITY AND ACCESS IMPROVEMENTS AND SAFETY ENHANCEMENTS. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5323 | REGION C | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY BY TOWN OF WENDELL - IN PROGRESS
WAKE | US 64 BUSINESS (WENDELL BOULEVARD) WENDELL BOULEV | SR 1007 (WENDELL FALLS PARKWAY) IN WENDELL. IMPROVE INTERSECTION AND INCLUDE CLOSURE OF WALL STREET. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6244 | EXEMPT | BGDA, L | 2022 | 110000 |  |  | 2023 | 423000 |  |  | 533000
WAKE | US 70 | I-540 TO HILLBURN DRIVE IN RALEIGH. ADD LANES AND CONVERT TO SUPERSTREET. | HIGHWAY | 5 | CAPITAL AREA MPO | U-2823 | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 37100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 84202000 |  |  | 122502000
WAKE | US 70 / NC 50 | SR 2026 (HAMMOND ROAD) / SR 2812 (TIMBER DRIVE) IN GARNER. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5744 | REGION C | T | 2028 | 14400000 | 2028 | 138000 | 2030 | 13998000 |  |  | 28536000
WAKE | US 70 WESTBOUND / NC 50 NORTHBOUND | REPLACE BRIDGE 910213 OVER US 401 (CAPITAL BOULEVARD) IN RALEIGH. | HIGHWAY | 5 | CAPITAL AREA MPO | B-5317 | REGION C | [10 empty] | SCOPE AND COST INCLUDED IN B-5121
WAKE | US 70/US 401/NC 50 (CAPITAL BOULEVARD) | REPLACE BRIDGE 910227 OVER PEACE STREET AND BRIDGE 910213 OVER US 401 (CAPITAL BOULEVARD) IN RALEIGH AND REVISE INTERCHANGE AT PEACE STREET. | HIGHWAY | 5 | CAPITAL AREA MPO | B-5121 | REGION C | [10 empty] | UNDER CONSTRUCTION; PARTICIPATION BY CITY OF RALEIGH; INCLUDES B-5317
WAKE | VARIOUS | NCDOT MULTIMODAL CONNECTED VEHICLE PILOT PROGRAM, NORTH CAROLINA STATE UNIVERSITY CAMPUS IN RALEIGH. | HIGHWAY | 5 | CAPITAL AREA MPO | HO-0001 | EXEMPT | DP, S |  |  |  |  | 2022 | 227000 | 2021 | 311000 | 538000 | "DP" FUNDS REFLECT FEDERAL ADVANCED TRANSPORTATION AND CONGESTION MANAGEMENT TECHNOLOGIES DEPLOYMENT (ATCMTD) PROGRAM GRANT
WAKE | VARIOUS | DOWNTOWN RALEIGH BUSINESS DISTRICT. TRAFFIC SIGNAL REVISIONS AT VARIOUS LOCATIONS. | HIGHWAY | 5 | CAPITAL AREA MPO | HS-2005F | DIVISION 5 | HSIP |  |  |  |  | 2023 | 200000 |  |  | 200000
WAKE | VARIOUS | TOWN OF MORRISVILLE. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5967 | REGION C | BGANY, T |  |  | 2025 | 33000 | 2026 | 953000 |  |  | 986000
WAKE | VARIOUS | TOWN OF FUQUAY-VARINA. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6022 | REGION C | BGANY |  |  | 2022 | 451000 | 2023 | 2743000 |  |  | 3194000
WAKE | VARIOUS | TOWN OF WAKE FOREST. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6023 | DIVISION 5 | BGANY |  |  | 2022 | 250000 | 2023 | 2743000 |  |  | 2993000
WAKE | VARIOUS | TOWN OF KNIGHTDALE. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6026 | DIVISION 5 | BGANY |  |  | 2022 | 450000 | 2023 | 1350000 |  |  | 1800000 | FINAL COST SHARE TO BE DETERMINED ON BASIS OF FUNCTIONAL CLASSIFICATION
WAKE | VARIOUS | APEX TOWNWIDE SIGNAL SYSTEM. UPGRADE EXISTING INFRASTRUCTURE AND INSTALL NEW FIBER, CONTROLLERS, SIGNALS, AND OTHER EQUIPMENT AS NECESSARY. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6117 | NOT FUNDED | BGANY | NOT FUNDED | 100000 | NOT FUNDED | 300000 | NOT FUNDED | 3800000 |  |  | 4200000
WAKE | VARIOUS | RALEIGH CITYWIDE SIGNAL SYSTEM. UPGRADE SOFTWARE FOR EXISTING ITS SYSTEM. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6119 | REGION C | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4300000 |  |  | 4600000
WAKE | VARIOUS | GARNER CITYWIDE SIGNAL SYSTEM | HIGHWAY | 5 | CAPITAL AREA MPO | U-6194 | DIVISION 5 | BGANY | 2027 | 100000 | 2027 | 360000 | 2028 | 3200000 |  |  | 3660000
WAKE | VARIOUS | DIVISION 5 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS - REGIONAL IMPACT CATEGORY | HIGHWAY | 5 | CAPITAL AREA MPO | W-5205REG | REGION C
WAKE | WEST STREET | CABARRUS STREET TO MARTIN STREET IN RALEIGH. EXTEND WEST STREET ON NEW LOCATION, WITH GRADE SEPARATION AT NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN "H" LINE. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5521 | DIVISION 5 | BGDA, L | 2022 | 2387000 | [6 empty] | 2387000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY BY CITY OF RALEIGH - IN PROGRESS
WAKE | AUTHORITY TRIANGLE TRANSIT | FIXED GUIDEWAY - COMMUTER RAIL SERVICE- DURHAM/RALEIGH | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TE-4903B | PUBLIC TRANSIT | FED |  |  |  |  | 2020 | 222000 |  |  | 222000
WAKE | CAPITAL AREA TRANSIT | PURCHASE REPLACEMENT HYBRID BUSES | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TA-4903A | PUBLIC TRANSIT | 5307, CMAQ, L, S | [6 empty] | 2020 | 1126000 | 1126000
WAKE | CAPITAL AREA TRANSIT | ADA EXPANSION BUS | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TA-5202 | PUBLIC TRANSIT | 5307, 5339, L | [6 empty] | 2020 | 1184000 | 1184000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | CAPITAL AREA TRANSIT | OPERATING ASSISTANCE | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TO-5128 | PUBLIC TRANSIT | 5307, L, SMAP | [6 empty] | 2021 | 152980000 | 152980000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | CAPITAL AREA TRANSIT | PLANNING ASSISTANCE - 5303 | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TP-5100A | PUBLIC TRANSIT | 5303, L, S | [6 empty] | 2020 | 1872000 | 1872000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | CAPITAL AREA TRANSIT | 5310 OPERATING | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TQ-6953 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2021 | 1200000 | 1200000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | CAPITAL AREA TRANSIT | 5310 ADMIN. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TQ-7006 | PUBLIC TRANSIT | 5310 | [6 empty] | 2020 | 65000 | 65000
WAKE | CAPITAL AREA TRANSIT | 5310 ADMINISTRATION | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TQ9037 | PUBLIC TRANSIT | 5310 | [6 empty] | 2020 | 65000 | 65000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | CAPITAL AREA TRANSIT | SAFETY & SECURITY - MIN. 1% SET ASIDE | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TS-5104 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2021 | 542000 | 542000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | CARY TRANSIT / C-TRAN | CONSTRUCT BUS MAINTENANCE FACILITY AT TOWERVIEW COURT IN CARY. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TD-5264B | DIVISION 5 | FEDT, L, T |  |  |  |  | 2020 | 7000000 |  |  | 7000000
WAKE | CARY TRANSIT/C-TRAN | DOWNTOWN CARY MULTI-MODAL FACILITY. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TD-5305 | PUBLIC TRANSIT | L |  |  |  |  | 2022 | 44200000 |  |  | 44200000
WAKE | CARY TRANSIT/C-TRAN | PREVENTIVE MAINTENANCE, BUS FACILITIES, SUPPORT EQUIPMENT, AND SOFTWARE | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TG-4806 | PUBLIC TRANSIT | 5307, 5339, L | [6 empty] | 2020 | 615000 | 615000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | CARY TRANSIT/C-TRAN | ROUTINE CAPITAL - COST OF CONTRACTING | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TG-4935A | PUBLIC TRANSIT | 5307, 5339, L | [6 empty] | 2020 | 34275000 | 34275000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | CARY TRANSIT/C-TRAN | OPERATING ASSISTANCE | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TO-5129 | PUBLIC TRANSIT | 5307, L, SMAP | [6 empty] | 2021 | 19401000 | 19401000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | CARY TRANSIT/C-TRAN | PLANNING ASSISTANCE | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TP-5112 | PUBLIC TRANSIT | 5307, 5311, L, S | [6 empty] | 2020 | 1836000 | 1836000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | GO RALEIGH | SIX EXPANSION BUSES FOR ADDING ROUTE EXPANSION SERVICE. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TA-5186 | DIVISION 5 | [10 empty] | ACQUISITION IN PROGRESS BY GO RALEIGH
WAKE | GO RALEIGH | INTERSECTION OF SR 2298 (EDENTON STREET) AND NORTH SALISBURY STREET IN RALEIGH. CONSTRUCT BUS STOP SHELTER. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TD-5293 | REGION C | [10 empty] | UNDER CONSTRUCTION BY GO TRIANGLE
WAKE | GO RALEIGH | PROJECT DEVELOPMENT AND FINAL DESIGN OF BUS RAPID TRANSIT IN WAKE TRANSIT WESTERN CORRIDOR (DOWNTOWN RALEIGH TO DOWNTOWN CARY). | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TL-0006 | PUBLIC TRANSIT | L |  |  |  |  | 2022 | 45168000 | 2022 | 1500000 | 46668000
WAKE | GO RALEIGH | CONSTRUCT BUS RAPID TRANSIT ON NEW BERN CORRIDOR. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TP-5160 | PUBLIC TRANSIT
WAKE | GO RALEIGH TRANSIT | US 64 BUSINESS (NEW HOPE ROAD) IN RALEIGH. CONSTRUCT TRANSFER FACILITY. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TD-4912 | DIVISION 5 | [10 empty] | UNDER CONSTRUCTION BY GO RALEIGH
WAKE | GO RALEIGH TRANSIT | SOUTH WILMINGTON STREET AT PECAN ROAD IN RALEIGH. CONSTRUCT OFF-STREET TRANSFER FACILITY. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TD-5272 | DIVISION 5 | [10 empty] | UNDER CONSTRUCTION BY GO RALEIGH
WAKE | GO RALEIGH TRANSIT | DESIGN, RIGHT OF WAY, AND CONSTRUCTION OF UP TO 100 NEW BUS STOP SITES IN THE CITY OF RALEIGH. SITES WILL BE BUILT FOR ADA ACCESSIBILITY AS WELL AS PASSENGER AMENITIES WHEN APPROPRIATE. PHASE PE | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TD-5309 | DIVISION 5 | BGDA, L | [6 empty] | 2020 | 752000 | 752000
WAKE | GO RALEIGH TRANSIT | DESIGN, RIGHT OF WAY, AND CONSTRUCTION OF UP TO 100 NEW BUS STOPS IN THE CITY OF RALEIGH. SITES WILL BE BUILT FOR ADA ACCESSIBILITY AS WELL AS PASSENGER AMENITIES WHEN APPROPRIATE. PHASE ROW | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TD-5309A | DIVISION 5 | BGDA, L | 2020 | 250000 | [6 empty] | 250000
WAKE | GO RALEIGH TRANSIT | DESIGN, RIGHT OF WAY, AND CONSTRUCTION OF UP TO 100 NEW BUS STOP SIGHTS IN THE CITY OF RALEIGH. SITES WILL BE BUILT FOR ADA ACCESSIBILITY AS WELL AS PASSENGER AMENITIES WHEN APPROPRIATE. PHASE CON | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TD-5309B | DIVISION 5 | BGDA, L |  |  |  |  | 2020 | 1500000 |  |  | 1500000
WAKE | GO TRIANGLE | UNION STATION IN RALEIGH. CONSTRUCT BUS COMPONENT. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TD-5269 | DIVISION 5 | DP, O, T |  |  |  |  | 2020 | 53160000 |  |  | 53160000 | "O" FUNDING REFLECTS WAKE COUNTY TAX DISTRICT FUNDS AND GO TRIANGLE FUNDS; "DP" FUNDING REFLECTS "BUILD" DISCRETIONARY AWARD; "T" FUNDING REFLECTS REIMBURSEMENT TO CITY OF RALEIGH
WAKE | GO TRIANGLE | EXPAND EXISTING GARAGE FACILITY IN MORRISVILLE. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TD-5285 | REGION C | [10 empty] | IN PROGRESS
WAKE | GO TRIANGLE | PARK AND RIDE LOT AT SR 1774 (DISTRICT DRIVE). ADD SPACES, IMPROVE LIGHTING AND CONSTRUCT SHELTERS. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TD-5287 | REGION C | [10 empty] | IN PROGRESS
WAKE | GOAPEX | CONSTRUCT IMPROVEMENTS AT 41 PROPOSED BUS STOPS TO SERVE THE FIRST LOCAL BUS ROUTE IN THE TOWN OF APEX CALLED APEX ROUTE 1 | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TM-0026 | DIVISION 5 | BGDA, L | [6 empty] | 2021 | 610000 | 610000
WAKE | GOCARY | CONSTRUCT BUS MAINTENANCE FACILITY AT TOWERVIEW COURT IN CARY. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TD-5264 | PUBLIC TRANSIT | L, T |  |  |  |  | 2022 | 20700000 |  |  | 20700000
WAKE | GOCARY | SEVERAL SIDEWALK IMPROVEMENT PROJECTS FROM (1) NORWELL BLVD BETWEEN BUXLEY BLUFF LN TO WESTON PKWAY (2) NORTHSIDE OF NOTTINGHAM DR FROM DONALDSON DR TO BUCK JONES ROAD AND (3) N. HARRISON AVE CONNECTING A BUS STOP AT W. JOHNSON ST TO ACADEMY ST. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TL-0019 | EXEMPT | CMAQ, L | 2022 | 167000 |  |  | 2022 | 1144000 | 2022 | 51000 | 1362000
WAKE | GORALEIGH | REPLACEMENT BUS AND BUS FACILITIES | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TA-4903 | PUBLIC TRANSIT | 5339, L | [6 empty] | 2021 | 16417000 | 16417000
WAKE | GORALEIGH | GORALEIGH PARK AND RIDE AT POOLE ROAD. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TA-5116 | PUBLIC TRANSIT | 5307 |  |  |  |  | 2021 | 455000 |  |  | 455000
WAKE | GORALEIGH | BUS REPLACEMENT | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TA-5140 | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2021 | 4500000 | 4500000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | GORALEIGH | GORALEIGH CAPITAL PROJECTS (PASSENGER AMENITIES, PEDESTRIAN CONNECTIONS, FACILITY MAINTENANCE, UPGRADE AND UPKEEPS ETC) | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TC-0015 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2021 | 10922000 | 10922000
WAKE | GORALEIGH | BUS STOP IMPROVEMENTS | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TD-5304 | PUBLIC TRANSIT | L | [6 empty] | 2022 | 3273000 | 3273000
WAKE | GORALEIGH | CONSTRUCT GORALEIGH COORDINATED ADA FACILITY. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TD-5308 | PUBLIC TRANSIT | L | 2022 | 2750000 |  |  | 2023 | 13800000 | 2022 | 4000000 | 20550000
WAKE | GORALEIGH | GORALEIGH CONSTRUCTION OF PARK AND RIDE IN ROLESVILLE. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TD-5317 | PUBLIC TRANSIT | L |  |  |  |  | 2021 | 55000 |  |  | 55000
WAKE | GORALEIGH | CONSTRUCT NEW TRANSIT CENTER AT MIDTOWN AREA OF RALEIGH | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TD-5318 | PUBLIC TRANSIT | L | 2024 | 2249000 |  |  | 2025 | 2989000 | 2024 | 547000 | 5785000
WAKE | GORALEIGH | GORALEIGH TRANSIT CENTER UPDATES AT CRABTREE VALLEY MALL | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TD-5319 | PUBLIC TRANSIT | L |  |  |  |  | 2022 | 324000 |  |  | 324000
WAKE | GORALEIGH | GORALEIGH TRANSIT CENTER UPDATES AT TRIANGLE TOWNE CENTER | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TD-5320 | PUBLIC TRANSIT | L |  |  |  |  | 2022 | 324000 |  |  | 324000
WAKE | GORALEIGH | FIXED ROUTE PREVENTATIVE MAINTENANCE | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TG-0013 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2021 | 9600000 | 9600000
WAKE | GORALEIGH | GORALEIGH CAPITAL PROJECTS. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TG-0015 | PUBLIC TRANSIT | 5307 | [6 empty] | 2021 | 4401000 | 4401000
WAKE | GORALEIGH | GORALEIGH ADA PARATRANSIT SERVICE. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TG-4729B | PUBLIC TRANSIT | 5307, L | [6 empty] | 2021 | 5000000 | 5000000
WAKE | GORALEIGH | ADA PARATRANSIT SERVICE | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TG-4792B | PUBLIC TRANSIT | 5307, L | [6 empty] | 2021 | 10000000 | 10000000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | GORALEIGH | CAPITAL COST OF CONTRACTING | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TG-6791 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2021 | 5000000 | 5000000
WAKE | GORALEIGH | DESIGN, PURCHASE, AND INSTALL NEW AMENITIES AT 13 BUS STOP LOCATIONS ALONG ROUTES IN WAKE COUNTY,UPGRADES INCLUDE SHELTERS, BENCH, PAD, OR SOME COMBINATIONS | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TG-6815 | DIVISION 5 | BGDA, L | [6 empty] | 2021 | 907000 | 907000
WAKE | GORALEIGH | DEVELOPED ENHANCED TRANSFER POINTS THROUGHOUT GO RALEIGH SYSTEM IN LOCATION WITH HIGH RIDERSHIP (75 + BOARDINGS PER DAY) | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TG-6816 | DIVISION 5 | BGDA, L | [6 empty] | 2021 | 1185000 | 1185000
WAKE | GORALEIGH | PROJECT DEVELOPMENT AND FINAL DESIGN ON BUS RAPID TRANSIT IN WAKE TRANSIT PLAN NORTHERN CORRIDOR. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TL-0007 | PUBLIC TRANSIT | L | [6 empty] | 2020 | 5540000 | 5540000
WAKE | GORALEIGH | PROJECT DEVELOPMENT AND FINAL DESIGN OF BUS RAPID TRANSIT IN WAKE TRANSIT SOUTHERN CORRIDOR ( DOWNTOWN RALEIGH TO DOWNTOWN GARNER) | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TL-0013 | PUBLIC TRANSIT | L |  |  |  |  | 2022 | 27777000 | 2022 | 1500000 | 29277000
WAKE | GORALEIGH | BUILD PARK AND RIDE FACILITY AT GORMAN STREET AT I-40 IN RALEIGH | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TL-0023 | PUBLIC TRANSIT | L |  |  |  |  | 2027 | 1614000 | 2025 | 1432000 | 3046000
WAKE | GORALEIGH | EXPANSION OF OPERATIONS AND MAINTENANCE FACILITY (I.E. ADMINISTRATIVE OFFICE EXPANSION AND BUS GARAGE) | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TM-0039 | PUBLIC TRANSIT | 5307, L |  |  |  |  | 2022 | 2000000 |  |  | 2000000
WAKE | GORALEIGH | GORALEIGH ACCESS/ADA PARATRANSIT FACILITY | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TO-0002 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2021 | 1368000 | 1368000
WAKE | GORALEIGH | TOWN OF WAKE FOREST REVERSE CIRCULATOR OPERATING ASSISTANCE | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TO-6168 | PUBLIC TRANSIT | L | [6 empty] | 2021 | 2283000 | 2283000
WAKE | GORALEIGH | PLANNING ASSISTANCE - 5307 | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TP-5100B | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2021 | 3826000 | 3826000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | GORALEIGH | 5310 CAPITAL AND ADMIN | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TQ-9037 | PUBLIC TRANSIT | 5310, L | [6 empty] | 2021 | 938000 | 938000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | GORALEIGH | MAJOR INVESTMENT STUDY/ALTERNATIVES ANALYSIS FOR BUS RAPID TRANSIT EXTENSION TO RESEARCH TRIANGLE PARK AND CLAYTON. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TU-0007 | PUBLIC TRANSIT | L | [6 empty] | 2021 | 430000 | 430000
WAKE | GOTRIANGLE | GOTRIANGLE IMPROVEMENTS AT EXISTING BUS STOPS (AMENITIES). | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TC-0016 | PUBLIC TRANSIT | BGDA, L | 2022 | 12000 |  |  | 2022 | 550000 | 2022 | 110000 | 672000
WAKE | GOTRIANGLE | GOTRIANGLE IMPROVEMENTS AT EXISTING BUS STOPS (ACCESSIBILITY). | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TC-0017 | PUBLIC TRANSIT | BGDA, L | 2022 | 14000 |  |  | 2022 | 330000 | 2022 | 130000 | 474000
WAKE | GOTRIANGLE | EXISTING PARK AND RIDE IMPROVEMENTS | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TD-5314 | PUBLIC TRANSIT | L | [6 empty] | 2022 | 1105000 | 1105000
WAKE | GOTRIANGLE | BUILD NEW PARK AND RIDE AT HILLSBOROUGH ST AND I-440 IN RALEIGH. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TD-5315 | PUBLIC TRANSIT | L |  |  |  |  | 2023 | 5200000 | 2022 | 2220000 | 7420000
WAKE | GOTRIANGLE | BUILD NEW PARK AND RIDE AT CREEDMOOR AND I-540 OR AT FALLS OF NEUSE AND I-540 IN RALEIGH. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TD-5316 | PUBLIC TRANSIT | L |  |  |  |  | 2024 | 1500000 | 2023 | 1100000 | 2600000
WAKE | GOTRIANGLE | PURCHASE AND INSTALL SIGNAGE AT DESIGNATED LOCATIONS ALONG I-540 AND I-40 FOR BUS ON SHOULDER SYSTEM. (BOSS) UTILIZE EASTBOUND SHOULDER OF I-540 BETWEEN NC-147 AND CAPITAL BLVD AND EASTBOUND ON I-40 BETWEEN WADE AVENUE AND S SAUNDERS STREET. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TG-6814 | EXEMPT | BGDA, L | [6 empty] | 2021 | 454000 | 454000
WAKE | GOTRIANGLE | EARLY PROJECT DEVELOPMENT ACTIVITIES FOR COMMUTER RAIL FROM GARNER TO WESTERN DURHAM | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TL-0008 | PUBLIC TRANSIT | L | [6 empty] | 2021 | 9200000 | 9200000
WAKE | GOTRIANGLE | CONSTRUCT DOWNTOWN APEX TRANSFER POINTS. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TL-0011 | PUBLIC TRANSIT | BGDA, L | 2022 | 18000 |  |  | 2022 | 252000 | 2022 | 64000 | 334000
WAKE | GOTRIANGLE | OPERATING ASSISTANCE FOR TOWN OF MORRISVILLE NODE BASED SMART SHUTTLE. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TM-0035 | PUBLIC TRANSIT | L | [6 empty] | 2021 | 3621000 | 3621000
WAKE | GOTRIANGLE | GOTRIANGLE WAKE COUNTY BUS PLAN UPDATE. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TU-0006 | PUBLIC TRANSIT | L | [6 empty] | 2021 | 750000 | 750000
WAKE | TRIANGLE TRANSIT AUTHORITY | EXPANSION BUS | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TA-4818A | PUBLIC TRANSIT | 5307, 5339 | [6 empty] | 2021 | 962000 | 962000
WAKE | TRIANGLE TRANSIT AUTHORITY | EXPANSION BUS | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TA-5123A | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 3242000 | 3242000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | TRIANGLE TRANSIT AUTHORITY | OPERATING ASSISTANCE | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TO-5131 | PUBLIC TRANSIT | L, SMAP | [6 empty] | 2021 | 37855000 | 37855000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | TRIANGLE TRANSIT AUTHORITY | PLANNING ASSISTANCE | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TP-4732B | PUBLIC TRANSIT | 5307, L, S | [6 empty] | 2020 | 2952000 | 2952000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | VARIOUS | TRIANGLE TOWN CENTER. CONSTRUCT TRANSIT CENTER AND PARK-AND-RIDE FACILITY. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TD-5307 | DIVISION 5 | L, O, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1500000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6658000 |  |  | 8158000
WAKE | VARIOUS | BUS RAPID TRANSIT SERVICE, MORRISVILLE TO CARY. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TO-6166A | REGION C | L, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 21993000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6114000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 115649000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1500000 | 145256000
WAKE | VARIOUS | BUS RAPID TRANSIT SERVICE, CARY TO RALEIGH. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TO-6166B | REGION C | L |  |  |  |  | 2022 | 45168000 | 2022 | 1500000 | 46668000
WAKE | VARIOUS | BUS RAPID TRANSIT SERVICE, RALEIGH TO GARNER. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TO-6166C | REGION C | L |  |  |  |  | 2022 | 27777000 | 2022 | 1500000 | 29277000
WAKE | VARIOUS | BUS RAPID TRANSIT NEW BERN CORRIDOR | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TP-5160A | DIVISION 5 | 5309, ARP, FUZ, L | 2021 | 3086000 |  |  | 2021 | 68507000 | 2020 | 20841000 | 92434000
WAKE | VARIOUS | BUS RAPID TRANSIT NEW BERN CORRIDOR, BETTERMENT FUNDING | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TP-5160B | DIVISION 5 | L |  |  |  |  | 2023 | 814000 |  |  | 814000
WAKE | WAKE COORDINATED TRANSIT SERVICE | WAKE COORDINATED TRANSIT SERVICES OPERATING ASSISTANCE. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TN-6116 | PUBLIC TRANSIT | L | [6 empty] | 2021 | 4070000 | 4070000
WAKE | WAKE COORDINATED TRANSPORTATION SERVICE | ADMINISTRATION | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TK-6170 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 1580000 | 1580000 | FUNDS AUTHORIZED IN PROGRESS
WAKE | CSX | CROSSING 630607N AT NEW HOPE CHURCH ROAD IN RALEIGH. CONSTRUCT GRADE SEPARATION. | RAIL | 5 | CAPITAL AREA MPO | P-5715 | REGION C | DP, T |  |  |  |  | 2023 | 19001000 |  |  | 19001000 | RIGHT-OF-WAY IN PROGRESS; "DP" FUNDING REFLECTS CONSOLIDATED RAIL INFRASTRUCTURE AND SAFETY IMPROVEMENTS (CRISI) PROGRAM AWARD
WAKE | CSX | CROSSING 643351A AT SR 1415 (NORTHEAST MAYNARD ROAD) IN CARY. CONSTRUCT GRADE SEPARATION. | RAIL | 5 | CAPITAL AREA MPO | P-5718 | REGION C | O, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 29344000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3344000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 23799000 |  |  | 56487000 | "O"FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION; TO BE LET WITH P-5734
WAKE | CSX | CROSSING 630601X AT SR 2006 (DURANT ROAD) IN RALEIGH. CONSTRUCT GRADE SEPARATION. | RAIL | 5 | CAPITAL AREA MPO | P-5720 | REGION C | T |  |  |  |  | 2023 | 18200000 |  |  | 18200000 | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH U-5307
WAKE | CSX S LINE | CONSTRUCT GRADE SEPARATION AT SR 2052 (ROGERS ROAD EXTENSION) CROSSING (633905Y) IN WAKE FOREST. | RAIL | 5 | CAPITAL AREA MPO | P-5707 | REGION C | T |  |  |  |  | 2024 | 24400000 |  |  | 24400000 | RIGHT-OF-WAY IN PROGRESS
WAKE | CSX S LINE | SR 2108 (MILLBROOK ROAD) IN RALEIGH. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 630605A. | RAIL | 5 | CAPITAL AREA MPO | P-5737 | STATEWIDE MOBILITY | DP, T | 2022 | 6111000 | 2022 | 1228000 | 2024 | 22200000 |  |  | 29539000 | RIGHT OF WAY IN PROGRESS; "DP" FUNDING REFLECTS CONSOLIDATED RAIL INFRASTRUCTURE AND SAFETY IMPROVEMENTS (CRISI) PROGRAM AWARD
WAKE | CSX S LINE | SR 1415 (WEST MAYNARD ROAD) IN CARY. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 643400U. | RAIL | 5 | CAPITAL AREA MPO | P-5739 | NOT FUNDED | O, T | NOT FUNDED | 2200000 |  |  | NOT FUNDED | 14401000 |  |  | 16601000 | "O" FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION
WAKE | FAYETTEVILLE STREET (SR 2513) | FAYETTEVILLE STREET AND THE CAROLINA COASTAL RAILWAY TRACKS CROSSING CLOSURE IN KNIGHTDALE. | RAIL | 5 | CAPITAL AREA MPO | Y-4805F | DIVISION 5 | RR |  |  |  |  | 2025 | 1600000 |  |  | 1600000
WAKE | GORALEIGH | RALEIGH UNION STATION BUS FACILITY INTER-CITY/COMMUTER RAIL PARK AND RIDE | RAIL | 5 | CAPITAL AREA MPO | TL-0020 | PUBLIC TRANSIT | CMAQ, L |  |  |  |  | 2022 | 5625000 |  |  | 5625000
WAKE | NCRR | RALEIGH UNION STATION PROJECT - PHASE I. CONSTRUCT RALEIGH TRAIN STATION AND ASSOCIATED RAIL TRACK AND SIDING IMPROVEMENTS TO INCREASE PASSENGER AND FREIGHT CAPACITY. | RAIL | 5 | CAPITAL AREA MPO | P-5500 | PRE-STI (TRANSITION) | [10 empty] | DP FUNDS - FEDERAL TIGER GRANT; O FUNDS - STATE LEGISLATIVE ALLOCATION FOR RAIL; PROJECT INCLUDES IN-KIND PROPERTY CONTRIBUTION BY TRIANGLE TRANSIT (CONTINGENT ON TT BOARD OF TRUSTEES APPROVAL) - 4 PARCELS TOTALING 3.5 ACRES WITH TAX VALUE OF $2.9 MILLION
WAKE | NCRR | CSXT S-LINE, TRACK AND SIGNAL IMPROVEMENTS - BOYLAN WYE CROSSOVER | RAIL | 5 | CAPITAL AREA MPO | P-5500A | [11 empty] | DELETED - WORK TO BE ACCOMPLISHED UNDER P-5005D.
WAKE | NCRR | STATION SITE WORK | RAIL | 5 | CAPITAL AREA MPO | P-5500B | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
WAKE | NCRR | TRACK IMPROVEMENTS | RAIL | 5 | CAPITAL AREA MPO | P-5500C | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
WAKE | NORFOLK SOUTHERN H LINE | CONSTRUCT GRADE SEPARATION AT HARRISON AVENUE CROSSING (734755X) IN CARY. | RAIL | 5 | CAPITAL AREA MPO | P-5708 | REGION C | O, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6000000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 16600000 |  |  | 22600000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN RAILROAD
WAKE | NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN H LINE | SR 2713 (VANDORA SPRINGS ROAD) IN GARNER. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 735324J. | RAIL | 5 | CAPITAL AREA MPO | P-5738 | NOT FUNDED | O, T | NOT FUNDED | 1800000 |  |  | NOT FUNDED | 11498000 |  |  | 13298000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION
WAKE | NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN H LINE | SR 1655 (TRINITY ROAD) IN CARY. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 630657S. | RAIL | 5 | CAPITAL AREA MPO | P-5734 | STATEWIDE MOBILITY | O, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 21000000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 16700000 |  |  | 37700000 | "O" FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION; TO BE LET WITH P-5718
WAKE | NORTH CAROLINA RAILROAD; NORFOLK SOUTHERN H LINE; | BERYL ROAD CROSSING IN RALEIGH. EXTEND BERYL ROAD TO ROYAL AVENUE, AND CLOSE CROSSING 630647L. | RAIL | 5 | CAPITAL AREA MPO | P-5736 | NOT FUNDED | O, T | NOT FUNDED | 200000 |  |  | NOT FUNDED | 3000000 |  |  | 3200000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION
WAKE | PIEDMONT CORRIDOR | CAPITAL YARD PHASE 1 IMPROVEMENTS - EXTEND TRACKS 1 AND 2, MAJOR WORK TRACK 3 | RAIL | 5 | CAPITAL AREA MPO | P-2918H | [11 empty] | IN PROGRESS
WAKE | VARIOUS | BOYLAN CROSSOVER IN RALEIGH. | RAIL | 5 | CAPITAL AREA MPO | P-5005D | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
WAKE, DURHAM | I-40 | EAST OF NC 147 TO SR 1728 (WADE AVENUE). PAVEMENT REHABILITATION. | HIGHWAY | 5 | CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | I-5995 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2025 | 32400000 |  |  | 32400000 | Combined with I-5996.
WAKE, DURHAM | I-540 | I-40 IN DURHAM TO US 70 IN RALEIGH. PAVEMENT REHABILITATION. | HIGHWAY | 5 | CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | I-5998 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2025 | 15000000 |  |  | 15000000 | COORDINATE WITH I-5999 AND I-6000
WAKE, DURHAM | I-540 | I-40 IN DURHAM TO US 1 IN RALEIGH. BRIDGE PRESERVATION / REHABILITATION. | HIGHWAY | 5 | CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | I-6000 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2026 | 7600000 |  |  | 7600000 | COORDINATE WITH I-5998 AND I-5999
WAKE, DURHAM | US 70 (GLENWOOD AVENUE) | WEST OF SR 3067 (T.W. ALEXANDER DRIVE) TO I-540 IN RALEIGH. UPGRADE ROADWAY TO IMPROVE CAPACITY, SAFETY AND TRAFFIC OPERATIONS INCLUDING INTERCHANGES AT VARIOUS LOCATIONS. | HIGHWAY | 5 | CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | U-5518 | STATEWIDE MOBILITY | NHP | 2025 | 153208000 | 2025 | 15714000 | 2025 | 168499000 |  |  | 337421000 | COORDINATE WITH U-2823 AND U-5720; DESIGN BUILD PROJECT
WAKE, DURHAM | VARIOUS | DIVISION 5 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS - DIVISION NEEDS CATEGORY | HIGHWAY | 5 | CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | W-5205DIV | DIVISION 5
WAKE, DURHAM | GOTRIANGLE TRANSIT | PURCHASE EXPANSION VEHICLES FOR DRX ROUTE. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | TA-6668 | REGION C | [10 empty] | IN ACQUISITION
WAKE, DURHAM, ORANGE | TRIANGLE J COUNCIL OF GOVERNMENTS | TRIANGLE J COUNCIL OF GOVERNMENTS (COG). TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN TRIANGLE OZONE NON-ATTAINMENT AREA. | HIGHWAY | 5, 7 | CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | C-4924 | EXEMPT
WAKE, DURHAM, ORANGE | TRIANGLE J COUNCIL OF GOVERNMENTS | TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN CAPITAL AREA MPO (CAMPO) | HIGHWAY | 5, 7 | CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | C-4924A | EXEMPT | [10 empty] | IN PROGRESS
WAKE, DURHAM, ORANGE | TRIANGLE J COUNCIL OF GOVERNMENTS | TRANSPORTATION DEMAND MANAGEMENT PROGRAM FOR ORGANIZATIONS IN DURHAM-CHAPEL HILL-CARRBORO (DCHC) | HIGHWAY | 5, 7 | CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | C-4924B | EXEMPT | CMAQ, L | [6 empty] | 2022 | 714000 | 714000 | IN PROGRESS
WAKE, DURHAM, ORANGE | AUTHORITY TRIANGLE TRANSIT | FIXED GUIDEWAY - LIGHT RAIL SERVICE- CARY/RALEIGH | PUBLIC TRANSIT | 5, 7 | CAPITAL AREA MPO | TE-4903A | PUBLIC TRANSIT | FED |  |  |  |  | 2020 | 1500000000 |  |  | 1500000000
WAKE, DURHAM, ORANGE | AUTHORITY TRIANGLE TRANSIT | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC INCLUDES ADA, PM AND SERVICE VEHICLES | PUBLIC TRANSIT | 5, 7 | CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | TG-4821B | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 7876000 | 7876000 | FUNDS AUTHORIZED IN PROGRESS
WAKE, FRANKLIN | I-87 / FUTURE I-87 / US 64 / US 264 | SR 1003 (ROLESVILLE ROAD) TO NASH COUNTY LINE. PAVEMENT REHABILITATION. | HIGHWAY | 5 | CAPITAL AREA MPO, KERR-TAR RPO | I-6001 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2025 | 41201000 |  |  | 41201000
WAKE, FRANKLIN, WARREN | VARIOUS | INSTALL LONG-LIFE PAVEMENT MARKINGS | HIGHWAY | 5 | CAPITAL AREA MPO, KERR-TAR RPO | W-5805F | DIVISION 5 | HSIP |  |  |  |  | 2021 | 2552000 |  |  | 2552000 | UNDER CONSTRUCTION
WAKE, HARNETT | NC 55 | NC 210 TO SR 4809 (JICARILLA LANE). PART ON NEW LOCATION. | HIGHWAY | 5, 6 | CAPITAL AREA MPO | R-5705B | REGION C | T | 2021 | 10172000 | 2021 | 1300000 | 2023 | 40900000 |  |  | 52372000
WAKE, JOHNSTON | I-40 | I-440 / US 64 (EXIT 301) TO NC 42 (EXIT 312). ADD 2 GENERAL-PURPOSE LANES IN EACH DIRECTION. | HIGHWAY | 4, 5 | CAPITAL AREA MPO | I-5111 | [11 empty] | UNDER CONSTRUCTION - DESIGN-BUILD PROJECT; GARVEE BONDS: $15 MILLION FOR RIGHT OF WAY - PAYBACK 2019-2033
WAKE, JOHNSTON | I-40; I-87; I-440; US 1 / US 64 | I-40 FROM SR 1728 (WADE AVENUE) TO NC 42, I-440, I-87 FROM I-40 TO I-540, US 1 FROM NC 540 TO I-40. CONVERT FACILITIES TO MANAGED FREEWAYS, TO INCLUDE RAMP METERING. | HIGHWAY | 4, 5 | CAPITAL AREA MPO | U-6101 | NOT FUNDED | NHP | NOT FUNDED | 1000000 | NOT FUNDED | 500000 | NOT FUNDED | 138201000 |  |  | 139701000
WAKE, JOHNSTON | NEW ROUTE (FUTURE NC 540) | SOUTHERN WAKE FREEWAY / TRIANGLE EXPRESSWAY SOUTHEAST EXTENSION (RALEIGH OUTER LOOP), EAST OF US 401 TO I-40. CONSTRUCT FREEWAY ON NEW LOCATION. | HIGHWAY | 4, 5 | CAPITAL AREA MPO | R-2828 | STATEWIDE MOBILITY | NHP |  |  |  |  | 2019 | 199023000 |  |  | 199023000 | UNDER CONSTRUCTION; COORDINATE WITH I-5111; NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT
WAKE, JOHNSTON | NEW ROUTE (FUTURE NC 540) | EASTERN WAKE FREEWAY / TRIANGLE EXPRESSWAY SOUTHEAST EXTENSION (RALEIGH OUTER LOOP), I-40 TO US 64 / US 264 BYPASS. FREEWAY ON NEW LOCATION. | HIGHWAY | 4, 5 | CAPITAL AREA MPO | R-2829 | STATEWIDE MOBILITY | BOND R, NHP, S(M) | 2025 | 105988000 | 2025 | 14660000 | 2026 | 590138000 |  |  | 710786000 | NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $262.5 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040
WAKE, JOHNSTON | VARIOUS | BUS RAPID TRANSIT SERVICE, MORRISVILLE TO CLAYTON. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | PUBLIC TRANSIT | 4, 5 | CAPITAL AREA MPO | TO-6166 | REGION A, C
WAKE, JOHNSTON, FRANKLIN, GRANVILLE | VARIOUS | PROJECTS TO IMPROVE CONGESTION AND AIR QUALITY IN THE CAPITAL AREA MPO. | HIGHWAY | 4, 5 | CAPITAL AREA MPO | C-5604 | EXEMPT | BGDA, CMAQ, L | 2020 | 1188000 |  |  | 2020 | 23622000 | 2020 | 4081000 | 28891000 | IN PROGRESS
WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | VARIOUS | PEDESTRIAN, BICYCLE, AND TRANSIT PROJECTS IN THE CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION (CAMPO). | BIKE/PED | 4, 5, 6 | CAPITAL AREA MPO | EL-5100 | DIVISION 4, 5, 6
WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | VARIOUS | CAPITAL AREA MPO: BICYCLE, PEDESTRIAN, TRANSIT, AND TRANSPORTATION ALTERNATIVES PROGRAM (TAP)-ELIGIBLE PROJECTS. | BIKE/PED | 4, 5, 6 | CAPITAL AREA MPO | U-5530 | DIVISION 4, 5, 6 | BGDA, L, TADA |  |  |  |  | 2020 | 3500000 |  |  | 3500000
WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | VARIOUS | INTERSECTION IMPROVEMENTS AT MULTIPLE LOCATIONS WITHIN THE CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION (CAMPO) BOUNDARY. | HIGHWAY | 4, 5, 6 | CAPITAL AREA MPO | HL-0008 | EXEMPT | [10 empty] | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY
WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | VARIOUS | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION (CAMPO) SURFACE TRANSPORTATION BLOCK GRANT DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. | HIGHWAY | 4, 5, 6 | CAPITAL AREA MPO | U-4735 | DIVISION 4, 5, 6 | BGDA |  |  |  |  | 2027 | 103155000 |  |  | 103155000
WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | VARIOUS | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION (CAMPO) PLANNING (PL) SUPPLEMENT. | HIGHWAY | 4, 5, 6 | CAPITAL AREA MPO | U-4850 | DIVISION 4, 5, 6 | BGDA, L | [6 empty] | 2022 | 19000000 | 19000000 | FORMERLY U-9999B - IN PROGRESS
WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | VARIOUS | OPERATIONAL IMPROVEMENTS FOR SAFETY AND CONGESTION MITIGATION. | HIGHWAY | 4, 5, 6 | CAPITAL AREA MPO | U-5118 | DIVISION 4, 5, 6 | BGDA, L |  |  |  |  | 2020 | 3750000 |  |  | 3750000 | PLANNING, DESIGN, RIGHT-OF-WAY AND CONSTRUCTION BY OTHERS - IN PROGRESS.
WAKE, JOHNSTON, FRANKLIN, GRANVILLE, HARNETT | VARIOUS | CAPITAL AREA METROPOLITAN PLANNING ORGANIZATION (CAMPO) TRANSPORTATION ALTERNATIVES DIRECT ATTRIBUTABLE (DA) FUNDS - RESERVED FOR FUTURE PROGRAMMING. | HIGHWAY | 4, 5, 6 | CAPITAL AREA MPO | U-6218 | DIVISION 4, 5, 6 | TADA |  |  |  |  | 2022 | 20456000 |  |  | 20456000
WAKE, LEE, VANCE | CSX S-LINE | SANFORD TO HENDERSON. TRANSIT-ORIENTED-DEVELOPMENT PLANNING. | PUBLIC TRANSIT | 5, 8 | CAPITAL AREA MPO, KERR-TAR RPO, TRIANGLE AREA RPO | TU-0004 | PUBLIC TRANSIT | FED, L, S | [6 empty] | 2021 | 1505000 | 1505000 | "FED" FUNDING REFLECTS FEDERAL TRANSIT ADMINISTRATION (FTA) TRANSIT-ORIENTED-DEVELOPMENT (TOD) GRANT FUNDS
WAKE, ORANGE | GOTRIANGLE TRANSIT | PURCHASE EXPANSION VEHICLES FOR CRX ROUTE. | PUBLIC TRANSIT | 5, 7 | CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | TA-6669 | REGION C, D | [10 empty] | IN ACQUISITION
WARREN | I-85 | NORTH OF SR 1237 (MANSON DREWRY ROAD) TO VIRGINIA STATE LINE | HIGHWAY | 5 | KERR-TAR RPO | I-0914BB | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
WARREN | NC 903 | NC 903 CAUSEWAY ON EATONS FERRY BRIDGE OVER LAKE GASTON. UPGRADE GUARDRAIL. | HIGHWAY | 5 | KERR-TAR RPO | HS-2005B | REGION C | HSIP |  |  |  |  | 2021 | 130000 |  |  | 130000 | UNDER CONSTRUCTION
WARREN, VANCE | I-85 | US 158 (MILE POST 213.5) IN VANCE COUNTY TO VIRGINIA STATE LINE. PAVEMENT REHABILITATION AND SIGN UPGRADES. | HIGHWAY | 5 | KERR-TAR RPO | I-0914 | PRE-STI (TRANSITION)
WARREN, VANCE | I-85 | REFURBISH SIGNS AND SIGNPOSTS | HIGHWAY | 5 | KERR-TAR RPO | I-0914A | [11 empty] | COMPLETE
WARREN, VANCE | I-85 | ITS DEPLOYMENT FOR PARTS BA AND BB | HIGHWAY | 5 | KERR-TAR RPO | I-0914BC | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
WASHINGTON | NC 32 | PRESERVATION OF BRIDGE 930015 ON NC 32 OVER THE ALBEMARLE SOUND. | HIGHWAY | 1 | ALBEMARLE RPO | HB-0016 | REGION A | BFP |  |  |  |  | 2025 | 50000000 |  |  | 50000000
WASHINGTON | SR 1106 (MORATTOCK ROAD) | SR 1100 (LONG RIDGE ROAD) TO NC 32 SOUTH. MODERNIZE ROADWAY. | HIGHWAY | 1 | ALBEMARLE RPO | R-5937 | DIVISION 1 | T | 2028 | 400000 | 2028 | 200000 | 2030 | 12300000 |  |  | 12900000
WASHINGTON | SR 1126 (ROPER NEWLAND ROAD) | SR 1128 (A CANAL ROAD) TO SR 1183 (SHORE DRIVE). MODERNIZE ROADWAY. | HIGHWAY | 1 | ALBEMARLE RPO | R-5936 | DIVISION 1 | T | 2026 | 200000 | 2026 | 200000 | 2028 | 18700000 |  |  | 19100000
WASHINGTON | WASHINGTON COUNTY | ADMINISTRATION | PUBLIC TRANSIT | 1 | ALBEMARLE RPO | TK-6171 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 356000 | 356000 | FUNDS AUTHORIZED IN PROGRESS
WATAUGA | TOWN OF BLOWING ROCK | MIDDLE FORK GREENWAY, SECTION 1. CONSTRUCT GREENWAY. NC FLAP BLOWING ROCK 321(1). | BIKE/PED | 11 | HIGH COUNTRY RPO | EB-5924 | EXEMPT | FLAP, L, S(M) | 2022 | 90000 |  |  | 2023 | 2014000 |  |  | 2104000 | PROJECT TO BE ADMINISTERED BY TOWN OF BLOWING ROCK - $145 K OF S(M) IS CONTINGENCY FUNDS ON WBS 44607
WATAUGA | US 221 | MAIN STREET IN BLOWING ROCK TO MOSES H CONE MEMORIAL PARK AND BASS LAKE. CONSTRUCT SIDEWALK. | BIKE/PED | 11 | HIGH COUNTRY RPO | EB-5798 | EXEMPT | [10 empty] | UNDER CONSTRUCTION. PROJECT TO BE ADMINISTERED BY THE TOWN OF BLOWING ROCK
WATAUGA | US 421 (KING STREET) MULTI-USE PATH | GROVE STREET TO BROOKSHIRE ROAD. CONSTRUCT MULTI-USE PATH. | BIKE/PED | 11 | HIGH COUNTRY RPO | EB-5983 | DIVISION 11 | L, TA5200 | 2024 | 20000 |  |  | 2025 | 1865000 | 2023 | 300000 | 2185000
WATAUGA | HUNTING HILLS LANE | REPLACE BRIDGE NO. 940346 OVER SOUTH FORK OF NEW RIVER IN BOONE. | HIGHWAY | 11 | HIGH COUNTRY RPO | B-5979 | DIVISION 11 | BGOFF, L | 2021 | 100000 |  |  | 2022 | 1500000 |  |  | 1600000
WATAUGA | NC 105 | SR 1136 (CLARKS CREEK ROAD) TO SR 1107 (NC 105 BYPASS) IN BOONE. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-2566B | REGION F | T | 2022 | 14365000 | 2022 | 9300000 | 2025 | 44301000 |  |  | 67966000 | BUILD NC BOND FUNDING: $4M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE);
WATAUGA | NC 105 | CONSTRUCT NEW BRIDGE OVER WATAUGA RIVER AND LEFT-TURN LANE AT SR 1112 (BROADSTONE ROAD). | HIGHWAY | 11 | HIGH COUNTRY RPO | R-2566BA | DIVISION 11 | T |  |  | 2019 | 2850000 | 2022 | 23680000 |  |  | 26530000 | WITHIN THE LIMITS OF R-2566 B. RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $6.2M FOR CONSTRUCTION, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE)
WATAUGA | NC 105 | SR 1658 (OLD SHULLS MILL ROAD) INTERSECTION. REALIGN SR 1658 (OLD SHULLS MILL ROAD). | HIGHWAY | 11 | HIGH COUNTRY RPO | R-2566BB | REGION F | T |  |  |  |  | 2023 | 1500000 |  |  | 1500000
WATAUGA | SR 1514 (BAMBOO ROAD); SR 1523 (WILSON RIDGE) | US 421/US 221 TO SR 1522 (DEERFIELD ROAD). MODERNIZE ROADWAY. | HIGHWAY | 11 | HIGH COUNTRY RPO | U-5810 | DIVISION 11 | T | 2022 | 13400000 | 2022 | 1500000 | 2024 | 25225000 |  |  | 40125000 | BUILD NC BOND FUNDING: $3.5M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); $10.2M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE)
WATAUGA | SR 1522 (DEERFIELD ROAD) | STATE FARM ROAD TO SR 1523 (WILSON RIDGE ROAD). UPGRADE ROADWAY. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5830 | DIVISION 11 | T | 2024 | 5800000 | 2024 | 1200000 | 2025 | 6200000 |  |  | 13200000
WATAUGA | US 221 / US 321 | DEERFIELD ROAD TO BOONE MALL. INSTALL PEDESTRIAN COUNTDOWN HEADS AND FLASHING YELLOW ARROWS AT VARIOUS INTERSECTIONS. | HIGHWAY | 11 | HIGH COUNTRY RPO | HS-2011B | STATEWIDE MOBILITY | HSIP |  |  |  |  | 2021 | 116000 |  |  | 116000
WATAUGA | US 321 | DEERFIELD ROAD AND MEADOWVIEW ROAD. REALIGN OFFSET INTERSECTION. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5874 | NOT FUNDED | NHP | NOT FUNDED | 5700000 | NOT FUNDED | 1000000 | NOT FUNDED | 7799000 |  |  | 14499000
WATAUGA | US 421 | SR 1180 (POPLAR GROVE CONNECTOR). CONSTRUCT ROUNDABOUT. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5872 | STATEWIDE MOBILITY | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3100000 |  |  | 8300000
WATAUGA | US 421 | TENNESSEE LINE TO US 321-US 421 JUNCTION NEAR VILAS. WIDEN TO MULTI-LANES. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5903 | NOT FUNDED | T | NOT FUNDED | 30600000 | NOT FUNDED | 1500000 | NOT FUNDED | 54902000 |  |  | 87002000
WATAUGA | US 421 (DANIEL BOONE PARKWAY) | US 421/321 WEST OF BOONE TO US 421 EAST OF BOONE. CONSTRUCT FREEWAY ON NEW LOCATION SOUTH OF BOONE. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5915 | DIVISION 11
WATAUGA | US 421 (DANIEL BOONE PARKWAY) | US 321/421 WEST OF BOONE TO NC 105 | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5915A | NOT FUNDED | T | NOT FUNDED | 81700000 | NOT FUNDED | 400000 | NOT FUNDED | 165600000 |  |  | 247700000
WATAUGA | US 421 (DANIEL BOONE PARKWAY) | NC 105 TO US 221/321 SOUTH OF BOONE | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5915B | DIVISION 11 | T | 2028 | 84800000 | 2028 | 600000 | 2031 | 246600000 |  |  | 332000000
WATAUGA | US 421 (DANIEL BOONE PARKWAY) | US 221/321 TO US 221/421 EAST OF BOONE | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5915C | NOT FUNDED | T | NOT FUNDED | 133800000 | NOT FUNDED | 400000 | NOT FUNDED | 384600000 |  |  | 518800000
WATAUGA | US 421/US 321 | US 321/US 421 JUNCTION NEAR VILAS TO SR 1107 (105 BYPASS) - TERMINI OF PROPOSED DANIEL BOONE PARKWAY (R-5915). WIDEN TO MULTI-LANES. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-2615 | REGION F | T | 2027 | 40900000 | 2027 | 1500000 | 2030 | 50200000 |  |  | 92600000
WATAUGA | APPALCART | ADMINISTRATION | PUBLIC TRANSIT | 11 | HIGH COUNTRY RPO | TK-6107 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 1872000 | 1872000 | FUNDS AUTHORIZED IN PROGRESS
WATAUGA | APPALCART | OPERATING ASSISTANCE | PUBLIC TRANSIT | 11 | HIGH COUNTRY RPO | TO-6101 | PUBLIC TRANSIT | 5311, L | [6 empty] | 2020 | 9544000 | 9544000 | FUNDS AUTHORIZED IN PROGRESS
WATAUGA | APPALCART | OPERATING ASSISTANCE | PUBLIC TRANSIT | 11 | HIGH COUNTRY RPO | TO-6104 | PUBLIC TRANSIT | SMAP | [6 empty] | 2020 | 2632000 | 2632000 | FUNDS AUTHORIZED IN PROGRESS
WATAUGA, AVERY | NC 105 | US 221 TO SR 1107 (NC 105 BYPASS) IN BOONE. WIDEN TO MULTI-LANES. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-2566
WAYNE | MOUNT OLIVE MUNICIPAL AIRPORT (W40) | EXTEND RUNWAY TO 5500 FEET. | AVIATION | 4 | EASTERN CAROLINA RPO | AV-5811 | DIVISION 4 | T |  |  |  |  | 2027 | 768000 |  |  | 768000
WAYNE | WAYNE EXECUTIVE JETPORT (GWW) | EXTEND RUNWAY. | AVIATION | 4 | GOLDSBORO URBAN AREA MPO | AV-5843 | DIVISION 4 | T |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6950000 |  |  | 6950000
WAYNE | GOLDSBORO | BERKELEY BOULEVARD, US 70 BUSINESS (EAST ASH STREET) TO SR 1900 (ELM STREET) IN GOLDSBORO. CONSTRUCT SIDEWALK ON EAST SIDE. | BIKE/PED | 4 | GOLDSBORO URBAN AREA MPO | EB-5850 | DIVISION 4 | L, TA5200 |  |  |  |  | 2025 | 127000 | 2024 | 19000 | 146000
WAYNE | STONEY CREEK GREENWAY | US 70 BYPASS TO SR 1560 (ROYALL AVENUE). CONSTRUCT 10 FOOT WIDE ASPHALT GREENWAY. | BIKE/PED | 4 | GOLDSBORO URBAN AREA MPO | EB-5707 | DIVISION 4 | L, SRTS |  |  |  |  | 2022 | 211000 |  |  | 211000 | UNDER CONSTRUCTION.
WAYNE | I-795 | WILSON COUNTY LINE TO SR 2075 (ASH STREET). UPGRADE GUARDRAIL, SHOULDER AND MEDIAN REPAIRS. | HIGHWAY | 4 | EASTERN CAROLINA RPO, GOLDSBORO URBAN AREA MPO | I-6047 | STATEWIDE MOBILITY | NHPIM, S(M) |  |  |  |  | 2020 | 6893000 |  |  | 6893000 | UNDER CONSTRUCTION. GARVEE BOND FUNDING $3,775,252; PAYBACK FY 2020-2034
WAYNE | NC 111 | INSTALL ALL WAY STOP UTILIZING EXISTING OVERHEAD FLASHERS AT NC 111 AND SR 1754 (ZION CHURCH ROAD). | HIGHWAY | 4 | EASTERN CAROLINA RPO | HS-2004E | REGION A | HSIP |  |  |  |  | 2022 | 48000 |  |  | 48000 | UNDER CONSTRUCTION.
WAYNE | NC 581 (BILL LANE BOULEVARD) | ARRINGTON BRIDGE ROAD TO NC 111. MODERNIZE ROADWAY. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-6207 | DIVISION 4 | T | 2027 | 1700000 | 2027 | 400000 | 2029 | 5000000 |  |  | 7100000
WAYNE | SR 1002 (PIKEVILLE-PRINCETON ROAD) | INSTALL ALL WAY STOP WITH ISLAND AT SR 1002 (PIKEVILLE-PRINCETON ROAD) AND SR 1320 (HINNANT ROAD). | HIGHWAY | 4 | EASTERN CAROLINA RPO | HS-2004D | DIVISION 4 | HSIP |  |  |  |  | 2022 | 25000 |  |  | 25000 | UNDER CONSTRUCTION.
WAYNE | SR 1006 (GRANTHAM SCHOOL ROAD) | REPLACE BRIDGE 950096 OVER THOROUGHFARE SWAMP. | HIGHWAY | 4 | EASTERN CAROLINA RPO | BR-0242 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 900000 |  |  | 900000 | PROJECT REPRESENTS HFB 4.R.103 PROJECT.
WAYNE | SR 1009 (SOUTH JORDAN CHAPEL ROAD) | REPLACE BRIDGE 950093 OVER FALLING CREEK. | HIGHWAY | 4 | EASTERN CAROLINA RPO | BR-0226 | HIGHWAY FUND | [10 empty] | UNDER CONSTRUCTION. PROJECT REPRESENTS HFB 4.R.96 PROJECT.
WAYNE | SR 1117 (THUNDER SWAMP ROAD) | REPLACE BRIDGE 950264 OVER THUNDER SWAMP. | HIGHWAY | 4 | EASTERN CAROLINA RPO | BR-0227 | DIVISION 4 | [10 empty] | UNDER CONSTRUCTION. PROJECT REPRESENTS HFB 4.R.91 PROJECT.
WAYNE | SR 1537 (AIRPORT ROAD) | INSTALL ALL WAY STOP AT SR 1537 (AIRPORT ROAD) AND SR 1545 (MT. CARMEL CHURCH ROAD). | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | HS-2004C | DIVISION 4 | HSIP |  |  |  |  | 2022 | 25000 |  |  | 25000 | UNDER CONSTRUCION.
WAYNE | SR 1556 (WAYNE MEMORIAL DRIVE) | SR 1003 (NEW HOPE ROAD) TO PROPOSED US 70 BYPASS IN GOLDSBORO. WIDEN TO MULTI-LANES. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-4753 | DIVISION 4 | T | 2019 | 4180000 |  |  | 2025 | 8260000 |  |  | 12440000 | RIGHT-OF-WAY IN PROGRESS
WAYNE | SR 1556 (WAYNE MEMORIAL DRIVE) | LOCKHAVEN DRIVE TO COUNTRY DAY ROAD. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-5994 | DIVISION 4 | T |  |  |  |  | 2023 | 450000 |  |  | 450000 | UNDER CONSTRUCTION
WAYNE | SR 1556 (WAYNE MEMORIAL DRIVE) | COUNTRY DAY ROAD TO NEW HOPE ROAD. ACCESS MANAGEMENT. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-6204 | DIVISION 4 | T | 2026 | 2900000 | 2026 | 2700000 | 2028 | 9400000 |  |  | 15000000
WAYNE | SR 1556 (WAYNE MEMORIAL DRIVE) | US 70 BYPASS TO SR 1572 (SAULSTON ROAD). WIDEN ROADWAY. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-6205 | DIVISION 4 | T | 2027 | 1900000 | 2027 | 1000000 | 2029 | 20300000 |  |  | 23200000
WAYNE | SR 1556 (WAYNE MEMORIAL DRIVE) | SR 1622 (WOODSIDE DRIVE) TO SR 1752 (SAULSTON-PATETOWN ROAD). SAFETY IMPROVEMENTS INCLUDING WIDENING, SHOULDERS, SUPERELEVATION REVISIONS, OVERLAYING PAVEMENT MARKINGS AND SIGNING. | HIGHWAY | 4 | EASTERN CAROLINA RPO | W-5500 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
WAYNE | SR 1713 (MILLER'S CHAPEL ROAD) | US 70 TO SR 1712 (THOROUGHFARE ROAD). MODERNIZE ROADWAY. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-6206 | DIVISION 4 | T | 2027 | 2500000 | 2027 | 900000 | 2029 | 5600000 |  |  | 9000000
WAYNE | SR 1744 (INDIAN SPRINGS ROAD) | INSTALL ALL WAY STOP AT SR 1744 (INDIAN SPRINGS ROAD) AND SR 1941 (NORTHEAST CHURCH ROAD). | HIGHWAY | 4 | EASTERN CAROLINA RPO | HS-2004I | DIVISION 4 | HSIP |  |  |  |  | 2022 | 28000 |  |  | 28000 | UNDER CONSTRUCTION.
WAYNE | SR 1958 (BENNETTS BRIDGE ROAD) | REPLACE BRIDGE 950117 OVER NE CAPE FEAR RIVER. | HIGHWAY | 4 | EASTERN CAROLINA RPO | B-4844 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 1200000 |  |  | 1200000 | UNDER CONSTRUCTION. HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS.
WAYNE | US 117 | SR 1135 (COUNTRY CLUB ROAD). CONSTRUCT INTERCHANGE WITH US 117. | HIGHWAY | 4 | EASTERN CAROLINA RPO | R-5719 | DIVISION 4 | [10 empty] | UNDER CONSTRUCTION
WAYNE | US 117 | SR 1120 (O'BERRY ROAD) IN GOLDSBORO. CONSTRUCT INTERCHANGE. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-5796 | DIVISION 4 | [10 empty] | UNDER CONSTRUCTION
WAYNE | US 117 (FUTURE I-795) | US 70 TO DUPLIN COUNTY LINE. PAVEMENT AND BRIDGE REHABILITATION. | HIGHWAY | 4 | EASTERN CAROLINA RPO, GOLDSBORO URBAN AREA MPO | I-6048 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2021 | 6892000 |  |  | 6892000
WAYNE | US 117 (FUTURE I-795) | NORTH OF SR 1135 (COUNTRY CLUB ROAD) TO SOUTH OF SR 1129 (SOUTH LANDFILL ROAD). | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO, EASTERN CAROLINA RPO | U-3125C | REGION A | NHP | 2026 | 100000 | 2026 | 138000 | 2028 | 13300000 |  |  | 13538000
WAYNE | US 117 (FUTURE I-795) | SOUTH OF SR 1129 (SOUTH LANDFILL ROAD) TO SOUTH OF SR 1927 (GENOA ROAD). | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-3125D | REGION A | NHP | 2027 | 13529000 | 2027 | 2172000 | 2029 | 59400000 |  |  | 75101000
WAYNE | US 117 (FUTURE I-795) | SOUTH OF SR 1927 (GENOA ROAD) TO NORTH OF NC 581 (ARRINGTON BRIDGE ROAD). | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-3125E | NOT FUNDED | NHP | NOT FUNDED | 35788000 | NOT FUNDED | 1513000 | NOT FUNDED | 135500000 |  |  | 172801000
WAYNE | US 117 (FUTURE I-795) | NORTH OF NC 581 (ARRINGTON BRIDGE ROAD) TO I-795. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-3125F | NOT FUNDED | NHP | NOT FUNDED | 20760000 | NOT FUNDED | 4729000 | NOT FUNDED | 62700000 |  |  | 88189000
WAYNE | US 117 BUS/US 117 (N. WILLIAMS STREET) | FROM NORTH OF US 70 TO SR 1571 (TOMMY'S ROAD) IN GOLDSBORO. WIDEN ROADWAY AND MAKE SAFETY IMPROVEMENTS. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-2714 | REGION A | L, T | 2020 | 3510000 |  |  | 2020 | 24187000 | 2020 | 4290000 | 31987000 | UNDER CONSTRUCTION. BUILD NC BOND FUNDING: $3,291,791 FOR PE, $2,733,041.73 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $41,064 FOR PE, $13,115,418 FOR CON PAYBACK 2021 - 2035 (FY 2021 / YR 2&3 SALE).
WAYNE | US 13 (BERKELEY BOULEVARD) | SR 1560 (ROYAL AVENUE) TO NORTH OF SR 1572 (SAULSTON ROAD) IN GOLDSBORO. WIDEN TO MULTI-LANES. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-3609
WAYNE | US 13 (BERKELEY BOULEVARD) | SR 1560 (ROYAL AVENUE) TO SR 1003 (NEW HOPE ROAD). | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-3609A | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
WAYNE | US 13 (BERKELEY BOULEVARD) | WIDEN TO MULTI-LANES FROM SR 1003 (NEW HOPE ROAD) TO US 70 BYPASS WITH INTERSECTION IMPROVEMENT AT SR1572 (SAULSTON ROAD) | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-3609B | REGION A | T | 2020 | 16339000 | 2020 | 3750000 | 2025 | 29670000 | 2020 | 2400000 | 52159000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,862,685 FOR PE, $1,253.83 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $10,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2038 (FY 2024 / YR 6 SALE).
WAYNE | US 13 (BERKELEY BOULEVARD) | REALIGNMENT OF HOOD SWAMP ROAD. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-3609BA | REGION A | T |  |  |  |  | 2022 | 1660000 |  |  | 1660000
WAYNE | US 13 (BERKELEY BOULEVARD) | REALIGNMENT OF SR 1709 (CENTRAL HEIGHTS ROAD) AT BERKELEY BOULEVARD IN GOLDSBORO. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-5724 | REGION A | T |  |  |  |  | 2023 | 14400000 |  |  | 14400000 | RIGHT-OF-WAY IN PROGRESS.
WAYNE | US 70 | SR 1719 (BESTON ROAD). IMPROVE INTERSECTION. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-5958 | REGION A | [10 empty] | UNDER CONSTRUCTION
WAYNE | US 70 | SR 1711 (NORTH OAK FOREST ROAD). IMPROVE INTERSECTION. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-6110 | REGION A | NHP | 2025 | 200000 | 2025 | 2200000 | 2027 | 4100000 |  |  | 6500000
WAYNE | US 70 BUSINESS (EAST ASH STREET) | SR 1579 (BERKELEY BOULEVARD) EAST TO US 70 IN GOLDSBORO. WIDEN TO MULTI-LANES. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-4407 | REGION A | T | 2026 | 3979000 | 2026 | 2090000 | 2028 | 17500000 |  |  | 23569000
WAYNE | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC | PUBLIC TRANSIT | 4 | GOLDSBORO URBAN AREA MPO | TG-6146 | PUBLIC TRANSIT | 5311 | [6 empty] | 2020 | 176000 | 176000 | FUNDS AUTHORIZED IN PROGRESS
WAYNE | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | ADMINISTRATION | PUBLIC TRANSIT | 4 | GOLDSBORO URBAN AREA MPO | TK-5179 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 1224000 | 1224000 | FUNDS AUTHORIZED IN PROGRESS
WAYNE | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | OPERATING ASSISTANCE | PUBLIC TRANSIT | 4 | GOLDSBORO URBAN AREA MPO | TO-4719 | PUBLIC TRANSIT | 5307, L, SMAP | [6 empty] | 2020 | 3360000 | 3360000 | FUNDS AUTHORIZED IN PROGRESS
WAYNE | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | OPERATING ASSISTANCE | PUBLIC TRANSIT | 4 | GOLDSBORO URBAN AREA MPO | TO-6107 | PUBLIC TRANSIT | 5311, L | [6 empty] | 2020 | 168000 | 168000 | FUNDS AUTHORIZED IN PROGRESS
WAYNE | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | PLANNING ASSISTANCE | PUBLIC TRANSIT | 4 | GOLDSBORO URBAN AREA MPO | TP-5116 | PUBLIC TRANSIT | 5303, L, S | [6 empty] | 2020 | 124000 | 124000 | FUNDS AUTHORIZED IN PROGRESS
WAYNE | GOLDSBORO-WAYNE TRANSPORTATION AUTHORITY | SAFETY & SECURITY - MIN. 1% SET ASIDE | PUBLIC TRANSIT | 4 | GOLDSBORO URBAN AREA MPO | TS-5129 | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 20000 | 20000 | FUNDS AUTHORIZED IN PROGRESS
WAYNE | TRANSPORTATION AUTHORITY GOLDSBORO-WAYNE | ROUTINE CAPITAL - BUS STOP SHELTERS, BENCHES, SHOP EQUIPMENT, SPARE PARTS, ENGINES, FAREBOX, SERVICE VEHICLES, ETC | PUBLIC TRANSIT | 4 | GOLDSBORO URBAN AREA MPO | TG-4752A | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 120000 | 120000 | FUNDS AUTHORIZED IN PROGRESS
WAYNE | TRANSPORTATION AUTHORITY GOLDSBORO-WAYNE | PREVENTIVE MAINTENANCE | PUBLIC TRANSIT | 4 | GOLDSBORO URBAN AREA MPO | TG-4752B | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 1004000 | 1004000 | FUNDS AUTHORIZED IN PROGRESS
WAYNE | TRANSPORTATION AUTHORITY GOLDSBORO-WAYNE | OPERATING ASSISTANCE - ADA PARATRANSIT SERVICE | PUBLIC TRANSIT | 4 | GOLDSBORO URBAN AREA MPO | TG-4752C | PUBLIC TRANSIT | 5307, L | [6 empty] | 2020 | 700000 | 700000 | FUNDS AUTHORIZED IN PROGRESS
WAYNE, DUPLIN | US 117 (FUTURE I-795) | SR 1006 (WEST TRADE STREET) TO NORTH OF SR 1135 (COUNTRY CLUB ROAD). | HIGHWAY | 3, 4 | EASTERN CAROLINA RPO | U-3125B | NOT FUNDED | NHP | NOT FUNDED | 25266000 | NOT FUNDED | 10475000 | NOT FUNDED | 73300000 |  |  | 109041000 | PROGRAMMED FOR PLANNING AND ENVIRONMENTAL STUDY ONLY.
WAYNE, DUPLIN, SAMPSON | US 117 (FUTURE I-795) | I-40 TO I-795. UPGRADE ROADWAY TO INTERSTATE STANDARDS, PART ON NEW LOCATION. | HIGHWAY | 3, 4 | GOLDSBORO URBAN AREA MPO, EASTERN CAROLINA RPO, MID-CAROLINA RPO | U-3125
WAYNE, GREENE | US 13 | SR 1572 (SAULSTON ROAD) TO SR 1700 (RODELL BARROW ROAD). MODERNIZE ROADWAY. | HIGHWAY | 2, 4 | GOLDSBORO URBAN AREA MPO, EASTERN CAROLINA RPO | R-5853 | DIVISION 2, 4 | T | 2025 | 2488000 | 2025 | 3040000 | 2027 | 8800000 |  |  | 14328000
WAYNE, JOHNSTON | US 70 | US 70 BYPASS TO EAST OF SR 2314 (PONDFIELD ROAD). UPGRADE TO FREEWAY STANDARDS. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO, EASTERN CAROLINA RPO, GOLDSBORO URBAN AREA MPO | R-5829
WAYNE, JOHNSTON | US 70 | US 70 BYPASS TO WEST OF SR 2372 (EDWARDS ROAD / NORTH PEARL STREET). UPGRADE TO FREEWAY STANDARDS. | HIGHWAY | 4 | EASTERN CAROLINA RPO, GOLDSBORO URBAN AREA MPO, UPPER COASTAL PLAIN RPO | R-5829A | STATEWIDE MOBILITY | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 40072000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7908000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 101600000 |  |  | 149580000
WILKES | WILKES COUNTY AIRPORT (UKF) | EXTEND RUNWAY TO 7,000 FEET. | AVIATION | 11 | HIGH COUNTRY RPO | AV-5894 | DIVISION 11 | T | 2023 | 600000 |  |  | 2024 | 12300000 |  |  | 12900000
WILKES | ROAD) SR 1185 (CURTIS BRIDGE | REPLACE BRIDGE 960730 OVER THE YADKIN RIVER. | HIGHWAY | 11 | HIGH COUNTRY RPO | HB-0020 | DIVISION 11 | BGOFF | 2023 | 800000 |  |  | 2026 | 8000000 |  |  | 8800000
WILKES | NC 115 | US 421 TO 2ND STREET. WIDEN ROADWAY. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5759 | DIVISION 11 | T | 2022 | 12615000 | 2022 | 900000 | 2024 | 31040000 | 2020 | 1365000 | 45920000 | BUILD NC BOND FUNDING: $1.057 M FOR PRELIMINARY ENGINEERING, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $1,129 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $13M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE)
WILKES | NC 268 | NC 18 TO SR 1966 (AIRPORT ROAD). CONSTRUCT SIDEWALK FROM NC 18 TO SHAVER STREET. WIDEN TO FIVE-LANES FROM SHAVER STREET TO FAIRPLAINS ROAD. WIDEN TO FOUR-LANES DIVIDED FROM FAIRPLAINS ROAD TO SR 1966 (AIRPORT ROAD). | HIGHWAY | 11 | HIGH COUNTRY RPO | R-2603 | PRE-STI (TRANSITION) | [10 empty] | UNDER CONSTRUCTION
WILKES | NC 268 | SR 1966 TO FOUR LANES WEST OF SR 2026 (AUSTIN TRAPHILL ROAD). MODERNIZE ROADWAY. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5906 | DIVISION 11 | BGLT5 | 2026 | 36000000 | 2026 | 600000 | 2029 | 52299000 |  |  | 88899000
WILKES | NC 268 | NC 268 EAST OF NORTH WILKESBORO. WIDEN MULTIPLE SECTIONS, IMPROVE SHOULDERS, AND INSTALL GUARDRAIL, RUMBLE STRIPS, AND PAVEMENT MARKINGS. | HIGHWAY | 11 | HIGH COUNTRY RPO | W-5503 | REGION F | [10 empty] | PART COMPLETE
WILKES | NC 268 | SR 1966 (AIRPORT ROAD) TO SR 2026 (AUSTIN TRAPHILL ROAD). INSTALL GUARDRAIL AND PAVEMENT MARKINGS. | HIGHWAY | 11 | HIGH COUNTRY RPO | W-5503A | REGION F | HSIP |  |  |  |  | 2021 | 1000000 |  |  | 1000000
WILKES | NEW ROUTE | NC 268 CONNECTOR, NC 18 TO US 421. CONSTRUCT MULTI-LANE FACILITY, PART ON NEW LOCATION. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-0616 | NOT FUNDED | T | NOT FUNDED | 18200000 | NOT FUNDED | 1100000 | NOT FUNDED | 132201000 |  |  | 151501000
WILKES | SR 1001 (OAKWOODS ROAD) | REPLACE BRIDGE 29 OVER CUB CREEK. | HIGHWAY | 11 | HIGH COUNTRY RPO | B-4676 | DIVISION 11 | HFB | 2023 | 700000 | 2023 | 400000 | 2024 | 3251000 |  |  | 4351000
WILKES | SR 1001 (OAKWOODS ROAD) | US 421 TO FOREST HILLS DRIVE. UPGRADE ROADWAY. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5772 | DIVISION 11 | T | 2026 | 3000000 | 2026 | 1500000 | 2028 | 10448000 |  |  | 14948000
WILKES | SR 1002 (TRAPHILL ROAD) | REPLACE BRIDGE 960663 ON SR 1002 OVER EAST PRONG ROARING RIVER. | HIGHWAY | 11 | HIGH COUNTRY RPO | BR-0125 | HIGHWAY FUND | DP, HFB | 2020 | 280000 |  |  | 2021 | 2650000 |  |  | 2930000 | DP REPRESENT FEDERAL BUILD GRANT FUNDING
WILKES | SR 1148 | REPLACE BRIDGE 960419 OVER NAKED CREEK. | HIGHWAY | 11 | HIGH COUNTRY RPO | BR-0209 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 650000 |  |  | 650000 | THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.153
WILKES | SR 1313 | REPLACE BRIDGE 960075 OVER FISH DAM CREEK. | HIGHWAY | 11 | HIGH COUNTRY RPO | B-4977 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 700000 |  |  | 700000 | LEVERAGE PROJECT FOR GREATTER BUILD GRANT
WILKES | SR 1745 (SHUMATE MOUNTAIN ROAD) | REPLACE BRIDGE 960166 ON SR 1745 OVER WEST PRONG ROARING RIVER. | HIGHWAY | 11 | HIGH COUNTRY RPO | BR-0124 | HIGHWAY FUND | DP, HFB | 2020 | 40000 |  |  | 2021 | 2900000 |  |  | 2940000 | HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP REPRESENT FEDERAL BUILD GRANT FUNDING
WILKES | SR 1749 (AUSTIN TRAPHILL ROAD) | REPLACE BRIDGE 960667 ON SR 1749 OVER SPARKS CREEK. | HIGHWAY | 11 | HIGH COUNTRY RPO | BR-0126 | HIGHWAY FUND | DP, HFB | 2020 | 80000 |  |  | 2021 | 1550000 |  |  | 1630000 | HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP REPRESENT FEDERAL BUILD GRANT FUNDING
WILKES | SR 2418 | REPLACE BRIDGE 960004 OVER LITTLE HUNTING CREEK. | HIGHWAY | 11 | HIGH COUNTRY RPO | BR-0108 | HIGHWAY FUND | HFB |  |  |  |  | 2022 | 1200000 |  |  | 1200000 | LEVERAGE PROJECT FOR GREATTER BUILD GRANT
WILKES | SR 2516 | REPLACE BRIDGE 960733 OVER CUB CREEK. | HIGHWAY | 11 | HIGH COUNTRY RPO | BR-0208 | HIGHWAY FUND | HFB |  |  |  |  | 2022 | 600000 |  |  | 600000 | THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.154
WILKES | US 421 | NC 16 TO US 421 BUSINESS. CONVERT EXISTING ROADWAY TO SUPERSTREET AND ADD SERVICE ROADS. | HIGHWAY | 11 | HIGH COUNTRY RPO | U-5312 | REGION F | NHP |  |  |  |  | 2023 | 31700000 |  |  | 31700000 | RIGHT-OF-WAY IN PROGRESS.
WILKES | WILKES TRANSPORTATION AUTHORITY | ADMINISTRATION | PUBLIC TRANSIT | 11 | HIGH COUNTRY RPO | TK-6172 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 912000 | 912000 | FUNDS AUTHORIZED IN PROGRESS
WILSON | WILSON | HOMINY CREEK GREENWAY AND TRAIL NETWORK PLAN. | BIKE/PED | 4 | UPPER COASTAL PLAIN RPO | BL-0069 | EXEMPT | DP | [6 empty] | 2022 | 950000 | 950000 | "DP" FUNDING REFLECTS REBUILDING AMERICAN INFRASTRUCTURE WITH SUSTAINABILITY AND EQUITY (RAISE) GRANT.
WILSON | I-795 | US 264 TO I-95. PAVEMENT REHABILITATION. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | I-5818 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
WILSON | I-95 | JOHNSTON COUNTY LINE (MILE MARKER 108.2) TO NORTH OF SR 1116 (GOVERNOR HUNT ROAD) (MILE MARKER 114.5). PAVEMENT REHABILITATION. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | I-5936 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2021 | 3303000 |  |  | 3303000
WILSON | NC 58 (NASH STREET NW) | SR 1330 (AIRPORT ROAD)/SR 1332 (LAKE WILSON ROAD). IMPROVE INTERSECTION. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | U-6111 | REGION A | T | 2027 | 700000 | 2027 | 400000 | 2029 | 5400000 |  |  | 6500000
WILSON | SR 1103 (WIGGINS MILL ROAD) | INSTALL ALL WAY STOP UTILIZING EXISTING OVERHEAD FLASHERS AT SR 1103 (WIGGINS MILL ROAD) AND SR 1169 (RADFORD ROAD). | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | HS-2004F | DIVISION 4 | HSIP |  |  |  |  | 2022 | 30000 |  |  | 30000 | LETTING COMBINED WITH HS-2004G AND HS-2004H.
WILSON | SR 1195 (REVELL ROAD) | REPLACE BRIDGE 970037 OVER BRANCH OF LITTLE BUFFALO CREEK. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | B-5999 | DIVISION 4 | [10 empty] | UNDER CONSTRUCTION
WILSON | SR 1309 (BLOOMERY ROAD) / SR 1382 (PACKHOUSE ROAD) | US 264 ALTERNATE TO NC 58. WIDEN AND UPGRADE FACILITY. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | U-5794 | DIVISION 4 | T | 2023 | 1000000 | 2023 | 946000 | 2025 | 9199000 |  |  | 11145000
WILSON | SR 1320 (AIRPORT BOULEVARD) | SR 1320 (AIRPORT BOULEVARD) AT CHELSEA DRIVE AND SR 1320 (AIRPORT BOULEVARD) AT JETSTREAM DRIVE IN WILSON. INSTALL TRAFFIC SIGNALS. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | HS-2004O | DIVISION 4 | HSIP |  |  |  |  | 2023 | 241000 |  |  | 241000
WILSON | SR 1339 (SHARPE SHORE ROAD) | REPLACE BRIDGE 970092 OVER TOWN SWAMP. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | B-5998 | DIVISION 4 | [10 empty] | UNDER CONSTRUCTION
WILSON | SR 1339 (SHARPE STORE ROAD) | REPLACE BRIDGE 970091 OVER TRIBUTARY OF TOWN CREEK. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | BR-0232 | DIVISION 4 | [10 empty] | UNDER CONSTRUCTION. PROJECT REPRESENTS HFB 4.R.94 PROJECT.
WILSON | SR 1356 (RALEIGH ROAD PARKWAY) | SR 1356 (RALEIGH ROAD PARKWAY) FROM ATLANTIC CHRISTIAN COLLEGE DRIVE (CITY STREET) TO NC 42/NC 58 IN WILSON. MODERNIZATION OF ROADWAY. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | HL-0034 | EXEMPT | BA |  |  | 2022 | 75000 | 2023 | 875000 | 2021 | 45000 | 995000
WILSON | SR 1400 (ROCK QUARRY ROAD) | REPLACE BRIDGE 970096 OVER TRIBUTARY OF TOWN CREEK. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | B-6000 | DIVISION 4 | [10 empty] | UNDER CONSTRUCTION
WILSON | SR 1418 (BRIDGERSVILLE ROAD) | REPLACE BRIDGE 970105 OVER CATTAIL SWAMP. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | BR-0233 | DIVISION 4 | [10 empty] | UNDER CONSTRUCTION. PROJECT REPRESENTS HFB 4.R.95 PROJECT.
WILSON | US 117 | REPLACE BRIDGE 47 OVER SEABOARD COAST LINE RAILROAD ON US 117. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | B-5666 | HIGHWAY FUND | HFB |  |  |  |  | 2022 | 4469000 |  |  | 4469000
WILSON | US 264 | US 264 FROM I-795 TO TOISNOT SWAMP. PAVEMENT REHABILITATION. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | HI-0006 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2022 | 7750000 |  |  | 7750000
WILSON | US 264 | US 264 FROM TOISNOT SWAMP TO THE GREENE COUNTY LINE. PAVEMENT REHABILITATION. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | HI-0007 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2022 | 7600000 |  |  | 7600000
WILSON | US 264 | US 264 FROM THE WILSON COUNTY LINE TO I-95. PAVEMENT REHABILITATION. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | HI-0014 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2026 | 7500000 |  |  | 7500000
WILSON | US 264 ALTERNATE (RALEIGH ROAD PARKWAY) | SR 1320 (AIRPORT BOULEVARD) TO EAST OF SR 1165 (FOREST HILLS ROAD). SAFETY IMPROVEMENTS. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | U-5941 | REGION A | T | 2026 | 12100000 | 2026 | 3900000 | 2028 | 11000000 |  |  | 27000000
WILSON | US 301 | SR 1606 (BLACK CREEK ROAD) TO SR 1515 (LIPSCOMB ROAD). UPGRADE ROADWAY INCLUDING BICYCLE AND PEDESTRIAN ACCOMODATIONS. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | U-5935 | REGION A | [10 empty] | UNDER CONSTRUCTION
WILSON | US 301 | US 301 AT NC 581. CONSTRUCT A REDUCED CONFLICT INTERSECTION WITH TRUCK BULB-OUTS AT THE ADJACENT U-TURN POINTS. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | W-5804A | REGION A | HSIP | 2021 | 100000 |  |  | 2022 | 2334000 |  |  | 2434000 | UNDER CONSTRUCTION.
WILSON | WILSON | WILSON CITY SIGNAL SYSTEM. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | U-5945 | NOT FUNDED | BG5200 |  |  | NOT FUNDED | 700000 | NOT FUNDED | 6600000 |  |  | 7300000
WILSON | CITY OF WILSON | ADMINISTRATION | PUBLIC TRANSIT | 4 | UPPER COASTAL PLAIN RPO | TK-5178 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 1304000 | 1304000 | FUNDS AUTHORIZED IN PROGRESS
WILSON | CITY OF WILSON | OPERATING ASSISTANCE | PUBLIC TRANSIT | 4 | UPPER COASTAL PLAIN RPO | TO-4779 | PUBLIC TRANSIT | 5311, L, SMAP | [6 empty] | 2020 | 4464000 | 4464000 | FUNDS AUTHORIZED IN PROGRESS
WILSON | WILSON COUNTY | ADMINISTRATION | PUBLIC TRANSIT | 4 | UPPER COASTAL PLAIN RPO | TK-6173 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 344000 | 344000 | FUNDS AUTHORIZED IN PROGRESS
WILSON | SR 1163 (GOLDSBORO STREET / HERRING AVENUE) | INSTALLATION OF ACTIVE WARNING DEVICES AT CSX CROSSING 629847Y IN WILSON. | RAIL | 4 | UPPER COASTAL PLAIN RPO | RX-2004A | DIVISION 4 | RR |  |  |  |  | 2024 | 800000 |  |  | 800000
YADKIN | I-77 | SOUTH OF SR 1125 (ASHBURY CHURCH ROAD-MILEPOST 71) TO US 21 IN YADKIN COUNTY (EXIT 79) | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | I-2808A | PRE-STI (TRANSITION) | [10 empty] | COMPLETE
YADKIN | I-77 | MILEMARKER 71.8 TO MILEMARKER 75.8. PAVEMENT REHABILITATION. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | I-5864 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2026 | 6285000 |  |  | 6285000 | COMBINE WITH I-5865 FOR LETTING.
YADKIN | I-77 | MILEMARKER 75.8 TO US 21 (EXIT 79). PAVEMENT REHABILITATION. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | I-5865 | STATEWIDE MOBILITY | NHPIM |  |  |  |  | 2026 | 2990000 |  |  | 2990000 | COMBINE WITH I-5864 FOR LETTING.
YADKIN | NC 67 | REPLACE BRIDGE 980035 OVER YADKIN RIVER. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | B-5825 | REGION F | T |  |  |  |  | 2021 | 13301000 |  |  | 13301000 | RIGHT-OF-WAY IN PROGRESS.
YADKIN | NC 67 | US 601 IN BOONVILLE TO WEST MAIN STREET IN EAST BEND. MODERNIZE ROADWAY WITH INTERSECTION IMPROVEMENTS AT NEBO ROAD. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5914 | DIVISION 11 | BGLT5 | 2026 | 9000000 | 2026 | 1000000 | 2028 | 39900000 |  |  | 49900000
YADKIN | SR 1119 | REPLACE BRIDGE 980028 OVER NORTH LITTLE HUNTING CREEK. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | BR-0205 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 2000000 |  |  | 2000000 | THIS PROJECT REPRESENTS HFB PROJECT NUMBER 17BP.11.R.130
YADKIN | SR 1152 | REPLACE BRIDGE 980020 OVER SOUTH DEEP CREEK. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | BR-0200 | HIGHWAY FUND | HFB |  |  |  |  | 2019 | 850000 |  |  | 850000 | UNDER CONSTRUCTION. THIS PROJECT REPRESENT HFB PROJECT NUMBER 17BP.11.R.183.
YADKIN | SR 1314 (EAST MAIN STREET) | US 601 TO SR 1765 (UNIFI INDUSTRIAL ROAD) IN YADKINVILLE. MODERNIZE ROADWAY, INCLUDING IMPROVEMENTS AT THE US 601 AND VAN BUREN STREET INTERSECTIONS. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5909 | DIVISION 11 | BGLT5 | 2026 | 1900000 | 2026 | 5800000 | 2028 | 4300000 |  |  | 12000000
YADKIN | SR 1325 (MOUNTAIN VIEW CHURCH ROAD) | REPLACE BRIDGE 980189 ON SR 1325 OVER SOUTH DEEP CREEK. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | BR-0127 | HIGHWAY FUND | DP, HFB | 2020 | 45000 |  |  | 2021 | 850000 |  |  | 895000 | HFB FUNDS REPRESENT HIGHWAY FUND BRIDGE FUNDS. DP REPRESENT FEDERAL BUILD GRANT FUNDING
YADKIN | SR 1512 | REPLACE BRIDGE 980080 OVER UT TO FARMERS CREEK. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | BR-0109 | HIGHWAY FUND | HFB | 2022 | 3000 | 2022 | 5000 | 2023 | 900000 |  |  | 908000 | LEVERAGE PROJECT FOR GREATTER BUILD GRANT
YADKIN | SR 1605 (OLD US 421) | SR 1146 (SHACKTOWN ROAD) TO SR 1711 (SPEER BRIDGE ROAD). CONSTRUCT NEW ROADWAY TO REALIGN SR 1605 WITH SR 1711 AND CONSTRUCT A ROUNDABOUT AT THE INTERSECTION WITH SR 1146. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5730 | DIVISION 11 | T |  |  |  |  | 2022 | 3216000 |  |  | 3216000
YADKIN | SR 1605 (OLD US 421) | SR 1600 (FALCON ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5912 | DIVISION 11 | T | 2023 | 600000 | 2023 | 100000 | 2024 | 1200000 |  |  | 1900000
YADKIN | US 21 BUS | REPLACE BRIDGE 980059 OVER JONESVILLE CREEK. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | B-4979 | HIGHWAY FUND | HFB |  |  |  |  | 2021 | 1600000 |  |  | 1600000 | LEVERAGE PROJECT FOR GREATTER BUILD GRANT
YADKIN | US 21 BUSINESS | REPLACE BRIDGE 980029 OVER I-77. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | B-5833 | REGION F | NHPB | 2021 | 1600000 |  |  | 2023 | 4600000 |  |  | 6200000
YADKIN | US 421 NORTHBOUND | REPLACE STRUCTURE 980105 OVER YADKIN RIVER OVERFLOW. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | B-5389 | HIGHWAY FUND | HFB | [9 empty] | UNDER CONSTRUCTION.
YADKIN | US 601 | US 601 (CAROLINA AVENUE) AND NC 67 (MAIN STREET). UPGRADE INTERSECTION. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5831 | DIVISION 11 | T |  |  |  |  | 2023 | 2750000 |  |  | 2750000 | RIGHT-OF-WAY IN PROGRESS
YADKIN | US 601 | NC 67 TO (SR 1502/1503) COUNTRY CLUB ROAD. MODERNIZE ROADWAY AND IMPROVE SR 1134 (MACKIE ROAD) INTERSECTION. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5896 | NOT FUNDED | T | NOT FUNDED | 2000000 | NOT FUNDED | 300000 | NOT FUNDED | 2100000 |  |  | 4400000
YADKIN | US 601 (SOUTH STATE STREET) | US 421 EASTBOUND RAMPS. INSTALL ROUNDABOUT. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5894 | REGION F | NHP | 2024 | 300000 | 2024 | 100000 | 2026 | 3300000 |  |  | 3700000 | COORDINATE WITH U-5809.
YADKIN | US 601 (STATE STREET) | US 421 TO SR 1146 (LEE AVENUE). CONSTRUCT MEDIAN AND ROUNDABOUTS. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | U-5809 | DIVISION 11 | T |  |  | 2023 | 800000 | 2024 | 11402000 |  |  | 12202000 | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5894.
YADKIN | VARIOUS | DIVISION 11 RUMBLE STRIPS, GUARDRAIL, SAFETY AND LIGHTING IMPROVEMENTS AT SELECTED LOCATIONS IN REGIONAL CATEGORY. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | W-5211REG | REGION F
YADKIN, SURRY | I-77 | SOUTH OF SR 1125 (MILE MARKER 71) IN YADKIN COUNTY TO US 21 BYPASS (MILE MARKER 83.5) IN SURRY COUNTY (EXIT 83). PAVEMENT REHABILITATION. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | I-2808 | [11 empty] | SECTION A - GARVEE BOND FUNDING $35 MILLION; PAYBACK FY 2007 - FY 2018. SEGMENT B TO BE ACCOMPLISHED UNDER I-5912.
YADKIN, SURRY | I-77 | US 21 IN YADKIN COUNTY (EXIT 79) TO US 21 BYPASS (EXIT 83) IN SURRY COUNTY | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | I-2808B | [11 empty] | SEGMENT B TO BE ACCOMPLISHED UNDER I-5912.
YADKIN, SURRY | I-77 | US 21 IN YADKIN COUNTY (EXIT 79) TO MILEMARKER 83.4 IN SURRY COUNTY . PAVEMENT REHABILITATION. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | I-5912 | STATEWIDE MOBILITY | [10 empty] | UNDER CONSTRUCTION
YADKIN, SURRY | NC 67, US 21 BUS | COMMERCE STREET IN ELKIN TO NORTH BRIDGE STREET IN JONESVILLE. WIDEN ROADWAY, CONSTRUCT ROUNDABOUTS AT WEST MAIN STREET AND ELM STREET AND ELM STREET AND NORTH BRIDGE STREET, AND IMPROVE BICYCLE AND PEDESTRIAN CONNECTIONS. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5913
YADKIN, SURRY | NC 67, US 21 BUSINESS | COMMERCE STREET IN ELKIN TO NORTH BRIDGE STREET IN JONESVILLE. WIDEN ROADWAY, CONSTRUCT ROUNDABOUTS AT WEST MAIN STREET AND ELM STREET AND ELM STREET AND NORTH BRIDGE STREET, AND IMPROVE BICYCLE AND PEDESTRIAN CONNECTIONS. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5913A | DIVISION 11 | BG5200 | 2023 | 1100000 | 2023 | 220000 | 2025 | 3300000 |  |  | 4620000
YANCEY | NC 197 | NC 197 FROM SR 1338 TO THE MITCHELL COUNTY LINE, NEAR GREEN MOUNTAIN. INSTALL SHOULDER GUARDRAIL. | HIGHWAY | 13 | HIGH COUNTRY RPO | W-5813H | REGION G | HSIP |  |  |  |  | 2022 | 474000 |  |  | 474000 | COMPLETE
YANCEY | AUTHORITY YANCEY COUNTY TRANSPORTATION | CONSTRUCT OFFICE / TRAINING / MAINTENANCE FACILITY. | PUBLIC TRANSIT | 13 | HIGH COUNTRY RPO | TA-6723 | DIVISION 13 | L, T |  |  |  |  | 2023 | 750000 | 2022 | 111000 | 861000 | LOCAL FUNDING PROVIDED BY YANCEY COUNTY
YANCEY | YANCEY COUNTY TRANSPORTATION AUTHORITY | ADMINISTRATION | PUBLIC TRANSIT | 13 | HIGH COUNTRY RPO | TK-6175 | PUBLIC TRANSIT | 5311, L, S | [6 empty] | 2020 | 580000 | 580000 | FUNDS AUTHORIZED IN PROGRESS
Note on S61: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: VERIFY IT'S COMPLETED W/ TAMARA
Note on S150: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: HICAMS has it completed, SAP not clear
Note on S354: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ACCEPTED 2/11/22
Note on S828: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: projects in sap doesn't line up with breaks
Note on S1037: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Where is this project?
Note on S2143: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: B BREAK IN SAP COMPLETE, A BREAK NOT IN SAP AT ALL. SEEM TO BE UNDER CONSTRUCTION AT THE SAME TIME

## Projects Eligible for Swaps
REVISED DRAFT 2024-2033 STATE TRANSPORTATION IMPROVEMENT PROGRAM: PROJECTS ELIGIBLE FOR SWAPS
NOTES: COSTS AND SCHEDULES ARE AS OF AUGUST 4, 2022 AND ARE SUBJECT TO CHANGE. PRIORITIZATION STATUS IS BASED ON THE FIRST YEAR OF RIGHT-OF-WAY, UTILITIES, OR CONSTRUCTION FUNDING. IF THE FIRST YEAR OF RIGHT-OF-WAY, UTILITIES, OR CONSTRUCTION FUNDING IS SCHEDULED ON OR BEFORE FISCAL YEAR 2028, THE PROJECT IS CONSIDERED "SCHEDULED FOR DELIVERY" AND DOES NOT HAVE TO BE REPRIORITIZED.
BASIC PROJECT INFORMATION | [6 empty] | PRIORITIZATION INFORMATION |  |  | FISCAL YEAR PROJECT PHASE SCHEDULED TO START
COUNTY(S) | ROUTE/CITY | DESCRIPTION | MODE | DIVISION(S) | MPOs/RPOs | PROJECT ID | STI CATEGORY FUNDED | PRIORITIZATION STATUS | FUNDING SOURCE (SEE FUNDING SOURCES TAB FOR MORE INFO) | RIGHT-OF-WAY PROJECTED SCHEDULE | STI FUNDS NEEDED FOR RIGHT-OF-WAY | UTILITIES PROJECTED SCHEDULE | STI FUNDS NEEDED FOR UTILITIES | CONSTRUCTION PROJECTED SCHEDULE | STI FUNDS NEEDED FOR CONSTRUCTION | TOTAL STI FUNDS | COMMENT
ALAMANCE | BURLINGTON- ALAMANCE REGIONAL AIRPORT (BUY) | CONSTRUCT 100 FT PAVED OVERRUN AND MAKE SAFETY ENHANCEMENTS. | AVIATION | 7 | BURLINGTON-GRAHAM MPO | AV-5851 | DIVISION 7 | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2024 | 2080000 | 2080000
ALAMANCE | LEE AVENUE | WEST LEBANON AVENUE TO SR 1454 (WEST HAGGARD AVENUE) IN ELON. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | BURLINGTON-GRAHAM MPO | EB-5988 | DIVISION 7 | SCHEDULED FOR DELIVERY | L, TA5200 | 2025 | 4000 |  |  | 2026 | 218000 | 222000
ALAMANCE | I-40 / I-85 | SR 1158 (HUFFMAN MILL ROAD) INTERCHANGE. CONSTRUCT ADDITIONAL LEFT TURN LANE ON I-40 WESTBOUND RAMP AND IMPROVE OPERATIONS AT SR 1308 (GARDEN ROAD) INTERSECTION. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | I-6009 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1000000 | 1800000
ALAMANCE | I-40 / I-85 | SR 1981 (TROLLINGWOOD-HAWFIELDS ROAD) IN MEBANE. UPGRADE INTERCHANGE. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | I-6059 | DIVISION 7 | WILL BE REPRIORITIZED | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7100000 | 7900000
ALAMANCE | NC 119 | SR 1981 (TROLLINGWOOD-HAWFIELDS ROAD) / SR 2126 (OLD HILLSBOROUGH ROAD TO LOWES BOULEVARD IN MEBANE. WIDEN TO MULTILANES. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6013 | DIVISION 7 | SCHEDULED FOR DELIVERY | T | 2023 | 5500000 | 2023 | 900000 | 2024 | 7200000 | 13600000 | IN PROGRESS
ALAMANCE | NC 49 (ROXBORO ROAD) | SR 1928 (WILKINS ROAD) AND SR 1927 (BASON ROAD). UPGRADE K-TYPE INTERSECTION. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6183 | DIVISION 7 | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2900000 | 4500000
ALAMANCE | NC 54 (CHAPEL HILL ROAD) | SR 1445 (SOUTH O'NEAL STREET) IN BURLINGTON. RECONFIGURE INTERSECTION TO MAKE O'NEAL STREET THE THROUGH MOVEMENT WITH NC 54 EAST OF THE INTERSECTION. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6184 | DIVISION 7 | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8400000 | 14600000
ALAMANCE | NC 54 (EAST HARDEN STREET) | SR 1945 (RIVERBEND ROAD) / SR 2431 (JOHNSON STREET) INTERSECTIONIN GRAHAM. INTERSECTION IMPROVEMENTS. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6115A | DIVISION 7 | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2000000 | 2700000
ALAMANCE | NC 54 (EAST HARDEN STREET) | I-40 / I-85 INTERCHANGE IN GRAHAM. UPGRADE RAMP INTERSECTIONS. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6115B | REGION D | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5399000 | 6299000
ALAMANCE | NC 54 (EAST HARDEN STREET) | SR 2106 (WOODY DRIVE) IN GRAHAM. INTERSECTION IMPROVEMENTS. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6115C | REGION D | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2100000 | 2900000
ALAMANCE | NC 54 (EAST HARDEN STREET) | SR 2106 (WOODY DRIVE) AND SR 2107 (WHITTEMORE ROAD) INTERSECTIONS IN GRAHAM. UPGRADE PIPE CULVERTS 000271 AND 000297. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6115D | REGION D | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1600000 | 1900000
ALAMANCE | NC 54 (WEST HARDEN STREET) | NC 49 (MAPLE AVENUE) IN BURLINGTON. INSTALL DUAL LEFT TURN LANES IN WESTBOUND DIRECTION. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6131 | REGION D | SCHEDULED FOR DELIVERY | T | 2025 | 4100000 | 2025 | 1100000 | 2026 | 3500000 | 8700000
ALAMANCE | NC 62 | SR 1430 (RAMADA ROAD) TO US 70 (CHURCH STREET) IN BURLINGTON. WIDEN TO MULTILANES. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-5844 | DIVISION 7 | SCHEDULED FOR DELIVERY | T | 2024 | 13300000 | 2024 | 3400000 | 2025 | 8700000 | 25400000
ALAMANCE | NC 62 (ALAMANCE ROAD) | SR 1155 (HATCHERY ROAD) / BONNIE LANE INTERSECTION IN BURLINGTON. INSTALL TRAFFIC SIGNAL AND ADD TURN LANES. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6114 | REGION D | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 900000 | 1800000
ALAMANCE | NC 87 (WEBB AVENUE) | SR 1515 (FLORA AVENUE). INSTALL TRAFFIC SIGNAL AND ADD TURN LANES. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6182 | DIVISION 7 | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 180000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1100000 | 2480000
ALAMANCE | SR 1455 (EAST HAGGARD AVENUE) | NC 87 (WEST WEBB AVENUE) / NC 100 (UNIVERSITY DRIVE) IN ELON. IMPROVE INTERSECTION. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6214 | DIVISION 7 | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5600000 | 11400000
ALAMANCE | SR 1716 (GRAHAM- HOPEDALE ROAD) | SR 1720 (WEST HANOVER ROAD) TO MORNINGSIDE DRIVE IN BURLINGTON. WIDEN TO MULTILANES WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6014 | DIVISION 7 | SCHEDULED FOR DELIVERY | T | 2023 | 4700000 | 2023 | 1200000 | 2025 | 13200000 | 19100000
ALAMANCE | SR 1716 (NORTH MAIN STREET) | SR 2396 (WEST PARKER STREET) IN GRAHAM. IMPROVE INTERSECTION. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6132 | DIVISION 7 | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1500000 | 2200000
ALAMANCE | US 70 (SOUTH CHURCH STREET) | TARLETON AVENUE TO FIFTH STREET IN BURLINGTON. WIDEN AND CONSTRUCT CENTER TURN LANE. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6009 | REGION D | SCHEDULED FOR DELIVERY | T | 2028 | 26600000 | 2028 | 5100000 | 2030 | 11700000 | 43400000
ALAMANCE | US 70 (SOUTH CHURCH STREET) | SR 1158 (HUFFMAN MILL ROAD) IN BURLINGTON. INTERSECTION IMPROVEMENTS. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6011 | REGION D | SCHEDULED FOR DELIVERY | T | 2022 | 3000000 | 2022 | 600000 | 2025 | 2400000 | 6000000 | RIGHT OF WAY IN PROGRESS
ALEXANDER | NC 16 | CATAWBA RIVER TO US 64 IN TAYLORSVILLE. UPGRADE AND MODERNIZE TWO-LANE ROADWAY. | HIGHWAY | 12 | GREATER HICKORY MPO | U-6151 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 17300000 | NOT FUNDED | 3500000 | NOT FUNDED | 55000000 | 75800000
ALEXANDER | US 64 | US 64 AND SR 1124. ADD LEFT TURN LANE ON WESTBOUND US 64/NC 90 | HIGHWAY | 12 | GREATER HICKORY MPO | U-6041 | DIVISION 12 | SCHEDULED FOR DELIVERY | T | 2024 | 200000 | 2024 | 400000 | 2025 | 1450000 | 2050000
ALEXANDER, CATAWBA | NC 127 | SR 1400 (CLONINGER MILL ROAD) TO SR 1156 (RICHEY ROAD). | HIGHWAY | 12 | GREATER HICKORY MPO | R-3603A | DIVISION 12 | SCHEDULED FOR DELIVERY | T | 2024 | 26900000 | 2024 | 100000 | 2026 | 55100000 | 82100000 | INCLUDES CONSTRUCTION OF RIGHT TURN LANE ON NC 127 AT SR 1146 (BETHLEHEM SCHOOL ROAD) (FORMERLY U-6040).
ANSON | NEW ROUTE - WADESBORO BYPASS | US 52 NORTH OF WADESBORO TO US 74 EAST OF WADESBORO. CONSTRUCT FREEWAY ON NEW LOCATION. | HIGHWAY | 10 | ROCKY RIVER RPO | R-5878B | REGION E | SCHEDULED FOR DELIVERY | T | 2027 | 32400000 | 2027 | 1300000 | 2029 | 121799000 | 155499000
ANSON | US 74 | NC 742 (GRAHAM STREET) TO ANSON HIGH SCHOOL ROAD. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 10 | ROCKY RIVER RPO | R-5871 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10800000 | 25100000
ANSON | US 74 (ANDREW JACKSON HIGHWAY) | GRAHAM STREET TO SR 1749. CONSTRUCT MEDIAN. | HIGHWAY | 10 | ROCKY RIVER RPO | R-5798 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | T | 2024 | 14800000 | 2024 | 4900000 | 2026 | 21300000 | 41000000
ANSON | CSX SF LINE | CONSTRUCT SIDING EXTENSION IN POLKTON. | RAIL | 10 | ROCKY RIVER RPO | P-5750A | REGION E | SCHEDULED FOR DELIVERY | DP, T | 2024 | 600000 |  |  | 2024 | 9837000 | 10437000
ANSON | CSX SF LINE | SR 1469 (FREEDOM ROAD) INTERSECTION. CONSTRUCT GRADE SEPARATION. | RAIL | 10 | ROCKY RIVER RPO | P-5750B | REGION E | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2026 | 16380000 | 16380000
ASHE | NC 88 | NC 88 TO NC 194. UPGRADE ROADWAY. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5832 | DIVISION 11 | SCHEDULED FOR DELIVERY | T | 2023 | 12200000 | 2023 | 1500000 | 2025 | 45191000 | 58891000 | BUILD NC BOND FUNDING: $19M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE)
ASHE | US 221 BUSINESS | NC 194 AND SR 1248 (BEAVER CREEK SCHOOL ROAD) INTERSECTION. CONSTRUCT SUPERSTREET INTERSECTION. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5833 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 1100000 | NOT FUNDED | 50000 | NOT FUNDED | 2800000 | 3950000
AVERY | NC 184 | NC 105 TO SR 1342 (HICKORY NUT GAP ROAD) IN BANNER ELK. WIDEN TO MULTI-LANES. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5902 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 18200000 | NOT FUNDED | 7900000 | NOT FUNDED | 64798000 | 90898000
AVERY, MITCHELL | US 19E | MULTI-LANES EAST OF SPRUCE PINE TO SR 1106. WIDEN TO MULTI-LANES. | HIGHWAY | 11, 13 | HIGH COUNTRY RPO | R-2520A | DIVISION 11, 13 | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 14700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 50801000 | 69501000
BEAUFORT | WARREN FIELD (OCW) | ACQUIRE LAND FOR AND CONSTRUCT RUNWAY 5-23 EXTENSION AND TAXIWAY. | AVIATION | 2 | MID-EAST RPO | AV-5743 | DIVISION 2 | SCHEDULED FOR DELIVERY | T | 2028 | 1635000 |  |  | 2029 | 3648000 | 5283000
BEAUFORT | NC 32 | BRICK KILN ROAD. IMPROVE INTERSECTION. | HIGHWAY | 2 | MID-EAST RPO | R-5897 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 454000 | NOT FUNDED | 200000 | NOT FUNDED | 1400000 | 2054000
BEAUFORT | SR 1306 (15TH STREET) | US 17 BUSINESS (CAROLINA AVENUE) TO BROWN STREET. WIDEN TO MULTI-LANES. | HIGHWAY | 2 | MID-EAST RPO | U-5860 | DIVISION 2 | SCHEDULED FOR DELIVERY | T | 2026 | 8900000 | 2026 | 2800000 | 2028 | 11000000 | 22700000
BERTIE | NC 45 | US 17 AT MIDWAY TO SOUTHERN CITY LIMITS OF COLERAIN. | HIGHWAY | 1 | PEANUT BELT RPO | R-5809B | DIVISION 1 | SCHEDULED FOR DELIVERY | T | 2024 | 3012000 | 2024 | 12944000 | 2026 | 33498000 | 49454000
BLADEN | FIELD (EYF) CURTIS L BROWN JR | EXTEND RUNWAY TO 5500 FEET AND PARALLEL TAXIWAY. | AVIATION | 6 | MID-CAROLINA RPO | AV-5826 | DIVISION 6 | WILL BE REPRIORITIZED | T |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5240000 | 5240000
BRUNSWICK | NC 211 (NORTH HOWE STREET) | EAST OWEN STREET TO DOSHER HOSPITAL IN SOUTHPORT. CONSTRUCT SIDEWALK. | BIKE/PED | 3 | CAPE FEAR RPO | EB-5982 | DIVISION 3 | SCHEDULED FOR DELIVERY | L, TA5200 | 2024 | 40000 |  |  | 2025 | 140000 | 180000
BRUNSWICK | NC 211 | SR 1112 (SUNSET HARBOR ROAD) TO NC 906 (MIDWAY ROAD). WIDEN ROADWAY. | HIGHWAY | 3 | CAPE FEAR RPO | R-5947 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 7300000 | NOT FUNDED | 4300000 | NOT FUNDED | 45700000 | 57300000
BRUNSWICK | US 17 | NC 904. CONVERT INTERSECTION TO SUPERSTREET. | HIGHWAY | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | R-5851 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 850000 | NOT FUNDED | 115000 | NOT FUNDED | 4950000 | 5915000
BRUNSWICK | US 17 | US 17 BUSINESS SOUTH OF SHALLOTTE AND US 17 BUSINESS NORTH OF SHALLOTTE. CONVERT INTERSECTIONS TO SUPERSTREETS. | HIGHWAY | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | R-5857 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | T | 2023 | 763000 | 2023 | 174000 | 2025 | 13500000 | 14437000
BRUNSWICK | US 17 | NC 211. CONVERT INTERSECTION TO INTERCHANGE. | HIGHWAY | 3 | CAPE FEAR RPO, GRAND STRAND AREA TRANSPORTATION STUDY | U-5932 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 38988000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1920000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 36102000 | 77010000
BRUNSWICK | US 17 (SHALLOTTE BYPASS) | SR 1357 (SMITH AVENUE). UPGRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | U-5862 | REGION B | SCHEDULED FOR DELIVERY | T | 2028 | 5240000 | 2028 | 1840000 | 2030 | 22000000 | 29080000
BRUNSWICK | US 17 (SHALLOTTE BYPASS) | US 17 BUSINESS SOUTH (MAIN STREET). UPGRADE EXISTING AT GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | U-6104 | NOT FUNDED | WILL BE REPRIORITIZED | NHP | NOT FUNDED | 4233000 | NOT FUNDED | 300000 | NOT FUNDED | 19200000 | 23733000
BRUNSWICK, NEW HANOVER | SOUTHPORT - FORT FISHER | CONSTRUCT MOORING FACILITIES. | FERRY | 3 | CAPE FEAR RPO, WILMINGTON URBAN AREA MPO | F-5707 | REGION B | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2025 | 5000000 | 5000000
BRUNSWICK, NEW HANOVER | SOUTHPORT-FORT FISHER | SOUTHPORT-FORT FISHER FERRY. CONSTRUCT RIVER CLASS FERRY. | FERRY | 3 | CAPE FEAR RPO, WILMINGTON URBAN AREA MPO | F-5705 | NOT FUNDED | WILL BE REPRIORITIZED | T |  |  |  |  | NOT FUNDED | 14000000 | 14000000
BUNCOMBE | DEAVERVIEW ROAD | US 19/23/74A (PATTON AVENUE) TO WESTMORE DRIVE IN ASHEVILLE. CONSTRUCT SIDEWALK. | BIKE/PED | 13 | FRENCH BROAD RIVER MPO | EB-5965 | DIVISION 13 | SCHEDULED FOR DELIVERY | L, TAANY | 2026 | 200000 |  |  | 2027 | 1796000 | 1996000
BUNCOMBE | MCDOWELL STREET CHOCTAW STREET | SOUTHSIDE AVENUE TO CHOCTAW STREET AT BILTMORE AVENUE. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | BIKE/PED | 13 | FRENCH BROAD RIVER MPO | EB-5919 | DIVISION 13 | SCHEDULED FOR DELIVERY | L, TAANY | 2022 | 21000 |  |  | 2024 | 256000 | 277000
BUNCOMBE | NORTH RAD GREENWAY | CONSTRUCT MULTI-USE PATH ALONG RIVERSIDE DRIVE FROM HILL STREET TO US 19/23/70 AT BROADWAY | BIKE/PED | 13 | FRENCH BROAD RIVER MPO | EB-5822 | DIVISION 13 | SCHEDULED FOR DELIVERY | BGDA, L, TAANY | 2023 | 103000 |  |  | 2025 | 3200000 | 3303000
BUNCOMBE | ASHEVILLE | US 19 (PATTON AVENUE) AND NC 63 (NEW LEICESTER HIGHWAY). CONSTRUCT FINAL INTERSECTION IMPROVEMENTS. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-5971B | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 35590000 | NOT FUNDED | 300000 | NOT FUNDED | 6500000 | 42390000
BUNCOMBE | ASHEVILLE | NC 63 (NEW LEICESTER HIGHWAY), US 19/23 (PATTON AVENUE) TO NEWFOUND ROAD. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-5972 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 66000000 | NOT FUNDED | 6700000 | NOT FUNDED | 31899000 | 104599000
BUNCOMBE | I-26 (US 19/US 23) | SR 1781 (BROADWAY STREET) TO US 25/70 | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | A-0010AA | REGION G | SCHEDULED FOR DELIVERY | T | 2028 | 42700000 | 2028 | 1000000 | 2031 | 279800000 | 323500000
BUNCOMBE | I-26/I-240 | NORTH OF I-40 TO SR 3548 (HAYWOOD ROAD). WIDEN TO SIX LANE FREEWAY. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-2513AC | REGION G | SCHEDULED FOR DELIVERY | T | 2023 | 38815000 | 2023 | 3000000 | 2024 | 179005000 | 220820000 | BUILD NC BOND FUNDING: $10.5M FOR RIGHT-OF-WAY, PAYBACK FY 2023-2036 (FY 2022 / YR 4 SALE); $45.3M FOR CONSTRUCTION, PAYBACK 2024-2038 (FY 2024 / YR 6 SALE).
BUNCOMBE | I-26/I-240 | I-26/I-40/I-240 FINAL INTERCHANGE IMPROVEMENTS | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-2513C | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4075000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 17400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 185001000 | 206476000
BUNCOMBE | I-40 | I-40/SR 1228 (LIBERTY ROAD). CONVERT GRADE SEPARATION TO AN INTERCHANGE AND CONSTRUCT TWO LANE ROADWAY NORTH OF I-40 TO SR 1224 AND FOUR LANE ROADWAY SOUTH OF I-40 TO US 19/US 23/NC 151 WITH PARTS ON NEW LOCATION. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-4759 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | BGANY, BGDA | 2019 | 15582000 | 2019 | 700000 | 2025 | 35200000 | 51482000 | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING - $1.3M FOR RIGHT-OF-WAY, PAYBACK FY 2019-2033
BUNCOMBE | I-40 | I-240 / US 74 ALTERNATE INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-6018 | NOT FUNDED | WILL BE REPRIORITIZED | NHP | NOT FUNDED | 4000000 | NOT FUNDED | 700000 | NOT FUNDED | 117200000 | 121900000
BUNCOMBE | I-40 | SR 2838 (PORTERS COVE ROAD) INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-6021 | NOT FUNDED | WILL BE REPRIORITIZED | NHP |  |  | NOT FUNDED | 200000 | NOT FUNDED | 1700000 | 1900000
BUNCOMBE | I-40 | SR 1200 (WIGGINS ROAD) TO SR 1224 (MONTE VISTA ROAD). ADD ADDITIONAL LANES. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-6054C | NOT FUNDED | WILL BE REPRIORITIZED | NHP | NOT FUNDED | 13900000 | NOT FUNDED | 4700000 | NOT FUNDED | 200199000 | 218799000
BUNCOMBE | I-40, I-26 | SR 3548 (HAYWOOD ROAD) TO US 19/23 AT SR 1781 (BROADWAY) | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-2513B | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | NHP, S(M) | 2024 | 174526000 | 2024 | 23200000 | 2024 | 686575000 | 884301000 | GARVEE BOND FUNDING: $75M FOR RIGHT-OF-WAY, PAYBACK FY 2025-2039; $75M FOR CONSTRUCTION, PAYBACK FY 2025-2039; $150M FOR CONSTRUCTION, PAYBACK FY 2027-2041. TO BE LET WITH I-2513D.
BUNCOMBE | NC 112 (SARDIS ROAD/ SANDHILL ROAD) | NC 191 (BREVARD ROAD) TO US 19/23 (SMOKEY PARK HIGHWAY). WIDEN ROADWAY. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-6047 | DIVISION 13 | SCHEDULED FOR DELIVERY | T | 2025 | 60800000 | 2025 | 6800000 | 2028 | 69000000 | 136600000
BUNCOMBE | NC 191 (BREVARD ROAD - OLD HAYWOOD ROAD) | SR 3498 (LEDBETTER ROAD) TO NORTH OF BLUE RIDGE PARKWAY. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-3403B | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 23800000 | NOT FUNDED | 3900000 | NOT FUNDED | 48873000 | 76573000
BUNCOMBE | NC 81 (SWANNANOA RIVER ROAD) | SR 3214 (BILTMORE AVENUE) TO US 74A (SOUTH TUNNEL ROAD). WIDEN EXISTING ROADWAY. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-5832 | DIVISION 13 | SCHEDULED FOR DELIVERY | T | 2028 | 24400000 | 2028 | 1700000 | 2030 | 21901000 | 48001000 | COORDINATE WITH U-6046.
BUNCOMBE | NC 81 (SWANNANOA RIVER ROAD) | US 70 (TUNNEL ROAD) TO US 74 (SOUTH TUNNEL ROAD). UPGRADE ROADWAY. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-6046 | DIVISION 13 | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 16300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 24700000 | 43100000 | COORDINATE WITH U-5832.
BUNCOMBE | RIVERWAY MULTI-MODAL NETWORK | CRAVEN STREET BRIDGE IMPROVEMENTS OVER THE FRENCH BROAD RIVER | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-5019E | DIVISION 13 | SCHEDULED FOR DELIVERY | BGANY, L |  |  |  |  | 2024 | 4200000 | 4200000
BUNCOMBE | SR 1332 (NORTH LOUISIANA AVENUE) | US 19/23 (PATTON AVENUE) TO SR 1338 (EMMA ROAD). MODERNIZE ROADWAY. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-6162 | DIVISION 13 | WILL BE REPRIORITIZED | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 13200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6000000 | 20000000
BUNCOMBE | SR 1477 (RIVERSIDE DRIVE) | SR 1517 (HILL STREET) TO SR 1781 (BROADWAY STREET) | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-2513D | DIVISION 13 | SCHEDULED FOR DELIVERY | BGANY | 2024 | 15300000 | 2024 | 3100000 | 2024 | 13100000 | 31500000 | TO BE LET WITH I-2513B.
BUNCOMBE | SR 2002 (RICEVILLE ROAD) | US 70 (TUNNEL ROAD) TO SR 2285 (CLEAR VISTA LANE). UPGRADE ROADWAY. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-5837 | DIVISION 13 | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9100000 | 25700000
BUNCOMBE | SR 2500 (BLUE RIDGE ROAD) | CONVERT I-40/SR 2500 (BLUE RIDGE ROAD) GRADE SEPARATION TO INTERCHANGE. WIDEN SR 2500 (BLUE RIDGE ROAD) TO THREE LANES FROM US 70 TO SOUTH OF I-40 AND UPGRADE ROADWAY SOUTH OF I-40 TO SR 2713. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-4409 | DIVISION 13 | SCHEDULED FOR DELIVERY | NHP, T | 2023 | 6300000 | 2023 | 900000 | 2025 | 26990000 | 34190000 | BUILD NC BOND FUNDING: $8M FOR CONSTRUCTION, PAYBACK FY 2026-2040 (FY 2026 / YR 8 SALE)
BUNCOMBE | SR 3116 (MILLS GAP ROAD) | US 25 (HENDERSONVILLE ROAD) TO SR 3157 (WESTON ROAD). UPGRADE EXISTING ROADWAY. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-5834 | DIVISION 13 | SCHEDULED FOR DELIVERY | T | 2019 | 12333000 |  |  | 2024 | 14925000 | 27258000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $6M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE).
BUNCOMBE | SR 3116 (MILLS GAP ROAD) | SR 3136 (CANE CREEK ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-6163 | DIVISION 13 | SCHEDULED FOR DELIVERY | S, T | 2024 |  | 2024 |  | 2024 | 2000000 | 2000000 | STATE FUNDS ARE HIGH IMPACT/LOW COST FUNDS
BUNCOMBE | SR 3556 (AMBOYROAD/ MEADOW ROAD) | I-240 TO NC 81/SR 3214 (BILTMORE AVENUE). WIDEN TO MULTI-LANES WITH NEW BRIDGE OVER THE FRENCH BROAD RIVER. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-4739 | DIVISION 13 | SCHEDULED FOR DELIVERY | BGANY | 2025 | 18500000 | 2025 | 7400000 | 2028 | 38900000 | 64800000
BUNCOMBE | US 25A (SWEETEN CREEK ROAD) | US 25 (HENDERSONVILLE ROAD) TO SR 3081 (ROCK HILL ROAD) | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-2801A | REGION G | SCHEDULED FOR DELIVERY | T | 2028 | 112100000 | 2028 | 6720000 | 2031 | 76500000 | 195320000
BUNCOMBE | WEAVERVILLE | US 19 BUSINESS (WEAVERVILLE HIGHWAY) AND SR 1740 (NEW STOCK ROAD). CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-5973 | NOT FUNDED | WILL BE REPRIORITIZED | T |  |  |  |  | NOT FUNDED | 200000 | 200000
BUNCOMBE, MADISON | US 25/70 | NORTH OF SR 1584 (TILLERY BRANCH ROAD) TO SR 1727 (MONTICELLO ROAD). UPGRADE ROADWAY TO SUPERSTREET. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO, LAND-OF-SKY RPO | U-6173 | NOT FUNDED | WILL BE REPRIORITIZED | BGANY | NOT FUNDED | 300000 | NOT FUNDED | 600000 | NOT FUNDED | 33249000 | 34149000
BURKE | COLLEGE STREET MULTIMODAL CONNECTOR | NORTH GREEN STREET TO US 70 IN MORGANTON. CONSTRUCT MULTI-USE PATH. | BIKE/PED | 13 | GREATER HICKORY MPO | EB-5978 | DIVISION 13 | SCHEDULED FOR DELIVERY | L, TAANY | 2022 | 80000 |  |  | 2024 | 2320000 | 2400000
BURKE | I-40 | SR 1734 (CAROLINA STREET SE)/SR 1826 - EXIT 111. REVISE INTERCHANGE. | HIGHWAY | 13 | GREATER HICKORY MPO | I-5008 | REGION G | WILL BE REPRIORITIZED | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 31600000 | 37400000 | PROJECT TO BE LET WITH I-5875.
BURKE | I-40 | US 64 (BURKEMONT ROAD). IMPROVE INTERCHANGE. | HIGHWAY | 13 | GREATER HICKORY MPO | I-5009 | REGION G | WILL BE REPRIORITIZED | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 16400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 26200000 | 48700000
BURKE | I-40 | SR 1142 (JAMESTOWN ROAD) - EXIT 100. UPGRADE INTERCHANGE. | HIGHWAY | 13 | GREATER HICKORY MPO | I-5874 | REGION G | WILL BE REPRIORITIZED | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 31300000 | 33200000
BURKE | I-40 | SR 1712 (DREXEL ROAD). UPGRADE INTERCHANGE. | HIGHWAY | 13 | GREATER HICKORY MPO | I-5875 | REGION G | WILL BE REPRIORITIZED | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 27200000 | 29300000 | PROJECT TO BE LET WITH I-5008
BURKE | I-40 | SR 1761 (OLD HIGHWAY NC 10) - EXIT 116. UPGRADE INTERCHANGE AND REMOVE TWO-WAY TRAFFIC. | HIGHWAY | 13 | GREATER HICKORY MPO | I-5971 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 21500000 | 23000000
BURKE | I-40 | SR 1744 (MINERAL SPRINGS MOUNTAIN ROAD)/SR 1744 (ELDRED STREET SE) - EXIT 112. CONSTRUCT INTERCHANGE IMPROVEMENTS. | HIGHWAY | 13 | GREATER HICKORY MPO | I-5975 | NOT FUNDED | WILL BE REPRIORITIZED | NHP | NOT FUNDED | 2660000 | NOT FUNDED | 100000 | NOT FUNDED | 5200000 | 7960000
BURKE | I-40 | EXIT 118 - SR 1761 (OLD NC 10). CONTRUCT INTERCHANGE IMPROVEMENTS. | HIGHWAY | 13 | GREATER HICKORY MPO | I-5990 | DIVISION 13 | SCHEDULED FOR DELIVERY | NHP | 2023 | 2500000 | 2023 | 1100000 | 2024 | 9600000 | 13200000
BURKE | I-40 | SR 1147 (CAUSBY ROAD). REDESIGN INTERCHANGE AND REMOVE TWO-WAY ON RAMP. | HIGHWAY | 13 | GREATER HICKORY MPO | I-6058 | NOT FUNDED | WILL BE REPRIORITIZED | NHP | NOT FUNDED | 300000 | NOT FUNDED | 1100000 | NOT FUNDED | 4300000 | 5700000
BURKE | NC 126 | SR 1250 (WATERMILL ROAD) TO SR 1254 (FISH HATCHERY ROAD). MODERNIZE ROADWAY. | HIGHWAY | 13 | GREATER HICKORY MPO | U-6164 | NOT FUNDED | WILL BE REPRIORITIZED | BGLT5 | NOT FUNDED | 3400000 | NOT FUNDED | 700000 | NOT FUNDED | 27201000 | 31301000
BURKE | NC 181 | SR 1414 (ST MARY'S CHURCH ROAD) TO MORGANTON ETJ. WIDEN EXISTING ROADWAY. | HIGHWAY | 13 | GREATER HICKORY MPO | U-5836 | REGION G | SCHEDULED FOR DELIVERY | T | 2027 | 3000000 |  |  | 2029 | 7800000 | 10800000 | 0
BURKE | NC 181 | SR 1440 TO SR 1419. WIDEN TO 3-LANES. | HIGHWAY | 13 | GREATER HICKORY MPO | U-5978 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 8500000 | NOT FUNDED | 1510000 | NOT FUNDED | 12900000 | 22910000
BURKE | US 64 (BURKEMONT AVENUE) | US 70 (W. FLEMING DRIVE) INTERSECTION. IMPROVE INTERSECTION. | HIGHWAY | 13 | GREATER HICKORY MPO | U-6123 | NOT FUNDED | WILL BE REPRIORITIZED | NHP | NOT FUNDED | 2300000 | NOT FUNDED | 500000 | NOT FUNDED | 9100000 | 11900000
CABARRUS | CONCORD REGIONAL AIRPORT (JQF) | SOUTH DEVELOPMENT AREA APRON EXPANSION - PHASE II: APRON EXPANSION (DESIGN & CONSTRUCTION) | AVIATION | 10 | CABARRUS-ROWAN MPO | AV-5731 | REGION E | SCHEDULED FOR DELIVERY | O, T |  |  |  |  | 2025 | 300000 | 300000
CABARRUS | CONCORD REGIONAL AIRPORT (JQF) | EXTEND RUNWAY SAFETY AREA. | AVIATION | 10 | CABARRUS-ROWAN MPO | AV-5889 | NOT FUNDED | WILL BE REPRIORITIZED | T |  |  |  |  | NOT FUNDED | 300000 | 300000 | PROJECT SWAPPED WITH AV-5892 PER AGREEMENT BETWEEN NCDOT AND MPO.
CABARRUS | CONCORD REGIONAL AIRPORT (JQF) | CONSTRUCT NORTH APRON EXPANSION. | AVIATION | 10 | CABARRUS-ROWAN MPO | AV-5892 | REGION E | SCHEDULED FOR DELIVERY | O, T |  |  |  |  | 2023 | 300000 | 300000 | OTHER FUNDING PROVIDED BY CONCORD REGIONAL AIRPORT. PROJECT SWAPPED WITH AV-5889 PER AGREEMENT BETWEEN NCDOT AND MPO.
CABARRUS | BRUTON SMITH BLVD/ CONCORD MILLS BLVD/ PORTION OF | US 29 TO WEDDINGTON ROAD. CONSTRUCT SIDEWALK ON BOTH SIDES OF THE ROAD, INCLUDING A PORTION OF WEDDINGTON ROAD. | BIKE/PED | 10 | CABARRUS-ROWAN MPO | EB-5732 | DIVISION 10 | SCHEDULED FOR DELIVERY | L, TAANY | 2023 | 80000 |  |  | 2024 | 4800000 | 4880000
CABARRUS | KANNAPOLIS | LITTLE TEXAS ROAD, LANE STREET TO DALE EARNHARDT BOULEVARD. CONSTRUCT SIDEWALK AND CURB AND GUTTER. | BIKE/PED | 10 | CABARRUS-ROWAN MPO | EB-5844 | DIVISION 10 | SCHEDULED FOR DELIVERY | CMAQ, L, TAANY | 2023 | 320000 |  |  | 2024 | 1280000 | 1600000
CABARRUS | GEORGE LILES PARKWAY | NC 49 TO SR 1304 (ROBERTA ROAD) | HIGHWAY | 10 | CABARRUS-ROWAN MPO | R-2246A | DIVISION 10 | SCHEDULED FOR DELIVERY | T | 2028 | 4100000 | 2028 | 2900000 | 2030 | 24100000 | 31100000
CABARRUS | NC 3 (DALE EARNHARDT BOULEVARD) | INTERSECTION OF NC 3 (DALE EARNHARDT BOULEVARD) AND US 29/601 (CANNON BOULEVARD). CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 10 | CABARRUS-ROWAN MPO | U-5761 | REGION E | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2024 | 8100000 | 8100000 | RIGHT-OF-WAY IN PROGRESS.
CABARRUS | NC 73 (DAVIDSON HIGHWAY) | EAST OF SR 1394 (POPLAR TENT ROAD) TO US 29. | HIGHWAY | 10 | CABARRUS-ROWAN MPO | R-5706B | REGION E | WILL BE REPRIORITIZED | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 70000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 175102000 | 252402000
CABARRUS | SR 1394 (POPLAR TENT ROAD) | EAST OF I-85 TO GEORGE LILES PARKWAY | HIGHWAY | 10 | CABARRUS-ROWAN MPO | U-3415A | DIVISION 10 | SCHEDULED FOR DELIVERY | T | 2024 | 12900000 | 2024 | 900000 | 2027 | 27712000 | 41512000
CABARRUS | US 29 | REALIGN UNION CEMETERY ROAD TO INTERSECT US 29 AT ROCK HILL CHURCH ROAD AND CONSTRUCT IMPROVEMENTS ALONG US 29 FROM 0.6 MILE WEST OF ROCK HILL CHURCH ROAD TO JUST EAST OF ROCK HILL CHURCH ROAD. | HIGHWAY | 10 | CABARRUS-ROWAN MPO | U-5956 | REGION E | SCHEDULED FOR DELIVERY | T | 2022 | 3400000 | 2022 | 2100000 | 2025 | 11800000 | 17300000
CABARRUS, MECKLENBURG | POPLAR TENT ROAD | DERITA ROAD TO NC 73. WIDEN TO FOUR-LANES. | HIGHWAY | 10 | CABARRUS-ROWAN MPO, CHARLOTTE REGIONAL TPO | U-6029 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 43403000 | NOT FUNDED | 1085000 | NOT FUNDED | 80200000 | 124688000
CALDWELL | SR 1001 (CONNELLY SPRINGS ROAD) | CATAWBA RIVER TO SR 1933 (SOUTH-WEST BOULEVARD) | HIGHWAY | 11 | GREATER HICKORY MPO | R-3430C | DIVISION 11 | SCHEDULED FOR DELIVERY | T | 2026 | 27500000 | 2026 | 4000000 | 2029 | 47001000 | 78501000
CALDWELL | SR 1130 (CAJAH MOUNTAIN ROAD) | SR 1001 (CONNELLY SPRINGS ROAD) TO US 321A. MODERNIZE ROADWAY. | HIGHWAY | 11 | GREATER HICKORY MPO | U-6157 | DIVISION 11 | SCHEDULED FOR DELIVERY | BGANY, T | 2023 | 15900000 | 2023 | 9100000 | 2025 | 24236000 | 49236000 | BUILD NC BOND FUNDING: $1.5M FOR CONSTRUCTION, PAYBACK FY 2026-2040 (FY 2026 / YR 8 SALE).
CALDWELL | US 321 | SR 1002 (DUDLEY SHOALS ROAD) GRADE SEPARATION. CONSTRUCT RAMP ONTO US 321 SOUTHBOUND. | HIGHWAY | 11 | GREATER HICKORY MPO | U-6161 | DIVISION 11 | SCHEDULED FOR DELIVERY | NHP | 2026 | 800000 | 2026 | 200000 | 2028 | 4000000 | 5000000 | COORDINATE WITH U-4700A
CALDWELL | US 321 ALT | SR 1109 (PINEWOOD ROAD) TO SR 1106 (DUKE STREET). UPGRADE ROADWAY. | HIGHWAY | 11 | GREATER HICKORY MPO | U-6034 | DIVISION 11 | SCHEDULED FOR DELIVERY | T | 2024 | 9000000 | 2024 | 3000000 | 2026 | 14400000 | 26400000
CAMDEN | NC 343 | US 158 IN CAMDEN TO SR 1119 (SOUTH TROTMAN ROAD) IN SHILOH. MODERNIZE ROADWAY AND REPLACE BRIDGES 140017 AND 140018 IN CAMDEN COUNTY. | HIGHWAY | 1 | ALBEMARLE RPO | R-5807 | DIVISION 1 | SCHEDULED FOR DELIVERY | T | 2024 | 508000 | 2024 | 9232000 | 2026 | 19700000 | 29440000
CAMDEN, CURRITUCK | SR 1227/SR 1208 (SOUTH MILLS ROAD) SR 1224/SR 1223 | NC 343 IN CAMDEN COUNTY TO NC 168 IN CURRITUCK COUNTY. WIDEN AND INTERSECTION IMPROVEMENTS. | HIGHWAY | 1 | ALBEMARLE RPO | R-5717 | DIVISION 1 | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2024 | 17900000 | 17900000 | RIGHT-OF-WAY IN PROGRESS.
CARTERET | NC 24 | NC 58. INTERSECTION IMPROVEMENTS. | HIGHWAY | 2 | DOWN EAST RPO | R-5858 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2025 | 6000000 | 6000000 | RIGHT OF WAY IN PROGRESS
CARTERET | NC 58 (EMERALD DRIVE) | LOON STREET. INSTALL ROUNDABOUT. | HIGHWAY | 2 | DOWN EAST RPO | R-5884 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 300000 | NOT FUNDED | 300000 | NOT FUNDED | 1400000 | 2000000
CARTERET | NC 58 (EMERALD DRIVE) | SR 1000 (COAST GUARD ROAD). INSTALL ROUNDABOUT. | HIGHWAY | 2 | DOWN EAST RPO | R-5886 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 300000 | NOT FUNDED | 1600000 | NOT FUNDED | 1700000 | 3600000
CARTERET | NC 58 (EMERALD DRIVE) | MANGROVE DRIVE. UPGRADE INTERSECTION. | HIGHWAY | 2 | DOWN EAST RPO | R-5944 | DIVISION 2 | SCHEDULED FOR DELIVERY | T | 2027 | 337000 | 2027 | 100000 | 2029 | 2650000 | 3087000
CARTERET | SR 1175 (BRIDGES STREET) | SR 1243 (BARBOUR ROAD). REALIGN INTERSECTIONS. | HIGHWAY | 2 | DOWN EAST RPO | R-5941 | DIVISION 2 | SCHEDULED FOR DELIVERY | T | 2027 | 7400000 | 2027 | 1100000 | 2029 | 2000000 | 10500000
CARTERET | SR 1176 (BRIDGES STREET EXTENSION) | SR 1738 (BRIDGES STREET) TO SR 1147 (MCCABE ROAD). WIDEN EXISTING ROADWAY AND CONSTRUCT PART ON NEW LOCATION. | HIGHWAY | 2 | DOWN EAST RPO | R-5727 | DIVISION 2 | SCHEDULED FOR DELIVERY | T | 2027 | 12700000 | 2027 | 1300000 | 2029 | 62699000 | 76699000
CARTERET | US 70 (ARENDELL STREET) | 4TH STREET TO SR 1175 (RADIO ISLAND ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 2 | DOWN EAST RPO | U-5876 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 85200000 | 103000000
CARTERET | US 70 (CEDAR STREET) | US 70 (LIVE OAK STREET). CONSTRUCT ROUNDABOUT. | HIGHWAY | 2 | DOWN EAST RPO | R-5962 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 3300000 | NOT FUNDED | 370000 | NOT FUNDED | 1700000 | 5370000
CARTERET | US 70 (LIVE OAK STREET) | NC 101 TO SR 1429 (OLGA ROAD). ACCESS MANAGEMENT. | HIGHWAY | 2 | DOWN EAST RPO | R-5945 | DIVISION 2 | SCHEDULED FOR DELIVERY | NHP | 2027 | 31800000 | 2027 | 600000 | 2029 | 23600000 | 56000000
CARTERET | US 70 (LIVE OAK STREET) | SR 1310 (LENNOXVILLE ROAD). UPGRADE INTERSECTION. | HIGHWAY | 2 | DOWN EAST RPO | R-5946 | DIVISION 2 | SCHEDULED FOR DELIVERY | NHP | 2027 | 4900000 | 2027 | 700000 | 2029 | 2200000 | 7800000
CARTERET | US 70 (LIVE OAK STREET) | NC 101. CONSTRUCT ONE LANE ROUNDABOUT. | HIGHWAY | 2 | DOWN EAST RPO | U-6058 | REGION B | SCHEDULED FOR DELIVERY | L, T | 2023 | 859000 | 2023 | 193000 | 2025 | 3534000 | 4586000 | LOCAL FUNDS CONTRIBUTION BY TOWN OF BEAUFORT.
CARTERET | US 70/NC 12 | SR 1429 (OLGA ROAD) TO SR 1350 (WHITEHURST ROAD). UPGRADE ROADWAY. | HIGHWAY | 2 | DOWN EAST RPO | R-4746 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 30900000 | NOT FUNDED | 9100000 | NOT FUNDED | 71199000 | 111199000
CARTERET | NS/NCRR EC LINE | CONSTRUCT GRADE SEPARATION AT US 70 EASTBOUND AND WESTBOUND. CLOSE EXISTING AT-GRADE CROSSING NEAR NEWPORT. | RAIL | 2 | DOWN EAST RPO | P-5742 | NOT FUNDED | WILL BE REPRIORITIZED | O, T | NOT FUNDED | 2000000 |  |  | NOT FUNDED | 12350000 | 14350000 | OTHER FUNDS PROVIDED BY NS.
CARTERET, HYDE | NC 12 | CEDAR ISLAND - OCRACOKE FERRY. REPLACE M/V SILVER LAKE SOUND CLASS FERRY | FERRY | 1, 2 | ALBEMARLE RPO, DOWN EAST RPO | F-5704 | DIVISION 1, 2 | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2025 | 25600000 | 25600000
CASWELL | NC 86 | US 158 TO VIRGINIA STATE LINE. CONSTRUCT PASSING LANES AND SHOULDER IMPROVEMENTS AT VARIOUS LOCATIONS, AND CONSTRUCT TURN LANES FROM SR 1300 (PARK SPRINGS ROAD) TO SOLID WASTE CONVENIENCE CENTER. | HIGHWAY | 7 | PIEDMONT TRIAD RPO | R-5822 | REGION D | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 183000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 14200000 | 14683000 | SCOPE INCLUDES SPOT ID H170625
CASWELL | US 158 / NC 86 | SR 1572 (COUNTY HOME ROAD) TO SR 1734 (RP FUQUAY ROAD). CONSTRUCT PASSING LANES. | HIGHWAY | 7 | PIEDMONT TRIAD RPO | R-5926 | DIVISION 7 | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 269000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 83000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3649000 | 4001000
CATAWBA | HICKORY REGIONAL AIRPORT (HKY) | 600 FEET EXTENSION OF RUNWAY 6 - PHASE I AND II. | AVIATION | 12 | GREATER HICKORY MPO | AV-5741 | DIVISION 12 | SCHEDULED FOR DELIVERY | O, T |  |  |  |  | 2024 | 3460000 | 3460000
CATAWBA | HICKORY REGIONAL AIRPORT (HKY) | LAND ACQUISITION AND OBSTRUCTION REMOVAL. | AVIATION | 12 | GREATER HICKORY MPO | AV-5752 | DIVISION 12 | SCHEDULED FOR DELIVERY | T | 2026 | 600000 |  |  |  |  | 600000
CATAWBA | HICKORY | SR 1453 (SPRINGS ROAD) TO NC 127 | HIGHWAY | 12 | GREATER HICKORY MPO | U-2307B | DIVISION 12 | SCHEDULED FOR DELIVERY | BGANY, BGDA, S(M), T | 2025 | 22600000 | 2025 | 9800000 | 2028 | 42000000 | 74400000
CATAWBA | I-40 | SR 1007 (LENOIR RHYNE BOULEVARD) INTERCHANGE. CONSTRUCT INTERCHANGE IMPROVEMENTS. | HIGHWAY | 12 | GREATER HICKORY MPO | I-5716 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | NHP |  |  |  |  | 2025 | 8500000 | 8500000 | RIGHT-OF-WAY IN PROGRESS
CATAWBA | I-40 | US 321 TO SR 1476 (FAIRGROVE CHURCH ROAD). WIDEN TO SIX LANES. | HIGHWAY | 12 | GREATER HICKORY MPO | I-5991A | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | NHP |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 69300000 | 69900000
CATAWBA | NC 127 | SR 1132 (HUFFMAN FARM ROAD) TO SR 1008 (ZION CHURCH ROAD). | HIGHWAY | 12 | GREATER HICKORY MPO | U-2530A | DIVISION 12 | SCHEDULED FOR DELIVERY | T | 2025 | 23900000 | 2025 | 3800000 | 2027 | 25501000 | 53201000
CATAWBA | NC 127 (2ND STREET NORTHEAST, NORTH CENTER STREET) | 8TH AVENUE NORTHEAST TO SR 1327 (30TH AVENUE NORTHWEST). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 12 | GREATER HICKORY MPO | U-6135 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 19700000 | NOT FUNDED | 6100000 | NOT FUNDED | 23299000 | 49099000
CATAWBA | SR 1005 (STARTOWN ROAD) | US 70 TO NC 10. WIDEN TO MULTI-LANES. | HIGHWAY | 12 | GREATER HICKORY MPO | R-5113 | DIVISION 12 | SCHEDULED FOR DELIVERY | T | 2028 | 38600000 | 2028 | 9700000 | 2031 | 42600000 | 90900000
CATAWBA | SR 1124 (33RD STREET SW) | SR 1124 (33RD STREET SW) AND (34TH STREET NW). REALIGN INTERSECTION. | HIGHWAY | 12 | GREATER HICKORY MPO | U-6042 | DIVISION 12 | SCHEDULED FOR DELIVERY | T | 2027 | 1400000 | 2027 | 200000 | 2029 | 3300000 | 4900000
CATAWBA | SR 1453 (16TH STREET NE, 12TH AVE NE, SPRINGS ROAD | 9TH AVENUE NE TO SR 1504 (CHARLOTTE STREET). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 12 | GREATER HICKORY MPO | U-6176 | DIVISION 12 | WILL BE REPRIORITIZED | BGANY, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 26200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 20500000 | 49600000
CATAWBA, CALDWELL, BURKE | US 321 | NORTH OF US 70 IN HICKORY TO US 321A | HIGHWAY | 11, 12, 13 | GREATER HICKORY MPO | U-4700A | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | L, NHP, S(M) | 2021 | 88015000 |  |  | 2025 | 156300000 | 244315000 | RIGHT-OF-WAY IN PROGRESS. GARVEE BOND FUNDING: $45M FOR RIGHT-OF-WAY, PAYBACK FY 2021-2035
CATAWBA, LINCOLN | NC 150 | RELOCATED NC 16 (STIP PROJECT R-2206) TO EAST OF SR 1840 (GREENWOOD ROAD). WIDEN TO 4-LANES WITH A BYPASS OF THE TERRELL HISTORIC DISTRICT. | HIGHWAY | 12 | GREATER HICKORY MPO, GASTON-CLEVELAND-LINCOLN MPO | R-2307A | REGION F | SCHEDULED FOR DELIVERY | BGANY, T | 2027 | 82300000 | 2027 | 17800000 | 2030 | 115901000 | 216001000
CHATHAM | SILER CITY MUNICIPAL AIRPORT (SCR) | EXTEND RUNWAY 22 AND PARALLEL TAXIWAY BY 500 FT, INCLUDING RELOCATION OF AIRPORT ROAD | AVIATION | 8 | TRIANGLE AREA RPO | AV-5816 | DIVISION 8 | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2758000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5000000 | 7758000
CHATHAM | SR 1107 (WEST 3RD STREET) | NORTH GARDEN AVENUE TO SR 1108 (NORTH CHATHAM AVENUE) IN SILER CITY. CONSTRUCT SIDEWALK. | BIKE/PED | 8 | TRIANGLE AREA RPO | EB-6006 | DIVISION 8 | SCHEDULED FOR DELIVERY | L, TA5200 | 2024 | 36000 |  |  | 2026 | 541000 | 577000
CHATHAM | SR 2106 (EAST CARDINAL STREET); SOUTH 10TH AVENUE | SR 2016 (EAST CARDINAL STREET) FROM SR 2223 (MATTHEWS STREET) TO SOUTH 10TH AVENUE, AND SOUTH 10TH AVENUE FROM EAST CARDINAL STREET TO SR 2103 (EAST RALEIGH STREET) IN SILER CITY. CONSTRUCT SIDEWALK. | BIKE/PED | 8 | TRIANGLE AREA RPO | EB-6007 | NOT FUNDED | WILL BE REPRIORITIZED | L, TA5200 | NOT FUNDED | 36000 |  |  | NOT FUNDED | 584000 | 620000
CHATHAM | NC 87 | NC 902 IN PITTSBORO TO US 64 BYPASS. WIDEN TO 12-FT LANES AND 4-FT PAVED SHOULDERS. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5961 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 2500000 | NOT FUNDED | 2200000 | NOT FUNDED | 13200000 | 17900000
CHATHAM | NEW ROUTE | US 64 BYPASS IN PITTSBORO TO US 15 / US 501. CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5930 | DIVISION 8 | SCHEDULED FOR DELIVERY | O, T | 2023 | 1692000 | 2023 | 360000 | 2024 | 23120000 | 25172000 | "O" FUNDING REFLECTS LOCAL PARTICIPATION
CHATHAM | NEW ROUTE | US 15 / US 501 / NC 87 TO US 64 BUSINESS. CONSTRUCT 2-LANE ROADWAY ON NEW LOCATION. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5963 | DIVISION 8 | SCHEDULED FOR DELIVERY | T | 2024 | 2399000 | 2024 | 360000 | 2027 | 53600000 | 56359000
CHATHAM | US 15 / US 501 | US 15 / US 501, NORTH OF US 64 BUSINESS TO POWELL PLACE LANE. MILL AND RESURFACE FROM NORTH OF US 64 BUSINESS TO LAUNIS STREET AND WIDEN FROM LAUNIS STREET TO POWELL PLACE LANE. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5724B | DIVISION 8 | SCHEDULED FOR DELIVERY | T | 2023 | 3900000 | 2023 | 1300000 | 2025 | 10200000 | 15400000
CHATHAM | US 64 (EAST 11TH STREET) | NORTH GLENN AVENUE TO EAST OF US 421 IN SILER CITY. UPGRADE ROADWAY TO INCLUDE MEDIAN FOR ACCESS CONTROL, SIDEWALKS, CROSSWALKS, BICYCLE LANES AND / OR MULTIUSE SIDEPATH. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5737 | REGION E | SCHEDULED FOR DELIVERY | T | 2023 | 5000000 | 2023 | 2800000 | 2026 | 20501000 | 28301000
CHATHAM, ORANGE | US 15 / US 501 | US 64 BYPASS TO SR 1919 (SMITH LEVEL ROAD). CONVERT REMAINING NON-SYNCHRONIZED SECTIONS OF FACILITY TO SYNCHRONIZED STREET. | HIGHWAY | 7, 8 | TRIANGLE AREA RPO, DURHAM-CHAPEL HILL-CARRBORO MPO | U-6192 | DIVISION 7, 8 | SCHEDULED FOR DELIVERY | T | 2027 | 9300000 | 2027 | 30000000 | 2030 | 78400000 | 117700000
CHATHAM, WAKE | US 64 | NC 751. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 5, 8 | TRIANGLE AREA RPO, CAPITAL AREA MPO | R-5887 | REGION C, E | SCHEDULED FOR DELIVERY | NHP | 2027 | 3300000 | 2027 | 1500000 | 2029 | 31000000 | 35800000
CHEROKEE | US 19/129 | GEORGIA STATE LINE TO US 64. WIDEN ROADWAY. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5861 | DIVISION 14 | SCHEDULED FOR DELIVERY | T | 2022 | 11400000 | 2022 | 1100000 | 2024 | 43400000 | 55900000
CHEROKEE | US 19/US 74/ US 129 | US 64 TO SR 1689 (CASINO PARKWAY). MODERNIZE ROADWAY. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5908 | DIVISION 14 | WILL BE REPRIORITIZED | BGLT5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 21400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 20401000 | 42901000
CHEROKEE, MACON | US 74 | SR 1393 (WAKEFIELD ROAD) TO SR 1310 (WAYAH ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5920 | NOT FUNDED | WILL BE REPRIORITIZED | BGLT5 | NOT FUNDED | 20000000 | NOT FUNDED | 1000000 | NOT FUNDED | 71998000 | 92998000
CLAY | US 64 | NC 175 TO SR 1349 (OLD HWY 64 EAST). WIDEN TO MULTI-LANE. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5922 | NOT FUNDED | WILL BE REPRIORITIZED | BGLT5 | NOT FUNDED | 3700000 | NOT FUNDED | 2700000 | NOT FUNDED | 39700000 | 46100000
CLAY, CHEROKEE | US 64 | US 64 BUSINESS WEST OF HAYESVILLE TO EAST OF NC 141. WIDEN TO FOUR-LANES DIVIDED. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5847 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 32000000 | NOT FUNDED | 6000000 | NOT FUNDED | 95901000 | 133901000 | WORK FOR B-5911 INCLUDED.
CLEVELAND | US 74 | US 74 BUSINESS TO NC 226. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-5713 | REGION F | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2024 | 1950000 | 1950000
CLEVELAND | US 74 (DIXON BOULEVARD) | NC 150 (DEKALB STREET) INTERSECTION. CONSTRUCT INTERCHANGE. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-2567 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 21200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 25200000 | 48100000 | TO BE LET WITH U-5929
CLEVELAND | US 74 (DIXON BOULEVARD) | INTERSECTION OF US 74 (DIXON BOULEVARD) AND NC 226 (EARL ROAD). CONSTRUCT IMPROVEMENTS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5929 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6500000 | 15700000 | TO BE LET WITH U-2567
CLEVELAND | US 74 SHELBY BYPASS | EAST OF NC 150 TO EXISTING US 74 WEST OF SR 2238 (LONG BRANCH ROAD). GRADING, STRUCTURE, PAVING. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-2707D | REGION F | SCHEDULED FOR DELIVERY | T | 2019 | 10040000 |  |  | 2024 | 85905000 | 95945000 | RIGHT-OF-WAY IN PROGRESS. R-2707D: BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); $45.3M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE)
CLEVELAND | US 74 SHELBY BYPASS | US 74 WEST OF SR 2238 TO WEST OF SR 1001 (STONEY POINT ROAD). GRADING, STRUCTURES, PAVING. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-2707E | REGION F | SCHEDULED FOR DELIVERY | T | 2019 | 14290000 |  |  | 2024 | 34300000 | 48590000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE)
CLEVELAND, GASTON | I-85 | SOUTH CAROLINA STATE LINE TO US 74 | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | I-5985A | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 150300000 | 157000000
COLUMBUS | NC 87 | NC 11 TO US 74/US 76 IN COLUMBUS COUNTY. | HIGHWAY | 6 | CAPE FEAR RPO | R-2561C | DIVISION 6 | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 26512000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4488000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 85800000 | 116800000
COLUMBUS | US 701 BYPASS | SR 1166 (PLEASANT PLAINS CHURCH ROAD) TO SR 1437 (VIRGIL AVENUE). | HIGHWAY | 6 | CAPE FEAR RPO | R-5020A | REGION C | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2026 | 39201000 | 39201000
COLUMBUS | US 701 BYPASS | SR 1305 (COMPLEX STREET). UPGRADE INTERSECTION. | HIGHWAY | 6 | CAPE FEAR RPO | R-5952 | DIVISION 6 | SCHEDULED FOR DELIVERY | T | 2025 | 2100000 | 2025 | 1300000 | 2027 | 17500000 | 20900000
COLUMBUS, ROBESON | US 74 | NC 41 NEAR LUMBERTON TO US 76 NEAR CHADBOURN. UPGRADE US 74 TO INTERSTATE STANDARDS. | HIGHWAY | 6 | CAPE FEAR RPO, LUMBER RIVER RPO | I-6011 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 179000 | NOT FUNDED | 1469000 | NOT FUNDED | 169100000 | 170748000
CRAVEN | COASTAL CAROLINA REGIONAL AIRPORT (EWN) | RUNWAY EXTENSION. | AVIATION | 2 | NEW BERN AREA MPO | AV-5891 | NOT FUNDED | WILL BE REPRIORITIZED | T |  |  |  |  | NOT FUNDED | 300000 | 300000
CRAVEN | NC 43 CONNECTOR | US 17 BUSINESS TO SOUTH OF US17/US 70. | HIGHWAY | 2 | NEW BERN AREA MPO | R-4463A | REGION B | SCHEDULED FOR DELIVERY | T | 2020 | 240000 |  |  | 2025 | 24500000 | 24740000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,335,267 FOR PE, $191,706.08 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE)
CRAVEN | NC 55 (NEUSE BOULEVARD) | US 17 BUSINESS (MLK BOULEVARD). CONSTRUCT ROUNDABOUT. | HIGHWAY | 2 | NEW BERN AREA MPO | U-5993 | REGION B | SCHEDULED FOR DELIVERY | T | 2026 | 400000 |  |  | 2028 | 3450000 | 3850000
CRAVEN | SR 1763 (MILLER BOULEVARD) | SR 1756 (LAKE ROAD) TO OUTER BANKS DRIVE. WIDEN TO MULTI-LANES. | HIGHWAY | 2 | DOWN EAST RPO | U-3431 | DIVISION 2 | SCHEDULED FOR DELIVERY | T | 2026 | 18759000 | 2026 | 4864000 | 2028 | 36400000 | 60023000
CRAVEN | US 17 | NORTH OF NC 43 TO SR 1438 (SPRUILL TOWN ROAD). | HIGHWAY | 2 | DOWN EAST RPO | R-2513A | DIVISION 2 | SCHEDULED FOR DELIVERY | T | 2026 | 3000000 | 2026 | 2400000 | 2028 | 15200000 | 20600000 | TO BE LET WITH R-3403B.
CRAVEN | US 17 | SR 1433 (ANTIOCH ROAD) TO NORTH OF NC 43. | HIGHWAY | 2 | DOWN EAST RPO, NEW BERN AREA MPO | R-3403B | REGION B | SCHEDULED FOR DELIVERY | T | 2027 | 6000000 | 2027 | 4500000 | 2029 | 71800000 | 82300000 | TO BE LET WITH R-2513A.
CRAVEN | US 17 ALTERNATE (MARTIN LUTHER KING JR. BOULEVARD) | US 70 TO SR 1278 (TRENT ROAD). UGRADE TO SUPERSTREET. | HIGHWAY | 2 | NEW BERN AREA MPO | U-6198 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 18000000 | NOT FUNDED | 3100000 | NOT FUNDED | 24700000 | 45800000
CRAVEN | US 70 | SR 1309 (GLENBURNIE ROAD). IMPROVE INTERCHANGE. | HIGHWAY | 2 | NEW BERN AREA MPO | U-6102 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 2700000 | NOT FUNDED | 500000 | NOT FUNDED | 21200000 | 24400000
CUMBERLAND | FAYETTEVILLE | CROSS CREEK PARKS CONNECTOR TRAIL, NC 24 (BRAGG BOULEVARD) TO RAY AVENUE IN FAYETTEVILLE. CONSTRUCT GREENWAY. | BIKE/PED | 6 | FAYETTEVILLE AREA MPO | EB-5907 | DIVISION 6 | SCHEDULED FOR DELIVERY | L, TAANY | 2024 | 8000 |  |  | 2026 | 674000 | 682000
CUMBERLAND | NC 210 (MURCHISON ROAD) | LANGDON STREET TO US 401 BYPASS. MODERNIZE ROADWAY. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-5015 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 14900000 | NOT FUNDED | 2200000 | NOT FUNDED | 8300000 | 25400000
CUMBERLAND | NC 24 (NORTH BRAGG BOULEVARD) | SR 1451 (MANCHESTER ROAD). CONSTRUCT INTERCHANGE. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-5930 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 22400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 67500000 | 97400000
CUMBERLAND | NC 24 / NC 87 | SR 1451 (MANCHESTER ROAD) TO NC 210 (LILLINGTON HIGHWAY). IMPROVE EXISTING MULTI-LANE FACILITY BY ADDING ACCESS MANAGEMENT AND OTHER IMPROVEMENTS. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-5802 | DIVISION 6 | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 33200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 25100000 | 63100000
CUMBERLAND | NC 59 (SOUTH MAIN STREET) | SR 1243 (SHIPMAN ROAD) TO SR 1118 (PARKTON ROAD). WIDEN TO THREE LANES. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-6001 | REGION C | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1028000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10699000 | 12427000
CUMBERLAND | SR 1003 (CAMDEN ROAD) | PROPOSED FAYETTEVILLE OUTER LOOP (U-2519) TO NC 59 (HOPE MILLS ROAD) IN FAYETTEVILLE. WIDEN TO MULTI-LANES. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-3422 | DIVISION 6 | SCHEDULED FOR DELIVERY | BGANY, T | 2021 | 9975000 | 2021 | 2825000 | 2024 | 36980000 | 49780000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $15,000,000 FOR CONSTRUCTION PAYBACK 2024 - 2038 (FY 2024 / YR 6 SALE)
CUMBERLAND | SR 1007 (ALL AMERICAN FREEWAY) | SR 1151 (OWEN DRIVE) TO NORTH OF SR 1437 (SANTA FE DRIVE). ADD ADDITIONAL LANES. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-4414 | REGION C | SCHEDULED FOR DELIVERY | NHP | 2028 | 1548000 | 2028 | 919000 | 2030 | 67100000 | 69567000
CUMBERLAND | SR 1104 (STRICKLAND BRIDGE ROAD) | US 401 TO FISHER ROAD. WIDEN ROADWAY. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-6210 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 15000000 | NOT FUNDED | 7900000 | NOT FUNDED | 22800000 | 45700000
CUMBERLAND | SR 1112 (ROCKFISH ROAD) | SR 1102 (GILLIS HILL ROAD) TO CAMDEN ROAD. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-6072A | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 13600000 | NOT FUNDED | 4960000 | NOT FUNDED | 24500000 | 43060000
CUMBERLAND | SR 1219 (IRELAND DRIVE) | SR 1141 (CUMBERLAND ROAD) TO US 401 (RAEFORD ROAD). WIDEN ROADWAY. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-6213 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 16600000 | NOT FUNDED | 19750000 | NOT FUNDED | 22500000 | 58850000
CUMBERLAND | SR 1400 (CLIFFDALE ROAD) | MCPHERSON CHURCH ROAD TO SR 1404 (MORGANTON ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-4404 | DIVISION 6 | SCHEDULED FOR DELIVERY | T | 2028 | 4392000 | 2028 | 1020000 | 2030 | 10400000 | 15812000
CUMBERLAND | SR 1400 (CLIFFDALE ROAD) | SR 1411 (BUNCE ROAD) TO MCPHERSON CHURCH ROAD. ACCESS MANAGEMENT. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-6209 | DIVISION 6 | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 32300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 17300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 36400000 | 86000000
CUMBERLAND | SR 1437 (SHAW RD) | NC 24/87 (BRAGG BLVD) TO NC 210 (MURCHISON ROAD). INTERCONNECT AND WIDEN TO MULTI-LANES. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-5101A | DIVISION 6 | SCHEDULED FOR DELIVERY | T | 2026 | 22090000 | 2026 | 9167000 | 2028 | 36600000 | 67857000 | BUILD NC BOND FUNDING: $15,000,000 FOR RIGHT OF WAY AND $5,000,000 FOR UTILITIES PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE).
CUMBERLAND | US 401 | US 401 BYPASS TO NORTH OF SLOCUMB ROAD. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-4403C | DIVISION 6 | SCHEDULED FOR DELIVERY | T | 2026 | 27001000 | 2026 | 26328000 | 2029 | 34700000 | 88029000 | BUILD NC BOND FUNDING: $17,000,000 FOR RIGHT OF WAY AND $16,000,000 FOR UTILITIES PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE).
CUMBERLAND | US 401 (RAEFORD ROAD) | EAST OF GLENSFORD DRIVE TO EAST OF ROBESON STREET. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-4405C | DIVISION 6 | SCHEDULED FOR DELIVERY | BGANY |  |  |  |  | 2024 | 41400000 | 41400000
CUMBERLAND | US 401 (ROBESON STREET) | US 401 (RAEFORD ROAD) TO WALTER STREET. ACCESS MANAGEMENT. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-6152 | NOT FUNDED | WILL BE REPRIORITIZED | NHP | NOT FUNDED | 17500000 | NOT FUNDED | 19700000 | NOT FUNDED | 19900000 | 57100000
CUMBERLAND | US 401 BUSINESS | US 401 BUSINESS (MARTIN LUTHER KING, JR. FREEWAY) TO US 401 BYPASS. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-4403B | REGION C | SCHEDULED FOR DELIVERY | NHP | 2027 | 10124000 | 2027 | 12020000 | 2029 | 33001000 | 55145000
CUMBERLAND | US 401 BUSINESS (SKIBO ROAD) | SR 1400 (CLIFFDALE ROAD). IMPROVE INTERSECTION | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-6133 | REGION C | SCHEDULED FOR DELIVERY | T | 2028 | 7900000 | 2028 | 1100000 | 2030 | 6900000 | 15900000
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | EXPANSION BUS. | PUBLIC TRANSIT | 6 | FAYETTEVILLE AREA MPO | TA-6685 | DIVISION 6 | SCHEDULED FOR DELIVERY | FEDT, L, T |  |  |  |  | 2026 | 49000 | 49000
CUMBERLAND, HOKE | SR 1102 (GILLIS HILL ROAD) | FROM SR 1418 (LINDSAY ROAD) TO NORTH OF SR 1112 (STONEY POINT ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 6, 8 | FAYETTEVILLE AREA MPO | U-5798B | DIVISION 6, 8 | SCHEDULED FOR DELIVERY | T | 2023 | 2437000 | 2023 | 715000 | 2025 | 11600000 | 14752000
CURRITUCK | NEW ROUTE | MID-CURRITUCK BRIDGE, COINJOCK TO COROLLA. NEW STRUCTURE OVER CURRITUCK SOUND AND UPGRADE APPROACHES. | HIGHWAY | 1 | ALBEMARLE RPO | R-2576 | DIVISION 1 | SCHEDULED FOR DELIVERY | BGLT5, BOND R, S(M) | 2024 |  | 2024 |  | 2024 | 210607000 | 210607000 | DESIGN BUILD PROJECT - NORTH CAROLINA TURNPIKE AUTHORITY PROJECT - GARVEE BOND FUNDING CON $130M PAYBACK FY 2024-2038.
CURRITUCK, CAMDEN | US 158 (SHORTCUT ROAD) | EAST OF NC 34 (SHAWBORO ROAD) AT BELCROSS IN CAMDEN COUNTY TO US 158/NC 168 (CARATOKE HIGHWAY) IN CURRITUCK COUNTY. WIDEN TO MULTI-LANES. | HIGHWAY | 1 | ALBEMARLE RPO | R-2574 | REGION A | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 24152000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5176000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 76200000 | 105528000
DARE | US 158 | CYPRESS KNEE LANE TO JEJAC STREET IN KITTY HAWK. CONSTRUCT SIDEWALK ON WEST SIDE. | BIKE/PED | 1 | ALBEMARLE RPO | EB-5848 | DIVISION 1 | SCHEDULED FOR DELIVERY | L, TALT5 |  |  |  |  | 2025 | 1024000 | 1024000
DARE | US 158 | US 64-NC 12 TO EASTERN END OF CURRITUCK SOUND BRIDGE. ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 1 | ALBEMARLE RPO | R-3419 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 20236000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9608000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 137000000 | 166844000
DARE | US 158 | NC 12. IMPROVE INTERSECTION. | HIGHWAY | 1 | ALBEMARLE RPO | R-4457 | NOT FUNDED | WILL BE REPRIORITIZED | NHP | NOT FUNDED | 1100000 | NOT FUNDED | 400000 | NOT FUNDED | 5800000 | 7300000
DARE, HYDE | HATTERAS - SOUTH DOCK | CONSTRUCT PASSENGER FERRY. | FERRY | 1 | ALBEMARLE RPO | F-5706 | NOT FUNDED | WILL BE REPRIORITIZED | T |  |  |  |  | NOT FUNDED | 6500000 | 6500000
DAVIDSON | NC 109 | NC 109 IN DENTON TO I-85 IN THOMASVILLE. WIDEN TO MULTILANES. | HIGHWAY | 9 | HIGH POINT URBAN AREA MPO | R-4734 | DIVISION 9 | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1336000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 132096000 | 133932000
DAVIDSON | NC 8 (WINSTON ROAD) | 9TH STREET TO SR 1408 (BIESECKER ROAD) IN LEXINGTON. WIDEN TO MULTILANES. | HIGHWAY | 9 | HIGH POINT URBAN AREA MPO | U-5757 | REGION D | SCHEDULED FOR DELIVERY | T | 2019 | 17575000 |  |  | 2024 | 8800000 | 26375000 | RIGHT-OF-WAY IN PROGRESS
DAVIDSON | SR 1508 (HICKORY TREE ROAD) | US 52 / NC 8 / FUTURE I-285 TO NC 150. WIDEN TO MULTILANES. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-5786 | DIVISION 9 | SCHEDULED FOR DELIVERY | T | 2026 | 5000000 | 2026 | 5100000 | 2028 | 22000000 | 32100000
DAVIDSON | NCRR / NORFOLK SOUTHERN MAIN LINE | SR 2165 (TURNER STREET) IN THOMASVILLE. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722327S. | RAIL | 9 | HIGH POINT URBAN AREA MPO | P-5751 | DIVISION 9 | SCHEDULED FOR DELIVERY | O, T | 2028 | 5000000 |  |  | 2031 | 21291000 | 26291000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION
DAVIDSON | NORFOLK SOUTHERN | KIMBERLY CLARK IN LEXINGTON. CONSTRUCT LEAD. | RAIL | 9 | HIGH POINT URBAN AREA MPO | P-5722 | REGION D | SCHEDULED FOR DELIVERY | O, T |  |  |  |  | 2024 | 1019000 | 1019000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION
DAVIDSON | NORFOLK SOUTHERN | CROSSING 722306Y (EAST 7TH AVENUE) IN LEXINGTON. CONSTRUCT GRADE SEPARATION IN VICINITY OF 5TH STREET AND CLOSE CROSSING 722306Y. | RAIL | 9 | HIGH POINT URBAN AREA MPO | P-5731 | DIVISION 9 | SCHEDULED FOR DELIVERY | DP, O, T | 2022 | 2400000 |  |  | 2022 | 8550000 | 10950000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION; "DP" FUNDING REFLECTS FEDERAL RAILROAD ADMINISTRATION BUILD GRANT
DAVIE | NEW ROUTE | SR 1630 (BALTIMORE ROAD) TO I-40. CONSTRUCT 2-LANE EXTENSION OF BALTIMORE ROAD AND INTERCHANGE AT I-40. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-6187 | DIVISION 9 | SCHEDULED FOR DELIVERY | BGANY, T | 2024 | 3400000 | 2024 | 300000 | 2025 | 30035000 | 33735000 | BUILD NC BONDS: $5 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE)
DAVIE | SR 1410 (FARMINGTON ROAD) | I-40 EASTBOUND RAMP AND US 158 INTERSECTION. CONSTRUCT ROUNDABOUTS. | HIGHWAY | 9 | NORTHWEST PIEDMONT RPO | R-5854 | DIVISION 9 | SCHEDULED FOR DELIVERY | T | 2023 | 100000 | 2023 | 300000 | 2025 | 1900000 | 2300000
DAVIE | US 601 | SR 1345 (BLAISE CHURCH ROAD) TO SR 1408 (CANA ROAD). WIDEN TO MULTILANES. | HIGHWAY | 9 | NORTHWEST PIEDMONT RPO | R-5736 | DIVISION 9 | SCHEDULED FOR DELIVERY | T | 2026 | 5000000 | 2026 | 800000 | 2028 | 17001000 | 22801000
DURHAM | NC 157 / SR 1322 (GUESS ROAD) | HILLCREST DRIVE TO SR 1407 (WEST CARVER STREET) IN DURHAM. CONSTRUCT SIDEWALKS ON BOTH SIDES. | BIKE/PED | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5834 | DIVISION 5 | SCHEDULED FOR DELIVERY | BGDACV, L, TAANY | 2025 | 163000 |  |  | 2026 | 1175000 | 1338000
DURHAM | NC 55 (ALSTON AVENUE) | SR 1171 (RIDDLE ROAD) TO CECIL STREET IN DURHAM. CONSTRUCT SIDEWALK ON EAST SIDE TO FILL IN MISSING GAPS. | BIKE/PED | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5835 | DIVISION 5 | SCHEDULED FOR DELIVERY | L, TAANY | 2027 | 40000 |  |  | 2028 | 957000 | 997000
DURHAM | I-40 | NC 55 (ALSTON AVENUE) TO NC 147 (DURHAM FREEWAY / TRIANGLE EXPRESSWAY) IN DURHAM. CONSTRUCT WESTBOUND AUXILIARY LANE. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-5707 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | NHP | 2024 | 900000 | 2024 | 205000 | 2026 | 8200000 | 9305000
DURHAM | I-40, NC 54 | EAST OF LITTLE CREEK TO EAST OF I-40. UPGRADE ROADWAY CORRIDOR AND CONSTRUCT INTERCHANGE IMPROVEMENTS AT I-40. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5774F | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 91472000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 638000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 81302000 | 173412000
DURHAM | I-85 / US 15 | EAST OF SR 1827 (MIDLAND TERRACE) TO SR 1632 (RED MILL ROAD) IN DURHAM. ADD LANES. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-6010 | NOT FUNDED | WILL BE REPRIORITIZED | NHP | NOT FUNDED | 10417000 | NOT FUNDED | 1774000 | NOT FUNDED | 55301000 | 67492000
DURHAM | I-885 | I-40 TO NC 147 IN DURHAM. ADD LANES AND REHABILITATE PAVEMENT. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5934 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | NHP |  |  | 2028 | 300000 | 2029 | 142301000 | 142601000
DURHAM | NC 147 (DURHAM FREEWAY) | SR 1127 (WEST CHAPEL HILL STREET) TO BRIGGS AVENUE IN DURHAM. CONSTRUCT AUXILIARY LANES AND OPERATIONAL IMPROVEMENTS. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5937 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7750000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 64301000 | 81351000
DURHAM | NC 54 | EAST OF SR1110 (BARBEE CHAPEL ROAD) TO EAST OF LITTLE CREEK. UPGRADE ROADWAY CORRIDOR. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5774C | REGION C | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 934000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 267000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10399000 | 11600000
DURHAM | NC 55 | MERIDIAN PARKWAY TO I-40 INTERCHANGE IN DURHAM. ADD THIRD SOUTHBOUND LANE AND UPGRADE RAMP TERMINALS. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-6118 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 300000 | NOT FUNDED | 200000 | NOT FUNDED | 4799000 | 5299000
DURHAM | NC 98 (HOLLOWAY STREET) | SR 1938 (JUNCTION ROAD) TO SR 1919 (LYNN ROAD) IN DURHAM. CONSTRUCT SAFETY IMPROVEMENTS AND WIDEN TO ADD MEDIAN, BICYCLE LANES, SIDEWALKS, TRANSIT STOP IMPROVEMENTS, AND TRAFFIC SIGNALS WHERE NEEDED. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-6120 | DIVISION 5 | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9999000 | 18199000
DURHAM | SR 1118 (FAYETTEVILLE ROAD) | WOODCROFT PARKWAY TO BARBEE ROAD IN DURHAM. WIDEN TO 4-LANE DIVIDED FACILITY WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-6021 | DIVISION 5 | SCHEDULED FOR DELIVERY | T | 2028 | 9100000 | 2028 | 1700000 | 2031 | 15200000 | 26000000
DURHAM | US 15 / US 501 | SR 1116 (GARRETT ROAD) IN DURHAM. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5717 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | NHP |  |  |  |  | 2026 | 32001000 | 32001000 | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH U-6067
DURHAM | US 15 / US 501 | I-40, SR (MOUNT MORIAH ROAD), AND SOUTHWEST DURHAM PARKWAY IN DURHAM. IMPROVE INTERCHANGE / INTERSECTION AREA. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-6067 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 42800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 62898000 | 109398000 | COORDINATE WITH U-5717
DURHAM | US 501 (ROXBORO ROAD) | SR 1448 (LATTA ROAD) / SR 1639 (INFINITY ROAD) INTERSECTION IN DURHAM. INTERSECTION IMPROVEMENTS. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5516 | REGION C | SCHEDULED FOR DELIVERY | L, NHP | 2026 | 9292000 | 2026 | 2076000 | 2028 | 12401000 | 23769000 | RIGHT-OF-WAY PARTICIPATION $2 MILLION BY CITY OF DURHAM
DURHAM | US 70 (MIAMI BOULEVARD) | LYNN ROAD TO SR 1959 (SOUTH MIAMI BOULEVARD) / SR 1811 (SHERRON ROAD). | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5720A | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 46400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1306000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 36502000 | 84208000
DURHAM | US 70 (MIAMI BOULEVARD) | SR 1959 (SOUTH MIAMI BOULEVARD) / SR 1811 (SHERRON ROAD) TO EAST OF SR 2095 (PAGE ROAD EXTENSION). | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5720B | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | T | 2027 | 140500000 | 2027 | 1218000 | 2030 | 81701000 | 223419000 | INCLUDES INTERCHANGE AT SR 1811
DURHAM | WOODCROFT PARKWAY EXTENSION | SR 1116 (GARRETT ROAD) TO NC 751 (HOPE VALLEY ROAD) IN DURHAM. CONSTRUCT ROADWAY ON NEW ALIGNMENT. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5823 | DIVISION 5 | SCHEDULED FOR DELIVERY | BGANY, L | 2024 | 465000 | 2024 | 320000 | 2025 | 3000000 | 3785000 | NON-STATE SYSTEM FACILITY - LOCAL MATCH BY CITY OF DURHAM
DURHAM | NORFOLK SOUTHERN H LINE | EAST DURHAM RAILROAD SAFETY PROJECT. PROJECT WILL STRAIGHTEN EXISTING RAILROAD CURVATURE BETWEEN CP NELSON AND CP EAST DURHAM AND INCLUDES A COMBINATION OF GRADE SEPARATIONS AND CLOSURES AT ELLIS ROAD SOUTH END (734737A), GLOVER ROAD (734735L), AND WRENN | RAIL | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | P-5706 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | T | 2023 | 11243000 | 2023 | 2604000 | 2027 | 33801000 | 47648000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION
DURHAM | NORFOLK SOUTHERN H LINE | CROSSING 734742W AT SR 1121 (CORNWALLIS ROAD) IN DURHAM. CONSTRUCT GRADE SEPARATION. | RAIL | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | P-5717 | REGION C | SCHEDULED FOR DELIVERY | T | 2022 | 5900000 | 2022 | 1878000 | 2024 | 25699000 | 33477000 | RIGHT-OF-WAY IN PROGRESS.
DURHAM, WAKE | I-40 SR 1728 (WADE AVENUE) | NC 54 (EXIT 273) TO SR 1728 (WADE AVENUE), I-40 TO SR 1664 (BLUE RIDGE ROAD) CONVERT FACILITY TO A MANAGED FREEWAY WITH RAMP METERING AND OTHER ATM / ITS COMPONENTS. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO, CAPITAL AREA MPO | I-6006 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 84699000 | 85699000
EDGECOMBE | TARBORO EDGECOMBE AIRPORT (ETC) | RUNWAY EXTENSION. | AVIATION | 4 | UPPER COASTAL PLAIN RPO | AV-5897 | DIVISION 4 | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2028 | 3790000 | 3790000
EDGECOMBE | EAST RALEIGH BOULEVARD | US 64 TO ARLINGTON STREET IN ROCKY MOUNT. PEDESTRIAN IMPROVEMENTS. | BIKE/PED | 4 | ROCKY MOUNT URBAN AREA MPO | EB-5984 | DIVISION 4 | SCHEDULED FOR DELIVERY | L, TA5200 |  |  |  |  | 2028 | 2160000 | 2160000
EDGECOMBE | NC 97 (ATLANTIC AVENUE) | US 64 TO EAST RALEIGH BOULEVARD IN ROCKY MOUNT. PEDESTRIAN IMPROVEMENTS. | BIKE/PED | 4 | ROCKY MOUNT URBAN AREA MPO | EB-5729 | DIVISION 4 | WILL BE REPRIORITIZED | L, TA5200 |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5920000 | 5920000
EDGECOMBE | US 258 | SR 1601 (COLONIAL ROAD) TO US 64. WIDEN ROADWAY. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | R-5949 | DIVISION 4 | SCHEDULED FOR DELIVERY | T | 2027 | 1900000 | 2027 | 900000 | 2029 | 25400000 | 28200000
EDGECOMBE, NASH | ROCKY MOUNT | US 301 BUSINESS, RIVER DRIVE TO MONK STREET IN ROCKY MOUNT. CONVERT ABANDONED RAILROAD TO MULTI-USE PATH. | BIKE/PED | 4 | ROCKY MOUNT URBAN AREA MPO | EB-5763 | DIVISION 4 | SCHEDULED FOR DELIVERY | L, TA5200 | 2024 | 240000 |  |  | 2025 | 1200000 | 1440000
FORSYTH | SALEM CREEK GREENWAY | FORSYTH TECHNICAL COMMUNITY COLLEGE TO EXISTING GREENWAY AT MARKETPLACE MALL IN WINSTON-SALEM. CONSTRUCT GREENWAY. | BIKE/PED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-5812 | DIVISION 9 | SCHEDULED FOR DELIVERY | L, TAANY |  |  |  |  | 2026 | 1200000 | 1200000
FORSYTH | SR 1122 (JONESTOWN ROAD) | EAST OF US 421 TO SR 1001 (COUNTRY CLUB ROAD) IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON EAST SIDE AND WEST SIDE OF JONESTOWN RD. | BIKE/PED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-5920 | DIVISION 9 | SCHEDULED FOR DELIVERY | L, TAANY | 2024 | 64000 | 2024 | 68000 | 2025 | 468000 | 600000
FORSYTH | I-40 | I-74 / US 311 TO SR 2643 (UNION CROSS ROAD). | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | I-5981A | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 61293000 | 67693000
FORSYTH | I-40 | SR 2643 (UNION CROSS ROAD) TO NC 66. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | I-5981B | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 38194000 | 40394000
FORSYTH | I-40 / US 311 | NC 109 (THOMASVILLE ROAD) / CLEMMONSVILLE ROAD SPLIT-DIAMOND INTERCHANGE IN WINSTON-SALEM. CONVERT HALF DIAMOND INTERCHANGE AT NC 109 TO FULL DIAMOND, AND REMOVE CONNECTOR ROADS AND HALF DIAMOND INTERCHANGE AT CLEMMONSVILLE ROAD | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | I-5880 | REGION D | SCHEDULED FOR DELIVERY | NHP, T | 2023 | 2600000 | 2023 | 800000 | 2025 | 24000000 | 27400000
FORSYTH | KERNERSVILLE SOUTHERN LOOP (PHASE I) | US 421 / BUSINESS 40 TO NC 66 (WEST MOUNTAIN STREET) IN KERNERSVILLE. WIDEN BIG MILL FARM ROAD AND SR 2649 (HOPKINS ROAD) AND CONSTRUCT INTERCHANGE AT US 421 / NC 150 / BUSINESS 40. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-5760 | DIVISION 9 | SCHEDULED FOR DELIVERY | T | 2022 | 11500000 | 2022 | 4000000 | 2025 | 44462000 | 59962000 | IN PROGRESS. BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE)
FORSYTH | NC 65 (BETHANIA-RURAL HALL ROAD) | US 52 TO SR 3983 (NORTHRIDGE DRIVE) IN RURAL HALL. WIDEN TO MULTILANES. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-6005 | DIVISION 9 | SCHEDULED FOR DELIVERY | T | 2023 | 3800000 | 2023 | 900000 | 2025 | 5300000 | 10000000 | RIGHT OF WAY IN PROGRESS
FORSYTH | NC 65 (BETHANIA-RURAL HALL ROAD) | SR 1647 (GLADE STREET) TO NC 66 IN RURAL HALL. WIDEN TO 3 LANES. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-6190 | DIVISION 9 | SCHEDULED FOR DELIVERY | T | 2027 | 1700000 | 2027 | 400000 | 2029 | 3100000 | 5200000
FORSYTH | NC 66 (OLD HOLLOW ROAD) | HARLEY DRIVE TO US 158 IN WALKERTOWN. WIDEN TO MULTILANES. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-5824 | DIVISION 9 | SCHEDULED FOR DELIVERY | T | 2021 | 18798000 |  |  | 2024 | 16406000 | 35204000 | RIGHT OF WAY IN PROGRESS
FORSYTH | NEW ROUTE | PROPOSED GREAT WAGON ROAD FROM SHALLOWFORD ROAD (SR 1001) TO LEWISVILLE-VIENNA ROAD (SR 1308) IN LEWISVILLE. MULTILANE FACILITY ON NEW LOCATION WITH BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-5536 | DIVISION 9 | SCHEDULED FOR DELIVERY | T | 2022 | 14500000 | 2022 | 656000 | 2024 | 12900000 | 28056000 | IN PROGRESS
FORSYTH | NEW ROUTE | FORUM PARKWAY CONNECTOR, SR 3955 (FORUM PARKWAY) TO NC 66 (UNIVERSITY PARKWAY) IN RURAL HALL. CONSTRUCT 2-LANE ROADWAY ON NEW LOCATION. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-5899 | DIVISION 9 | SCHEDULED FOR DELIVERY | T | 2022 | 4300000 | 2022 | 1300000 | 2024 | 9001000 | 14601000 | RIGHT OF WAY IN PROGRESS
FORSYTH | NEW ROUTE | SR 1969 (PINEY GROVE ROAD) TO NC 150 (NORTH MAIN STREET) IN KERNERSVILLE. CONSTRUCT TWO-LANE DIVIDED FACILITY WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-6003 | DIVISION 9 | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2024 | 12100000 | 12100000 | RIGHT-OF-WAY IN PROGRESS
FORSYTH | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, US 158 TO SOUTH OF I-40 | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247A | NOT FUNDED | WILL BE REPRIORITIZED | NHP, T | NOT FUNDED | 13200000 | NOT FUNDED | 18900000 | NOT FUNDED | 39101000 | 71201000 | DESIGN-BUILD PROJECT
FORSYTH | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, SOUTH OF I-40 TO SOUTH OF US 421 INTERCHANGE | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247B | NOT FUNDED | WILL BE REPRIORITIZED | NHP, T | NOT FUNDED | 31900000 | NOT FUNDED | 3000000 | NOT FUNDED | 149499000 | 184399000 | DESIGN-BUILD PROJECT
FORSYTH | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, INTERCHANGE WITH US 421 AND INTERCHANGE WITH SR 1140 (PEACE HAVEN ROAD) | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247CA | REGION D | WILL BE REPRIORITIZED | NHP, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 270000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 140900000 | 141770000 | DESIGN-BUILD PROJECT
FORSYTH | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, NORTH OF US 421 INTERCHANGE TO SR 1348 (ROBINHOOD ROAD) | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247CB | REGION D | WILL BE REPRIORITIZED | NHP, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 82499000 | 97299000 | DESIGN-BUILD PROJECT
FORSYTH | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, NORTH OF SR 1348 (MEADOWLARK DRIVE-ROBINHOOD ROAD) TO NC 67 | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247D | REGION D | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 65001000 | 68501000
FORSYTH | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, NC 67 TO SOUTH OF US 52 | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247EA | REGION D | SCHEDULED FOR DELIVERY | NHP, T | 2028 | 14700000 | 2028 | 1100000 | 2030 | 160199000 | 175999000 | IN PROGRESS
FORSYTH | SR 1103 (LEWISVILLE- CLEMMONS ROAD) | US 158 TO SR 1891 (PEACE HAVEN ROAD) IN CLEMMONS. ACCESS MANAGEMENT AND OPERATIONAL IMPROVEMENTS. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-6004 | DIVISION 9 | SCHEDULED FOR DELIVERY | BGANY, T | 2024 | 15400000 | 2024 | 2600000 | 2026 | 23735000 | 41735000 | BUILD NC BONDS: $5 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE)
FORSYTH | SR 1156 (LEWISVILLE- CLEMMONS ROAD) | SR 1103 (STYERS FERRY ROAD) TO SR 1101 (SHALLOWFORD ROAD) IN LEWISVILLE. WIDEN TO 3 LANES WITH BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-6189 | DIVISION 9 | SCHEDULED FOR DELIVERY | T | 2027 | 10700000 | 2027 | 800000 | 2029 | 12400000 | 23900000
FORSYTH | SR 1969 (PINEY GROVE ROAD) | NORTH OF NELSON STREET TO SR 2031 (BROWN ROAD) IN KERNERSVILLE. WIDEN TO 3 LANES WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-6188 | DIVISION 9 | SCHEDULED FOR DELIVERY | T | 2027 | 1100000 | 2027 | 400000 | 2029 | 4100000 | 5600000
FORSYTH | US 158 | MULTI-LANES NORTH OF US 421 / I-40 BUSINESS TO SR 1965 (BELEWS CREEK ROAD) | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | R-2577A | REGION D | SCHEDULED FOR DELIVERY | T | 2021 | 36300000 | 2021 | 469000 | 2024 | 61904000 | 98673000 | RIGHT OF WAY IN PROGRESS; BUILD NC BONDS: $15 MILLION FOR CONSTRUCTION - PAYBACK 2024-2038 (FY 2024 / YR 6 SALE)
FORSYTH, GUILFORD | US 158 | SR 1965 (BELEWS CREEK ROAD) IN FORSYTH COUNTY TO SR 2034 (ANTHONY ROAD) IN GUILFORD COUNTY | HIGHWAY | 7, 9 | WINSTON-SALEM URBAN AREA MPO, GREENSBORO URBAN AREA MPO | R-2577B | REGION D | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 38800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 60300000 | 108800000
FORSYTH, GUILFORD | US 421 (SALEM PARKWAY) | FUTURE I-74 IN KERNERSVILLE TO I-40 IN GUILFORD COUNTY. WIDEN TO 6 LANES. | HIGHWAY | 7, 9 | WINSTON-SALEM URBAN AREA MPO, GREENSBORO URBAN AREA MPO | U-6068 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 57300000 | NOT FUNDED | 2114000 | NOT FUNDED | 71300000 | 130714000 | COORDINATE WITH U-6059B
FRANKLIN | TRIANGLE NORTH EXECUTIVE AIRPORT (LHZ) | CONSTRUCT RUNWAY EXTENSION, TO INCLUDE RELOCATION OF UTILITIES, NAVAID AND ROADWAYS. | AVIATION | 5 | CAPITAL AREA MPO | AV-5819 | DIVISION 5 | SCHEDULED FOR DELIVERY | T | 2026 | 3300000 |  |  | 2028 | 22000000 | 25300000
FRANKLIN | NC 56 | SR 1114 (PEACH ORCHARD ROAD) TO US 401 IN LOUISBURG. WIDEN TO 4 LANES. | HIGHWAY | 5 | KERR-TAR RPO | R-5893 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 5900000 | NOT FUNDED | 9000000 | NOT FUNDED | 21899000 | 36799000
FRANKLIN | US 401 | SR 1103 (FLAT ROCK CHURCH ROAD / CLIFTON POND ROAD) TO SR 1700 (FOX PARK ROAD) SOUTH OF LOUISBURG | HIGHWAY | 5 | CAPITAL AREA MPO, KERR-TAR RPO | R-2814D | DIVISION 5 | SCHEDULED FOR DELIVERY | BGLT5 | 2028 | 3049000 | 2028 | 3200000 | 2031 | 48700000 | 54949000
FRANKLIN | US 401 / NC 39 | NC 56 / NC 581 (NASH STREET) TO SR 1229 (MAIN STREET). WIDEN TO MULTILANES. | HIGHWAY | 5 | KERR-TAR RPO | R-3608 | REGION C | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 15299000 | 21099000 | COORDINATE WITH U-6024
FRANKLIN | US 401 / NC 39 (BICKETT BOULEVARD) | BURKE BOULEVARD TO NC 56 / NC 581 (NASH STREET) IN LOUISBURG. CONVERT 5-LANE SECTION TO 4-LANE DIVIDED FACILITY WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | 5 | KERR-TAR RPO | U-6024 | DIVISION 5 | SCHEDULED FOR DELIVERY | T | 2028 | 3200000 | 2028 | 1800000 | 2031 | 15998000 | 20998000 | COORDINATE WITH R-3608
GASTON | CRAMERTON | SR 2014 (LAKEWOOD ROAD), SR 2565 (EAGLE ROAD) TO LAKE DRIVE. CONSTRUCT SIDEWALK AND PEDESTRIAN BRIDGE OVER SOUTH FORK RIVER INLET. | BIKE/PED | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5913 | DIVISION 12 | SCHEDULED FOR DELIVERY | L, TAANY |  |  |  |  | 2025 | 283000 | 283000
GASTON | NC 279 (NEW HOPE ROAD) | US 29/74 (FRANKLIN BOULEVARD) TO HUNT AVENUE. CONSTRUCT SIDEWALK ON EAST SIDE OF NC 279 (NEW HOPE ROAD) FROM US 29/74 (FRANKLIN BOULEVARD) TO COURT DRIVE AND WEST SIDE OF NC 279 FROM COURT DRIVE TO HUNT AVENUE. | BIKE/PED | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5975 | DIVISION 12 | SCHEDULED FOR DELIVERY | L, TA5200 |  |  |  |  | 2024 | 1652000 | 1652000
GASTON | NC 279 (SOUTH NEW HOPE ROAD) | SR 2200 (ARMSTRONG PARK ROAD) TO SR 1255 (HUDSON BOULEVARD). CONSTRUCT MISSING SIDEWALK ON SOUTH SIDE OF NC 279. | BIKE/PED | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5743 | DIVISION 12 | SCHEDULED FOR DELIVERY | L, TA5200 |  |  |  |  | 2024 | 1028000 | 1028000
GASTON | SOUTH MARIETTA STREET/ HILLTOP DRIVE | HUDSON BOULEVARD TO CLYDE STREET. CONSTRUCT SIDEWALK ON ONE SIDE OF ROAD. | BIKE/PED | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5768 | DIVISION 12 | SCHEDULED FOR DELIVERY | L, TA5200 | 2023 | 48000 |  |  | 2024 | 1008000 | 1056000
GASTON | SR 1255 (HUDSON BLVD) SR 2466 (REDBUD DR) | SR 1255 (HUDSON BOULEVARD) FROM SR 2200 (GASTON DAY SCHOOL ROAD) TO SR 2466 (REDBUD DRIVE). SR 2466 (REDBUD DRIVE) FROM SR 1255 (HUDSON BOULEVARD) TO NC 279 (SOUTH NEW HOPE ROAD). CONSTRUCT SIDEWALK ON ONE SIDE. | BIKE/PED | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5745 | DIVISION 12 | SCHEDULED FOR DELIVERY | L, TA5200 | 2023 | 108000 |  |  | 2024 | 984000 | 1092000
GASTON | SR 2044 (TUCKASEEGEE ROAD) MOUNT HOLLY | NC 273 TO MARINA VILLAGE DRIVE. CONSTRUCT SIDEWALK ON SOUTH SIDE. MARINA VILLAGE DRIVE NORTH TO BROOME STREET. CONSTRUCT SIDEWALK ON WEST SIDE. | BIKE/PED | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5912 | DIVISION 12 | SCHEDULED FOR DELIVERY | L, TAANY | 2025 | 582000 |  |  | 2027 | 1396000 | 1978000
GASTON | SR 2200 (COX ROAD) | I-85 TO COURT DRIVE. CONSTRUCT SIDEWALK ON BOTH SIDES OF SR 2200 (COX ROAD). | BIKE/PED | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5976 | DIVISION 12 | SCHEDULED FOR DELIVERY | L, TA5200 |  |  |  |  | 2024 | 1120000 | 1120000
GASTON | I-85 | US 321 TO NC 273. WIDEN TO EIGHT LANES. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | I-5719 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | NHP, S(M) | 2024 | 132025000 | 2024 | 71100000 | 2024 | 507375000 | 710500000 | DESIGN-BUILD PROJECT - TO BE LET WITH U-5800. INCLUDES IMPROVEMENTS PREVIOUSLY FUNDED UNDER I-5713 (COX ROAD INTERCHANGE IMPROVEMENTS) AND U-3608 (NC 7 OPERATIONAL IMPROVEMENTS). GARVEE BOND FUNDING: $75M FOR ROW, $225M FOR CONSTRUCTION (2 SALES).
GASTON | I-85 | US 74 TO US 321 | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | I-5985B | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 219401000 | 233101000
GASTON | NC 27 (WEST CHARLOTTE AVENUE) | INTERSECTION OF NC 27 (WEST CHARLOTTE AVENUE) AND SR 2534 (HAWTHORNE STREET). CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5819 | DIVISION 12 | SCHEDULED FOR DELIVERY | T | 2028 | 700000 | 2028 | 600000 | 2030 | 2800000 | 4100000
GASTON | NC 273 | SR 2525 (SOUTH POINT ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6150 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 300000 | NOT FUNDED | 1500000 | NOT FUNDED | 1700000 | 3500000
GASTON | NC 274 (UNION ROAD) | OSCEOLA STREET TO NIBLICK DRIVE. UPGRADE ROADWAY. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5961 | REGION F | SCHEDULED FOR DELIVERY | O, T | 2024 | 13400000 | 2024 | 3700000 | 2027 | 4999000 | 22099000 | $5M IN OTHER FUNDING PROVIDED BY CITY OF GASTONIA
GASTON | NC 275 | INTERSECTION OF NC 275 AND NC 274, INTERSECTION OF NC 275 AND SR 1327 (FAIRVIEW ROAD), AND INTERSECTION OF SR 1456 (WHITE JENKINS ROAD) AND SR 1327 (FAIRVIEW ROAD). IMPROVE INTERSECTIONS AND CLOSE INTERSECTION OF NC 275 AND SR 1456 (WHITE JENKINS ROAD) | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6078 | DIVISION 12 | SCHEDULED FOR DELIVERY | T | 2025 | 2000000 | 2025 | 2500000 | 2027 | 3900000 | 8400000
GASTON | NC 279 | NORTH OF SR 2275 (ROBINSON-CLEMMER ROAD) TO WEST OF NC 275 IN DALLAS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-2523B | REGION F | SCHEDULED FOR DELIVERY | T | 2026 | 12500000 | 2026 | 2300000 | 2028 | 20199000 | 34999000 | INCLUDES IMPROVEMENTS AT NC 279 (LOWER DALLAS HIGHWAY) AND NC 275 (DALLAS STANLEY HIGHWAY) INTERSECTION (FORMERLY U-5778).
GASTON | NC 279 (NEW HOPE ROAD) | SR 2478 (TITMAN ROAD) TO SR 2435 (UNION-NEW HOPE ROAD). WIDEN TO 4-LANES. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5821 | DIVISION 12 | SCHEDULED FOR DELIVERY | T | 2023 | 56675000 | 2023 | 6000000 | 2026 | 44900000 | 107575000 | BUILD NC BOND FUNDING - $25M FOR RIGHT-OF-WAY, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE)
GASTON | NC 279 (NORTH NEW HOPE ROAD) | US 29/74 (FRANKLIN BOULEVARD) INTERSECTION. ADD RIGHT TURN LANE FROM NC 279 (NORTH NEW HOPE ROAD) TO US 29/74 (FRANKLIN BOULEVARD). | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6138 | REGION F | SCHEDULED FOR DELIVERY | T | 2025 | 5600000 | 2025 | 300000 | 2026 | 800000 | 6700000
GASTON | NC 7 | INTERSECTION OF NC 7/US 74 AND NC 7/US 29. CONSTRUCT NORTHBOUND THROUGH LANE AND INTERSECTION IMPROVEMENTS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5800 | REGION F | SCHEDULED FOR DELIVERY | T | 2024 | 2400000 | 2024 | 3600000 | 2024 | 4400000 | 10400000 | DESIGN-BUILD PROJECT. TO BE LET WITH I-5719.
GASTON | SR 2200 (COX ROAD) | I-85 TO US 29/74. SELECTIVE WIDENING AND OPERATIONAL IMPROVEMENTS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6044 | DIVISION 12 | SCHEDULED FOR DELIVERY | T | 2025 | 21100000 | 2025 | 1200000 | 2028 | 5400000 | 27700000
GASTON | US 29 (FRANKLIN BOULEVARD) | US 29 (FRANKLIN BOULEVARD) AND NC 274. CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5965 | REGION F | SCHEDULED FOR DELIVERY | T | 2023 | 6900000 | 2023 | 300000 | 2025 | 3600000 | 10800000
GASTON | US 29/74 (FRANKLIN BOULEVARD) | SR 2329 (REDBUD DRIVE) INTERSECTION. IMPROVE INTERSECTION AREA INCLUDING NEW GRADE-SEPARATED CROSSING OF US 29/74. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6141 | NOT FUNDED | WILL BE REPRIORITIZED | NHP | NOT FUNDED | 12200000 | NOT FUNDED | 900000 | NOT FUNDED | 8800000 | 21900000
GASTON | US 29/74 (WILKINSON BOULEVARD) | MARKET STREET TO SR 2015 (ALBERTA AVENUE. WIDEN TO SIX LANES (INCLUDES REPLACEMENT OF BRDIGE 350082 OVER SOUTH FORK OF CATAWBA RIVER). | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6146 | REGION F | SCHEDULED FOR DELIVERY | HFB, T | 2022 | 8380000 | 2022 | 5500000 | 2024 | 28302000 | 42182000 | BFP IS FOR BRIDGE REPLACEMENT OVER SOUTH FORK OF CATAWBA RIVER. BUILD NC BOND FUNDING: $2M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE);
GASTON | US 29/US 74 (FRANKLIN BOULEVARD) | SR 2200 (COX ROAD) TO 400 FEET EAST OF LINEBERGER ROAD. ADD LANE IN THE EASTBOUND DIRECTION. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6043 | DIVISION 12 | SCHEDULED FOR DELIVERY | T | 2023 | 600000 | 2023 | 900000 | 2025 | 2699000 | 4199000
GASTON | US 321 (SOUTH YORK ROAD) | 19TH AVENUE TO CLYDE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5970 | REGION F | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1900000 | 4500000
GASTON | US 74 (WILKINSON BOULEVARD) | US 74 (WILKINSON BOULEVARD) AT NC 273 (PARK STREET). CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5959 | REGION F | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6000000 | 16700000
GATES, CHOWAN | NC 32 | NC 37 (GLIDEN ROAD) TO VIRGINIA STATE LINE. MODERNIZE ROADWAY. | HIGHWAY | 1 | ALBEMARLE RPO | R-5938 | DIVISION 1 | SCHEDULED FOR DELIVERY | T | 2028 | 29185000 | 2028 | 26976000 | 2030 | 75900000 | 132061000
GRAHAM | NC 143 | WEST BUFFALO CREEK TO NC 143 BUSINESS. UPGRADE CORRIDOR. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-2822B | REGION G | SCHEDULED FOR DELIVERY | T | 2023 | 1100000 | 2023 | 700000 | 2025 | 29201000 | 31001000
GRAHAM | NC 28 | SWAIN/GRAHAM COUNTY LINE AT LITTLE TENNESSEE RIVER TO WOODS ROAD AT FONTANA DAM VILLAGE. UPGRADE ROADWAY. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5839BA | DIVISION 14 | SCHEDULED FOR DELIVERY | T | 2027 | 100000 | 2027 | 200000 | 2029 | 13001000 | 13301000
GRANVILLE | NC 56 (EAST C STREET) | SR 1215 (WEST LYON STATION ROAD) IN BUTNER. REALIGN INTERSECTION. | HIGHWAY | 5 | KERR-TAR RPO | U-6020 | DIVISION 5 | SCHEDULED FOR DELIVERY | L, T |  |  |  |  | 2025 | 3650000 | 3650000 | RIGHT-OF-WAY IN PROGRESS; "L" FUNDING REFLECTS PARTICIPATION BY TOWN OF BUTNER
GREENE | NC 58 (KINGOLD BOULEVARD) | SR 1105 (GREENRIDGE ROAD) TO CAROLINA DRIVE. UPGRADE ROADWAY. | HIGHWAY | 2 | EASTERN CAROLINA RPO | R-5898 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 200000 | NOT FUNDED | 200000 | NOT FUNDED | 7500000 | 7900000
GREENE | US 13 | SR 1104 (HULL ROAD). UPGRADE INTERSECTION. | HIGHWAY | 2 | EASTERN CAROLINA RPO | R-5943 | DIVISION 2 | SCHEDULED FOR DELIVERY | T | 2026 | 2000000 | 2026 | 300000 | 2028 | 1200000 | 3500000
GREENE | US 13/US 258 | NC 91 TO US 258 SPLIT. UPGRADE TO FREEWAY. | HIGHWAY | 2 | EASTERN CAROLINA RPO | R-5942 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 11800000 | NOT FUNDED | 2300000 | NOT FUNDED | 62202000 | 76302000
GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | SURFACE MOVEMENT GUIDANCE AND CONTROL SYSTEM (SMGCS) UPDATE. | AVIATION | 7 | GREENSBORO URBAN AREA MPO | AV-5711 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | O, T |  |  |  |  | 2025 | 1500000 | 1500000 | WORK PERFORMED BY PIEDMONT TRIAD AIRPORT AUTHORITY
GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | RUNWAY 5R-23L GROUP VI UPGRADE. | AVIATION | 7 | GREENSBORO URBAN AREA MPO | AV-5715 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | O, T |  |  |  |  | 2024 | 1500000 | 1500000
GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | TAXIWAY F. CONSTRUCT TAXIWAY INCLUDING BRIDGE OVER TED JOHNSON PARKWAY. | AVIATION | 7 | GREENSBORO URBAN AREA MPO | AV-5803 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | O, T |  |  |  |  | 2024 | 1500000 | 1500000
GUILFORD | BENJAMIN PARKWAY; WESTOVER TERRACE | BENJAMIN PARKWAY FROM ELAM AVENUE TO BATTLEGROUND AVENUE, AND WESTOVER TERRACE FROM BENJAMIN PARKWAY TO SEMINOLE DRIVE IN GREENSBORO. CONSTRUCT SIDEWALK ON BENJAMIN PARKWAY FROM ELAM AVENUE TO AYCOCK STREET, CONSTRUCT SIDEPATH ON BENJAMIN PARKWAY FROM AYC | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-5986 | DIVISION 7 | SCHEDULED FOR DELIVERY | L, TAANY | 2022 | 56000 |  |  | 2024 | 960000 | 1016000
GUILFORD | CEDROW DRIVE | WEST OF I-74 TO EAST OF I-74 IN HIGH POINT. CONSTRUCT MULTIUSE FACILITY ACROSS I-74. | BIKE/PED | 7 | HIGH POINT URBAN AREA MPO | EB-5989 | DIVISION 7 | SCHEDULED FOR DELIVERY | L, TA5200 | 2025 | 40000 |  |  | 2026 | 960000 | 1000000
GUILFORD | GREEN VALLEY ROAD | FRIENDLY AVENUE TO WESTOVER TERRACE IN GREENSBORO. CONSTRUCT SIDEWALKS. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-5997 | DIVISION 7 | SCHEDULED FOR DELIVERY | L, TAANY | 2023 | 36000 |  |  | 2025 | 286000 | 322000
GUILFORD | HIGH POINT RAILROAD ESPLANADE | LIINDSAY STREET TO CENTENNIAL STREET IN HIGH POINT. CONSTRUCT GREENWAY. | BIKE/PED | 7 | HIGH POINT URBAN AREA MPO | EB-5990 | DIVISION 7 | WILL BE REPRIORITIZED | L, TA5200 |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6400000 | 6400000
GUILFORD | JOHNSON STREET | PARRIS AVENUE TO SR 1896 (EAST HARTLEY DRIVE) IN HIGH POINT. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | HIGH POINT URBAN AREA MPO | EB-5999 | DIVISION 7 | WILL BE REPRIORITIZED | L, TA5200 |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 116000 | 116000
GUILFORD | LAWNDALE DRIVE | PISGAH CHURCH ROAD TO LAKE BRANDT ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-5995 | DIVISION 7 | SCHEDULED FOR DELIVERY | L, TAANY | 2023 | 38000 |  |  | 2025 | 305000 | 343000
GUILFORD | NC 68 (EASTCHESTER DRIVE) | CENTENNIAL STREET TO LASSITER DRIVE IN HIGH POINT. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | HIGH POINT URBAN AREA MPO | EB-5922 | DIVISION 7 | SCHEDULED FOR DELIVERY | L, TA5200 |  |  |  |  | 2025 | 108000 | 108000
GUILFORD | OLD BATTLEGROUND ROAD | LAKE BRANDT ROAD TO BICENTENNIAL GREENWAY IN GREENSBORO. CONSTRUCT MULTIUSE PATH. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-5987 | DIVISION 7 | SCHEDULED FOR DELIVERY | L, TAANY | 2024 | 9000 |  |  | 2025 | 710000 | 719000
GUILFORD | SPRING GARDEN STREET | SR 1008 (WEST MARKET STREET) TO POMONA DRIVE AND MERRITT DRIVE TO HOLDEN ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-5992 | DIVISION 7 | WILL BE REPRIORITIZED | L, TAANY |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 252000 | 252000
GUILFORD | SR 1001 (NORTH CHURCH STREET) | HENRY STREET / ELECTRA DRIVE TO LEES CHAPEL ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-5996 | DIVISION 7 | WILL BE REPRIORITIZED | L, TAANY |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 347000 | 347000
GUILFORD | SR 1536 (PENNY ROAD) | CITY LAKE PARK TO PIEDMONT ENVIRONMENTAL CENTER IN HIGH POINT. CONSTRUCT MULTIUSE PATH. | BIKE/PED | 7 | HIGH POINT URBAN AREA MPO | EB-6000 | DIVISION 7 | WILL BE REPRIORITIZED | L, TA5200 |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1200000 | 1200000
GUILFORD | SR 2526 (SUMMIT AVENUE) | SULLIVAN STREET TO FOURTH STREET IN GREENSBORO. CONSTRUCT BICYCLE, PEDESTRIAN AND SAFETY IMPROVEMENTS. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-6009 | DIVISION 7 | WILL BE REPRIORITIZED | L, TAANY |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2975000 | 2975000
GUILFORD | SUMMERFIELD SOUTH GREENWAY | US 220 TO CENTERFIELD ROAD IN SUMMERFIELD. CONSTRUCT MULTIUSE PATH. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-5900 | DIVISION 7 | SCHEDULED FOR DELIVERY | L, TAANY | 2022 | 312000 |  |  | 2024 | 3117000 | 3429000
GUILFORD | US 70 (WEST WENDOVER AVENUE) | NC 68 (EASTCHESTER DRIVE) TO GIBSON PARK ENTRANCE IN HIGH POINT. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | HIGH POINT URBAN AREA MPO | EB-6010 | DIVISION 7 | WILL BE REPRIORITIZED | L, TA5200 |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 176000 | 176000 | COORDINATE WITH U-6121
GUILFORD | I-40 | SR 1860 (MACY GROVE ROAD). CONVERT GRADE SEPARATION TO INTERCHANGE. | HIGHWAY | 7 | HIGH POINT URBAN AREA MPO | I-5980 | REGION D | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3824000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 33700000 | 40924000
GUILFORD | I-40 / BUSINESS 85 / US 29 / US 70 / US 220 | US 220 / SR 1398 (FREEMAN MILL ROAD) TO US 29 / US 70 / US 220 IN GREENSBORO. ADD LANES, IMPROVE SR 1007 (RANDLEMAN ROAD) AND ELM-EUGENE STREET INTERCHANGES, AND REPLACE NORFOLK-SOUTHERN RAILROAD BRIDGE OVERPASS EAST OF ELM-EUGENE STREET. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | I-5965 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 11000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3732000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 109201000 | 123933000 | COORDINATE WITH B-5356 AND B-5718
GUILFORD | I-40 / I-85 | SR 3056 (ROCK CREEK DAIRY ROAD) INTERCHANGE. UPGRADE INTERCHANGE AREA. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | I-6004 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 429000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10900000 | 12729000
GUILFORD | I-40 / US 421 | SR 1850 (SANDY RIDGE ROAD) IN GREENSBORO. INTERCHANGE IMPROVEMENTS. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | I-5712 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | NHP | 2025 | 12633000 | 2025 | 502000 | 2027 | 14499000 | 27634000
GUILFORD | MCCONNELL ROAD | GORRELL STREET AND WILLOW HOPE STREET IN GREENSBORO. CONSTRUCT ROUNDABOUT. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6185 | DIVISION 7 | WILL BE REPRIORITIZED | BGANY, L | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 480000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 160000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1040000 | 1680000 | NON-SYSTEM FACILITY - LOCAL MATCH BY CITY OF GREENSBORO
GUILFORD | NC 62 | SR 1007 (RANDLEMAN ROAD). CONSTRUCT TURN LANES. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6212 | DIVISION 7 | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1500000 | 1800000
GUILFORD | NC 68 | SR 1523 (HICKSWOOD ROAD) TO SR 1556 (GALLIMORE DAIRY ROAD) IN HIGH POINT. UPGRADE TO SUPERSTREET. | HIGHWAY | 7 | HIGH POINT URBAN AREA MPO | U-5974 | REGION D | SCHEDULED FOR DELIVERY | T | 2027 | 19400000 | 2027 | 6600000 | 2029 | 48100000 | 74100000 | COORDINATE WITH U-6122; BUILD NC BONDS: $40 MILLION FOR CONSTRUCTION - PAYBACK 2027-2041
GUILFORD | NC 68 | SR 1556 (GALLIMORE DAIRY ROAD) TO TRIAD CENTER DRIVE IN GREENSBORO. UPGRADE CORRIDOR TO SUPERSTREET. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO, HIGH POINT URBAN AREA MPO | U-6122 | REGION D | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 14200000 | 22700000 | COORDINATE WITH U-5974
GUILFORD | NC 68 | SR 2129 (FOGLEMAN ROAD) TO SR 2017 / SR 2269 (ALCORN ROAD) IN OAK RIDGE. ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6127 | REGION D | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9800000 | 12300000 | COORDINATE WITH R-5725
GUILFORD | PISGAH CHURCH ROAD | NORTH ELM STREET IN GREENSBORO. INTERSECTION IMPROVEMENTS. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-5842 | DIVISION 7 | SCHEDULED FOR DELIVERY | BGANY, L | 2023 | 144000 |  |  | 2024 | 600000 | 744000 | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO
GUILFORD | SR 1001 (CHURCH STREET) | US 220 (WENDOVER AVENUE) TO EAST CONE BOULEVARD IN GREENSBORO. ADD LANES. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-5851 | DIVISION 7 | SCHEDULED FOR DELIVERY | T | 2028 | 9400000 | 2028 | 997000 | 2030 | 11999000 | 22396000
GUILFORD | SR 1001 (NORTH CHURCH STREET) | SR 2516 (ARCHERGATE ROAD) AND SR 2329 (SPENCER-DIXON ROAD) IN GREENSBORO. REALIGN INTERSECTION. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6186 | DIVISION 7 | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2850000 | 4950000
GUILFORD | SR 1007 (RANDLEMAN ROAD) | ELMSLEY DRIVE TO GLENDALE DRIVE IN GREENSBORO. WIDEN TO MULTLANES. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-5850 | DIVISION 7 | SCHEDULED FOR DELIVERY | T | 2022 | 800000 | 2022 | 500000 | 2025 | 3000000 | 4300000 | RIGHT OF WAY IN PROGRESS
GUILFORD | SR 1818 (JOHNSON STREET) / SR 1850 (SANDY RIDGE RO | SR 1820 (SKEET CLUB ROAD) TO SOUTH OF I-40 IN HIGH POINT. WIDEN TO FOUR LANES. | HIGHWAY | 7 | HIGH POINT URBAN AREA MPO | U-4758 | DIVISION 7 | SCHEDULED FOR DELIVERY | BG5200, HP, S(M) | 2022 | 13221000 | 2022 | 7200000 | 2024 | 48200000 | 68621000
GUILFORD | SR 1850 (SANDY RIDGE ROAD) | I-40 TO SR 1008 (WEST MARKET STREET) IN GREENSBORO. WIDEN TO MULTILANES. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6045 | DIVISION 7 | SCHEDULED FOR DELIVERY | T | 2027 | 6800000 | 2027 | 1200000 | 2030 | 23100000 | 31100000
GUILFORD | SR 2085 (BENJAMIN PARKWAY / BRYAN BOULEVARD) | US 70 (WENDOVER AVENUE) TO HOLDEN ROAD IN GREENSBORO. ADD LANES. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-5852 | DIVISION 7 | SCHEDULED FOR DELIVERY | T | 2023 | 855000 | 2023 | 600000 | 2025 | 11600000 | 13055000
GUILFORD | SR 2085 (BRYAN BOULEVARD) | NEW GARDEN ROAD AT HORSEPEN CREEK ROAD IN GREENSBORO. INTERCHANGE IMPROVEMENTS, INCLUDING NEW RAMP FROM WESTBOUND NEW GARDEN ROAD TO WESTBOUND SR 2085. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6008 | DIVISION 7 | SCHEDULED FOR DELIVERY | T | 2027 | 1600000 | 2027 | 300000 | 2029 | 4600000 | 6500000
GUILFORD | SR 2133 (PLEASANT RIDGE ROAD) | SR 2136 (FLEMING ROAD) IN SUMMERFIELD. CONSTRUCT TURN LANES. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6211 | DIVISION 7 | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2100000 | 3500000
GUILFORD | SR 2835 (MCKNIGHT MILL ROAD) | SR 2842 (MINORWOOD ROAD). UPGRADE INTERSECTION. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6181 | DIVISION 7 | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 216000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1400000 | 1916000
GUILFORD | US 220 (BATTLEGROUND AVENUE) | WESTRIDGE ROAD TO COTSWOLD AVENUE IN GREENSBORO. ADD LANES. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-5892 | REGION D | SCHEDULED FOR DELIVERY | NHP | 2023 | 7532000 | 2023 | 1472000 | 2026 | 12400000 | 21404000
GUILFORD | US 29; US 70; US 220 | SR 4240 (GATE CITY BOULEVARD) TO SOUTH OF I-785 IN GREENSBORO. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS AND SAFETY ENHANCEMENTS, INCLUDING RAMP CLOSURES AND CONSOLIDATIONS, RECONFIGURE SR 2526 (SUMMIT AVENUE) / PHILLIPS AVENUE INTERCHANGE, AND REPLACE BRI | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6100 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 2937000 | NOT FUNDED | 1115000 | NOT FUNDED | 102500000 | 106552000
GUILFORD | US 70 (WENDOVER AVENUE) | NC 68 (EASTCHESTER DRIVE) IN HIGH POINT TO SR 1541 (GUILFORD COLLEGE ROAD) IN GREENSBORO. WIDEN TO 6 LANES AND CONSTRUCT SIDEWALKS. | HIGHWAY | 7 | HIGH POINT URBAN AREA MPO, GREENSBORO URBAN AREA MPO | U-6121 | DIVISION 7 | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 19101000 | 27301000 | COORDINATE WITH EB-6010
GUILFORD | US 70 / US 220 (WENDOVER AVENUE) | US 220 (BATTLEGROUND AVENUE) IN GREENSBORO. RECONFIGURE BATTLEGROUND AVENUE, LAWNDALE DRIVE, AND WESTOVER TERRACE BETWEEN FERNWOOD DRIVE AND WENDOVER AVENUE. IMPROVE TRAFFIC FLOW AND SAFETY. IMPROVE WENDOVER AVENUE CONNECTIONS AT WESTOVER TERRACE, BATTLEG | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6108 | REGION D | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 44600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 12500000 | 58700000
GUILFORD | VARIOUS | LAWNDALE DRIVE AND PISGAH CHURCH ROAD IN GREENSBORO. INTERSECTION IMPROVEMENTS AT LAWNDALE ROAD AND PISGAH CHURCH ROAD, AT LAWNDALE ROAD AND MARTINSVILLE ROAD, AND AT MARTINSVILLE ROAD AND PISGAH CHURCH ROAD | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-5812 | DIVISION 7 | SCHEDULED FOR DELIVERY | BGANY, L | 2023 | 144000 |  |  | 2024 | 600000 | 744000 | NON-STATE-SYSTEM FACILITY- LOCAL MATCH BY CITY OF GREENSBORO
GUILFORD | WEST FRIENDLY AVENUE | PEMBROKE ROAD INTERSECTION AND GREEN VALLEY ROAD INTERSECTION IN GREENSBORO. CONSTRUCT INTERSECTION AND PEDESTRIAN IMPROVEMENTS. FROM PEMBROKE ROAD TO GREEN VALLEY ROAD, CONSTRUCT ROADWAY AND ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6129 | DIVISION 7 | WILL BE REPRIORITIZED | BGANY, L | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 120000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 42000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 440000 | 602000 | NON-STATE-SYSTEM FACILITY - LOCAL MATCH BY CITY OF GREENSBORO
GUILFORD | NCRR / NORFOLK SOUTHERN MAIN LINE | HOSKINS STREET IN HIGH POINT. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722351T. | RAIL | 7 | HIGH POINT URBAN AREA MPO | P-5752 | DIVISION 7 | WILL BE REPRIORITIZED | O, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2900000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 18100000 | 21000000
GUILFORD | NCRR NORFOLK SOUTHERN | POMONA YARD. EXTEND AUXILIARY TRACK AND ADD POWER TURNOUTS. | RAIL | 7 | GREENSBORO URBAN AREA MPO | P-5714 | REGION D | SCHEDULED FOR DELIVERY | O, T |  |  |  |  | 2024 | 1600000 | 1600000 | "O" FUNDING REFLECTS CONTRIBUTION BY NORFOLK SOUTHERN CORPORATION
GUILFORD | NCRR NORFOLK SOUTHERN H LINE | SOUTH ENGLISH STREET IN GREENSBORO. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722955X. | RAIL | 7 | GREENSBORO URBAN AREA MPO | P-5747 | REGION D | SCHEDULED FOR DELIVERY | O, T | 2025 | 2300000 |  |  | 2026 | 14155000 | 16455000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION
GUILFORD | NORFOLK SOUTHERN | JAMESTOWN SIDING IN JAMESTOWN. CONSTRUCT EXTENSION. | RAIL | 7 | HIGH POINT URBAN AREA MPO | P-5721 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | O, T |  |  |  |  | 2024 | 2035000 | 2035000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION
GUILFORD | NORFOLK SOUTHERN H LINE | CONSTRUCT GRADE SEPARATION AT FRANKLIN BOULEVARD CROSSING (722959A) IN GREENSBORO, AND CLOSE O'FERRELL STREET CROSSING (722961B). | RAIL | 7 | GREENSBORO URBAN AREA MPO | P-5709 | REGION D | SCHEDULED FOR DELIVERY | O, T | 2022 | 3484000 | 2022 | 1566000 | 2024 | 17025000 | 22075000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION
GUILFORD | NORFOLK SOUTHERN MAIN LINE | SR 1584 (YANCEYVILLE STREET) IN GREENSBORO. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722542D. | RAIL | 7 | GREENSBORO URBAN AREA MPO | P-5735 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | O, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3500000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 11890000 | 15390000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN RAILROAD
GUILFORD | NORTH CAROLINA RAILROAD (NCRR) / NORFOLK SOUTHERN | SR 1424 (HILLTOP ROAD) IN GREENSBORO. CONVERT AT-GRADE CROSSING TO GRADE SEPARATION. | RAIL | 7 | GREENSBORO URBAN AREA MPO | P-5713 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | O, T | 2024 | 3431000 | 2024 | 952000 | 2026 | 8633000 | 13016000 | "O" FUNDING REFLECTS NORFOLK SOUTHERN RAILROAD PARTICIPATION
GUILFORD, FORSYTH | I-40 | NC 66 TO US 421 / BUSINESS 40. | HIGHWAY | 7, 9 | HIGH POINT URBAN AREA MPO, WINSTON-SALEM URBAN AREA MPO | I-5981C | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 38798000 | 39198000
HALIFAX | (IXA) HALIFAX NORTHAMPTON REGIONAL AIRPORT | CONSTRUCT TAXI LANE AND PREPARATION FOR ADDITIONAL T-HANGARS. | AVIATION | 4 | PEANUT BELT RPO | AV-5822 | DIVISION 4 | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2024 | 744000 | 744000
HALIFAX | HALIFAX NORTHAMPTON REGIONAL AIRPORT (IXA) | CONSTRUCT TAXILANE AND APRON. | AVIATION | 4 | PEANUT BELT RPO | AV-5833 | DIVISION 4 | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2026 | 715000 | 715000
HALIFAX | EAST 10TH STREET | MARSHALL STREET TO PARKE AVENUE IN ROANOKE RAPIDS. CONSTRUCT SIDEWALK ON BOTH SIDES OF ROAD. | BIKE/PED | 4 | PEANUT BELT RPO | EB-5843 | DIVISION 4 | SCHEDULED FOR DELIVERY | L, TA5200 |  |  |  |  | 2025 | 160000 | 160000
HALIFAX, NORTHAMPTON | CSX A LINE | CONSTRUCT NEW MAIN TRACK BETWEEN MP A-80.7 AND MP A-82.4 INCLUDING REHABILITATION OF CSX SA-LINE BRIDGE OVER ROANOKE RIVER. NEW CONNECTION BETWEEN A-LINE AND SA-LINE AT MP A-80.7. RECONSTRUCT MAIN TRACK BETWEEN MP A-82.4 AND MP A-84.7. CREATE SECOND MAIN. | RAIL | 1, 4 | PEANUT BELT RPO | P-5741 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5000000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 62000000 | 67000000
HARNETT | NC 55 | NC 27 IN COATS TO SR 1006 (OLD STAGE ROAD (NORTH)). WIDEN ROADWAY. | HIGHWAY | 6 | MID-CAROLINA RPO | R-5953 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 12476000 | NOT FUNDED | 869000 | NOT FUNDED | 62300000 | 75645000
HARNETT | NC 87/24 | SR 1117 (NURSERY ROAD). INTERSECTION IMPROVEMENTS. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-5933 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | T | 2023 | 16000 | 2023 | 22000 | 2025 | 3000000 | 3038000
HARNETT | US 401 (NORTH MAIN STREET) | PARKER LANE TO MCKINNEY PARKWAY. CONSTRUCT MEDIAN. | HIGHWAY | 6 | MID-CAROLINA RPO | R-5890 | REGION C | SCHEDULED FOR DELIVERY | T | 2028 | 100000 | 2028 | 200000 | 2030 | 4500000 | 4800000
HAYWOOD | US 19 (SOCO ROAD) | SR 1304 (FIE TOP ROAD AT GHOST TOWN IN THE SKY) TO BLUE RIDGE PARKWAY. MODERNIZE ROADWAY. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-6160 | NOT FUNDED | WILL BE REPRIORITIZED | BGLT5 | NOT FUNDED | 14700000 | NOT FUNDED | 400000 | NOT FUNDED | 20201000 | 35301000
HAYWOOD | US 23 BUSINESS (SOUTH MAIN STREET) | SR 1164 (HYATT CREEK ROAD) TO US 276 (PIGEON STREET). WIDEN TO MULTI-LANES. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-4712 | DIVISION 14 | SCHEDULED FOR DELIVERY | T | 2027 | 25200000 | 2027 | 3800000 | 2030 | 20000000 | 49000000
HAYWOOD | US 276 | SR 1134 (CRYMES COVE ROAD) AND RACCOON ROAD. INTERSECTION REALIGNMENT. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-6158 | DIVISION 14 | SCHEDULED FOR DELIVERY | T | 2028 | 500000 | 2028 | 200000 | 2030 | 3100000 | 3800000
HAYWOOD | US 276 (JONATHAN CREEK) | US 19 TO I-40 UPGRADE. MODERNIZE ROADWAY. | HIGHWAY | 14 | LAND-OF-SKY RPO, FRENCH BROAD RIVER MPO | R-5921 | DIVISION 14 | SCHEDULED FOR DELIVERY | BGLT5 | 2023 | 600000 | 2023 | 3200000 | 2024 | 32600000 | 36400000
HAYWOOD | US 276 (RUSS AVENUE) | US 23-74 (GREAT SMOKEY MOUNTAIN EXPRESSWAY) TO US 19 (DELLWOOD ROAD). ACCESS MANAGEMENT. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-6159 | DIVISION 14 | SCHEDULED FOR DELIVERY | BGANY | 2028 | 14500000 | 2028 | 2300000 | 2030 | 13401000 | 30201000
HAYWOOD, BUNCOMBE | US 19, US 23 | SR 1836 (CHESTNUT MOUNTAIN ROAD) TO SR 1200 (WIGGINS ROAD). UPGRADE ROADWAY. | HIGHWAY | 13, 14 | FRENCH BROAD RIVER MPO | U-6048 | DIVISION 13, 14 | SCHEDULED FOR DELIVERY | T | 2028 | 300000 | 2028 | 700000 | 2030 | 28200000 | 29200000
HAYWOOD, JACKSON | US 23/US 74 (GREAT SMOKEY MOUNTAINS EXPRESSWAY) | SR 1777 (BALSAM VIEW DRIVE) TO SR 1158 (OLD BALSAM ROAD) MODERNIZE ROADWAY. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO, SOUTHWESTERN RPO | U-6172 | DIVISION 14 | WILL BE REPRIORITIZED | BGLT5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9650000 | 10950000
HENDERSON | BLYTHE STREET | BLYTHE STREET, US 64 (BREVARD ROAD) TO NC 191 (HAYWOOD ROAD). CONSTRUCT SIDEWALKS. | BIKE/PED | 14 | FRENCH BROAD RIVER MPO | EB-5860 | DIVISION 14 | SCHEDULED FOR DELIVERY | L, TAANY | 2025 | 36000 | 2025 | 28000 | 2026 | 1040000 | 1104000
HENDERSON | GROVE STREET | BARNWELL STREET TO US 176 (SPARTANBURG HIGHWAY). CONSTRUCT SIDEWALK. | BIKE/PED | 14 | FRENCH BROAD RIVER MPO | EB-5963 | DIVISION 14 | SCHEDULED FOR DELIVERY | L, TAANY | 2025 | 640000 | 2025 | 76000 | 2026 | 720000 | 1436000
HENDERSON | I-26 | US 25 TO US 64 | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | I-4400A | NOT FUNDED | WILL BE REPRIORITIZED | NHP | NOT FUNDED | 1600000 | NOT FUNDED | 500000 | NOT FUNDED | 114800000 | 116900000
HENDERSON | I-26 | US 64 INTERCHANGE IMPROVEMENTS | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | I-4400BA | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | T |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 29100000 | 29500000
HENDERSON | NC 191 | SR 1381 (MOUNTAIN ROAD) TO NC 280 SOUTH OF MILLS RIVER. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | R-2588B | DIVISION 14 | SCHEDULED FOR DELIVERY | T | 2022 | 15500000 | 2022 | 12100000 | 2024 | 92500000 | 120100000 | INCLUDES REPLACEMENT OF BRIDGE 440121 OVER FRENCH BROAD RIVER OVERFLOW (FORMERLY B-5901).
HENDERSON | NC 225 (SOUTH MAIN STREET) | SOUTH MAIN STREET AT SOUTH KING STREET TO US 176. WIDEN BRIDGE 440143 TO 5-LANES. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-6049 | REGION G | SCHEDULED FOR DELIVERY | T | 2023 | 3400000 | 2023 | 400000 | 2026 | 4000000 | 7800000 | COORDINATE WITH U-5886
HENDERSON | NC 280 (BOYLSTON HIGHWAY) | NC 191 (HAYWOOD ROAD) TO NC 191 (OLD HAYWOOD ROAD). CONSTRUCT ACCESS MANAGEMENT AND INTERSECTION IMPROVEMENTS. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-6124 | NOT FUNDED | WILL BE REPRIORITIZED | NHP | NOT FUNDED | 3300000 | NOT FUNDED | 1800000 | NOT FUNDED | 23000000 | 28100000
HENDERSON | SR 1127 (KANUGA ROAD) | US 25 BUSINESS (CHURCH STREET) TO SR 1123 (LITTLE RIVER ROAD). UPGRADE ROADWAY. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | R-5748 | DIVISION 14 | SCHEDULED FOR DELIVERY | T | 2027 | 12500000 | 2027 | 17600000 | 2029 | 22100000 | 52200000
HENDERSON | SR 1170 (WHITE STREET) | SR 1171 (WILLOW ROAD) TO US 176 (SPARTANBURG HIGHWAY). REALIGN AND EXTEND ROADWAY. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-5886 | DIVISION 14 | SCHEDULED FOR DELIVERY | T | 2023 | 18700000 | 2023 | 2600000 | 2026 | 15200000 | 36500000 | COORDINATE WITH U-6049.
HENDERSON | US 64 | SR 1180 (BLYTHE STREET) TO SR 1173 (WHITE PINE DRIVE)/SR 1186 (DANIEL DRIVE). WIDEN ROADWAY. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-5783 | REGION G | SCHEDULED FOR DELIVERY | T | 2022 | 17400000 | 2022 | 3900000 | 2024 | 20199000 | 41499000
HERTFORD | TRI-COUNTY AIRPORT (ASJ) | RUNWAY EXTENSION. | AVIATION | 1 | PEANUT BELT RPO | AV-5778 | DIVISION 1 | WILL BE REPRIORITIZED | T |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1658000 | 1658000
HERTFORD | TRI-COUNTY AIRPORT (ASJ) | CONSTRUCT ACCESS ROAD TO T-HANGARS. | AVIATION | 1 | PEANUT BELT RPO | AV-5878 | NOT FUNDED | WILL BE REPRIORITIZED | T |  |  |  |  | NOT FUNDED | 2106000 | 2106000
HERTFORD | US 13/NC 11 | NC 11/NC 561 INTERSECTION NEAR AHOSKIE TO US 13/US 158/NC 45 INTERSECTION NEAR WINTON. | HIGHWAY | 1 | PEANUT BELT RPO | R-5311B | REGION A | SCHEDULED FOR DELIVERY | T | 2028 | 6300000 | 2028 | 1200000 | 2030 | 101401000 | 108901000
HERTFORD | US 13/NC 42/NC 561 (MEMORIAL DRIVE) | PEACHTREE STREET TO NC 42. WIDEN TO MULTI-LANES. | HIGHWAY | 1 | PEANUT BELT RPO | R-5796 | REGION A | SCHEDULED FOR DELIVERY | T | 2024 | 2575000 | 2024 | 1570000 | 2025 | 13735000 | 17880000 | INCLUDES B-5605. BUILD NC BOND FUNDING: $5,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE).
HOKE | SR 1305 (WAYSIDE ROAD); SR 1418 (LINDSAY ROAD) | SR 1305, US 401 TO PLANK ROAD, AND SR 1418, US 401 TO SR 1406 (ROCKFISH ROAD). WIDEN TO MULTILANES. | HIGHWAY | 8 | FAYETTEVILLE AREA MPO | U-5753 | DIVISION 8 | SCHEDULED FOR DELIVERY | BGANY, T | 2022 | 42100000 | 2022 | 5000000 | 2024 | 48270000 | 95370000 | INCLUDES H111245; COORDINATE WITH U-5798 AND U-5857; BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2024-2038 (FY 2024 / YR 6 SALE)
HOKE | SR 1406 (ROCKFISH ROAD); NEW ROUTE (GILLIS HILL RO | SR 1406 (ROCKFISH ROAD) FROM SR 1003 (CAMDEN ROAD) TO NORTH OF WESTFIELD DRIVE AND GILLIS HILL ROAD EXTENSION FROM NORTH OF WESTFIELD DRIVE TO SR 1418 (LINDSAY ROAD). WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | HIGHWAY | 8 | FAYETTEVILLE AREA MPO | U-5857 | DIVISION 8 | SCHEDULED FOR DELIVERY | T | 2027 | 18000000 | 2027 | 5700000 | 2029 | 46000000 | 69700000 | COORDINATE WITH U-5753 AND U-5798.
HOKE, MOORE | NC 211 | US 15 / US 501 IN ABERDEEN TO EAST OF SR 1244 (WEST PALMER STREET) / SR 1311 (MOCKINGBIRD HILL ROAD) IN RAEFORD. WIDEN TO MULTILANES. | HIGHWAY | 8 | LUMBER RIVER RPO, TRIANGLE AREA RPO | R-5709 | REGION E | SCHEDULED FOR DELIVERY | T | 2021 | 50805000 | 2021 | 4976000 | 2024 | 132600000 | 188381000 | RIGHT OF WAY IN PROGRESS
HOKE, SCOTLAND | US 401 | US 401 BUSINESS NORTH OF LAURINBURG TO US 401 BUSINESS EAST OF RAEFORD. CONSTRUCT PASSING LANES, TURN LANES, AND PAVED SHOULDERS. | HIGHWAY | 8 | LUMBER RIVER RPO, FAYETTEVILLE AREA MPO | R-3333 | NOT FUNDED | WILL BE REPRIORITIZED | NHP | NOT FUNDED | 273000 | NOT FUNDED | 15507000 | NOT FUNDED | 38800000 | 54580000
IREDELL | STATESVILLE REGIONAL AIRPORT (SVH) | RELOCATE EAST AVIATION DRIVE TO ALLOW FOR FUTURE RUNWAY EXTENSION. | AVIATION | 12 | CHARLOTTE REGIONAL TPO | AV-5896 | DIVISION 12 | SCHEDULED FOR DELIVERY | T | 2026 | 5610000 |  |  | 2027 | 3725000 | 9335000
IREDELL | I-77 | I-77 AT SR 1302 (CORNELIUS ROAD). CONVERT GRADE SEPARATION TO INTERCHANGE. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | I-5962 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | NHP, O | 2026 | 3000000 | 2026 | 500000 | 2028 | 33861000 | 37361000 | OTHER FUNDS PROVIDED BY TOWN OF MOORESVILLE
IREDELL | NC 115 | SR 1645 (OLD WILKESBORO ROAD) TO HARTNESS ROAD. WIDEN TO MULTI-LANES. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-5779 | REGION F | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 22100000 | 37600000
IREDELL | NC 150 | INTERSECTION OF NC 150 AND SR 2399 (WIGGINS ROAD). REALIGN INTERSECTION. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-5780 | REGION F | SCHEDULED FOR DELIVERY | T | 2019 | 550000 |  |  | 2024 | 1450000 | 2000000 | RIGHT-OF-WAY IN PROGRESS. PROJECT TO BE LET WITH W-5601U.
IREDELL | NC 150 (OAK RIDGE FARM HIGHWAY) | NC 115 TO NC 801 (PARK AVENUE). WIDEN TO MULTI-LANES. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-5960 | REGION F | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 18700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 27000000 | 49500000
IREDELL | NC 3 | CABARRUS-IREDELL COUNTY LINE TO SR 1147 (ROCKY RIVER ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-6145 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 5200000 | NOT FUNDED | 3300000 | NOT FUNDED | 28801000 | 37301000
IREDELL | SR 1005 (OLD MOUNTAIN ROAD) | US 21/NC 115 (NORTH MAIN STREET) TO SR 1004 (BUFFALO SHOALS ROAD). WIDEN TO FOUR LANES WITH A MEDIAN. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-6175 | NOT FUNDED | WILL BE REPRIORITIZED | BGLT5 | NOT FUNDED | 21800000 | NOT FUNDED | 3540000 | NOT FUNDED | 28602000 | 53942000
IREDELL | SR 1100 (BRAWLEY SCHOOL ROAD) | I-77 TO US 21 | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | R-3833C | DIVISION 12 | SCHEDULED FOR DELIVERY | L, T | 2019 | 5050000 |  |  | 2024 | 24080000 | 29130000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $10M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE).
IREDELL | SR 1109 (WILLIAMSON ROAD) | I-77 TO SR 1100 (BRAWLEY SCHOOL ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | R-5100A | DIVISION 12 | SCHEDULED FOR DELIVERY | T | 2020 | 8850000 | 2022 | 5300000 | 2025 | 39300000 | 53450000 | BUILD NC BOND FUNDING: $466,370 FOR PE, PAYBACK FY 2020-2034 (FY 2019/YR 1 SALE); $142,461 FOR ROW, PAYBACK FY 2020-2034 (FY 2019/YR 1 SALE); $3M FOR ROW, PAYBACK FY 2022-2036 (FY 2022/YR 4 SALE).
IREDELL | SR 1109 (WILLIAMSON ROAD) | SR 1100 (BRAWLEY SCHOOL ROAD) TO NC 150. WIDEN TO MULTI-LANES. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | R-5100B | DIVISION 12 | SCHEDULED FOR DELIVERY | T | 2019 | 9515000 | 2022 | 1300000 | 2025 | 5900000 | 16715000 | RIGHT-OF-WAY IN PROGRESS; BUILD NC BOND FUNDING: $347,148 FOR ROW, PAYBACK FY 2020-2034 (FY 2019/YR 1 SALE); $2M FOR ROW, PAYBACK FY 2022-2036 (FY 2022/YR 4 SALE).
IREDELL | SR 1246 (FAIRVIEW ROAD) | EXTEND SR 1246 (FAIRVIEW ROAD) OVER I-77 TO CONNECT WITH SR 1206 (ALCOVE ROAD) AND CONSTRUCT PARALLEL NORTH-SOUTH CONNECTOR ROADS TO SR 1109 (WILLIAMSON ROAD). | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-5817 | DIVISION 12 | SCHEDULED FOR DELIVERY | BA, BGANY, BGDA, T | 2019 | 3075000 | 2019 | 1900000 | 2025 | 19225000 | 24200000 | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5100. BUILD NC BOND FUNDING: $5.3M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE).
IREDELL | SR 1305 (OATES ROAD - MIDNIGHT LANE) | US 21 (CHARLOTTE HIGHWAY) TO SR 1474 (BLUEFIELD ROAD). WIDEN TO THREE-LANES WITH OVERPASS OVER I-77. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-5816 | DIVISION 12 | SCHEDULED FOR DELIVERY | T | 2026 | 12600000 | 2026 | 3200000 | 2029 | 29601000 | 45401000
IREDELL | US 21 | INTERSECTION OF US 21 AND SR 2375 (HOUSTON ROAD)/SR 1312 (FLOWER HOUSE ROAD). REALIGN AND SIGNALIZE. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | R-5711 | REGION F | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2025 | 2950000 | 2950000 | RIGHT-OF-WAY IN PROGRESS
IREDELL | US 21 - NC 115 | CEDAR LANE IN TROUTMAN TO BARIUM LANE IN BARIUM SPRINGS. WIDEN TO MULTI-LANES. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | R-2522 | REGION F | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 14900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 16800000 | 34800000
IREDELL | US 21 (CHARLOTTE HIGHWAY) | NC 150 (PLAZA DRIVE) TO SR 1245 (MEDICAL PARK ROAD). WIDEN TO 4-LANES DIVIDED. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-6037 | DIVISION 12 | SCHEDULED FOR DELIVERY | T | 2027 | 15500000 | 2027 | 4600000 | 2030 | 23800000 | 43900000
IREDELL | US 64 (DAVIE AVENUE) | US 64 (DAVIE AVENUE) AND US 21 (SULLIVAN ROAD). CONVERT 5-APPROACH INTERSECTION TO A SINGLE LANE ROUNDABOUT. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-5964 | REGION F | SCHEDULED FOR DELIVERY | T | 2024 | 11000000 | 2024 | 700000 | 2026 | 3298000 | 14998000
IREDELL, CATAWBA | NC 150 | EAST OF SR 1840 (GREENWOOD ROAD) IN CATAWBA COUNTY TO WEST OF SR 1303/SR 1180 (PERTH ROAD/DOOLIE ROAD) IN IREDELL COUNTY. WIDEN TO 4-LANES. SR 1383/SR 1180 TO US 21 IN IREDELL COUNTY. WIDEN TO 6-LANES. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO, GREATER HICKORY MPO | R-2307B | REGION F | SCHEDULED FOR DELIVERY | S(M), T, T(DA) |  |  |  |  | 2025 | 164500000 | 164500000 | RIGHT-OF-WAY IN PROGRESS. $5M IN STBG-DA FUNDS SWITCHED WITH $5M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP.
JACKSON | NC 107 | 500 FEET SOUTH OF SR 1135 (SHOOK COVE ROAD) TO 1000 FEET NORTH OF THE LAKE TUCKASEEGEE DAM. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5841A | DIVISION 14 | SCHEDULED FOR DELIVERY | T | 2028 | 2600000 | 2028 | 200000 | 2030 | 17899000 | 20699000
JACKSON | NC 107 (US 23 BUSINESS) | NC 116 TO US 23 BUSINESS. US 23 BUSINESS, SR 1432 (SKYLAND DRIVE) TO MUNICIPAL DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5600 | REGION G | SCHEDULED FOR DELIVERY | T | 2022 | 58440000 | 2022 | 7200000 | 2025 | 56199000 | 121839000 | BUILD NC BOND FUNDING: $20M FOR RIGHT OF WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE).
JACKSON | US 64 | NC 107 INTERSECTION. IMPROVE INTERSECTION AND ADD AUXILLARY LANE FROM PEBBLE CREEK DRIVE TO US 64/NC 107 INTERSECTION. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5881 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 14900000 | NOT FUNDED | 800000 | NOT FUNDED | 6700000 | 22400000
JACKSON | US 74 (GREAT SMOKEY MOUNTAINS EXPRESSWAY) | US 441 GATEWAY INTERCHANGE TO SR 1391 (WEST PINEY MOUNTAIN ROAD). MODERNIZE ROADWAY, INCLUDING REPLACEMENT OF BRIDGE 490043 OVER THE TUCKASEGEE RIVER. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5907 | DIVISION 14 | SCHEDULED FOR DELIVERY | BGLT5 | 2028 | 3500000 | 2028 | 200000 | 2030 | 19900000 | 23600000
JOHNSTON | EAST CLAYTON CONNECTOR GREENWAY | SR 2851 (EAST FRONT STREET) TO SR 1902 (GLEN LAUREL ROAD). CONSTRUCT GREENWAY. | BIKE/PED | 4 | CAPITAL AREA MPO | EB-6016 | DIVISION 4 | SCHEDULED FOR DELIVERY | L, TAANY | 2027 | 8000 |  |  | 2028 | 994000 | 1002000
JOHNSTON | MOUNTAINS TO SEA TRAIL | FOX RIDGE ROAD TO NEUSE RIVER BRIDGE. CONSTRUCT GREENWAY. | BIKE/PED | 4 | CAPITAL AREA MPO | EB-6017 | DIVISION 4 | SCHEDULED FOR DELIVERY | L, TAANY |  |  |  |  | 2028 | 318000 | 318000
JOHNSTON | CLAYTON | CLAYTON SIGNAL SYSTEM. | HIGHWAY | 4 | CAPITAL AREA MPO | U-5943 | REGION A | SCHEDULED FOR DELIVERY | BGANY | 2023 | 100000 | 2023 | 198000 | 2025 | 2834000 | 3132000
JOHNSTON | I-95 | US 70 BUSINESS. UPGRADE INTERCHANGE. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | I-5972 | REGION A | SCHEDULED FOR DELIVERY | NHFP, NHP |  |  |  |  | 2024 | 32100000 | 32100000 | RIGHT-OF-WAY IN PROGRESS
JOHNSTON | I-95 | US 701/NC 96. CONSTRUCT INTERCHANGE. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | I-5974 | REGION A | SCHEDULED FOR DELIVERY | NHP | 2026 | 5096000 | 2026 | 2026000 | 2028 | 48399000 | 55521000
JOHNSTON | I-95 | SR 1007 (BROGDEN ROAD). IMPROVE INTERCHANGE. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | I-6061 | DIVISION 4 | SCHEDULED FOR DELIVERY | T | 2027 | 1300000 | 2027 | 1900000 | 2029 | 17200000 | 20400000
JOHNSTON | I-95 | SR 2339 (BAGLEY ROAD). IMPROVE INTERCHANGE. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | I-6062 | DIVISION 4 | SCHEDULED FOR DELIVERY | T | 2027 | 3600000 | 2027 | 1300000 | 2029 | 19000000 | 23900000
JOHNSTON | NC 210 | NC 50 TO SR 1330 (RALEIGH ROAD). UPGRADE TO SUPERSTREET. | HIGHWAY | 4 | CAPITAL AREA MPO | U-6203 | DIVISION 4 | SCHEDULED FOR DELIVERY | T | 2026 | 28964000 | 2026 | 4360000 | 2028 | 45201000 | 78525000
JOHNSTON | NC 242 | SR 1168 (TARHEEL ROAD) TO I-40. WIDEN ROADWAY. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | R-5761 | DIVISION 4 | SCHEDULED FOR DELIVERY | T | 2027 | 2200000 | 2027 | 500000 | 2029 | 13300000 | 16000000
JOHNSTON | NC 42 | NC 50 TO US 70 BUSINESS. WIDEN TO MULTI-LANES. | HIGHWAY | 4 | CAPITAL AREA MPO | R-3410 | REGION A | SCHEDULED FOR DELIVERY | BGANY | 2027 | 14696000 | 2027 | 19600000 | 2029 | 74201000 | 108497000
JOHNSTON | NC 42 | SR 1003 (BUFFALO ROAD) TO WILSON COUNTY LINE. MODERNIZE ROADWAY. | HIGHWAY | 4 | CAPITAL AREA MPO, UPPER COASTAL PLAIN RPO | U-5998 | DIVISION 4 | SCHEDULED FOR DELIVERY | T | 2025 | 3400000 | 2025 | 3000000 | 2027 | 14800000 | 21200000
JOHNSTON | NEW ROUTE | SR 1010 (CLEVELAND ROAD) TO NC 42. CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | 4 | CAPITAL AREA MPO | U-6208 | DIVISION 4 | SCHEDULED FOR DELIVERY | T | 2027 | 3000000 | 2027 | 10000000 | 2029 | 14500000 | 27500000
JOHNSTON | SR 1003 (BUFFALO ROAD) | US 70 TO SR 1934 (OLD BEULAH ROAD). WIDEN TO THREE LANES. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | R-5718 | DIVISION 4 | SCHEDULED FOR DELIVERY | BG5200, T | 2022 | 6937000 | 2022 | 1190000 | 2025 | 14300000 | 22427000 | RIGHT-OF-WAY IN PROGRESS.
JOHNSTON | SR 1010 (CLEVELAND ROAD) | NC 42 TO SR 1555 (BARBER MILL ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 4 | CAPITAL AREA MPO | U-6216 | DIVISION 4 | SCHEDULED FOR DELIVERY | T | 2027 | 35700000 | 2027 | 14900000 | 2029 | 42000000 | 92600000
JOHNSTON | SR 1501 (SWIFT CREEK ROAD) | AIRPORT INDUSTRIAL DRIVE TO DRIVEWAY JUST NORTH OF JOHNSTON COUNTY AIRPORT. WIDEN ROADWAY. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | R-5950 | DIVISION 4 | SCHEDULED FOR DELIVERY | T | 2027 | 1400000 | 2027 | 200000 | 2029 | 2900000 | 4500000
JOHNSTON | US 301/NC 39/NC 96 | SR 1623 (BOOKER DAIRY ROAD) TO SR 2302 (RICKS ROAD). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | U-5726 | DIVISION 4 | SCHEDULED FOR DELIVERY | T | 2025 | 11200000 | 2025 | 1400000 | 2027 | 14600000 | 27200000
JOHNSTON | US 70 | US 301 TO I-95. ACCESS MANAGEMENT. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | R-5795 | REGION A | SCHEDULED FOR DELIVERY | T | 2027 | 4631000 | 2027 | 4400000 | 2029 | 11700000 | 20731000
JOHNSTON | US 70 | WEST OF SR 2372 (EDWARDS ROAD / NORTH PEARL STREET) TO EAST OF SR 2314 (PONDFIELD ROAD). UPGRADE TO FREEWAY STANDARDS. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | R-5829B | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 13076000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4774000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 71903000 | 89753000
JOHNSTON | JOHNSTON COUNTY | PURCHASE EXPANSION VEHICLES. | PUBLIC TRANSIT | 4 | UPPER COASTAL PLAIN RPO, CAPITAL AREA MPO | TA-6720 | DIVISION 4 | SCHEDULED FOR DELIVERY | 5311, L, T |  |  |  |  | 2026 | 33000 | 33000
JOHNSTON | NS/NCRR H LINE | CONSTRUCT GRADE SEPARATION AT SR 1553 (SHOTWELL ROAD). CLOSE EXISTING AT-GRADE CROSSING IN CLAYTON. | RAIL | 4 | CAPITAL AREA MPO | P-5743 | NOT FUNDED | WILL BE REPRIORITIZED | O, T | NOT FUNDED | 3000000 |  |  | NOT FUNDED | 10570000 | 13570000 | OTHER FUNDS PROVIDED BY NS.
JOHNSTON, WAKE | US 70 BUSINESS | GREENFIELD PARKWAY TO NC 42. UPGRADE ROADWAY TO SUPERSTREET. | HIGHWAY | 4, 5 | CAPITAL AREA MPO | U-6113 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 7600000 | NOT FUNDED | 1500000 | NOT FUNDED | 83200000 | 92300000
JOHNSTON, WAKE | VARIOUS | BUS RAPID TRANSIT SERVICE, GARNER TO CLAYTON. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | PUBLIC TRANSIT | 4, 5 | CAPITAL AREA MPO | TO-6166D | REGION A, C | WILL BE REPRIORITIZED | L, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7649000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2126000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 40224000 | 49999000
LEE | RALEIGH EXECUTIVE JETPORT (TTA) | RUNWAY 21 AND RUNWAY 3 BYPASS TAXIWAY. CONSTRUCT AIRPLANE RUN-UP LANE AT EACH END OF TAXIWAY. | AVIATION | 8 | TRIANGLE AREA RPO | AV-5899 | DIVISION 8 | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2024 | 1400000 | 1400000
LEE | MCIVER STREET | MOORE STREET TO OAKWOOD AVENUE IN SANFORD. CONSTRUCT SIDEWALKS. | BIKE/PED | 8 | TRIANGLE AREA RPO | EB-6003 | NOT FUNDED | WILL BE REPRIORITIZED | L, TA5200 |  |  |  |  | NOT FUNDED | 691000 | 691000
LEE | NC 42 (WICKER STREET) | LEGION DRIVE TO NORTH OF HIGH RIDGE DRIVE AT KIWANIS FAMILY PARK IN SANFORD. CONSTRUCT MULTIUSE PATH. | BIKE/PED | 8 | TRIANGLE AREA RPO | EB-5742 | DIVISION 8 | SCHEDULED FOR DELIVERY | L, TA5200 |  |  |  |  | 2024 | 809000 | 809000 | PLANNING / DESIGN / RIGHT OF WAY / CONSTRUCTION BY CITY OF SANFORD - IN PROGRESS
LEE | SR 1002 (CHARLOTTE AVENUE) | CHATHAM STREET TO SR 1002 (11TH STREET) IN SANFORD. CONSTRUCT SIDEWALKS AND IMPLEMENT ROAD DIET WITH BICYCLE LANES. | BIKE/PED | 8 | TRIANGLE AREA RPO | EB-6002 | DIVISION 8 | SCHEDULED FOR DELIVERY | L, TA5200 |  |  |  |  | 2025 | 1028000 | 1028000
LEE | NEW ROUTE | SR 1133 (LEE AVENUE) TO EXISTING COMMERCE DRIVE IN SANFORD. CONSTRUCT 2-LANE EXTENSION OF COMMERCE DRIVE. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5960 | DIVISION 8 | SCHEDULED FOR DELIVERY | T | 2028 | 138000 | 2028 | 104000 | 2030 | 6500000 | 6742000
LEE | SR 1237 (CARTHAGE STREET) | SR 1152 (FIRE TOWER ROAD) TO NC 42 (WICKER STREET) IN SANFORD. WIDEN ROADWAY. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5709 | DIVISION 8 | SCHEDULED FOR DELIVERY | T | 2022 | 3000000 | 2022 | 1700000 | 2024 | 13199000 | 17899000
LEE | SR 1521 (KELLY DRIVE) | SR 1519 (NASH STREET) TO NORTHEAST OF CENTRAL CAROLINA COMMUNITY COLLEGE. CONSTRUCT 3-LANE REALIGNMENT OF KELLY DRIVE. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5959 | DIVISION 8 | SCHEDULED FOR DELIVERY | T | 2023 | 1900000 | 2023 | 700000 | 2025 | 7300000 | 9900000
LEE | US 1 / US 15 / US 501 | SOUTH OF SR 1198 (BRYAN DRIVE) TO SR 1237 (CARTHAGE STREET) IN SANFORD. UPGRADE TO SUPERSTREET AND RELOCATE NC 78 (TRAMWAY ROAD). | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5727 | REGION E | SCHEDULED FOR DELIVERY | NHP, T | 2023 | 12000000 | 2023 | 900000 | 2026 | 17300000 | 30200000 | COORDINATE WITH U-5975
LEE | US 1 / US 15 / US 501 | US 15 / US 501 (WHITE HILL ROAD) / SR 1179 (ROCKY FORK CHURCH ROAD) TO SOUTH OF SR 1198 (BRYAN DRIVE). UPGRADE TO SUPERSTREET. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5975 | REGION E | SCHEDULED FOR DELIVERY | T | 2023 | 4100000 | 2023 | 2800000 | 2026 | 13900000 | 20800000 | COORDINATE WITH U-5727
LEE | US 421 BUSINESS / NC 87 | US 1 / US 15 / US 501 TO FORMER ATLANTIC COAST LINE RAILROAD CROSSING EAST OF WASHINGTON AVENUE IN SANFORD. RECONSTRUCT AS A "COMPLETE STREET" WITH IMPROVEMENTS SUCH AS MEDIANS, SIDEWALKS, BICYCLE FACILITIES, AND STREETSCAPING. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5722 | REGION E | SCHEDULED FOR DELIVERY | T | 2027 | 24700000 | 2027 | 7564000 | 2030 | 15099000 | 47363000
LENOIR | SR 1569 (CAREY ROAD EXTENSION) | SR 1572 (ROUSE ROAD) TO US 258. CONSTRUCT MULTI-LANES ON NEW LOCATION. | HIGHWAY | 2 | EASTERN CAROLINA RPO | U-3618 | DIVISION 2 | SCHEDULED FOR DELIVERY | T | 2026 | 4700000 | 2026 | 1000000 | 2028 | 28301000 | 34001000
LENOIR | US 70 | SR 1227 (JIM SUTTON ROAD)/SR 1252 (WILLIE MEASLEY ROAD). CONSTRUCT AT GRADE INTERSECTION TO INTERCHANGE | HIGHWAY | 2 | EASTERN CAROLINA RPO | R-5813 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 10100000 | NOT FUNDED | 3262000 | NOT FUNDED | 55501000 | 68863000
LENOIR | US 70 (FUTURE I-42) | SR 1522 (ALBERT SUGGS ROAD) TO NC 148 (HARVEY PARKWAY). | HIGHWAY | 2 | EASTERN CAROLINA RPO | R-2553B | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 8300000 | NOT FUNDED | 6000000 | NOT FUNDED | 55801000 | 70101000
LENOIR | US 70 (FUTURE I-42) | NC 148 (HARVEY PARKWAY) TO US 70 EAST OF NC 58. | HIGHWAY | 2 | EASTERN CAROLINA RPO | R-2553C | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 82600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 320700000 | 407200000
LENOIR, GREENE | US 258 | SR 1101 (BROWNTOWN ROAD) TO SR 2010 (C. F. HARVEY PARKWAY). WIDEN TO MULTI-LANES. | HIGHWAY | 2 | EASTERN CAROLINA RPO | R-5814 | DIVISION 2 | SCHEDULED FOR DELIVERY | T | 2027 | 11900000 | 2027 | 3400000 | 2029 | 31302000 | 46602000
LINCOLN | NC 150 | US 321 AT LINCOLNTON TO US 321 BYPASS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-0617C | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 600000 | NOT FUNDED | 3900000 | NOT FUNDED | 71600000 | 76100000
LINCOLN | NC 16 | SR 1389 (FAIRFIELD FOREST ROAD) TO SR 1379 (WEBBS ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6144 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 5500000 | NOT FUNDED | 4900000 | NOT FUNDED | 21599000 | 31999000
LINCOLN | NC 16 BUSINESS | NC 16 BUSINESS, SR 1373 (CAMPGROUND ROAD), SR 1386 (WILL PROCTOR ROAD). REALIGN OFFSET INTERSECTIONS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5962 | REGION F | SCHEDULED FOR DELIVERY | O, T | 2024 | 3300000 | 2024 | 300000 | 2026 | 3912000 | 7512000 | OTHER FUNDING PROVIDED BY LINCOLN COUNTY
LINCOLN | NC 16 BYPASS | SR 1380 (OPTIMIST CLUB ROAD) INTERSECTION. UPGRADE AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6134 | REGION F | SCHEDULED FOR DELIVERY | T | 2024 | 500000 | 2024 | 100000 | 2026 | 25400000 | 26000000
LINCOLN | NC 27 (EAST MAIN STREET) | US 321 BUS TO NC 150 (EAST). CONSTRUCT ACCESS MANAGEMENT AND INTERSECTION IMPROVEMENTS. INCLUDES CONSTRUCTION OF NORTHBOUND TURN LANE FROM SR 1294 (LITHINA INN ROAD) TO NC 27 (E MAIN STREET) AND WIDENING OF BRIDGE #540042 OVER SEABOARD RR ON NC 150. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6140 | REGION F | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 35000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 33500000 | 77800000
LINCOLN | NC 73 | SR 1383 (INGLESIDE FARM ROAD) TO NC 16. WIDEN TO MULTI-LANES. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6139 | NOT FUNDED | WILL BE REPRIORITIZED | NHP | NOT FUNDED | 5900000 | NOT FUNDED | 1500000 | NOT FUNDED | 42000000 | 49400000
LINCOLN | NC 73 EXTENSION | US 321 TO SR 1356 (CAMP CREEK ROAD) CONSTRUCT MULTI-LANES ON NEW LOCATION. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6142 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 32300000 | NOT FUNDED | 4800000 | NOT FUNDED | 69302000 | 106402000
LINCOLN, MECKLENBURG | NC 73 | NC 16 TO VANCE ROAD EXTENSION/BEATTIES FORD ROAD. | HIGHWAY | 10, 12 | GASTON-CLEVELAND-LINCOLN MPO, CHARLOTTE REGIONAL TPO | R-5721A | REGION E, F | SCHEDULED FOR DELIVERY | T | 2026 | 46400000 | 2026 | 10400000 | 2029 | 102002000 | 158802000
MACON | MACON COUNTY AIRPORT | EXTEND RUNWAY. | AVIATION | 14 | SOUTHWESTERN RPO | AV-5850 | DIVISION 14 | SCHEDULED FOR DELIVERY | T | 2028 | 166000 |  |  | 2029 | 4834000 | 5000000
MACON | EAST MAIN ST/US 441 BUS | NC 28 (HIGHLANDS ROAD). CONSTRUCT SIDEWALK LOOP. | BIKE/PED | 14 | SOUTHWESTERN RPO | EB-5964 | DIVISION 14 | SCHEDULED FOR DELIVERY | L, TA5200 | 2023 | 16000 |  |  | 2024 | 144000 | 160000
MACON | US 23/US 441 | SR 1652 (WIDE HORIZON DRIVE)/SR 1152 (BELDEN CIRCLE) TO SR 1649 (PRENTISS BRIDGE ROAD). | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5734B | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 13800000 | NOT FUNDED | 3200000 | NOT FUNDED | 26600000 | 43600000
MACON | US 23/US 441 | SR 1649 (PRENTISS BRIDGE ROAD) TO GEORGIA STATE LINE. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5734C | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 5000000 | NOT FUNDED | 600000 | NOT FUNDED | 53600000 | 59200000
MADISON | MARSHALL | US 25/70, SR 1601 (DERINGER DRIVE) TO BEGINNING OF INGLE'S PARKING LOT. CONSTRUCT SIDEWALKS, INSTALL CROSSWALKS, ADA RAMPS, PEDESTRIAN SIGNAL AND PEDESTRIAN REFUGE. | BIKE/PED | 13 | LAND-OF-SKY RPO | EB-5918 | DIVISION 13 | SCHEDULED FOR DELIVERY | L, TALT5 |  |  |  |  | 2024 | 120000 | 120000
MADISON | US 25 | US 25/70 BUSINESS (NORTH MAIN STREET) TO SR 1143 (BRUSH CREEK ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 13 | LAND-OF-SKY RPO | R-5837 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 5100000 | NOT FUNDED | 9700000 | NOT FUNDED | 18500000 | 33300000
MADISON | US 25/70 | EAST OF SR 1392 (SKYWAY DRIVE) TO US 25/70 BUSINESS (NORTH MAIN STREET). MODERNIZE ROADWAY. | HIGHWAY | 13 | LAND-OF-SKY RPO | R-5924 | NOT FUNDED | WILL BE REPRIORITIZED | BGLT5 | NOT FUNDED | 1800000 | NOT FUNDED | 3000000 | NOT FUNDED | 32101000 | 36901000
MARTIN | EAST MAIN STREET | BOULEVARD STREET TO RIVER ROAD IN WILLIAMSTON. INSTALL SIDEWALKS AND CURB RAMPS. | BIKE/PED | 1 | MID-EAST RPO | EB-5979 | DIVISION 1 | SCHEDULED FOR DELIVERY | L, TA5200 |  |  |  |  | 2027 | 72000 | 72000
MARTIN | US 13/US 17 | MAIN STREET IN WILLIAMSTON. IMPROVE INTERSECTION. | HIGHWAY | 1 | MID-EAST RPO | R-5879 | REGION A | SCHEDULED FOR DELIVERY | NHP | 2025 | 100000 | 2025 | 200000 | 2027 | 2350000 | 2650000
MARTIN | US 17 | SR 1119 (RALPH TAYLOR ROAD) TO SR 1205 (HOLLY CREEK ROAD). ACCESS MANAGEMENT. | HIGHWAY | 1 | MID-EAST RPO | R-5810 | DIVISION 1 | SCHEDULED FOR DELIVERY | T | 2023 | 15000 | 2023 | 180000 | 2025 | 7300000 | 7495000
McDOWELL | FONTA FLORA TRAIL | US 70 TO RESISTOFLEX ROAD. CONSTRUCT GREENWAY. | BIKE/PED | 13 | FOOTHILLS RPO | EB-5916 | DIVISION 13 | SCHEDULED FOR DELIVERY | L, TA5200 | 2023 | 60000 |  |  | 2024 | 2450000 | 2510000
McDOWELL | NC 226 | US 221 TO NC 226A. WIDEN ROADWAY TO 3 LANES. | HIGHWAY | 13 | FOOTHILLS RPO | R-5923 | NOT FUNDED | WILL BE REPRIORITIZED | BGLT5 | NOT FUNDED | 100000 | NOT FUNDED | 600000 | NOT FUNDED | 4300000 | 5000000
McDOWELL | US 221 | NORTH OF I-40 TO SR 1153 (GOOSE CREEK ROAD) | HIGHWAY | 13 | FOOTHILLS RPO | R-0204E | DIVISION 13 | SCHEDULED FOR DELIVERY | T | 2025 | 8000000 | 2025 | 1200000 | 2028 | 38698000 | 47898000
McDOWELL | US 221 BUSINESS | US 221/NC 226 TO GEORGIA AVENUE. WIDEN EXISTING ROADWAY. | HIGHWAY | 13 | FOOTHILLS RPO | U-5835 | DIVISION 13 | SCHEDULED FOR DELIVERY | T | 2023 | 6600000 | 2023 | 2000000 | 2025 | 15945000 | 24545000 | BUILD NC BOND FUNDING: $4M FOR CONSTRUCTION, PAYBACK FY 2026-2040 (FY 2026 / YR 8 SALE)
MECKLENBURG | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT (CLT) | CONSTRUCT FOURTH PARALLEL RUNWAY. | AVIATION | 10 | CHARLOTTE REGIONAL TPO | AV-5879 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | O, T |  |  |  |  | 2024 | 500000 | 500000 | OTHER FUNDING PROVIDED BY CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT
MECKLENBURG | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT (CLT) | EXPAND CONCOURSE A (PHASE II). | AVIATION | 10 | CHARLOTTE REGIONAL TPO | AV-5893 | REGION E | SCHEDULED FOR DELIVERY | O, T |  |  |  |  | 2025 | 500000 | 500000 | OTHER FUNDING PROVIDED BY CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT
MECKLENBURG | IRWIN CREEK GREENWAY EASTERN EXTENSION | EXISTING IRWIN CREEK GREENWAY TO HAMILTON STREET. CONSTRUCT GREENWAY. | BIKE/PED | 10 | CHARLOTTE REGIONAL TPO | EB-5970 | DIVISION 10 | SCHEDULED FOR DELIVERY | L, TAANY |  |  |  |  | 2028 | 3246000 | 3246000
MECKLENBURG | JETTON STREET | GRIFFITH STREET TO POTTS STREET. CONSTRUCT SIDEWALK ON SOUTH SIDE OF JETTON STREET. | BIKE/PED | 10 | CHARLOTTE REGIONAL TPO | EB-5971 | DIVISION 10 | SCHEDULED FOR DELIVERY | L, TAANY |  |  |  |  | 2025 | 232000 | 232000
MECKLENBURG | NC 51 MULTI-USE PATH | TRADE STREET TO INDEPENDENCE POINTE PARKWAY. CONSTRUCT MULTI-USE PATH ON SOUTH SIDE OF NC 51. | BIKE/PED | 10 | CHARLOTTE REGIONAL TPO | EB-5969 | DIVISION 10 | SCHEDULED FOR DELIVERY | L, TAANY |  |  |  |  | 2025 | 860000 | 860000
MECKLENBURG | ARDREY KELL ROAD | US 521 (JOHNSTON ROAD) TO SR 3624 (REA ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6167 | NOT FUNDED | WILL BE REPRIORITIZED | BGANY | NOT FUNDED | 94300000 | NOT FUNDED | 1500000 | NOT FUNDED | 31401000 | 127201000
MECKLENBURG | BAILEY ROAD EXTENSION | US 21 (STATESVILLE ROAD) TO FUTURE NORTHCROSS DRIVE EXTENSION. CONSTRUCT 2 LANE ROADWAY ON NEW LOCATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6171 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 900000 | NOT FUNDED | 2300000 | NOT FUNDED | 19500000 | 22700000
MECKLENBURG | CHARLOTTE | SR 2940 (EASTWAY DRIVE) AND SHAMROCK DRIVE. CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5803 | DIVISION 10 | SCHEDULED FOR DELIVERY | L, T, T(DA) | 2024 | 2400000 |  |  | 2025 | 13419000 | 15819000 | LOCAL CONTRIBUTION OF $5M BY CITY OF CHARLOTTE FOR RIGHT-OF-WAY AND CONSTRUCTION - CITY PAYING 100% OF PRELIMINARY ENGINEERING AND UTILITIES. $7.82M IN STBG-DA FUNDS SWITCHED WITH $7.82M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP.
MECKLENBURG | I-277 | KENILWORTH AVENUE TO NORTH DAVIDSON STREET AND US 74 (INDEPENDENCE BOULEVARD) FROM I-277 TO PECAN AVENUE. UPGRADE INTERCHANGES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6022A | NOT FUNDED | WILL BE REPRIORITIZED | NHP | NOT FUNDED | 55600000 | NOT FUNDED | 1100000 | NOT FUNDED | 250401000 | 307101000
MECKLENBURG | I-485 | I-485 AND NC 16 (PROVIDENCE ROAD). CONSTRUCT INTERCHANGE IMPROVEMENTS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-5963 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 11100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 28900000 | 41300000
MECKLENBURG | I-485 | NC 51 (PINEVILLE-MATTHEWS ROAD) INTERCHNAGE. IMPROVE INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6015 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 8400000 | NOT FUNDED | 1100000 | NOT FUNDED | 9999000 | 19499000
MECKLENBURG | I-485 | NC 49 (SOUTH TRYON STREET) INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6019 | NOT FUNDED | WILL BE REPRIORITIZED | NHP | NOT FUNDED | 14900000 | NOT FUNDED | 4700000 | NOT FUNDED | 20701000 | 40301000
MECKLENBURG | I-77 | NC 73 INTERCHANGE. UPGRADE EXISTING INTERCHANGE TO SPLIT DIAMOND CONFIGURATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-5715 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | NHP | 2023 | 1551000 | 2023 | 2400000 | 2025 | 39499000 | 43450000
MECKLENBURG | I-77 | SOUTH CAROLINA STATE LINE TO I-277/US 74 (BELK FREEWAY). WIDEN EXISTING FREEWAY TO TEN LANES BY CONSTRUCTING MANAGED LANES, RECONSTRUCT I-77/I-277 (BELK FREEWAY) INTERCHANGE, AND INSTALL RAMP METERS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-5718A | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | BOND R, NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 660000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 30900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 206999000 | 897899000
MECKLENBURG | I-77 | I-85 INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6014 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 96100000 | 97700000
MECKLENBURG | I-77 | US 21/SR 2108 (SUNSET ROAD) INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6056 | NOT FUNDED | WILL BE REPRIORITIZED | NHP | NOT FUNDED | 300000 | NOT FUNDED | 200000 | NOT FUNDED | 8200000 | 8700000
MECKLENBURG | I-85 | I-485 INTERCHANGE NORTHEAST OF CHARLOTTE. IMPROVE INTERCHANGE | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6012 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1800000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 11500000 | 13500000
MECKLENBURG | I-85 | NC 24 (W.T. HARRIS BOULEVARD) INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6013 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 16000000 | 17100000
MECKLENBURG | I-85 | I-485 INTERCHANGE WEST OF CHARLOTTE. IMPROVE INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6016 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 22400000 | 24800000
MECKLENBURG | I-85 | SR 2472 (MALLARD CREEK CHURCH ROAD) INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6017 | NOT FUNDED | WILL BE REPRIORITIZED | NHP | NOT FUNDED | 1100000 | NOT FUNDED | 1800000 | NOT FUNDED | 13099000 | 15999000
MECKLENBURG | I-85 | NC 16 (BROOKSHIRE BOULEVARD) INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6020 | NOT FUNDED | WILL BE REPRIORITIZED | NHP | NOT FUNDED | 10000000 | NOT FUNDED | 2000000 | NOT FUNDED | 15299000 | 27299000
MECKLENBURG | I-85 | SR 2480 (SUGAR CREEK ROAD) INTERCHANGE. IMPROVE INTERCHANGE | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6053 | NOT FUNDED | WILL BE REPRIORITIZED | NHP | NOT FUNDED | 51100000 | NOT FUNDED | 2200000 | NOT FUNDED | 21300000 | 74600000
MECKLENBURG | NC 115 (OLD STATESVILLE ROAD) | NC 24 (HARRIS BOULEVARD) TO I-485. WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5772 | REGION E | SCHEDULED FOR DELIVERY | T | 2028 | 6500000 | 2028 | 4300000 | 2030 | 33700000 | 44500000
MECKLENBURG | NC 16 (BROOKSHIRE BOULEVARD) | I-85 TO IDAHO DRIVE. ADD WESTBOUND THROUGH LANE ON NC 16 BETWEEN A POINT WEST OF IDAHO DRIVE AND I-85. CONVERT NC 16 AND IDAHO DRIVE INTERSECTION TO AN INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5955B | REGION E | SCHEDULED FOR DELIVERY | T | 2025 | 4300000 | 2025 | 345000 | 2028 | 12700000 | 17345000
MECKLENBURG | NC 160 | SOUTH CAROLINA LINE TO NC 49 (SOUTH TRYON ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5766A | REGION E | SCHEDULED FOR DELIVERY | T | 2025 | 20500000 | 2025 | 4100000 | 2028 | 65399000 | 89999000
MECKLENBURG | NC 160 | NC 49 (SOUTH TRYON ROAD) TO I-485. WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5766B | REGION E | SCHEDULED FOR DELIVERY | T | 2025 | 65400000 | 2025 | 6500000 | 2028 | 65799000 | 137699000
MECKLENBURG | NC 27 (FREEDOM DRIVE) | SR 1644 (TODDVILLE ROAD) TO SR 1600 (MOORES CHAPEL ROAD). WIDEN TO 4-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5957 | REGION E | SCHEDULED FOR DELIVERY | T | 2026 | 13100000 | 2026 | 500000 | 2028 | 17899000 | 31499000
MECKLENBURG | NC 49 & BACK CREEK CHURCH ROAD | NC 49, JOHN KIRK DRIVE TO I-485. WIDEN EXISTING ROADWAY. REALIGN BACK CREEK CHURCH ROAD ON NEW LOCATION TO THE NC 49 AND MALLARD CREEK CHURCH ROAD INTERSECTION. CLOSE EXISTING AT GRADE RAIL CROSSING AT NC 49 AND BACK CREEK CHURCH ROAD. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5768 | REGION E | SCHEDULED FOR DELIVERY | L, T | 2026 | 29400000 | 2026 | 4000000 | 2029 | 44200000 | 77600000 | LOCAL FUNDING PROVIDED BY THE CITY OF CHARLOTTE
MECKLENBURG | NC 51 | MATTHEWS TOWNSHIP PARKWAY TO SR 3128 (LAWYERS ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5007 | REGION E | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 100000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 58699000 | 169199000
MECKLENBURG | NC 51 (MATTHEWS TOWNSHIP PARKWAY) | SR 3356 (SARDIS ROAD) TO SR 1010 (EAST JOHN STREET/ MONROE ROAD). WIDEN EXISTING ROADWAY. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5763 | REGION E | SCHEDULED FOR DELIVERY | T | 2026 | 16000000 | 2026 | 5600000 | 2029 | 21700000 | 43300000
MECKLENBURG | NC 73 | NC 115 TO SR 2693 (DAVIDSON-CONCORD ROAD). | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | R-2632AB | REGION E | SCHEDULED FOR DELIVERY | NHP | 2023 | 4400000 | 2023 | 4700000 | 2026 | 46900000 | 56000000
MECKLENBURG | NC 73 | VANCE ROAD EXTENSION/BEATTIES FORD ROAD TO SR 5544 (WEST CATAWBA AVENUE). | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | R-5721B | REGION E | SCHEDULED FOR DELIVERY | T | 2023 | 15497000 | 2023 | 3000000 | 2026 | 28099000 | 46596000
MECKLENBURG | NC 73 (SAM FURR ROAD) | SR 5544 (WEST CATAWBA AVENUE) TO SR 2316 (NORTHCROSS DRIVE). WIDEN EXISTING ROADWAY. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5765 | REGION E | SCHEDULED FOR DELIVERY | T | 2023 | 58500000 | 2023 | 7500000 | 2026 | 31499000 | 97499000 | COORDINATE WITH R-5721.
MECKLENBURG | NEW ROUTE | SR 3168 (SAM NEWELL ROAD) TO SR 5215 (NORTHEAST PARKWAY. CONSTRUCT MULTI-LANES ON NEW LOCATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6166 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 6600000 | NOT FUNDED | 500000 | NOT FUNDED | 8498000 | 15598000
MECKLENBURG | SR 1009 (JOHN STREET-OLD MONROE ROAD) | SR 3448-SR 3474 (TRADE STREET) TO WEST OF I-485. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-4714AA | DIVISION 10 | SCHEDULED FOR DELIVERY | BGANY, T | 2028 | 9148000 | 2028 | 1900000 | 2030 | 14300000 | 25348000
MECKLENBURG | SR 1441 (CAROWINDS BOULEVARD EXTENSION) | NC 49 (SOUTH TRYON STREET TO NC 160 (STEELE CREEK ROAD). CONSTRUCT TWO LANE DIVIDED ROADWAY ON NEW LOCATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6168 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 9700000 | NOT FUNDED | 1600000 | NOT FUNDED | 18800000 | 30100000
MECKLENBURG | SR 2136 (GILEAD ROAD) | US 21 (STATESVILLE ROAD) TO NC 115. WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5807 | DIVISION 10 | SCHEDULED FOR DELIVERY | T | 2028 | 33700000 | 2028 | 2000000 | 2030 | 8700000 | 44400000
MECKLENBURG | SR 2467 (MALLARD CREEK ROAD) | SR 2472 (MALLARD CREEK CHURCH ROAD) TO BREEZEWOOD DRIVE. WIDEN TO FOUR-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6028 | DIVISION 10 | SCHEDULED FOR DELIVERY | T | 2026 | 7700000 | 2026 | 4000000 | 2028 | 20400000 | 32100000
MECKLENBURG | SR 3440 (MCKEE ROAD) EXTENSION | SR 3448 (PLEASANT PLAINS ROAD) TO SR 1009 (JOHN STREET) | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-4713A | DIVISION 10 | SCHEDULED FOR DELIVERY | L, T | 2020 | 2680000 | 2021 | 500000 | 2024 | 6260000 | 9440000 | BUILD NC BOND FUNDING: $888,488 FOR PE, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $280,117 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR 1 SALE); $4M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE)
MECKLENBURG | SR 3687 (PARK ROAD) | JOHNSTON ROAD TO NC 51 (PINEVILLE-MATTHEWS ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6165 | NOT FUNDED | WILL BE REPRIORITIZED | BGANY | NOT FUNDED | 21255000 | NOT FUNDED | 2000000 | NOT FUNDED | 9400000 | 32655000
MECKLENBURG | SR 4979 (BALLANTYNE COMMONS PARKWAY) | ANNALEXA LANE TO WILLIAMS POND LANE. WIDEN TO FOUR-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6030 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 22700000 | NOT FUNDED | 4610000 | NOT FUNDED | 24298000 | 51608000
MECKLENBURG | SR 5544 (WEST CATAWBA AVENUE) | NC 73 (SAM FURR ROAD) TO SR 2151 (JETTON ROAD). WIDEN TO FOUR-LANES DIVIDED. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | R-2555B | DIVISION 10 | SCHEDULED FOR DELIVERY | L, T |  |  |  |  | 2025 | 26520000 | 26520000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $12M FOR CONSTRUCTION, PAYBACK FY 2025-2026 (FY 2024 / YR 5/6 SALE).
MECKLENBURG | US 21 | SR 2136 (GILEAD ROAD) TO HOLLY POINT DRIVE. WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5771 | REGION E | SCHEDULED FOR DELIVERY | BA, T | 2022 | 52600000 | 2022 | 1640000 | 2025 | 22401000 | 76641000
MECKLENBURG | US 21 (STATESVILLE ROAD) | NORTHCROSS CENTER COURT TO SR 2147 (WESTMORELAND ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5767 | REGION E | SCHEDULED FOR DELIVERY | T | 2026 | 39080000 | 2026 | 4400000 | 2029 | 27302000 | 70782000 | BUILD NC BOND FUNDING: $11.8M FOR RIGHT OF WAY PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE)
MECKLENBURG | US 521 (LANCASTER HIGHWAY/ JOHNSTON ROAD) | SOUTH CAROLINA STATE LINE TO SR 4979 (BALLANTYNE COMMONS PARKWAY). WIDEN TO MULTILANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6109 | REGION E | SCHEDULED FOR DELIVERY | NHP | 2024 | 5000000 | 2024 | 1700000 | 2026 | 47400000 | 54100000
MECKLENBURG | US 74 | SHARON FOREST DRIVE AND HARRIS BOULEVARD/VILLAGE LAKE DRIVE INTERSECTION AREA. CONSTRUCT GRADE SEPARATION AT SHARON FOREST DRIVE AND INTERCHANGE AT VILLAGE LAKE DRIVE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2509AA | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | NHP | 2024 | 64400000 | 2024 | 1800000 | 2027 | 40400000 | 106600000 | SEGMENTS C1, C2
MECKLENBURG | US 74 | SARDIS ROAD AND SAM NEWELL ROAD INTERSECTION AREA. CONSTRUCT INTERCHANGES AT SARDIS ROAD NORTH AND SAM NEWELL ROAD, CONSTRUCT EXTENSION OF SARDIS ROAD NORTH FROM US 74 TO AREQUIPA DRIVE EXTENSION, AND CONSTRUCT EXTENSION OF AREQUIPA DRIVE FROM SARDIS ROA | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2509AB | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | NHP | 2024 | 66500000 | 2024 | 2700000 | 2027 | 45306000 | 114506000 | SEGMENTS C6, C7A, C8
MECKLENBURG | US 74 | INDEPENDENCE POINTE PARKWAY. CONSTRUCT ROADWAY ON NEW LOCATION FROM WINDSOR SQUARE DRIVE TO NC 51 (MATTHEWS TOWNSHIP PARKWAY). | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2509AC | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | NHP | 2024 | 18200000 | 2024 | 3000000 | 2027 | 11200000 | 32400000 | SEGMENT C11
MECKLENBURG | US 74 | MATTHEWS-MINT HILL ROAD INTERSECTION AREA. CONSTRUCT INTERCHANGE AT MATTHEWS-MINT HILL ROAD AND EXTENSION OF NORTHEAST PARKWAY FROM OVERCASH DRIVE TO WAITING STREET. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2509AD | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | NHP | 2024 | 51600000 | 2024 | 1800000 | 2027 | 27000000 | 80400000 | SEGMENT C10, C13
MECKLENBURG | US 74 | WEST OF IDLEWILD ROAD TO WALLACE LANE. ADD GENERAL PURPOSE AND EXPRESS LANES AND CONSTRUCT EXPRESS LANE INTERCHANGE ON WEST SIDE OF CONFERENCE DRIVE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2509B | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | NHP | 2024 | 26000000 | 2024 |  | 2027 | 25250000 | 51250000 | SEGMENT M1
MECKLENBURG | US 74 | WALLACE LANE TO SARDIS ROAD. ADD GENERAL PURPOSE AND EXPRESS LANES AND CONSTRUCT EXPRESS LANE INTERCHANGE AT SARDIS ROAD. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2509C | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | NHP | 2024 | 39200000 | 2024 | 5600000 | 2027 | 70350000 | 115150000 | SEGMENT M2
MECKLENBURG | US 74 | SARDIS ROAD TO I-485. ADD GENERAL PURPOSE AND EXPRESS LANES, CONSTRUCT EXPRESS LANE INTERCHANGES AT I-485 AND EAST SIDE OF CONFERENCE DRIVE, AND RECONSTRUCT INTERCHANGE AT NC 51 (MATTHEWS TOWNSHIP PARKWAY). | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2509D | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 92300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 202206000 | 304806000 | SEGMENTS C14, M3
MECKLENBURG | US 74 (INDEPENDENCE BOULEVARD) | I-277 TO WEST OF IDLEWILD ROAD. WIDEN ROADWAY TO ALLOW FOR TWO-WAY EXPRESS LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6103 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 93200000 | 104800000
MECKLENBURG | US 74 PARALLEL ROUTES | KREFELD DRIVE, AREQUIPA DRIVE, AND INDEPENDENCE POINTE PARKWAY. CONSTRUCT MULTIPLE SEGMENTS, PART ON NEW LOCATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2509E | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 55800000 | NOT FUNDED | 4100000 | NOT FUNDED | 69400000 | 129300000 | SEGMENTS C3, C4, C5, C7B, C9, C12
MECKLENBURG | CLANTON ROAD | EXTEND CLANTON ROAD TO US 29/74 (WILKINSON BOULEVARD) WITH A GRADE SEPARATION OF NORFOLK SOUTHERN RAILROAD AND CLOSE THE DONALD ROSS ROAD CROSSING. | RAIL | 10 | CHARLOTTE REGIONAL TPO | P-5730 | REGION E | SCHEDULED FOR DELIVERY | O, T | 2024 | 4400000 |  |  | 2025 | 15865000 | 20265000
MECKLENBURG, CABARRUS | NC 73 (DAVIDSON HIGHWAY) | EAST OF SR 2693 (DAVIDSON-CONCORD ROAD) TO EAST OF SR 1394 (POPLAR TENT ROAD). | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | R-5706A | REGION E | SCHEDULED FOR DELIVERY | NHP | 2024 | 7000000 | 2024 | 2900000 | 2026 | 29600000 | 39500000
MECKLENBURG, CABARRUS | SR 2467 (MALLARD CREEK ROAD)/ SR 1445 (DERITA ROAD | I-485 TO CONCORD MILLS BOULEVARD (SR 2894). WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | U-6032 | DIVISION 10 | SCHEDULED FOR DELIVERY | T | 2022 | 14400000 | 2022 | 2600000 | 2025 | 27525000 | 44525000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $6M FOR CONSTRUCTION, PAYBACK FY 2025-2038 (FY 2024 / YR 6 SALE)
MITCHELL | NC 226 | BLUE RIDGE PARKWAY TO SR 1274 (SUMMIT AVENUE). WIDEN TO 3-LANES. | HIGHWAY | 13 | HIGH COUNTRY RPO | R-5804 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 15900000 | NOT FUNDED | 3200000 | NOT FUNDED | 33298000 | 52398000
MONTGOMERY | NC 109 | SR 1127 (HEARNE FARM ROAD) TO SR 1174 (PEE DEE ROAD). | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-5826B | DIVISION 8 | SCHEDULED FOR DELIVERY | T | 2023 | 500000 | 2023 | 105000 | 2026 | 8800000 | 9405000
MONTGOMERY | NC 24 / NC 27 | NC 73 TO TROY BYPASS. WIDEN TO MULTILANES. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-2527 | REGION E | SCHEDULED FOR DELIVERY | BGLT5, T | 2019 | 854000 |  |  | 2024 | 91402000 | 92256000 | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $6.062 MILLION FOR PE AND $665,000 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE)
MOORE | SR 2055 (NORTH POPLAR STREET) | JOHNSON STREET TO US 1 (SANDHILLS BOULEVARD) IN ABERDEEN. CONSTRUCT SIDEWALK. | BIKE/PED | 8 | TRIANGLE AREA RPO | EB-6001 | DIVISION 8 | SCHEDULED FOR DELIVERY | L, TA5200 | 2024 | 27000 |  |  | 2025 | 272000 | 299000 | COORDINATE WITH U-5815
MOORE | VARIOUS | CONSTRUCT PEDESTRIAN IMPROVEMENTS AT 5 INTERSECTIONS AND ONE MID-BLOCK LOCATION IN THE CENTRAL BUSINESS DISTRICT OF ABERDEEN. | BIKE/PED | 8 | TRIANGLE AREA RPO | EB-6005 | NOT FUNDED | WILL BE REPRIORITIZED | L, TA5200 |  |  |  |  | NOT FUNDED | 147000 | 147000
MOORE | NC 211 | NC 73 IN WEST END TO WEST OF SR 1241 (HOLLY GROVE SCHOOL ROAD). WIDEN TO MULTILANES. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5726 | REGION E | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2025 | 32500000 | 32500000 | RIGHT-OF-WAY IN PROGRESS
MOORE | NC 24 / NC 27 | SR 1006 (GLENDON-CARTHAGE ROAD) IN CARTHAGE. IMPROVE INTERSECTION AND ADJACENT INTERSECTIONS OF EACH FACILITY WITH US 15 / US 501. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5929 | DIVISION 8 | SCHEDULED FOR DELIVERY | T | 2023 | 200000 | 2023 | 1100000 | 2025 | 6100000 | 7400000 | COORDINATE WITH U-3628
MOORE | NC 24 / NC 27 | COURTHOUSE WEST OF NC 22 (MCNEILL STREET) TO US 15 / US 501 IN CARTHAGE. WIDEN TO THREE LANES WITH CURB AND GUTTER AND BICYCLE / PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-3628 | REGION E | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2025 | 3000000 | 3000000 | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH R-5929
MOORE | NC 5 | US 1 IN ABERDEEN TO THE INTERSECTION OF TROTTER DRIVE / BLAKE BOULEVARD IN PINEHURST. WIDEN TO MULTILANES. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5756 | REGION E | SCHEDULED FOR DELIVERY | T | 2023 | 5300000 | 2023 | 5818000 | 2025 | 33999000 | 45117000
MOORE | NC 5 (BEULAH HILL ROAD) | INTERSECTION OF TROTTER DRIVE / BLAKE BOULEVARD TO NC 211 IN PINEHURST. ADD TURN LANES, SIGNAL IMPROVEMENTS, AND OTHER OPERATIONAL IMPROVEMENTS ALONG CORRIDOR AS APPROPRIATE. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5892 | REGION E | SCHEDULED FOR DELIVERY | T | 2028 | 20105000 | 2028 | 1892000 | 2030 | 17500000 | 39497000
MOORE | NC 690 (LOBELIA ROAD) | US 1 IN VASS TO CUMBERLAND COUNTY LINE. UPGRADE ROADWAY, TO INCLUDE TURN LANES AT VARIOUS LOCATIONS AND SOME REALIGNMENT. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5824 | REGION E | SCHEDULED FOR DELIVERY | T | 2023 | 1700000 | 2023 | 1100000 | 2025 | 31200000 | 34000000
MOORE | US 1 (SANDHILLS BOULEVARD) | SR 1112 (ROSELAND ROAD) TO KNIGHT STREET IN ABERDEEN. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5815A | REGION E | SCHEDULED FOR DELIVERY | T | 2025 | 700000 | 2025 | 1600000 | 2027 | 4401000 | 6701000
MOORE | US 1 (SANDHILLS BOULEVARD) | KNIGHT STREET IN ABERDEEN TO OLD US 1 IN SOUTHERN PINES, TO INCLUDE SR 1112 (ROSELAND ROAD) REALIGNMENT AT US1 AND RADII IMPROVEMENT I AT US 15 / US 501 / NC 211. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5815B | REGION E | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2025 | 25100000 | 25100000 | RIGHT-OF-WAY IN PROGRESS
MOORE | US 15 / US 501 | NC 2 AND NC 211 TRAFFIC CIRCLE IN PINEHURST TO NC 73. WIDEN TO MULTILANES. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5927 | DIVISION 8 | SCHEDULED FOR DELIVERY | T | 2026 | 1200000 | 2026 | 4100000 | 2029 | 43701000 | 49001000
MOORE | US 15 / US 501 | SR 1905 (VOIT GILMORE LANE) IN SOUTHERN PINES TO SR 1208 PAGE ROAD IN PINEHURST. UPGRADE SR 1208 INTERSECTION AND CONSTRUCT IMPROVEMENTS TO PINEHURST TRAFFIC CIRCLE AND APPROACHES. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5976 | DIVISION 8 | SCHEDULED FOR DELIVERY | T | 2024 | 25800000 | 2024 | 630000 | 2026 | 30971000 | 57401000 | BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE)
MOORE | US 15 / US 501 / NC 211 | SR 1205 / SR 1309 (MORGANTON ROAD) IN SOUTHERN PINES. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5891 | REGION E | SCHEDULED FOR DELIVERY | T | 2027 | 1900000 | 2027 | 1180000 | 2029 | 20600000 | 23680000
MOORE | US 15 / US 501 / NC 211 | US 1 (SANDHILLS BOULEVARD) IN ABERDEEN TO BRUCEWOOD ROAD IN SOUTHERN PINES. ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5814 | REGION E | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2025 | 14700000 | 14700000 | RIGHT-OF-WAY IN PROGRESS; COORDINATE WITH U-5815
MOORE, MONTGOMERY | NC 24 / NC 27 | I-73 / I-74 / US 220 TO SR 1644 (OLD GLENDON ROAD). MODERNIZE ROADWAY. | HIGHWAY | 8 | TRIANGLE AREA RPO, PIEDMONT TRIAD RPO | R-5932 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 5800000 | NOT FUNDED | 14400000 | NOT FUNDED | 50200000 | 70400000
NASH | US 301 BUSINESS (CHURCH STREET) | US 64 TO NC 97 (RALEIGH BOULEVARD) OVERPASS. CONSTRUCT STREETSCAPE IMPROVEMENTS. ADD SIDEWALK AND BICYCLE LANES. | BIKE/PED | 4 | ROCKY MOUNT URBAN AREA MPO | EB-5761 | DIVISION 4 | SCHEDULED FOR DELIVERY | L, TA5200 | 2024 |  |  |  | 2025 | 2000000 | 2000000
NASH | US 64 BUSINESS (THOMAS STREET) | SR 1005 (EAST RALEIGH BOULEVARD TO US 64 BUSINESS (SUNSET AVENUE) IN ROCKY MOUNT. ADD PEDESTRIAN SIGNALS. | BIKE/PED | 4 | ROCKY MOUNT URBAN AREA MPO | EB-5905 | DIVISION 4 | SCHEDULED FOR DELIVERY | BG5200, L |  |  |  |  | 2027 | 96000 | 96000
NASH | NC 43 | SR 1613 (WOODRUFF AVENUE) TO I-95. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | U-2561C | DIVISION 4 | SCHEDULED FOR DELIVERY | T | 2026 | 3132000 | 2026 | 2968000 | 2028 | 7600000 | 13700000 | PLANNING/DESIGN IN PROGRESS.
NASH | NC 48 | SR 1524 (RED OAK/BATTLEBORO ROAD) TO NC 4. WIDEN TO MULTI-LANES. | HIGHWAY | 4 | ROCKY MOUNT URBAN AREA MPO | U-5911 | DIVISION 4 | SCHEDULED FOR DELIVERY | T | 2025 | 69000 | 2025 | 2136000 | 2027 | 5625000 | 7830000
NASH | TAR RIVER TRANSIT | ENLARGE DRIVERS BREAKROOM | PUBLIC TRANSIT | 4 | ROCKY MOUNT URBAN AREA MPO | TD-5281 | DIVISION 4 | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2025 | 15000 | 15000
NASH, EDGECOMBE | US 64 | NC 58 (WASHINGTON STREET), EXIT 459, TO SR 1233 (THOMAS ROAD) OVERPASS. UPGRADE TO INTERSTATE STANDARDS. | HIGHWAY | 4 | ROCKY MOUNT URBAN AREA MPO | U-6149 | NOT FUNDED | WILL BE REPRIORITIZED | NHP | NOT FUNDED | 11800000 | NOT FUNDED | 2200000 | NOT FUNDED | 137000000 | 151000000
NEW HANOVER | INTERNATIONAL (ILM) WILMINGTON | INCREASE WIDTH OF ALL TAXIWAYS. | AVIATION | 3 | WILMINGTON URBAN AREA MPO | AV-5796 | NOT FUNDED | WILL BE REPRIORITIZED | O, T |  |  |  |  | NOT FUNDED | 500000 | 500000 | OTHER FUNDS PROVIDED BY ILM.
NEW HANOVER | WILIMINGTON INTERNATION (ILM) | TAXIWAY J IMPROVEMENTS. | AVIATION | 3 | WILMINGTON URBAN AREA MPO | AV-5886 | NOT FUNDED | WILL BE REPRIORITIZED | O, T |  |  |  |  | NOT FUNDED | 500000 | 500000 | OTHER FUNDS PROVIDED BY ILM.
NEW HANOVER | WILMINGTON INTERNATIONAL (ILM) | EXPAND THE GENERAL AVIATION APRON. | AVIATION | 3 | WILMINGTON URBAN AREA MPO | AV-5795 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | O, T |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 500000 | 500000 | OTHER FUNDS PROVIDED BY ILM.
NEW HANOVER | WILMINGTON INTERNATIONAL (ILM) | TAXIWAY IMPROVEMENTS. | AVIATION | 3 | WILMINGTON URBAN AREA MPO | AV-5798 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | O, T |  |  |  |  | 2028 | 500000 | 500000 | OTHER FUNDS PROVIDED BY ILM.
NEW HANOVER | WILMINGTON INTERNATIONAL (ILM) | WIDEN NORTH-SOUTH TAXIWAY SYSTEM. | AVIATION | 3 | WILMINGTON URBAN AREA MPO | AV-5799 | NOT FUNDED | WILL BE REPRIORITIZED | O, T |  |  |  |  | NOT FUNDED | 500000 | 500000 | OTHER FUNDS PROVIDED BY ILM.
NEW HANOVER | WILMINGTON INTERNATIONAL AIRPORT (ILM) | REHABILITATE RUNWAY. | AVIATION | 3 | WILMINGTON URBAN AREA MPO | AV-5885 | NOT FUNDED | WILL BE REPRIORITIZED | O, T |  |  |  |  | NOT FUNDED | 500000 | 500000 | OTHER FUNDS PROVIDED BY ILM.
NEW HANOVER | SR 1219 (SOUTH 17TH STREET) | HARBOUR DRIVE TO SHIPYARD BOULEVARD. CONSTRUCT MULTI-USE PATH. | BIKE/PED | 3 | WILMINGTON URBAN AREA MPO | EB-5600 | DIVISION 3 | SCHEDULED FOR DELIVERY | BGANY, L | 2024 | 24000 |  |  | 2024 | 590000 | 614000 | PLANNING, DESIGN, RIGHT-OF-WAY, AND CONSTRUCTION BY CITY OF WILMINGTON.
NEW HANOVER | NC 132 (COLLEGE ROAD) | SR 1272 (NEW CENTRE DRIVE) TO US 117 (SHIPYARD BOULEVARD). ACCESS MANAGEMENT AND TRAVEL TIME IMPROVEMENTS. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5702A | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | NHP | 2028 | 15148000 | 2028 | 5380000 | 2030 | 16000000 | 36528000 | PLANNING/DESIGN IN PROGRESS. PROJECT TO BE LET WITH U-5704.
NEW HANOVER | NC 132 (COLLEGE ROAD) | US 117 (SHIPYARD BOULEVARD) TO US 421 (CAROLINA BEACH ROAD). ACCESS MANAGEMENT AND TRAVEL TIME IMPROVEMENTS. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5702B | NOT FUNDED | WILL BE REPRIORITIZED | NHP | NOT FUNDED | 14240000 | NOT FUNDED | 8592000 | NOT FUNDED | 33800000 | 56632000
NEW HANOVER | NC 132 (COLLEGE ROAD) | US 76 (OLEANDER DRIVE). INTERSECTION IMPROVEMENTS. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5704 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 21183000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2422000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 14100000 | 37705000 | PROJECT TO BE LET WITH U-5702A.
NEW HANOVER | NC 132 (COLLEGE ROAD) | SR 2048 (GORDON ROAD) TO SR 1272 (NEW CENTRE DRIVE). UPGRADE ROADWAY. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5881 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 20192000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8128000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 74300000 | 102620000 | PROJECT TO BE LET WITH U-5792.
NEW HANOVER | NC 133 (CASTLE HAYNE ROAD) | I-140/US 17 (WILMINGTON BYPASS) TO SR 1310 (DIVISION DRIVE) IN WILMINGTON. WIDEN TO MULTI-LANES | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5863 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 4800000 | NOT FUNDED | 4600000 | NOT FUNDED | 26800000 | 36200000
NEW HANOVER | NC 133 (CASTLE HAYNE ROAD) | NORTH 23RD STREET. CONSTRUCT A ROUNDABOUT. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5954 | REGION B | SCHEDULED FOR DELIVERY | T | 2025 | 721000 | 2025 | 507000 | 2027 | 3800000 | 5028000
NEW HANOVER | SR 1175 (KERR AVENUE) | SR 1175 (KERR AVENUE) INTERCHANGE AT US 74 (MLK, JR. PARKWAY). | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-3338C | REGION B | SCHEDULED FOR DELIVERY | BGANY |  |  |  |  | 2026 | 26800000 | 26800000 | RIGHT-OF-WAY IN PROGRESS
NEW HANOVER | SR 1175 (KERR AVENUE) | SR 1411 (WRIGHTSVILLE AVENUE) TO US 76 (OLEANDER DRIVE). CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-6201 | DIVISION 3 | SCHEDULED FOR DELIVERY | T | 2028 | 4200000 | 2028 | 400000 | 2030 | 4498000 | 9098000
NEW HANOVER | SR 1209 (INDEPENDENCE BOULEVARD EXTENSION) | RANDALL PARKWAY TO US 74 (MLK, JR. PARKWAY) IN WILMINGTON. MULTI-LANES ON NEW LOCATION. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-4434 | DIVISION 3 | SCHEDULED FOR DELIVERY | BGANY | 2026 | 88700000 | 2026 | 3632000 | 2028 | 122350000 | 214682000
NEW HANOVER | SR 2048 (GORDON ROAD) | US 17 (MARKET STREET) TO I-40. WIDEN ROADWAY. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-6202 | DIVISION 3 | SCHEDULED FOR DELIVERY | T | 2022 | 12835000 | 2022 | 5300000 | 2024 | 33600000 | 51735000 | BUILD NC BOND FUNDING: $5,000,000 FOR RIGHT-OF-WAY PAYBACK 2022 - 2036 (FY 2022 / YR 4 SALE).
NEW HANOVER | US 17 BUSINESS (MARKET STREET) | CSX RAILROAD TO CINEMA DRIVE; JACKSONVILLE STREET TO NORTH OF US 117/NC 132 (COLLEGE ROAD). | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-4902B | REGION B | SCHEDULED FOR DELIVERY | T | 2027 | 10000000 | 2027 | 2900000 | 2029 | 9700000 | 22600000
NEW HANOVER | US 17 BUSINESS (MARKET STREET) | NORTH OF US 117/NC 132 (COLLEGE ROAD) TO STATION ROAD. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-4902C | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | T | 2027 | 46089000 | 2027 | 10811000 | 2029 | 55100000 | 112000000 | INCLUDES U-5880.
NEW HANOVER | US 421 | US 421 (BURNETT AVENUE) TO US 117 (SHIPYARD BOULEVARD) IN WILMINGTON. UPGRADE ROADWAY. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5729REG | REGION B | SCHEDULED FOR DELIVERY | T | 2027 | 21200000 | 2027 | 6560000 | 2029 | 16160000 | 43920000
NEW HANOVER | US 421 | US 117 (SHIPYARD BOULEVARD). INTERSECTION IMPROVEMENTS. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5729SW | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | T | 2027 | 5300000 | 2027 | 1640000 | 2029 | 4040000 | 10980000
NEW HANOVER | US 421 (CAROLINA BEACH ROAD) | NC 132 (SOUTH COLLEGE ROAD) TO SANDERS ROAD IN WILMINGTON. WIDEN EXISTING ROADWAY AND CONSTRUCT FLYOVERS AT US 421 AND NC 132. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5790 | DIVISION 3 | SCHEDULED FOR DELIVERY | T | 2027 | 6065000 | 2027 | 6428000 | 2029 | 20500000 | 32993000
NEW HANOVER | US 421 (SOUTH FRONT STREET) | US 17 BUSINESS/US 76/US 421 (CAPE FEAR MEMORIAL BRIDGE) TO US 421 (BURNETT BOULEVARD) IN WILMINGTON. WIDEN TO MULTI-LANES. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5734 | REGION B | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 13940000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1032000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10299000 | 25271000
NEW HANOVER | US 74 | US 17/US 421 IN WILMINGTON. CONSTRUCT A FLY-OVER AND FREE FLOW RAMP AT INTERCHANGE. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5731 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | T | 2026 | 5200000 | 2026 | 241000 | 2028 | 31499000 | 36940000
NEW HANOVER | US 74 (EASTWOOD ROAD) | SR 1409 (MILITARY CUTOFF ROAD) INTERSECTION IN WILMINGTON. CONVERT AT-GRADE INTERSECTION TO AN INTERCHANGE. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5710 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | NHP | 2023 | 22700000 | 2023 | 5200000 | 2025 | 38500000 | 66400000
NEW HANOVER | US 74 (MARTIN LUTHER KING, JR. PARKWAY) | US 117/NC 132 (COLLEGE ROAD) IN WILMINGTON. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5792 | DIVISION 3 | SCHEDULED FOR DELIVERY | T | 2024 | 4753000 | 2024 | 2696000 | 2026 | 40305000 | 47754000 | PROJECT TO BE LET WITH U-5881. BUILD NC BOND FUNDING: $15,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE).
NEW HANOVER | US 76 (OLEANDER DRIVE) | GREENVILLE LOOP ROAD AND GREENVILLE AVENUE. UPGRADE INTERSECTION. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-6128 | NOT FUNDED | WILL BE REPRIORITIZED | BGANY | NOT FUNDED | 3700000 | NOT FUNDED | 600000 | NOT FUNDED | 3600000 | 7900000
NEW HANOVER | WILMINGTON | WILMINGTON CITYWIDE SIGNAL SYSTEM. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-6199 | DIVISION 3 | SCHEDULED FOR DELIVERY | T | 2028 | 100000 | 2028 | 950000 | 2030 | 15360000 | 16410000
NORTHAMPTON | NC 305 | SEABOARD TOWN LIMITS TO HERTFORD COUNTY LINE. UPGRADE ROADWAY. | HIGHWAY | 1 | PEANUT BELT RPO | R-5757 | DIVISION 1 | SCHEDULED FOR DELIVERY | BGLT5 | 2023 | 1524000 | 2023 | 4122000 | 2024 | 46500000 | 52146000
NORTHAMPTON | NC 46 | NC 48 IN GASTON TO THE VIRGINIA STATE LINE. UPGRADE AND WIDEN EXISTING FACILITY. | HIGHWAY | 1 | PEANUT BELT RPO | R-5739 | DIVISION 1 | SCHEDULED FOR DELIVERY | T | 2022 | 2765000 | 2022 | 10800000 | 2025 | 28100000 | 41665000 | RIGHT-OF-WAY IN PROGRESS.
ONSLOW | ALBERT J. ELLIS AIRPORT (OAJ) | EXTEND RUNWAY 23 AND TAXIWAY A. | AVIATION | 3 | JACKSONVILLE URBAN AREA MPO | AV-5806 | REGION B | SCHEDULED FOR DELIVERY | O, T |  |  |  |  | 2025 | 300000 | 300000 | OTHER FUNDS ARE AIRPORT FUNDS
ONSLOW | NC 210 | US 17 TO SOUTH OF SR 1518 (OLD FOLKSTONE ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5949 | REGION B | SCHEDULED FOR DELIVERY | T | 2028 | 8344000 | 2028 | 17594000 | 2030 | 69901000 | 95839000
ONSLOW | NC 24 | US 258 (RICHLANDS HIGHWAY) INTERSECTION. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5716 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | T | 2027 | 26700000 | 2027 | 2700000 | 2029 | 40700000 | 70100000 | PROJECT BEING LET WITH U-5739
ONSLOW | NC 24 (LEJEUNE BOULEVARD) | NC 53 (WESTERN BOULEVARD) IN JACKSONVILLE. UPGRADE INTERSECTION AND DRAINAGE. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5508 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | T | 2027 | 799000 | 2027 | 150000 | 2029 | 1650000 | 2599000 | COMBINE WITH U-5736 AND U-4007E.
ONSLOW | NC 24 (LEJEUNE BOULEVARD) | NC 24 BUSINESS (JOHNSON BOULEVARD) TO NC 172. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5741 | REGION B | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7367000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3664000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 49600000 | 60631000 | PROJECT INCLUDES B-5650
ONSLOW | NC 24 (WEST CORBETT AVENUE) | BELGRADE-SWANSBORO ROAD TO FRONT STREET. CONSTRUCT SUPERSTREET. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | R-5885 | NOT FUNDED | WILL BE REPRIORITIZED | NHP | NOT FUNDED | 15304000 | NOT FUNDED | 802000 | NOT FUNDED | 28699000 | 44805000
ONSLOW | NC 53 | NC 53: FROM US 17 (MARINE BOULEVARD) TO SR 2716 (EXCHANGE DRIVE). | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-4007E | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | T | 2027 | 8100000 | 2027 | 400000 | 2029 | 7200000 | 15700000 | COMBINED WITH U-5736 AND U-5508.
ONSLOW | NC 53 (WESTERN BOULEVARD) | US 17 (MARINE BOULEVARD) TO NC 24 (LEJEUNE BOULEVARD) IN JACKSONVILLE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5736 | REGION B | SCHEDULED FOR DELIVERY | T | 2027 | 10500000 | 2027 | 2440000 | 2029 | 31300000 | 44240000 | COMBINED WITH U-4007E AND U-5508.
ONSLOW | NC 53 (WESTERN BOULEVARD) | SR 2714 (JACKSONVILLE PARKWAY). IMPROVE INTERSECTION. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5789 | REGION B | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2025 | 4550000 | 4550000 | RIGHT-OF-WAY IN PROGRESS
ONSLOW | NC 53 (WESTERN BOULEVARD) | SR 1308 (GUM BRANCH ROAD) TO US 17 (MARINE BOULEVARD). UPGRADE TO SUPERSTREET. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-6081 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 2400000 | NOT FUNDED | 1000000 | NOT FUNDED | 50800000 | 54200000
ONSLOW | SR 1308 (BELL FORK ROAD) | SR 1403 (COUNTRY CLUB ROAD/HARGETT STREET). IMPROVE INTERSECTION. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-6082 | DIVISION 3 | SCHEDULED FOR DELIVERY | T | 2025 | 1300000 | 2025 | 900000 | 2027 | 4300000 | 6500000
ONSLOW | SR 1308 (GUM BRANCH ROAD) | SR 1322 (SUMMERSILL SCHOOL ROAD) TO SR 1324 (RAMSEY ROAD). | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5793A | DIVISION 3 | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9200000 | 17000000
ONSLOW | SR 1308 (GUM BRANCH ROAD) | SR 1324 (RAMSEY ROAD) TO SR 1390 (COUNTRY CLUB BOULEVARD). | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5793B | DIVISION 3 | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 15600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 40100000 | 62800000
ONSLOW | SR 1308 (GUM BRANCH ROAD) | WILLIAMSBURG PARKWAY TO INDIAN DRIVE. UPGRADE TO SUPERSTREET. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-6200 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 2127000 | NOT FUNDED | 1137000 | NOT FUNDED | 8800000 | 12064000
ONSLOW | SR 1336 (HENDERSON ROAD) | SR 1308 (GUM BRANCH ROAD) TO NC 53 (WESTERN BOULEVARD). UPGRADE TO SUPERSTREET. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5903 | DIVISION 3 | SCHEDULED FOR DELIVERY | T | 2028 | 7400000 | 2028 | 4400000 | 2030 | 43600000 | 55400000
ONSLOW | SR 1509 (QUEENS CREEK ROAD) | JONES ROAD TO SR 1565 (SMALLWOOD ROAD). WIDEN ROADWAY. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | R-5948 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 4600000 | NOT FUNDED | 10300000 | NOT FUNDED | 12600000 | 27500000
ONSLOW | SR 2714 | NC 53 (WESTERN BOULEVARD) TO SR 1324 (RAMSEY ROAD). | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5791A | DIVISION 3 | SCHEDULED FOR DELIVERY | T | 2024 | 6708000 | 2024 | 1964000 | 2026 | 43295000 | 51967000 | PLANNING/DESIGN IN PROGRESS. BUILD NC BOND FUNDING: $16,000,000 FOR CONSTRUCTION PAYBACK 2026 - 2040 (FY 2026 / YR 8 SALE).
ONSLOW | SR 2715 (TRADE STREET) | NC 53 (WESTERN BOULEVARD) TO MCDANIEL DRIVE IN JACKSONVILLE. CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5787 | DIVISION 3 | SCHEDULED FOR DELIVERY | T | 2023 | 13600000 | 2023 | 2208000 | 2025 | 5200000 | 21008000
ONSLOW | US 17 | US 17 BUSINESS (MARINE BOULEVARD). UPGRADE AT-GRADE INTERSECTION TO PARTIAL INTERCHANGE. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5951 | REGION B | SCHEDULED FOR DELIVERY | T | 2028 | 400000 | 2028 | 69000 | 2030 | 14200000 | 14669000
ONSLOW | US 17 | NC 172 (SNEADS FERRY ROAD/SR 1518 (OLD FOLKSTONE ROAD). INSTALL SUPER-STREET WITH INTERSECTION IMPROVEMENTS. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-6065 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | HSIP, T | 2024 | 1000000 | 2024 | 1178000 | 2026 | 8701000 | 10879000
ONSLOW | US 17 | MCDANIEL DRIVE /WORKSHOP LANE. UPGRADE INTERSECTION. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-6107 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3000000 | 4100000
ONSLOW | US 17 (WILMINGTON HIGHWAY) | SR 1130 (OLD MAPLEHURST ROAD) IN JACKSONVILLE. CONSTRUCT INTERCHANGE AND ASSOCIATED IMPROVEMENTS TO MCAS NEW RIVER MAIN GATE. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5735 | REGION B | SCHEDULED FOR DELIVERY | T | 2027 | 28865000 | 2027 | 8328000 | 2029 | 51624000 | 88817000
ONSLOW | US 17 BUSINESS (MARINE BOULEVARD) | SR 1308 (BELL FORK ROAD) IN JACKSONVILLE. IMPROVE INTERSECTION. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5728 | REGION B | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2025 | 4000000 | 4000000 | RIGHT-OF-WAY IN PROGRESS
ONSLOW | US 17 BUSINESS (MARINE BOULEVARD) | SR 1336 (HENDERSON DRIVE). IMPROVE INTERSECTION. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5950 | REGION B | SCHEDULED FOR DELIVERY | T | 2025 | 75000 | 2025 | 154000 | 2027 | 825000 | 1054000
ONSLOW | US 258/NC 24 (RICHLANDS HIGHWAY) | SR 1212 (PONY FARM ROAD) TO SR 1213 (BLUE CREEK ROAD). CONSTRUCT SUPERSTREET. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5739 | REGION B | SCHEDULED FOR DELIVERY | T | 2027 | 3500000 | 2027 | 2900000 | 2029 | 19800000 | 26200000 | PROJECT BEING LET WITH WITH U-5716.
ONSLOW | US 258/NC 24 (RICHLANDS HIGHWAY) | SR 1329 (RHODESTOWN FIRE DEPARTMENT ROAD). IMPROVE INTERSECTION. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-6148 | NOT FUNDED | WILL BE REPRIORITIZED | NHP | NOT FUNDED | 329000 | NOT FUNDED | 140000 | NOT FUNDED | 750000 | 1219000
ORANGE | BARNES STREET | KING STREET TO SR 1005 (JONES FERRY ROAD) IN CARRBORO. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5890 | DIVISION 7 | SCHEDULED FOR DELIVERY | L, TAANY | 2024 | 13000 |  |  | 2025 | 184000 | 197000
ORANGE | NC 54 | ANDERSON PARK TO JAMES STREET IN CARRBORO. CONSTRUCT MULTIUSE PATH ON NORTH SIDE OF NC 54. | BIKE/PED | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5994 | DIVISION 7 | WILL BE REPRIORITIZED | L, TAANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 34000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 950000 | 984000
ORANGE | SR 1005 (JONES FERRY ROAD) | DAVIE ROAD TO SR 1010 (WEST MAIN STREET) IN CARRBORO. CONSTRUCT SIDEWALK ON NORTH SIDE. | BIKE/PED | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5880 | DIVISION 7 | SCHEDULED FOR DELIVERY | L, TAANY | 2024 | 25000 |  |  | 2025 | 353000 | 378000
ORANGE | SR 1780 (ESTES DRIVE) | SR 1772 (NORTH GREENSBORO STREET) TO SOUTH OF NORFOLK-SOUTHERN RR TRACKS IN CARRBORO | BIKE/PED | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5886A | DIVISION 7 | SCHEDULED FOR DELIVERY | L, TAANY | 2024 | 37000 |  |  | 2026 | 678000 | 715000 | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CARRBORO. CONSTRUCTION ADMINISTRATION BY DIV. 7.
ORANGE | SR 1780 (ESTES DRIVE) | SOUTH OF NORFOLK-SOUTHERN RR TRACKS TO NC 86 (MARTIN LUTHER KING, JR. BLVD) IN CHAPEL HILL | BIKE/PED | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5886B | DIVISION 7 | SCHEDULED FOR DELIVERY | L, TAANY | 2023 | 691000 |  |  | 2025 | 2483000 | 3174000 | PLANNING / DESIGN / RIGHT-OF-WAY BY TOWN OF CHAPEL HILL. CONSTRUCTION ADMINISTRATION BY DIV. 7.
ORANGE | US 15 / US 501 | WILLOW DRIVE TO SR 1741 / SR 1838 (OLD DURHAM-CHAPEL HILL ROAD) IN CHAPEL HILL. CONSTRUCT MULTIUSE PATHS. | BIKE/PED | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5998 | DIVISION 7 | SCHEDULED FOR DELIVERY | L, TAANY |  |  |  |  | 2026 | 1635000 | 1635000 | COORDINATE WITH U-5304
ORANGE | I-40 | NC 86 UPGRADE TO SUPERSTREET FROM NORTHWOOD DRIVE TO RAMP C/D AT I-40 INTERCHANGE. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-3306AC | REGION D | SCHEDULED FOR DELIVERY | NHP | 2024 | 550000 | 2024 | 450000 | 2026 | 4350000 | 5350000
ORANGE | I-85 | SR 1009 (SOUTH CHURTON STREET) IN HILLSBOROUGH. INTERCHANGE IMPROVEMENTS. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-5967 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | NHP | 2028 | 52800000 | 2028 | 1200000 | 2031 | 57200000 | 111200000
ORANGE | I-85 | NC 86 IN HILLSBOROUGH. UPGRADE INTERCHANGE. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-5984 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 58200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 44100000 | 104400000 | COORDINATE WITH I-305
ORANGE | NC 54 | SR 1006 (ORANGE GROVE ROAD) TO SR 1107 / SR 1937 (OLD FAYETTEVILLE ROAD). CONSTRUCT OPERATIONAL IMPROVEMENTS, INCLUDING BICYCLE/PEDESTRIAN ACCOMMODATIONS | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | R-5821A | REGION D | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7000000 | 17100000
ORANGE | SR 1009 (SOUTH CHURTON STREET) | I-40 TO ENO RIVER IN HILLSBOROUGH. WIDEN TO MULTILANES. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5845 | DIVISION 7 | SCHEDULED FOR DELIVERY | T | 2028 | 10200000 | 2028 | 1200000 | 2031 | 24000000 | 35400000
ORANGE | US 15 / US 501 | NC 86 (SOUTH COLUMBIA STREET). INTERCHANGE IMPROVEMENTS. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5304A | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 10000000 | NOT FUNDED | 1040000 | NOT FUNDED | 22001000 | 33041000
ORANGE | US 15 / US 501 | NC 86 (SOUTH COLUMBIA STREET) TO NC 54 (RALEIGH ROAD). CAPACITY IMPROVEMENTS , WITH SIDEWALKS, WIDE OUTSIDE LANES AND TRANSIT ACCOMMODATIONS. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5304B | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 6000000 | NOT FUNDED | 285000 | NOT FUNDED | 22001000 | 28286000
ORANGE | US 15 / US 501 | NC 54 (RALEIGH ROAD). TO SR 1742 (EPHESUS CHURCH ROAD). CAPACITY IMPROVEMENTS , WITH SIDEWALKS, WIDE OUTSIDE LANES AND TRANSIT ACCOMMODATIONS. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5304D | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 5000000 | NOT FUNDED | 344000 | NOT FUNDED | 30001000 | 35345000
ORANGE | US 15 / US 501 | SR 1902 (MANNING DRIVE). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5304E | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 12000000 | NOT FUNDED | 446000 | NOT FUNDED | 25000000 | 37446000
ORANGE | GO TRIANGLE | UNC HOSPITALS AREA IN CHAPEL HILL. CONSTRUCT NEIGHBORHOOD TRANSIT CENTER TRANSFER STATION. 400; 405; 420; 800; 805; CRX; FCX | PUBLIC TRANSIT | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TD-5284 | REGION D | SCHEDULED FOR DELIVERY | 5307, L, T |  |  |  |  | 2024 | 36000 | 36000
ORANGE, DURHAM | I-85 | WEST OF SR 1006 (ORANGE GROVE ROAD) IN ORANGE COUNTY TO WEST OF SR 1400 (SPARGER ROAD) IN DURHAM COUNTY. ADD LANES. | HIGHWAY | 5, 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-0305 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 17900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 120898000 | 139998000 | COORDINATE WITH I-5967, I-5984 AND U-5845
ORANGE, DURHAM | NC 54 | WEST OF US 15 / US 501 IN ORANGE COUNTY TO EAST OF SR 1110 (BARBEE CHAPEL ROAD) IN DURHAM COUNTY. UPGRADE ROADWAY CORRIDOR. | HIGHWAY | 5, 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5774B | REGION C, D | SCHEDULED FOR DELIVERY | T | 2027 | 43000000 | 2027 | 74000 | 2030 | 23300000 | 66374000
ORANGE, DURHAM | US 15 / US 501 | SR 1742 (EPHESUS CHURCH ROAD) TO I-40. CORRIDOR CAPACITY IMPROVEMENTS. | HIGHWAY | 5, 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5304F | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 6000000 | NOT FUNDED | 726000 | NOT FUNDED | 26999000 | 33725000
PASQUOTANK | US 17 (HUGHES BOULEVARD) | SR 1308 (CHURCH STREET) TO US 17 BUSINESS (NORTH ROAD STREET). ACCESS MANAGEMENT. | HIGHWAY | 1 | ALBEMARLE RPO | U-5940 | REGION A | SCHEDULED FOR DELIVERY | T | 2025 | 15988000 | 2025 | 476000 | 2027 | 12899000 | 29363000
PASQUOTANK | US 17 BUSINESS | SR 1145 (OAK STUMP ROAD). IMPROVE INTERSECTION. | HIGHWAY | 1 | ALBEMARLE RPO | U-5939 | REGION A | SCHEDULED FOR DELIVERY | T | 2024 | 2807000 | 2024 | 299000 | 2025 | 7000000 | 10106000
PENDER | HENDERSON FIELD (ACZ) | APRON EXPANSION. | AVIATION | 3 | CAPE FEAR RPO | AV-5815 | DIVISION 3 | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2024 | 5239000 | 5239000
PENDER | NC 210 | SR 1560 (WATTS LANDING ROAD). CONSTRUCT ROUNDABOUT. | HIGHWAY | 3 | CAPE FEAR RPO | R-5899 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 1044000 | NOT FUNDED | 117000 | NOT FUNDED | 2600000 | 3761000
PENDER | NC 50/NC 210 | SR 1534 (BELT ROAD). CONSTRUCT ROUNDABOUT. | HIGHWAY | 3 | CAPE FEAR RPO | R-5900 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 5000000 | NOT FUNDED | 800000 | NOT FUNDED | 1300000 | 7100000
PENDER | NC 53 | US 117 BUSINESS (WALKER STREET/WILMINGTON STREET). IMPROVE INTERSECTION. | HIGHWAY | 3 | CAPE FEAR RPO | R-5701 | REGION B | SCHEDULED FOR DELIVERY | L, T | 2025 | 10000 | 2025 | 172000 | 2027 | 1450000 | 1632000
PENDER | NC 53 | US 117 BYPASS TO STAG PARK ROAD. WIDEN TO THREE LANES. | HIGHWAY | 3 | CAPE FEAR RPO | R-5850 | DIVISION 3 | SCHEDULED FOR DELIVERY | T | 2023 | 5900000 | 2023 | 1908000 | 2025 | 6300000 | 14108000
PENDER | US 17 | NC 210 (SURF CITY). INTERSECTION IMPROVEMENT AT US 17 AND NC 210 NEAR SURF CITY. | HIGHWAY | 3 | CAPE FEAR RPO | R-5877 | NOT FUNDED | WILL BE REPRIORITIZED | NHP | NOT FUNDED | 6000000 | NOT FUNDED | 2100000 | NOT FUNDED | 11900000 | 20000000
PENDER | US 17 | US 17 FROM SR 1582 (WASHINGTON ACRES ROAD) TO VISTA LANE. CONVERT TO SUPERSTREET. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5732 | REGION B | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2026 | 35900000 | 35900000 | RIGHT OF WAY IN PROGRESS
PENDER, NEW HANOVER | US 17 | US 17 BYPASS SOUTH OF HAMPSTEAD TO NC 210. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | R-3300A | REGION B | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2027 | 146860000 | 146860000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $11,000,000 FOR CONSTRUCTION PAYBACK 2027 - 2040 (FY 2026 / YR 8 SALE).
PERQUIMANS | SR 1300 (NEW HOPE ROAD) | WOODLAND CHURCH ROAD TO WOODVILLE ROAD (SR 1329). MODERNIZE ROADWAY. | HIGHWAY | 1 | ALBEMARLE RPO | R-5939 | DIVISION 1 | SCHEDULED FOR DELIVERY | T | 2028 | 5400000 | 2028 | 1400000 | 2030 | 14100000 | 20900000
PERQUIMANS | US 17 | SR 1336 (HARVEY POINT ROAD) AND SR 1338 (WAYNE FORK ROAD). CONVERT AT-GRADE INTERSECTION TO AN INTERCHANGE. | HIGHWAY | 1 | ALBEMARLE RPO | R-5869A | DIVISION 1 | SCHEDULED FOR DELIVERY | NHP | 2028 | 6000000 | 2028 | 900000 | 2030 | 30000000 | 36900000 | FORMERLY IDENTIFIED AS R-4459
PERQUIMANS | US 17 | SR 1300 (NEW HOPE ROAD). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 1 | ALBEMARLE RPO | R-5869B | DIVISION 1 | SCHEDULED FOR DELIVERY | NHP | 2028 | 3400000 | 2028 | 500000 | 2030 | 19800000 | 23700000 | FORMERLY IDENTIFIED AS R-4458
PERSON | PERSON COUNTY EXECUTIVE AIRPORT (TDF) | EXTEND RUNWAY TO TOTAL LENGTH OF 7000 FT, CONSTRUCT TAXIWAY EXTENSION AND RELOCATE SR 1311 (CATES MILL ROAD). | AVIATION | 5 | KERR-TAR RPO | AV-5818 | DIVISION 5 | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2028 | 15160000 | 15160000
PERSON | US 501 | SOUTH OF US 158 TO NC 157. | HIGHWAY | 5 | KERR-TAR RPO | U-5969A | DIVISION 5 | SCHEDULED FOR DELIVERY | T | 2027 | 7200000 | 2027 | 1288000 | 2029 | 4400000 | 12888000
PERSON | US 501 | NC 157 TO SR 1596 (WEST MOREHEAD STREET) | HIGHWAY | 5 | KERR-TAR RPO | U-5969B | REGION C | SCHEDULED FOR DELIVERY | T | 2023 | 6700000 | 2023 | 917000 | 2025 | 9200000 | 16817000
PERSON | US 501 / NC 49 | SR 1596 (WEST MOREHEAD STREET) TO SR 1601 (NORTH MAIN STREET) | HIGHWAY | 5 | KERR-TAR RPO | U-5969C | REGION C | SCHEDULED FOR DELIVERY | T | 2023 | 6300000 | 2023 | 1346000 | 2025 | 6600000 | 14246000
PITT | NC 11 (MEMORIAL DRIVE) | NC 43 (WEST FIFTH STREET) TO SR 1128 (DAVENPORT FARM ROAD) IN GREENVILLE. CONSTRUCT SIDEWALK. | BIKE/PED | 2 | GREENVILLE URBAN AREA MPO | EB-5981 | NOT FUNDED | WILL BE REPRIORITIZED | L, TA5200 | NOT FUNDED | 32000 |  |  | NOT FUNDED | 1635000 | 1667000
PITT | US 264-A (GREENVILLE BOULEVARD) | US 264-A TO US 13 (DICKINSON AVENUE) IN GREENVILLE. CONSTRUCT SIDEWALK AND CURB AND GUTTER. | BIKE/PED | 2 | GREENVILLE URBAN AREA MPO | EB-5980 | NOT FUNDED | WILL BE REPRIORITIZED | L, TA5200 | NOT FUNDED | 40000 |  |  | NOT FUNDED | 630000 | 670000
PITT | GREENVILLE | GREENVILLE SIGNAL SYSTEM. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-5952 | REGION B | SCHEDULED FOR DELIVERY | BG5200 |  |  | 2026 | 750000 | 2028 | 12000000 | 12750000
PITT | NC 33 | SR 1755 (BLACKJACK-SIMPSON ROAD) TO SR 1760 (MOBLEYS BRIDGE ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO, MID-EAST RPO | U-6215 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 30100000 | NOT FUNDED | 2900000 | NOT FUNDED | 70099000 | 103099000
PITT | NC 33 (10TH STREET) | OXFORD ROAD TO SR 1702 (EVANS STREET). ACCESS MANAGEMENT. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-6125 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 6800000 | NOT FUNDED | 3500000 | NOT FUNDED | 14199000 | 24499000
PITT | NC 43 | SR 1708 (FIRETOWER ROAD) TO SR 1711 (WORTHINGTON ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-5991 | DIVISION 2 | SCHEDULED FOR DELIVERY | T | 2027 | 14000000 | 2027 | 7500000 | 2029 | 30200000 | 51700000
PITT | NC 43 (CHARLES BOULEVARD) | US 264A (GREENVILLE BOULEVARD) TO SR 1726 (BELLS FORK ROAD). ACCESS MANAGEMENT. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-6147 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 5900000 | NOT FUNDED | 800000 | NOT FUNDED | 12001000 | 18701000
PITT | SR 1203 (ALLEN ROAD) | SR 1467 (STANTONSBURG ROAD) TO US 13 (DICKINSON AVENUE EXTENSION). WIDEN TO MULTI-LANES. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-5875 | DIVISION 2 | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2024 | 27800000 | 27800000 | RIGHT-OF-WAY IN PROGRESS.
PITT | SR 1467 (STANTONSBURG ROAD) | SR 1204 (B'S BARBEQUE ROAD) TO NC 11 (MEMORIAL DRIVE). ACCESS MANAGEMENT. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-6195 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 2800000 | NOT FUNDED | 1200000 | NOT FUNDED | 17200000 | 21200000
PITT | SR 1700 (EVANS STREET/ OLD TAR ROAD) | SR 1711 (WORTHINGTON ROAD) IN WINTERVILLE TO US 264 ALTERNATE (GREENVILLE BOULEVARD) IN GREENVILLE. WIDEN TO MULTI-LANES. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-2817 | DIVISION 2 | SCHEDULED FOR DELIVERY | BG5200 | 2019 | 22800000 | 2019 | 3972000 | 2025 | 67545000 | 94317000 | RIGHT-OF-WAY IN PROGRESS.
PITT | SR 1702 (EVANS STREET) | SR 1155 (RED BANKS ROAD) TO WEST 5TH STREET. ACCESS MANAGEMENT. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-6196 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 9500000 | NOT FUNDED | 2900000 | NOT FUNDED | 9300000 | 21700000
PITT | SR 1704 (FOURTEENTH STREET) | RED BANKS ROAD TO SR 1708 (FIRETOWER ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-5917 | DIVISION 2 | SCHEDULED FOR DELIVERY | T | 2019 | 952000 | 2024 | 2772000 | 2026 | 14901000 | 18625000 | RIGHT-OF-WAY IN PROGRESS. TO BE LET WITH U-5785. BUILD NC BOND FUNDING: $793,508.60 FOR ROW PAYBACK 2019 - 2033, $1,349,849 FOR PE PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE).
PITT | SR 1708 (FIRETOWER ROAD) | WEST OF EAST ARLINGTON BOULEVARD TO SR 1704 (FOURTEENTH STREET) IN GREENVILLE. WIDEN TO MULTI-LANES. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-5785 | DIVISION 2 | SCHEDULED FOR DELIVERY | T | 2024 | 17620000 | 2024 | 1000000 | 2026 | 20500000 | 39120000 | TO BE LET WITH U-5917.
PITT | SR 1708 (FIRETOWER ROAD) | SR 1704 (FOURTEENTH STREET) TO NC 33 (EAST 10TH STREET) IN GREENVILLE. WIDEN TO MULTI-LANES. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-5870 | DIVISION 2 | SCHEDULED FOR DELIVERY | T | 2024 | 12616000 | 2024 | 1600000 | 2026 | 28200000 | 42416000
PITT | SR 1711 (WORTHINGTON ROAD) | SR 1725 (COUNTY HOME ROAD). UPGRADE INTERSECTION. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-6197 | DIVISION 2 | SCHEDULED FOR DELIVERY | T | 2027 | 900000 | 2027 | 500000 | 2029 | 1600000 | 3000000
PITT | US 13 (MEMORIAL DRIVE) | NC 43 (5TH STREET). UPGRADE INTERSECTION. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-5730 | REGION B | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2025 | 825000 | 825000 | RIGHT-OF-WAY IN PROGRESS
POLK | I-26 | CONSTRUCT IMPROVEMENTS ON NC 108 AT EXIT 67. | HIGHWAY | 14 | FOOTHILLS RPO | I-4729B | REGION G | SCHEDULED FOR DELIVERY | T | 2019 | 10200000 | 2027 | 2000000 | 2029 | 22599000 | 34799000 | RIGHT-OF-WAY IN PROGRESS
POLK | NC 9 | US 74 TO NC 108. ADD PAVED SHOULDERS. | HIGHWAY | 14 | FOOTHILLS RPO | R-5840 | DIVISION 14 | SCHEDULED FOR DELIVERY | T | 2022 | 2200000 | 2022 | 1400000 | 2025 | 8600000 | 12200000
POLK | US 74 | NC 108 INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | 14 | FOOTHILLS RPO | R-5873 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | NHP |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3200000 | 3400000
RANDOLPH | REGIONAL AIRPORT (HBI) ASHEBORO | CONSTRUCT TAXILANE EXTENSION, EXTEND ACCESS ROAD, AND CONSTRUCT NEW ACCESS ROAD. | AVIATION | 8 | PIEDMONT TRIAD RPO | AV-5858 | DIVISION 8 | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2025 | 3455000 | 3455000
RANDOLPH | SR 1950 (WEST NAOMI STREET) | WEST ACADEMY STREET TO US 220 BUSINESS (SOUTH MAIN STREET) IN RANDLEMAN. CONSTRUCT SIDEWALK, IMPLEMENT ROAD DIET, AND INSTALL RAISED CROSSWALK AND MEDIAN. | BIKE/PED | 8 | PIEDMONT TRIAD RPO | EB-5898 | DIVISION 8 | SCHEDULED FOR DELIVERY | L, TA5200 | 2024 | 20000 |  |  | 2024 | 206000 | 226000
RANDOLPH | US 64 / NC 49 (EAST DIXIE DRIVE) | EXECUTIVE WAY TO CENTERPOINT PLAZA SHOPPING CENTER IN ASHEBORO. CONSTRUCT SIDEWALK. | BIKE/PED | 8 | PIEDMONT TRIAD RPO | EB-6004 | DIVISION 8 | SCHEDULED FOR DELIVERY | L, TA5200 |  |  |  |  | 2024 | 104000 | 104000
RANDOLPH | I-85 | SR 1009 (SOUTH MAIN STREET) IN ARCHDALE. INTERCHANGE IMPROVEMENTS. | HIGHWAY | 8 | HIGH POINT URBAN AREA MPO | U-5770 | REGION E | SCHEDULED FOR DELIVERY | T | 2022 | 5833000 | 2022 | 2200000 |  |  | 8033000
RANDOLPH | NC 159 (ZOO PARKWAY) | RIDGE STREET IN ASHEBORO. IMPROVE INTERSECTION. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-5958 | DIVISION 8 | SCHEDULED FOR DELIVERY | T | 2023 | 320000 | 2023 | 265000 | 2025 | 1450000 | 2035000
RANDOLPH | NC 42 | SR 2237 (EAST SALISBURY STREET) TO NORTH OF US 64 / NC 49 (DIXIE DRIVE) IN ASHEBORO. WIDEN TO THREE LANES. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | U-5743 | REGION E | SCHEDULED FOR DELIVERY | T | 2022 | 1083000 | 2022 | 900000 | 2024 | 8099000 | 10082000
RANDOLPH | NC 42 (EAST SALISBURY STREET) | SR 2189 (MARTIN LUTHER KING, JR. DRIVE) / NORTH RANDOLPH AVENUE TO SR 2237 (EAST SALISBURY STREET) IN ASHEBORO. IMPROVE CORRIDOR. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-5957 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 2100000 | NOT FUNDED | 700000 | NOT FUNDED | 3400000 | 6200000
RANDOLPH | NC 49 | SR 1174 (WAYNICK MEADOW ROAD) TO SOUTH OF SR 1193 (OLD NC 49). WIDEN TO MULTILANES. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-5931 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 2964000 | NOT FUNDED | 5766000 | NOT FUNDED | 79999000 | 88729000
RANDOLPH | NC 62 | SR 3252 (SURRETT DRIVE) IN TRINITY TO SR 1009 (NORTH MAIN STREET) IN ARCHDALE. MODERNIZE ROADWAY. | HIGHWAY | 8 | HIGH POINT URBAN AREA MPO | U-6191 | DIVISION 8 | SCHEDULED FOR DELIVERY | T | 2027 | 5700000 | 2027 | 4700000 | 2029 | 12400000 | 22800000
RANDOLPH | SR 1009 (SOUTH MAIN STREET) | WEST OF COLUMBUS AVENUE TO SR 3182 (COMANCHE ROAD/TARHEEL ROAD). MILLING AND RESURFACING. | HIGHWAY | 8 | HIGH POINT URBAN AREA MPO | U-5770A | REGION E | SCHEDULED FOR DELIVERY | S, T |  |  |  |  | 2023 | 1024000 | 1024000
RANDOLPH | SR 1009 (SOUTH MAIN STREET) | WEST OF COLUMBUS AVENUE TO SR 3182 (COMANCHE ROAD/TARHEEL ROAD). CONSTRUCT DDI AND RCI IMPROVEMENTS. | HIGHWAY | 8 | HIGH POINT URBAN AREA MPO | U-5770B | REGION E | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2025 | 17500000 | 17500000
RANDOLPH | SR 1547 (FINCH FARM ROAD) | SR 3106 (KENNEDY ROAD) TO I-85 IN TRINITY. WIDEN TO MULTILANES. | HIGHWAY | 8 | HIGH POINT URBAN AREA MPO | U-5308 | DIVISION 8 | SCHEDULED FOR DELIVERY | T | 2019 | 2459000 | 2019 | 3500000 | 2025 | 26800000 | 32759000 | RIGHT-OF-WAY IN PROGRESS; BUILD NC BONDS: $2.1 MILLION FOR PE AND $190,000 FOR RIGHT-OF-WAY - PAYBACK 2020-2033 (FY 2019 / YR 1 SALE)
RANDOLPH | SR 1712 (PINEVIEW STREET) | WEST OF SYLVAN STREET TO US 220 BUSINESS IN ASHEBORO. WIDEN TO MULTILANES. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | U-5711 | DIVISION 8 | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2024 | 4950000 | 4950000 | RIGHT-OF-WAY IN PROGRESS
RANDOLPH | US 220 BUSINESS | SR 2123 (CAUDLE ROAD) TO SR 2270 (US 311 EXTENSION) IN RANDLEMAN. WIDEN TO 4-LANE DIVIDED FACILITY. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | U-6006 | DIVISION 8 | SCHEDULED FOR DELIVERY | T | 2023 | 1000000 | 2023 | 2748000 | 2026 | 8500000 | 12248000 | COORDINATE WITH R-5956
RANDOLPH | US 220 BUSINESS (NORTH FAYETTEVILLE STREET) | SR 2269 (VISION DRIVE) TO SR 2149 (HUB MORRIS ROAD). WIDEN TO MULTILANES. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-5956A | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 6200000 | NOT FUNDED | 5300000 | NOT FUNDED | 18200000 | 29700000
RANDOLPH | US 220 BUSINESS (NORTH FAYETTEVILLE STREET) | SR 2149 (HUB MORRIS ROAD) TO SR 2123 (CAUDLE ROAD). WIDEN TO MULTILANES. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-5956B | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 3200000 | NOT FUNDED | 6005000 | NOT FUNDED | 9399000 | 18604000
RANDOLPH | US 64 | SR 1409 (LAKE PARK ROAD) TO ASHEBORO BYPASS | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-2220DA | REGION E | SCHEDULED FOR DELIVERY | T | 2027 | 6796000 | 2027 | 7554000 | 2029 | 52800000 | 67150000
RANDOLPH, GUILFORD | SR 1577 / SR 1004 (ARCHDALE ROAD) | US 311 (MAIN STREET) TO EAST OF SPRINGWOOD LANE IN ARCHDALE. WIDEN TO MULTILANES. | HIGHWAY | 7, 8 | HIGH POINT URBAN AREA MPO | U-3400 | DIVISION 7, 8 | SCHEDULED FOR DELIVERY | T | 2023 | 7900000 | 2023 | 12126000 | 2026 | 18600000 | 38626000
RANDOLPH, GUILFORD | SR 1595 / SR 4053 (SURRETT DRIVE) | I-85 IN TRINITY TO SR 1300 (WEST FAIRFIELD ROAD) IN HIGH POINT. WIDEN TO MULTILANES. | HIGHWAY | 7, 8 | HIGH POINT URBAN AREA MPO | U-5864 | DIVISION 7, 8 | SCHEDULED FOR DELIVERY | T | 2026 | 5064000 | 2026 | 5100000 | 2029 | 23700000 | 33864000
RICHMOND | RICHMOND COUNTY AIRPORT (RCZ) | EXTEND RUNWAY 14-32 TO 5500 FEET. | AVIATION | 8 | LUMBER RIVER RPO | AV-5763 | DIVISION 8 | WILL BE REPRIORITIZED | T |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5065000 | 5065000
RICHMOND | SR 1639 (SPRING STREET); SR 1615 (SOUTH MAIN STREE | SPRING STREET FROM SR 1640 (WIREGRASS ROAD) TO NC 177 AND MAIN STREET FROM BRIDGES STREET TO NC 38 IN HAMLET. CONSTRUCT SIDEWALKS. | BIKE/PED | 8 | LUMBER RIVER RPO | EB-6018 | DIVISION 8 | SCHEDULED FOR DELIVERY | L, TA5200 | 2024 | 58000 | 2024 | 44000 | 2025 | 576000 | 678000
RICHMOND | US 1 | US 74 BUSINESS TO NORTH OF SR 1606 (FOX ROAD) | HIGHWAY | 8 | LUMBER RIVER RPO | R-2501BC | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 24248000 | NOT FUNDED | 6950000 | NOT FUNDED | 101101000 | 132299000 | COORDINATE WITH R-5928
RICHMOND | US 1 | SR 1640 (WIREGRASS ROAD) TO LOCH LAURIN LANE. WIDEN TO MULTILANES. | HIGHWAY | 8 | LUMBER RIVER RPO | R-5928 | DIVISION 8 | SCHEDULED FOR DELIVERY | T | 2027 | 5000000 | 2027 | 2900000 | 2029 | 28901000 | 36801000 | COORDINATE WITH R-2501BC
RICHMOND | US 1 (PROPOSED) /SR 1516 (GREENE STREET) | US 220 TO US 1 IN ROCKINGHAM. WIDEN TO 3-LANE FACILITY AND RE-ROUTE US 1 ALONG PROJECT. | HIGHWAY | 8 | LUMBER RIVER RPO | U-6027 | DIVISION 8 | SCHEDULED FOR DELIVERY | T | 2023 | 1200000 | 2023 | 500000 | 2025 | 5700000 | 7400000
RICHMOND | US 74 / FUTURE I-74 | US 1 (EXIT 311). INTERCHANGE IMPROVEMENTS. | HIGHWAY | 8 | LUMBER RIVER RPO | I-5979 | DIVISION 8 | SCHEDULED FOR DELIVERY | NHP | 2022 | 500000 | 2022 | 420000 | 2024 | 5500000 | 6420000
RICHMOND | VARIOUS | US 74 BUSINESS TO SR 1426 (ABERDEEN ROAD). CONSTRUCT TWO LANE FACILITY UTILIZING SECTIONS OF SR 1641 (CLEMMER ROAD) AND SR 1645 (MT. OLIVE CHURCH ROAD), REMAINDER ON NEW LOCATION. | HIGHWAY | 8 | LUMBER RIVER RPO | U-5706 | DIVISION 8 | SCHEDULED FOR DELIVERY | T | 2023 | 8600000 | 2023 | 1800000 | 2026 | 31070000 | 41470000 | BUILD NC BONDS: $10 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE)
ROBESON | LUMBERTON REGIONAL AIRPORT (LBT) | RUNWAY 13-31. CONSTRUCT TAXIWAYS. | AVIATION | 6 | LUMBER RIVER RPO | AV-5901 | DIVISION 6 | WILL BE REPRIORITIZED | T |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3100000 | 3100000
ROBESON | NC 711 (THIRD STREET) | SR 1563 (UNION CHAPEL ROAD) TO WALMART SHOPPING CENTER/JOHNES ROAD IN PEMBROKE. CONSTRUCT SIDEWALKS. | BIKE/PED | 6 | LUMBER RIVER RPO | EB-6013 | DIVISION 6 | SCHEDULED FOR DELIVERY | L, TA5200 | 2028 | 134000 |  |  | 2029 | 678000 | 812000
ROBESON | I-95 | CONSTRUCT WEIGH IN MOTION STATION. | HIGHWAY | 6 | LUMBER RIVER RPO | I-5987AA | REGION C | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2025 | 2400000 | 2400000
ROBESON | NC 20 | SR 1743 (COVINGTON FARM ROAD) TO I-95. WIDEN TO MULTI-LANES. | HIGHWAY | 6 | LUMBER RIVER RPO | R-5904 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 5400000 | NOT FUNDED | 3400000 | NOT FUNDED | 18800000 | 27600000
ROBESON | NC 41 (EAST ELIZABETHTOWN ROAD) | SR 2110 (SNAKE ROAD) TO SYCAMORE LANE. WIDEN EXISTING ROADWAY. | HIGHWAY | 6 | LUMBER RIVER RPO | R-5888 | REGION C | SCHEDULED FOR DELIVERY | T | 2028 | 900000 | 2028 | 300000 | 2030 | 5800000 | 7000000
ROBESON | NC 41 (MARTIN LUTHER KING DRIVE) | US 74 TO MARION ROAD. WIDEN ROADWAY. | HIGHWAY | 6 | LUMBER RIVER RPO | R-5951 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 10500000 | NOT FUNDED | 3200000 | NOT FUNDED | 18600000 | 32300000
ROBESON | NC 711 | SR 1340 (ODOM STREET-PHILADELPHUS ROAD) IN PEMBROKE TO SR 1557 (REDMOND ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 6 | LUMBER RIVER RPO | R-4428 | REGION C | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 9263000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1220000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 11600000 | 22083000
ROBESON | SR 1945 (MEADOW ROAD) | SR 1984 (LINKHAW ROAD). IMPROVE INTERSECTION. | HIGHWAY | 6 | LUMBER RIVER RPO | R-5954 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 100000 | NOT FUNDED | 300000 | NOT FUNDED | 2000000 | 2400000
ROBESON | SR 1997 (FAYETTEVILLE ROAD) | I-95 TO FARRINGTON STREET. WIDEN ROADWAY. | HIGHWAY | 6 | LUMBER RIVER RPO | R-5955 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 16000000 | NOT FUNDED | 6900000 | NOT FUNDED | 16300000 | 39200000
ROBESON | SR 1997 (FAYETTEVILLE ROAD) | FARRINGTON STREET TO EAST 22ND STREET. WIDEN TO MULTI-LANES. | HIGHWAY | 6 | LUMBER RIVER RPO | U-5797 | DIVISION 6 | SCHEDULED FOR DELIVERY | T | 2023 | 7100000 | 2023 | 2208000 | 2024 | 22100000 | 31408000
ROBESON | US 74 | CONVERT AT-GRADE INTERSECTION OF US 74 AND SR 2225 (CREEK ROAD) TO GRADE SEPARATION. | HIGHWAY | 6 | LUMBER RIVER RPO | I-6011A | DIVISION 6 | SCHEDULED FOR DELIVERY | T | 2025 | 55000 | 2025 | 352000 | 2027 | 7400000 | 7807000
ROCKINGHAM | ROCKINGHAM COUNTY / NC SHILOH AIRPORT (SIF) | CONSTRUCT T-HANGAR TAXILANES FOR ADDITION OF T-HANGARS. | AVIATION | 7 | PIEDMONT TRIAD RPO | AV-5898 | DIVISION 7 | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2025 | 770000 | 770000
ROCKINGHAM | ROCKINGHAM COUNTY AIRPORT (SIF) | EXTEND RUNWAY TO 5500 FT. | AVIATION | 7 | PIEDMONT TRIAD RPO | AV-5852 | DIVISION 7 | WILL BE REPRIORITIZED | T |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2000000 | 2000000
ROCKINGHAM | FUTURE I-73 / US 220 | US 311 / NC 135 INTERCHANGE. REPLACE BRIDGE 780074 AND UPGRADE INTERCHANGE. | HIGHWAY | 7 | PIEDMONT TRIAD RPO | I-5898 | REGION D | SCHEDULED FOR DELIVERY | T | 2022 | 1500000 | 2022 | 1600000 | 2025 | 14000000 | 17100000 | IN PROGRESS
ROCKINGHAM | NC 65 / NC 87 | WEST OF SR 2371 (OLD COUNTY HOME ROAD) IN WENTWORTH TO SR 1001 (SANDY CROSS ROAD) / SR 1998 (WENTWORTH STREET) | HIGHWAY | 7 | PIEDMONT TRIAD RPO | R-5766A | DIVISION 7 | SCHEDULED FOR DELIVERY | T | 2024 | 8700000 | 2024 | 2200000 | 2026 | 13100000 | 24000000
ROCKINGHAM | NC 65 / NC 87 | SR 1001 (SANDY CROSS ROAD) / SR 1998 (WENTWORTH STREET) TO SR 2413 (VANCE STREET EXTENSION) | HIGHWAY | 7 | PIEDMONT TRIAD RPO | R-5766B | DIVISION 7 | SCHEDULED FOR DELIVERY | T | 2024 | 4000000 | 2024 | 900000 | 2026 | 8800000 | 13700000
ROCKINGHAM | NC 65 / NC 87 | SR 2413 (VANCE STREET EXTENSION) TO US 158 / US 29 BUSINESS IN REIDSVILLE | HIGHWAY | 7 | PIEDMONT TRIAD RPO | R-5766C | DIVISION 7 | SCHEDULED FOR DELIVERY | T | 2024 | 5900000 | 2024 | 1700000 | 2026 | 14900000 | 22500000
ROCKINGHAM | US 311 / NC 14 (SOUTH VAN BUREN ROAD) | SR 2066 (KINGS HIGHWAY) IN EDEN. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 7 | PIEDMONT TRIAD RPO | U-5893 | REGION D | SCHEDULED FOR DELIVERY | T | 2024 | 1644000 | 2024 | 717000 | 2026 | 12199000 | 14560000
ROCKINGHAM, GUILFORD | NC 65 / NC 68 | NC 65 IN STOKESDALE (SOUTHERNMOST INTERSECTION) TO US 220 / FUTURE I-73. WIDEN TO MULTILANES. | HIGHWAY | 7 | PIEDMONT TRIAD RPO, GREENSBORO URBAN AREA MPO | R-5823 | DIVISION 7 | SCHEDULED FOR DELIVERY | T | 2024 | 10500000 | 2024 | 424000 | 2026 | 28200000 | 39124000
ROCKINGHAM, GUILFORD | US 29 (FUTURE I-785) | SR 2565 (HICONE ROAD) IN GREENSBORO TO US 158 / NC 14 IN REIDSVILLE. UPGRADE CORRIDOR TO INTERSTATE STANDARDS. | HIGHWAY | 7 | PIEDMONT TRIAD RPO, GREENSBORO URBAN AREA MPO | R-5889 | REGION D | SCHEDULED FOR DELIVERY | T | 2028 | 26500000 | 2028 | 7300000 | 2031 | 186200000 | 220000000
ROWAN | SR 2739 (NORTH MAIN STREET) | 12TH STREET TO 22ND STREET IN KANNAPOLIS. CONSTRUCT SIDEWALK. | BIKE/PED | 9 | CABARRUS-ROWAN MPO | EB-5921 | DIVISION 9 | SCHEDULED FOR DELIVERY | L, TAANY | 2024 | 360000 |  |  | 2025 | 1520000 | 1880000 | COORDINATE WITH U-6062
ROWAN | THIRD STREET GREENWAY | 3RD STREET TO YADKIN RIVER IN SPENCER. CONSTRUCT ALTERNATE ROUTE, INCLUDING SPUR FROM GRANTS CREEK. | BIKE/PED | 9 | CABARRUS-ROWAN MPO | EB-5861 | DIVISION 9 | SCHEDULED FOR DELIVERY | L, TAANY |  |  |  |  | 2024 | 3578000 | 3578000
ROWAN | NEW ROUTE | AIRPORT PARKWAY, SR 1710 (HARRISON ROAD) NEAR US 70 / US 601 (JAKE ALEXANDER BOULEVARD) TO SR 2539 (PEACH ORCHARD ROAD) AT US 29 IN SALISBURY. CONSTRUCT 2-LANE ROADWAY ON MULTILANE RIGHT OF WAY. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | U-5901 | DIVISION 9 | SCHEDULED FOR DELIVERY | T | 2027 | 8900000 | 2027 | 6900000 | 2030 | 39502000 | 55302000
ROWAN | US 29 | NC 152 IN CHINA GROVE. RAMP AND INTERSECTION IMPROVEMENTS. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | U-6130 | REGION D | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2500000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2000000 | 4800000
ROWAN | US 52 | PROPOSED MISENHEIMER BYPASS TO PROPOSED ROCKWELL BYPASS. WIDEN TO MULTILANES. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | R-5860 | DIVISION 9 | SCHEDULED FOR DELIVERY | T | 2027 | 7047000 | 2027 | 846000 | 2029 | 39321000 | 47214000
ROWAN | NORFOLK SOUTHERN | CITY OF SALISBURY. UPGRADE STATION BUILDING, EXPAND WAITING SPACE AND SURFACE PARKING. | RAIL | 9 | CABARRUS-ROWAN MPO | P-5733 | DIVISION 9 | SCHEDULED FOR DELIVERY | L, T | 2025 | 600000 |  |  | 2026 | 2300000 | 2900000
ROWAN | RAILROAD NORFOLK SOUTHERN | NS MAINLINE IN ROWAN COUNTY. CONSTRUCT TRACK IMPROVEMENTS, SECOND PLATFORM, PEDESTRIAN UNDERPASS, SITEWORK, RETAINING WALL AND SIGNAL EQUIPMENT. | RAIL | 9 | CABARRUS-ROWAN MPO | P-5726 | REGION D | SCHEDULED FOR DELIVERY | O, T |  |  |  |  | 2024 | 7820000 | 7820000 | "O" FUNDING REFLECTS PARTICIPATION BY CITY OF SALISBURY
ROWAN, CABARRUS | SR 2739 (NORTH MAIN STREET / SOUTH MAIN STREET) | SR 2000 (JACKSON PARK ROAD) / NORTH LOOP ROAD IN KANNAPOLIS TO SR 1211 (KIMBALL ROAD) IN CHINA GROVE. UPGRADE ROADWAY INCORPORATING BICYCLE LANES AND SIDEWALKS. | HIGHWAY | 9, 10 | CABARRUS-ROWAN MPO | U-6062 | DIVISION 9, 10 | SCHEDULED FOR DELIVERY | T | 2028 | 28900000 | 2028 | 3900000 | 2031 | 28400000 | 61200000 | COORDINATE WITH EB-5921
RUTHERFORD | THERMAL BELT RAIL TRAIL IN RUTHERFORDTON. | CONSTRUCT SIDEWALK CONNECTIONS TO THERMAL BELT RAIL TRAIL ALONG VICTORY DRIVE, ALLEN STREET/RAILROAD STREET, PINE STREET, BROADWAY, EAST LIBERTY STREET/BEAVER STREET, MAIN STREET, AND WESTVIEW STREET | BIKE/PED | 13 | FOOTHILLS RPO | EB-5966 | DIVISION 13 | SCHEDULED FOR DELIVERY | L, TA5200 | 2025 | 240000 |  |  | 2026 | 600000 | 840000
RUTHERFORD | NC 108 (CHARLOTTE STREET) | NC 108 (MAPLE STREET), SOUTH WASHINGTON STREET, MONFREDO STREET INTERSECTION IN RUTHERFORDTON. IMPROVE INTERSECTION. | HIGHWAY | 13 | FOOTHILLS RPO | R-5916 | NOT FUNDED | WILL BE REPRIORITIZED | BG5200 | NOT FUNDED | 2100000 | NOT FUNDED | 200000 | NOT FUNDED | 1200000 | 3500000
RUTHERFORD | US 221 | NORTH OF US 74 BYPASS TO SOUTH OF US 74 BUSINESS | HIGHWAY | 13 | FOOTHILLS RPO | R-2233BA | DIVISION 13 | SCHEDULED FOR DELIVERY | T | 2024 | 12000000 | 2024 | 3200000 | 2027 | 85100000 | 100300000
RUTHERFORD | US 221 | NORTH OF SR 1366 (ROPER LOOP ROAD) TO SR 1325 (NANNEY TOWN ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 13 | FOOTHILLS RPO | R-2597A | NOT FUNDED | WILL BE REPRIORITIZED | NHP | NOT FUNDED | 12600000 | NOT FUNDED | 3400000 | NOT FUNDED | 69201000 | 85201000
RUTHERFORD | US 221 | SR 2201 (THUNDER ROAD) / SR 1005 (COXE ROAD) INTERSECTION. IMPROVE INTERSECTION. | HIGHWAY | 13 | FOOTHILLS RPO | R-5880 | NOT FUNDED | WILL BE REPRIORITIZED | NHP | NOT FUNDED | 500000 | NOT FUNDED | 400000 | NOT FUNDED | 2500000 | 3400000
RUTHERFORD | US 221A (EAST MAIN STREET) | KENTUCKY STREET/OAKLAND ROAD INTERSECTION IN RUTHERFORDTON. IMPROVE INTERSECTION | HIGHWAY | 13 | FOOTHILLS RPO | R-5918 | NOT FUNDED | WILL BE REPRIORITIZED | BG5200 | NOT FUNDED | 3100000 | NOT FUNDED | 400000 | NOT FUNDED | 3100000 | 6600000
RUTHERFORD | US 64 (EAST MOUNTAIN STREET) | NORTH WASHINGTON STREET INTERSECTION IN RUTHERFORDTON. IMPROVE INTERSECTION. | HIGHWAY | 13 | FOOTHILLS RPO | R-5917 | NOT FUNDED | WILL BE REPRIORITIZED | BG5200 | NOT FUNDED | 1400000 | NOT FUNDED | 300000 | NOT FUNDED | 900000 | 2600000
SAMPSON | CLINTON SAMPSON COUNTY AIRPORT (CTZ) | OVERLAY RUNWAY TO ACCOMMODATE LARGER AIRCRAFT. | AVIATION | 3 | MID-CAROLINA RPO | AV-5823 | DIVISION 3 | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2025 | 1904000 | 1904000
SAMPSON | BEAMAN STREET | NORTH BOULEVARD TO SAMPSON REGIONAL MEDICAL CENTER IN CLINTON. CONSTRUCT SIDEWALK. | BIKE/PED | 3 | MID-CAROLINA RPO | EB-6011 | NOT FUNDED | WILL BE REPRIORITIZED | L, TA5200 | NOT FUNDED | 8000 |  |  | NOT FUNDED | 84000 | 92000
SAMPSON | NC 24 (SOUTHWEST BOULEVARD/MLK JR BOULEVARD) | BUTLER ROAD/TRAM ROAD. IMPROVE INTERSECTION. | HIGHWAY | 3 | MID-CAROLINA RPO | U-6126 | NOT FUNDED | WILL BE REPRIORITIZED | NHP | NOT FUNDED | 302000 | NOT FUNDED | 126000 | NOT FUNDED | 2500000 | 2928000
SAMPSON, DUPLIN | NC 24 | SR 1935 (CECIL ODIE ROAD) IN SAMPSON COUNTY TO I-40 IN DUPLIN COUNTY. | HIGHWAY | 3 | MID-CAROLINA RPO, EASTERN CAROLINA RPO | R-2303F | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 16800000 | NOT FUNDED | 1960000 | NOT FUNDED | 276700000 | 295460000 | PLANNING/DESIGN IN PROGRESS.
SCOTLAND | LAURINBURG- MAXTON AIRPORT (MEB) | CONSTRUCT 1500 FT RUNWAY EXTENSION. | AVIATION | 8 | LUMBER RIVER RPO | AV-5854 | DIVISION 8 | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2024 | 6390000 | 6390000
SCOTLAND | SR 1108 (WEST BOULEVARD) | SR 1105 (TURNPIKE ROAD) TO GLASGOW DRIVE AND EAST OF US 15 / US 401 / US 501 TO SUNSET DRIVE IN LAURINBURG. | BIKE/PED | 8 | LUMBER RIVER RPO | EB-5872A | DIVISION 8 | SCHEDULED FOR DELIVERY | L, TA5200 | 2024 | 133000 |  |  | 2024 | 348000 | 481000
SCOTLAND | US 401 BUSINESS (SOUTH MAIN STREET | PLAZA ROAD TO CREPE MYRTLE AVENUE IN LAURINBURG. CONSTRUCT SIDEWALKS | BIKE/PED | 8 | LUMBER RIVER RPO | EB-6015B | DIVISION 8 | SCHEDULED FOR DELIVERY | L, TA5200 | 2024 | 42000 |  |  | 2025 | 218000 | 260000
SCOTLAND | US 15 / US 401 | SOUTH CAROLINA STATE LINE TO SOUTH OF SR 1105 (TURNPIKE ROAD) IN LAURINBURG. WIDEN TO MULTILANES. | HIGHWAY | 8 | LUMBER RIVER RPO | U-5977 | REGION E | SCHEDULED FOR DELIVERY | T | 2028 | 4800000 | 2028 | 2900000 | 2030 | 19400000 | 27100000
SCOTLAND, RICHMOND | US 74 / FUTURE I-74 | US 74 BUSINESS EAST OF HAMLET TO US 74 BUSINESS WEST OF LAURINBURG. UPGRADE CORRIDOR TO INTERSTATE STANDARDS. | HIGHWAY | 8 | LUMBER RIVER RPO | I-6055 | REGION E | SCHEDULED FOR DELIVERY | T | 2027 | 27600000 | 2027 | 8584000 | 2030 | 187500000 | 223684000
STANLY | STANLY COUNTY AIRPORT (VUJ) | ACQUIRE LAND FOR EXPANSION AND PERFORM ESA TO DETERMINE STATUS OF STRUCTURES ON PROPERTY. CLEAR AND GRUBB LAND REQUIRED FOR EXPANSION AND DEMOLISH HOUSES ON PROPERTY ACQUIRED. | AVIATION | 10 | ROCKY RIVER RPO | AV-5817 | DIVISION 10 | SCHEDULED FOR DELIVERY | T | 2025 | 2860000 |  |  | 2027 | 1776000 | 4636000
STANLY | ALBEMARLE | US 52, WEST MAIN STREET TO SNUGGES STREET. CONSTRUCT SIDEWALK ON EAST SIDE OF ROAD | BIKE/PED | 10 | ROCKY RIVER RPO | EB-5841 | DIVISION 10 | SCHEDULED FOR DELIVERY | L, TA5200 | 2025 | 200000 |  |  | 2026 | 200000 | 400000
STANLY | NORTH SECOND AVENUE | PARK RIDGE TO SALISBURY AVENUE. CONSTRUCT SIDEWALKS, ADA RAMPS, AND CROSSWALKS. | BIKE/PED | 10 | ROCKY RIVER RPO | EB-5972 | DIVISION 10 | SCHEDULED FOR DELIVERY | L, TA5200 | 2026 | 104000 |  |  | 2027 | 360000 | 464000
STANLY | SALISBURY AVENUE | US 52 TO NORTH SECOND STREET. CONSTRUCT BIKE LANES. | BIKE/PED | 10 | ROCKY RIVER RPO | EB-5973 | DIVISION 10 | SCHEDULED FOR DELIVERY | L, TA5200 |  |  |  |  | 2025 | 96000 | 96000
STANLY | US 52 BUSINESS RAMP | NC 24/27 TO SECOND STREET. CONSTRUCT SIDEWALK ALONG US 52 BUSINESS RAMP | BIKE/PED | 10 | ROCKY RIVER RPO | EB-5974 | NOT FUNDED | WILL BE REPRIORITIZED | L, TA5200 | NOT FUNDED | 24000 |  |  | NOT FUNDED | 160000 | 184000
SURRY | MOUNT AIRY | S. SOUTH STREET, WORTH STREET TO ROCKFORD STREET. ROCKFORD STREET, PENN STREET TO US 52. WORTH STREET, SOUTH STREET TO US 52. CONSTRUCT SIDEWALK. | BIKE/PED | 11 | NORTHWEST PIEDMONT RPO | EB-5845 | DIVISION 11 | SCHEDULED FOR DELIVERY | L, TA5200 | 2023 | 129000 |  |  | 2024 | 344000 | 473000
SURRY | US 21 BUSINESS (NORTH BRIDGE STREET) | NC 268 (CC CAMP ROAD) TO HIGHLAND AVENUE. CONSTRUCT SIDEWALK ON WEST SIDE OF ROADWAY. | BIKE/PED | 11 | NORTHWEST PIEDMONT RPO | EB-5961 | DIVISION 11 | SCHEDULED FOR DELIVERY | L, TA5200 | 2023 | 42000 |  |  | 2024 | 140000 | 182000
SURRY | NC 103 (EAST PINE STREET) | SR 1742 (QUAKER ROAD) INTERSECTION. IMPROVE INTERSECTION. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5895 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 2700000 | NOT FUNDED | 390000 | NOT FUNDED | 1600000 | 4690000
SURRY | NC 89 (WEST PINE STREET) | SR 1397 (ROUND PEAK CHURCH ROAD) INTERSECTION. IMPROVE INTERSECTION. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5901 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 500000 | NOT FUNDED | 100000 | NOT FUNDED | 3900000 | 4500000
SURRY | NC 89 (WEST PINE STREET) | SR 1387 (TOAST ROAD) TO SR 1396 (PINE RIDGE ROAD). MODERNIZE ROADWAY AND IMPROVE INTERSECTION AT SR 1396 (PINE RIDGE ROAD). | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5905 | DIVISION 11 | SCHEDULED FOR DELIVERY | BG5200 | 2026 | 5900000 | 2026 | 5800000 | 2028 | 38501000 | 50201000
SURRY | US 601 | I-74 TO SR 1104 (CODY TRAIL). WIDEN TO 4-LANES. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5836 | DIVISION 11 | SCHEDULED FOR DELIVERY | T | 2024 | 3100000 | 2024 | 1700000 | 2026 | 76000000 | 80800000
SWAIN | US 19 | SR 1152 (HUGHES BRANCH ROAD) IN BRYSON CITY TO SR 1195 (US 19A). MODERNIZE ROADWAY. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-4751 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 25000000 | NOT FUNDED | 4900000 | NOT FUNDED | 75000000 | 104900000
TRANSYLVANIA | BREVARD | CONSTRUCT BICYCLE AND PEDESTRIAN BRIDGE FROM CITY OF BREVARD EXISTING SHARED USE PATH ACROSS DAVIDSON RIVER. | BIKE/PED | 14 | LAND-OF-SKY RPO | EB-5858 | DIVISION 14 | SCHEDULED FOR DELIVERY | L, TA5200 | 2022 | 16000 |  |  | 2024 | 960000 | 976000
TRANSYLVANIA | SR 1540 (WILSON ROAD) | SR 1504 (OLD US 64) TO US 276. UPGRADE ROADWAY. | HIGHWAY | 14 | LAND-OF-SKY RPO | R-5763 | DIVISION 14 | SCHEDULED FOR DELIVERY | T | 2022 | 17400000 | 2022 | 2400000 | 2024 | 40200000 | 60000000
TRANSYLVANIA | US 178 | SR 1156 (MAIN STREET) IN ROSMAN TO SR 1133 (MIDDLEFORK ROAD) MODERNIZE ROADWAY. | HIGHWAY | 14 | LAND-OF-SKY RPO | R-5919 | DIVISION 14 | WILL BE REPRIORITIZED | BGLT5 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 10100000 | 12700000
TRANSYLVANIA | US 64 | US 276, NC 280 INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 14 | LAND-OF-SKY RPO | R-5799 | REGION G | SCHEDULED FOR DELIVERY | T | 2022 | 5890000 | 2022 | 600000 | 2024 | 16000000 | 22490000 | BUILD NC BOND FUNDING: $1M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE)
TRANSYLVANIA | US 64 (SOUTH BROAD STREET) | US 64 BUSINESS (SOUTH CALDWELL STREET), SR 1116 (NORTH COUNTRY CLUB ROAD) INTERSECTION. IMPROVE INTERSECTION ALIGNMENT. | HIGHWAY | 14 | LAND-OF-SKY RPO | R-5882 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 4400000 | NOT FUNDED | 1200000 | NOT FUNDED | 1900000 | 7500000
TRANSYLVANIA | US 64, US 276 | FORTUNE COVE ROAD TO US 64 BUSINESS (NORTH CALDWELL STREET). CONSTRUCT MEDIAN AND ACCESS CONTROL MEASURES. | HIGHWAY | 14 | LAND-OF-SKY RPO | R-5800 | REGION G | SCHEDULED FOR DELIVERY | T | 2023 | 14800000 | 2023 | 3900000 | 2025 | 17801000 | 36501000 | RIGHT-OF-WAY IN PROGRESS
TYRRELL | US 64 | COLUMBIA TO ALLIGATOR RIVER BRIDGE. MODERNIZE ROADWAY. | HIGHWAY | 1 | ALBEMARLE RPO | R-5940 | DIVISION 1 | SCHEDULED FOR DELIVERY | NHP | 2028 | 900000 | 2028 | 9100000 | 2030 | 47100000 | 57100000
UNION | CHARLOTTE-MONROE EXECUTIVE AIRPORT (EQY) | RELOCATE AND WIDEN THE EXISTING PARALLEL TAXIWAY SECTION BETWEEN THE EXISTING RAMP AND THE RUNWAY 5 TAXIWAY EXTENSION. | AVIATION | 10 | CHARLOTTE REGIONAL TPO | AV-5814 | DIVISION 10 | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2028 | 8800000 | 8800000
UNION | NC 16 (PROVIDENCE ROAD SOUTH) | SR 1316 (REA ROAD EXTENSION) TO SR 1307 (BONDS GROVE CHURCH RD). WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5769A | REGION E | SCHEDULED FOR DELIVERY | T | 2024 | 10700000 | 2024 | 4400000 | 2027 | 26401000 | 41501000
UNION | NC 16 (PROVIDENCE ROAD SOUTH) | SR 1307 (BONDS GROVE CHURCH RD) TO SR 3530 (WAXHAW PARKWAY) IN WAXHAW. WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5769B | REGION E | SCHEDULED FOR DELIVERY | T | 2024 | 15500000 | 2024 | 2800000 | 2027 | 31400000 | 49700000
UNION | NC 84 | NC 16 TO SR 1008 (WAXHAW-INDIAN TRAIL ROAD) IN WESLEY CHAPEL. CONSTRUCT FOUR LANE ROADWAY, PART ON NEW LOCATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-3467 | REGION E | SCHEDULED FOR DELIVERY | BGANY | 2024 | 70000000 | 2024 | 3000000 | 2027 | 44900000 | 117900000
UNION | SR 1004 (LAWYERS ROAD) | I-485 TO SR 1524 (STEVENS MILL ROAD). WIDEN ROADWAY TO FOUR LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6170 | NOT FUNDED | WILL BE REPRIORITIZED | BGANY | NOT FUNDED | 3000000 | NOT FUNDED | 1400000 | NOT FUNDED | 8800000 | 13200000
UNION | SR 1009 (CHARLOTTE AVENUE) | SEYMOUR STREET TO NC 200 (DICKERSON BOULEVARD). WIDEN TO FOUR-LANES DIVIDED. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6031 | DIVISION 10 | SCHEDULED FOR DELIVERY | T | 2028 | 7700000 | 2028 | 4500000 | 2030 | 10100000 | 22300000
UNION | SR 1009 (JOHN STREET-OLD MONROE ROAD) | WEST OF MORNINGSIDE MEADOW LANE TO EAST OF SR 1377 (WESLEY CHAPEL-STOUTS ROAD) | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-4714B | DIVISION 10 | SCHEDULED FOR DELIVERY | BGANY, BGDA, O, S(M), T | 2021 | 44000000 | 2021 | 2300000 | 2024 | 48675000 | 94975000 | TO BE LET WITH U-4714AC. BUILD NC BOND FUNDING: $20M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE); $8.5M FOR CONSTRUCTION, PAYBACK FY 2026-2040 (FY 2026 / YR 8 SALE).
UNION | SR 1009 (OLD MONROE ROAD) | SR 1377 (WESLEY CHAPEL-STOUTS ROAD) TO SR 1349 (AIRPORT ROAD). | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6169 | NOT FUNDED | WILL BE REPRIORITIZED | BGANY | NOT FUNDED | 3000000 | NOT FUNDED | 2800000 | NOT FUNDED | 26100000 | 31900000
UNION | US 601 | EXISTING US 74 TO THE MONROE BYPASS. WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-4024 | REGION E | SCHEDULED FOR DELIVERY | T | 2028 | 3300000 | 2028 | 400000 | 2030 | 13700000 | 17400000 | COORDINATE WITH U-5723
UNION | US 74 | US 601 INTERCHANGE. CONSTRUCT IMPROVEMENTS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5723 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2025 | 15001000 | 15001000 | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-4024
UNION | US 74 | NC 200 (DICKERSON BOULEVARD) TO SR 1007 (ROCKY RIVER ROAD). WIDEN EXISTING ROADWAY. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5764 | REGION E | SCHEDULED FOR DELIVERY | T | 2025 | 24500000 | 2025 | 2700000 | 2028 | 43399000 | 70599000 | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5931
UNION | US 74 | INTERSECTION OF US 74 AND SECREST SHORTCUT ROAD. CONSTRUCT IMPROVEMENTS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5931 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | T | 2025 | 1100000 | 2025 | 1000000 | 2028 | 4600000 | 6700000 | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH U-5764.
UNION | US 74 (ROOSEVELT BLVD) | REALIGN JAMES HAMILTON ROAD TO INTERSECT WITH SR 1514 (ROCKY RIVER ROAD) AT MYERS ROAD. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5703B | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | O, T | 2023 | 3456000 |  | 325000 | 2025 | 1491000 | 5272000
UNION | CSX SF LINE | SR 1377 (WESLEY CHAPEL STOUTS ROAD). CONSTRUCT GRADE SEPERATION. | RAIL | 10 | CHARLOTTE REGIONAL TPO | P-5744 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | DP, O, T | 2025 | 5820000 | 2025 | 826000 | 2027 | 5766000 | 12412000 | DP REPRESENTS FEDERAL CRISI GRANT. OTHER FUNDING PROVIDED BY CSX.
UNION, MECKLENBURG | IDLEWILD ROAD | SR 3175 (STALLINGS ROAD) TO SR 1524 (STEVENS MILL ROAD). WIDEN EXISTING ROADWAY. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-4913 | DIVISION 10 | SCHEDULED FOR DELIVERY | T | 2026 | 8000000 | 2026 | 3900000 | 2028 | 28000000 | 39900000
UNION, MECKLENBURG | SR 1009 (JOHN STREET-OLD MONROE ROAD) | EAST OF I-485 TO WEST OF MORNINGSIDE MEADOW LANE | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-4714AC | DIVISION 10 | SCHEDULED FOR DELIVERY | BGANY, BGDA, S(M), T, T(DA) | 2019 | 11780000 | 2019 | 2200000 | 2024 | 20439000 | 34419000 | TO BE LET WITH U-4714B. BUILD NC BOND FUNDING: $8.4M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE). $7.7M IN STBG-DA FUNDS SWITCHED WITH $7.7M IN STATE TRUST FUNDS "T(DA)" AS PART OF FUND SWAP.
VANCE | SR 1162 (DABNEY DRIVE) | COBLE BOULEVARD TO US 158 BUSINESS IN HENDERSON. CORRIDOR UPGRADE. | HIGHWAY | 5 | KERR-TAR RPO | U-5890 | DIVISION 5 | SCHEDULED FOR DELIVERY | T | 2026 | 41300000 | 2026 | 7300000 | 2028 | 16800000 | 65400000
WAKE | SR 1012 (WESTERN BOULEVARD) | CONSTRUCT BICYCLE / PEDESTRIAN TUNNEL IMMEDIATELY WEST OF SR 1321 (AVENT FERRY ROAD) IN RALEIGH. | BIKE/PED | 5 | CAPITAL AREA MPO | EB-5718 | DIVISION 5 | SCHEDULED FOR DELIVERY | L, TAANY |  |  |  |  | 2025 | 3200000 | 3200000 | COORDINATE WITH B-5675 (NON-STIP PROJECT) AND TO-6166
WAKE | SR 1637 (CHURCH STREET) | SR 3014 (MORRISVILLE-CARPENTER ROAD) TO DURHAM COUNTY LINE IN MORRISVILLE. CONSTRUCT SIDEWALKS TO FILL IN GAPS. | BIKE/PED | 5 | CAPITAL AREA MPO | EB-5838 | DIVISION 5 | SCHEDULED FOR DELIVERY | L, TAANY | 2023 | 200000 |  |  | 2024 | 1160000 | 1360000
WAKE | I-40 | I-440 / US 1 / US 64 INTERCHANGE IN RALEIGH. RECONSTRUCT INTERCHANGE. | HIGHWAY | 5 | CAPITAL AREA MPO | I-5703 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | NHP | 2026 | 29600000 | 2026 | 3600000 | 2026 | 119100000 | 152300000 | DESIGN-BUILD PROJECT - TO BE LET WITH I-5701
WAKE | I-40 | SR 1002 (AVIATION PARKWAY) TO SR 1652 (HARRISON AVENUE) IN CARY. CONSTRUCT AUXILIARY LANES IN BOTH DIRECTIONS. | HIGHWAY | 5 | CAPITAL AREA MPO | I-5966 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | NHP | 2027 | 700000 | 2027 | 138000 | 2030 | 47701000 | 48539000
WAKE | I-40 / US 64 | I-440 / US 1 / US 64 TO SR 1370 (LAKE WHEELER ROAD) IN RALEIGH. ADD LANES. | HIGHWAY | 5 | CAPITAL AREA MPO | I-5701 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | NHP | 2026 |  | 2026 | 1100000 | 2026 | 62800000 | 63900000 | DESIGN-BUILD PROJECT - TO BE LET WITH I-5703
WAKE | I-440 / US 1 | SR 2000 (WAKE FOREST ROAD) IN RALEIGH. INTERCHANGE IMPROVEMENTS. | HIGHWAY | 5 | CAPITAL AREA MPO | I-5708 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | NHP | 2019 | 1736000 |  |  | 2025 | 9100000 | 10836000 | RIGHT-OF-WAY IN PROGRESS; GARVEE BONDS: $1.445 MILLION FOR RIGHT-OF-WAY - PAYBACK 2019 - 2033
WAKE | I-440 / US 1 | US 70 (GLENWOOD AVENUE) IN RALEIGH. CONSTRUCT INTERCHANGE IMPROVEMENTS, REVISE US 70 INTERSECTION WITH SR 1670 (BLUE RIDGE ROAD) / SR 1820 (LEAD MINE ROAD), AND REPLACE BRIDGE 910494 ON SR 1670. | HIGHWAY | 5 | CAPITAL AREA MPO | I-5870 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 193100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 213701000 | 411801000
WAKE | I-440 / US 1 | US 401 (CAPITAL BOULEVARD) IN RALEIGH. INTERCHANGE IMPROVEMENTS. | HIGHWAY | 5 | CAPITAL AREA MPO | I-5970 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 48400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 89899000 | 141599000
WAKE | I-540 | US 70 TO SR 1829 (LEESVILLE ROAD) IN RALEIGH. CONSTRUCT EASTBOUND AUXILIARY LANE. | HIGHWAY | 5 | CAPITAL AREA MPO | I-5968 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | NHP | 2028 | 3200000 | 2028 | 10000 | 2030 | 20501000 | 23711000
WAKE | I-87 / US 64 / US 264 | US 64 BUSINESS (WENDELL BOULEVARD) TO US 264. WIDEN TO 6 LANES. | HIGHWAY | 5 | CAPITAL AREA MPO | I-6005 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 53699000 | 56499000
WAKE | I-87 / US 64 / US 264 | SR 2233 (SMITHFIELD ROAD). CONVERT INTERCHANGE TO DIVERGING DIAMOND. | HIGHWAY | 5 | CAPITAL AREA MPO | I-6007 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 16199000 | 22099000
WAKE | NC 50 (CREEDMOOR ROAD) | I-540 TO NORTH OF NC 98. WIDEN TO MULTILANE DIVIDED ROADWAY. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5891 | REGION C | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 56400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1700000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 66001000 | 124101000
WAKE | NC 55 (WILLIAMS STREET) | US 1 TO NORTH OF SR 1160 (OLIVE CHAPEL ROAD). CONVERT EXISTING MULTILANES TO MEDIAN DIVIDED SECTION AND WIDEN REMAINING 2-LANE SECTIONS TO MULTILANES. | HIGHWAY | 5 | CAPITAL AREA MPO | U-2901B | REGION C | SCHEDULED FOR DELIVERY | T | 2028 | 12000000 | 2028 | 3900000 | 2031 | 37001000 | 52901000
WAKE | NEW ROUTE | SR 1613 (MCCRIMMON PARKWAY) TO NC 540 IN MORRISVILLE. CONSTRUCT MULTILANE FACILITY ON NEW LOCATION. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5966 | REGION C | SCHEDULED FOR DELIVERY | T | 2028 | 12900000 | 2028 | 2398000 | 2030 | 93701000 | 108999000 | NORTH CAROLINA TURNPIKE AUTHORITY PROJECT
WAKE | SR 1002 (AVIATION PARKWAY) | NC 54 TO I-40 IN MORRISVILLE. WIDEN TO MULTILANES WITH INTERCHANGE MODIFICATIONS AT I-40. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5811 | DIVISION 5 | SCHEDULED FOR DELIVERY | T | 2026 | 8420000 | 2026 | 556000 | 2028 | 31401000 | 40377000
WAKE | SR 1010 (TEN-TEN ROAD) | APEX PEAKWAY IN APEX TO SR 1300 (KILDARE FARM ROAD) IN CARY. WIDEN TO MULTILANES. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5825 | DIVISION 5 | SCHEDULED FOR DELIVERY | T | 2028 | 26800000 | 2028 | 4700000 | 2031 | 45701000 | 77201000 | COORDINATE WITH U-6066
WAKE | SR 1115 (AVENT FERRY ROAD) | SR 1116 (CASS HOLT ROAD) TO NC 55 BYPASS IN HOLLY SPRINGS. WIDEN TO MULTILANES, WITH INTERSECTION IMPROVEMENTS AT SR 1116 (CASS HOLT ROAD), SR 1101 (PINEY GROVE-WILBON ROAD) AND NC 55 BYPASS. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5889 | DIVISION 5 | SCHEDULED FOR DELIVERY | T | 2026 | 1200000 | 2026 | 500000 | 2028 | 7300000 | 9000000
WAKE | SR 1152 (HOLLY SPRINGS ROAD) | SR 1010 (TEN-TEN ROAD) TO SR 3977 (CARY PARKWAY). IMPROVE INTERSECTIONS AT SR 1010, SR 1379 (PENNY ROAD), AND SR 3977. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6217 | DIVISION 5 | SCHEDULED FOR DELIVERY | T | 2028 | 13400000 | 2028 | 1142000 | 2031 | 27100000 | 41642000
WAKE | SR 1664 (DURALEIGH ROAD) | SR 3009 (EDWARDS MILL ROAD) IN RALEIGH. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6193 | DIVISION 5 | SCHEDULED FOR DELIVERY | T | 2027 | 6700000 | 2027 | 300000 | 2029 | 10200000 | 17200000
WAKE | SR 1728 (WADE AVENUE) | I-40 TO I-440 IN RALEIGH. ADD LANES. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5936 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 74499000 | 76699000
WAKE | US 1 | I-540 TO NORTH OF SR 2006 (DURANT ROAD) IN RALEIGH. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5307A | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | T | 2025 | 94300000 | 2025 | 12200000 | 2025 | 184700000 | 291200000 | DESIGN-BUILD PROJECT
WAKE | US 1 | NORTH OF SR 2006 (DURANT ROAD) IN RALEIGH TO NORTH OF SR 2045 (BURLINGTON MILLS ROAD) IN WAKE FOREST. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5307B | REGION C | SCHEDULED FOR DELIVERY | T | 2027 | 80053000 | 2027 | 6700000 | 2029 | 92399000 | 179152000 | BUILD NC BONDS: $19 MILLION FOR RIGHT OF WAY - PAYBACK 2026-2040 (FY 2026 / YR 8 SALE)
WAKE | US 1 | NORTH OF SR 2045 (BURLINGTON MILLS ROAD) TO SOUTH OF NC 98 BUSINESS IN WAKE FOREST. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5307C | REGION C | SCHEDULED FOR DELIVERY | T | 2027 | 28200000 | 2027 | 5100000 | 2029 | 108800000 | 142100000
WAKE | US 1 | SOUTH OF NC 98 BUSINESS TO SR1909 (PURNELL ROAD) / SR 1931 (HARRIS ROAD) IN WAKE FOREST. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5307D | REGION C | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 48900000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 8300000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 83999000 | 141199000
WAKE | US 1 | NC 55 IN APEX TO US 64 IN CARY. ADD LANES. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6066 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 32400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 40800000 | 74800000 | COORDINATE WITH U-5825
WAKE | US 401 | SR 1467 / SR 2839 (ALLEN STREET) TO SR 1010 (TEN-TEN ROAD). ADD LANES. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5746 | REGION C | SCHEDULED FOR DELIVERY | T |  |  | 2022 | 605000 | 2024 | 5400000 | 6005000 | RIGHT-OF-WAY IN PROGRESS
WAKE | US 401 | NC 55 / NC 42 IN FUQUAY-VARINA. IMPROVE US 401 INTERSECTION WITH NC 55 / NC 42. PROJECT WILL INCLUDE IMPROVEMENTS TO NC 55 INTERSECTION WITH NC 42, AND CONSTRUCTION OF CONNECTOR FROM NC 55 TO SR 5056 (JUDD PARKWAY). | HIGHWAY | 5 | CAPITAL AREA MPO | U-5751 | REGION C | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 39150000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2620000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 47498000 | 89268000
WAKE | US 401 | SR 1010 (TEN-TEN ROAD). CONVERT EXISTING SIGNALIZED INTERSECTION TO SQUARE-LOOP INTERCHANGE. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6112 | REGION C | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 56400000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1600000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 24100000 | 82100000 | COORDINATE WITH R-2721 AND U-5746
WAKE | US 401 | SR 1375 (SIMPKINS ROAD) TO SR 2538 (MECHANICAL BOULEVARD) IN GARNER. WIDEN TO 6 LANES AND CONVERT TO SUPERSTREET. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6116 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 2200000 | NOT FUNDED | 1400000 | NOT FUNDED | 4500000 | 8100000
WAKE | US 64 | WEST OF SR 1308 (LAURA DUNCAN ROAD) TO US 1 IN APEX AND CARY. CORRIDOR UPGRADE AND IMPROVEMENTS. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5301 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | T | 2026 | 100556000 | 2026 | 4012000 | 2029 | 134599000 | 239167000
WAKE | US 70 | I-540 TO HILLBURN DRIVE IN RALEIGH. ADD LANES AND CONVERT TO SUPERSTREET. | HIGHWAY | 5 | CAPITAL AREA MPO | U-2823 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 37100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 84202000 | 122502000
WAKE | US 70 / NC 50 | SR 2026 (HAMMOND ROAD) / SR 2812 (TIMBER DRIVE) IN GARNER. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5744 | REGION C | SCHEDULED FOR DELIVERY | T | 2028 | 14400000 | 2028 | 138000 | 2030 | 13998000 | 28536000
WAKE | VARIOUS | TOWN OF MORRISVILLE. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5967 | REGION C | SCHEDULED FOR DELIVERY | BGANY, T |  |  | 2025 | 33000 | 2026 | 953000 | 986000
WAKE | VARIOUS | APEX TOWNWIDE SIGNAL SYSTEM. UPGRADE EXISTING INFRASTRUCTURE AND INSTALL NEW FIBER, CONTROLLERS, SIGNALS, AND OTHER EQUIPMENT AS NECESSARY. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6117 | NOT FUNDED | WILL BE REPRIORITIZED | BGANY | NOT FUNDED | 100000 | NOT FUNDED | 300000 | NOT FUNDED | 3800000 | 4200000
WAKE | VARIOUS | RALEIGH CITYWIDE SIGNAL SYSTEM. UPGRADE SOFTWARE FOR EXISTING ITS SYSTEM. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6119 | REGION C | WILL BE REPRIORITIZED | BGANY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 100000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 4300000 | 4600000
WAKE | VARIOUS | GARNER CITYWIDE SIGNAL SYSTEM | HIGHWAY | 5 | CAPITAL AREA MPO | U-6194 | DIVISION 5 | SCHEDULED FOR DELIVERY | BGANY | 2027 | 100000 | 2027 | 360000 | 2028 | 3200000 | 3660000
WAKE | VARIOUS | TRIANGLE TOWN CENTER. CONSTRUCT TRANSIT CENTER AND PARK-AND-RIDE FACILITY. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TD-5307 | DIVISION 5 | WILL BE REPRIORITIZED | L, O, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 1750000 | 1750000
WAKE | VARIOUS | BUS RAPID TRANSIT SERVICE, MORRISVILLE TO CARY. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TO-6166A | REGION C | WILL BE REPRIORITIZED | L, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7649000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2126000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 40224000 | 49999000
WAKE | CSX | CROSSING 643351A AT SR 1415 (NORTHEAST MAYNARD ROAD) IN CARY. CONSTRUCT GRADE SEPARATION. | RAIL | 5 | CAPITAL AREA MPO | P-5718 | REGION C | WILL BE REPRIORITIZED | O, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 29344000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3344000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 22610000 | 55298000 | "O"FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION; TO BE LET WITH P-5734
WAKE | CSX S LINE | CONSTRUCT GRADE SEPARATION AT SR 2052 (ROGERS ROAD EXTENSION) CROSSING (633905Y) IN WAKE FOREST. | RAIL | 5 | CAPITAL AREA MPO | P-5707 | REGION C | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2024 | 24400000 | 24400000 | RIGHT-OF-WAY IN PROGRESS
WAKE | CSX S LINE | SR 2108 (MILLBROOK ROAD) IN RALEIGH. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 630605A. | RAIL | 5 | CAPITAL AREA MPO | P-5737 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | DP, T | 2022 | 6111000 | 2022 | 1228000 | 2024 | 13200000 | 20539000 | RIGHT OF WAY IN PROGRESS; "DP" FUNDING REFLECTS CONSOLIDATED RAIL INFRASTRUCTURE AND SAFETY IMPROVEMENTS (CRISI) PROGRAM AWARD
WAKE | CSX S LINE | SR 1415 (WEST MAYNARD ROAD) IN CARY. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 643400U. | RAIL | 5 | CAPITAL AREA MPO | P-5739 | NOT FUNDED | WILL BE REPRIORITIZED | O, T | NOT FUNDED | 2200000 |  |  | NOT FUNDED | 13680000 | 15880000 | "O" FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION
WAKE | NORFOLK SOUTHERN H LINE | CONSTRUCT GRADE SEPARATION AT HARRISON AVENUE CROSSING (734755X) IN CARY. | RAIL | 5 | CAPITAL AREA MPO | P-5708 | REGION C | WILL BE REPRIORITIZED | O, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6000000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 15774000 | 21774000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN RAILROAD
WAKE | NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN H LINE | SR 2713 (VANDORA SPRINGS ROAD) IN GARNER. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 735324J. | RAIL | 5 | CAPITAL AREA MPO | P-5738 | NOT FUNDED | WILL BE REPRIORITIZED | O, T | NOT FUNDED | 1800000 |  |  | NOT FUNDED | 10924000 | 12724000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION
WAKE | NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN H LINE | SR 1655 (TRINITY ROAD) IN CARY. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 630657S. | RAIL | 5 | CAPITAL AREA MPO | P-5734 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | O, T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 21000000 |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 15865000 | 36865000 | "O" FUNDING REFLECTS PARTICIPATION BY CSX CORPORATION; TO BE LET WITH P-5718
WAKE | NORTH CAROLINA RAILROAD; NORFOLK SOUTHERN H LINE; | BERYL ROAD CROSSING IN RALEIGH. EXTEND BERYL ROAD TO ROYAL AVENUE, AND CLOSE CROSSING 630647L. | RAIL | 5 | CAPITAL AREA MPO | P-5736 | NOT FUNDED | WILL BE REPRIORITIZED | O, T | NOT FUNDED | 200000 |  |  | NOT FUNDED | 2996000 | 3196000 | "O" FUNDING REFLECTS PARTICIPATION BY NORFOLK SOUTHERN CORPORATION
WAKE, DURHAM | US 70 (GLENWOOD AVENUE) | WEST OF SR 3067 (T.W. ALEXANDER DRIVE) TO I-540 IN RALEIGH. UPGRADE ROADWAY TO IMPROVE CAPACITY, SAFETY AND TRAFFIC OPERATIONS INCLUDING INTERCHANGES AT VARIOUS LOCATIONS. | HIGHWAY | 5 | CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | U-5518 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | NHP | 2025 | 153208000 | 2025 | 15714000 | 2025 | 168499000 | 337421000 | COORDINATE WITH U-2823 AND U-5720; DESIGN BUILD PROJECT
WAKE, JOHNSTON | I-40; I-87; I-440; US 1 / US 64 | I-40 FROM SR 1728 (WADE AVENUE) TO NC 42, I-440, I-87 FROM I-40 TO I-540, US 1 FROM NC 540 TO I-40. CONVERT FACILITIES TO MANAGED FREEWAYS, TO INCLUDE RAMP METERING. | HIGHWAY | 4, 5 | CAPITAL AREA MPO | U-6101 | NOT FUNDED | WILL BE REPRIORITIZED | NHP | NOT FUNDED | 1000000 | NOT FUNDED | 500000 | NOT FUNDED | 138201000 | 139701000
WAKE, JOHNSTON | NEW ROUTE (FUTURE NC 540) | EASTERN WAKE FREEWAY / TRIANGLE EXPRESSWAY SOUTHEAST EXTENSION (RALEIGH OUTER LOOP), I-40 TO US 64 / US 264 BYPASS. FREEWAY ON NEW LOCATION. | HIGHWAY | 4, 5 | CAPITAL AREA MPO | R-2829 | STATEWIDE MOBILITY | SCHEDULED FOR DELIVERY | BOND R, NHP, S(M) | 2025 |  | 2025 |  | 2026 | 425338000 | 425338000 | NORTH CAROLINA TURNPIKE AUTHORITY DESIGN-BUILD PROJECT; GARVEE BONDS: $262.5 MILLION FOR CONSTRUCTION - PAYBACK 2026-2040
WASHINGTON | SR 1106 (MORATTOCK ROAD) | SR 1100 (LONG RIDGE ROAD) TO NC 32 SOUTH. MODERNIZE ROADWAY. | HIGHWAY | 1 | ALBEMARLE RPO | R-5937 | DIVISION 1 | SCHEDULED FOR DELIVERY | T | 2028 | 400000 | 2028 | 200000 | 2030 | 12300000 | 12900000
WASHINGTON | SR 1126 (ROPER NEWLAND ROAD) | SR 1128 (A CANAL ROAD) TO SR 1183 (SHORE DRIVE). MODERNIZE ROADWAY. | HIGHWAY | 1 | ALBEMARLE RPO | R-5936 | DIVISION 1 | SCHEDULED FOR DELIVERY | T | 2026 | 200000 | 2026 | 200000 | 2028 | 18700000 | 19100000
WATAUGA | US 421 (KING STREET) MULTI-USE PATH | GROVE STREET TO BROOKSHIRE ROAD. CONSTRUCT MULTI-USE PATH. | BIKE/PED | 11 | HIGH COUNTRY RPO | EB-5983 | DIVISION 11 | SCHEDULED FOR DELIVERY | L, TA5200 | 2024 | 16000 |  |  | 2025 | 1492000 | 1508000
WATAUGA | NC 105 | SR 1136 (CLARKS CREEK ROAD) TO SR 1107 (NC 105 BYPASS) IN BOONE. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-2566B | REGION F | SCHEDULED FOR DELIVERY | T | 2022 | 14365000 | 2022 | 9300000 | 2025 | 44301000 | 67966000 | BUILD NC BOND FUNDING: $4M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE);
WATAUGA | SR 1514 (BAMBOO ROAD); SR 1523 (WILSON RIDGE) | US 421/US 221 TO SR 1522 (DEERFIELD ROAD). MODERNIZE ROADWAY. | HIGHWAY | 11 | HIGH COUNTRY RPO | U-5810 | DIVISION 11 | SCHEDULED FOR DELIVERY | T | 2022 | 13400000 | 2022 | 1500000 | 2024 | 25225000 | 40125000 | BUILD NC BOND FUNDING: $3.5M FOR RIGHT-OF-WAY, PAYBACK FY 2022-2036 (FY 2022 / YR 4 SALE); $10.2M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE)
WATAUGA | SR 1522 (DEERFIELD ROAD) | STATE FARM ROAD TO SR 1523 (WILSON RIDGE ROAD). UPGRADE ROADWAY. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5830 | DIVISION 11 | SCHEDULED FOR DELIVERY | T | 2024 | 5800000 | 2024 | 1200000 | 2025 | 6200000 | 13200000
WATAUGA | US 321 | DEERFIELD ROAD AND MEADOWVIEW ROAD. REALIGN OFFSET INTERSECTION. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5874 | NOT FUNDED | WILL BE REPRIORITIZED | NHP | NOT FUNDED | 5700000 | NOT FUNDED | 1000000 | NOT FUNDED | 7799000 | 14499000
WATAUGA | US 421 | SR 1180 (POPLAR GROVE CONNECTOR). CONSTRUCT ROUNDABOUT. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5872 | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | NHP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 5000000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 200000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 3100000 | 8300000
WATAUGA | US 421 | TENNESSEE LINE TO US 321-US 421 JUNCTION NEAR VILAS. WIDEN TO MULTI-LANES. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5903 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 30600000 | NOT FUNDED | 1500000 | NOT FUNDED | 54902000 | 87002000
WATAUGA | US 421 (DANIEL BOONE PARKWAY) | US 321/421 WEST OF BOONE TO NC 105 | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5915A | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 81700000 | NOT FUNDED | 400000 | NOT FUNDED | 165600000 | 247700000
WATAUGA | US 421 (DANIEL BOONE PARKWAY) | NC 105 TO US 221/321 SOUTH OF BOONE | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5915B | DIVISION 11 | SCHEDULED FOR DELIVERY | T | 2028 | 84800000 | 2028 | 600000 | 2031 | 246600000 | 332000000
WATAUGA | US 421 (DANIEL BOONE PARKWAY) | US 221/321 TO US 221/421 EAST OF BOONE | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5915C | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 133800000 | NOT FUNDED | 400000 | NOT FUNDED | 384600000 | 518800000
WATAUGA | US 421/US 321 | US 321/US 421 JUNCTION NEAR VILAS TO SR 1107 (105 BYPASS) - TERMINI OF PROPOSED DANIEL BOONE PARKWAY (R-5915). WIDEN TO MULTI-LANES. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-2615 | REGION F | SCHEDULED FOR DELIVERY | T | 2027 | 40900000 | 2027 | 1500000 | 2030 | 50200000 | 92600000
WAYNE | MOUNT OLIVE MUNICIPAL AIRPORT (W40) | EXTEND RUNWAY TO 5500 FEET. | AVIATION | 4 | EASTERN CAROLINA RPO | AV-5811 | DIVISION 4 | SCHEDULED FOR DELIVERY | T |  |  |  |  | 2027 | 768000 | 768000
WAYNE | WAYNE EXECUTIVE JETPORT (GWW) | EXTEND RUNWAY. | AVIATION | 4 | GOLDSBORO URBAN AREA MPO | AV-5843 | DIVISION 4 | WILL BE REPRIORITIZED | T |  |  |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 6950000 | 6950000
WAYNE | GOLDSBORO | BERKELEY BOULEVARD, US 70 BUSINESS (EAST ASH STREET) TO SR 1900 (ELM STREET) IN GOLDSBORO. CONSTRUCT SIDEWALK ON EAST SIDE. | BIKE/PED | 4 | GOLDSBORO URBAN AREA MPO | EB-5850 | DIVISION 4 | SCHEDULED FOR DELIVERY | L, TA5200 |  |  |  |  | 2025 | 101000 | 101000
WAYNE | NC 581 (BILL LANE BOULEVARD) | ARRINGTON BRIDGE ROAD TO NC 111. MODERNIZE ROADWAY. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-6207 | DIVISION 4 | SCHEDULED FOR DELIVERY | T | 2027 | 1700000 | 2027 | 400000 | 2029 | 5000000 | 7100000
WAYNE | SR 1556 (WAYNE MEMORIAL DRIVE) | SR 1003 (NEW HOPE ROAD) TO PROPOSED US 70 BYPASS IN GOLDSBORO. WIDEN TO MULTI-LANES. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-4753 | DIVISION 4 | SCHEDULED FOR DELIVERY | T | 2019 | 4180000 |  |  | 2025 | 8260000 | 12440000 | RIGHT-OF-WAY IN PROGRESS
WAYNE | SR 1556 (WAYNE MEMORIAL DRIVE) | COUNTRY DAY ROAD TO NEW HOPE ROAD. ACCESS MANAGEMENT. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-6204 | DIVISION 4 | SCHEDULED FOR DELIVERY | T | 2026 | 2900000 | 2026 | 2700000 | 2028 | 9400000 | 15000000
WAYNE | SR 1556 (WAYNE MEMORIAL DRIVE) | US 70 BYPASS TO SR 1572 (SAULSTON ROAD). WIDEN ROADWAY. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-6205 | DIVISION 4 | SCHEDULED FOR DELIVERY | T | 2027 | 1900000 | 2027 | 1000000 | 2029 | 20300000 | 23200000
WAYNE | SR 1713 (MILLER'S CHAPEL ROAD) | US 70 TO SR 1712 (THOROUGHFARE ROAD). MODERNIZE ROADWAY. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-6206 | DIVISION 4 | SCHEDULED FOR DELIVERY | T | 2027 | 2500000 | 2027 | 900000 | 2029 | 5600000 | 9000000
WAYNE | US 117 (FUTURE I-795) | NORTH OF SR 1135 (COUNTRY CLUB ROAD) TO SOUTH OF SR 1129 (SOUTH LANDFILL ROAD). | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO, EASTERN CAROLINA RPO | U-3125C | REGION A | SCHEDULED FOR DELIVERY | NHP | 2026 | 100000 | 2026 | 138000 | 2028 | 13300000 | 13538000
WAYNE | US 117 (FUTURE I-795) | SOUTH OF SR 1129 (SOUTH LANDFILL ROAD) TO SOUTH OF SR 1927 (GENOA ROAD). | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-3125D | REGION A | SCHEDULED FOR DELIVERY | NHP | 2027 | 13529000 | 2027 | 2172000 | 2029 | 59400000 | 75101000
WAYNE | US 117 (FUTURE I-795) | SOUTH OF SR 1927 (GENOA ROAD) TO NORTH OF NC 581 (ARRINGTON BRIDGE ROAD). | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-3125E | NOT FUNDED | WILL BE REPRIORITIZED | NHP | NOT FUNDED | 35788000 | NOT FUNDED | 1513000 | NOT FUNDED | 135500000 | 172801000
WAYNE | US 117 (FUTURE I-795) | NORTH OF NC 581 (ARRINGTON BRIDGE ROAD) TO I-795. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-3125F | NOT FUNDED | WILL BE REPRIORITIZED | NHP | NOT FUNDED | 20760000 | NOT FUNDED | 4729000 | NOT FUNDED | 62700000 | 88189000
WAYNE | US 13 (BERKELEY BOULEVARD) | WIDEN TO MULTI-LANES FROM SR 1003 (NEW HOPE ROAD) TO US 70 BYPASS WITH INTERSECTION IMPROVEMENT AT SR1572 (SAULSTON ROAD) | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-3609B | REGION A | SCHEDULED FOR DELIVERY | T | 2020 | 16339000 | 2020 | 3750000 | 2025 | 29670000 | 49759000 | RIGHT-OF-WAY IN PROGRESS. BUILD NC BOND FUNDING: $1,862,685 FOR PE, $1,253.83 FOR ROW PAYBACK 2020 - 2034 (FY 2019 / YR 1 SALE); $10,000,000 FOR CONSTRUCTION PAYBACK 2025 - 2038 (FY 2024 / YR 6 SALE).
WAYNE | US 70 | SR 1711 (NORTH OAK FOREST ROAD). IMPROVE INTERSECTION. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-6110 | REGION A | SCHEDULED FOR DELIVERY | NHP | 2025 | 200000 | 2025 | 2200000 | 2027 | 4100000 | 6500000
WAYNE | US 70 BUSINESS (EAST ASH STREET) | SR 1579 (BERKELEY BOULEVARD) EAST TO US 70 IN GOLDSBORO. WIDEN TO MULTI-LANES. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-4407 | REGION A | SCHEDULED FOR DELIVERY | T | 2026 | 3979000 | 2026 | 2090000 | 2028 | 17500000 | 23569000
WAYNE, GREENE | US 13 | SR 1572 (SAULSTON ROAD) TO SR 1700 (RODELL BARROW ROAD). MODERNIZE ROADWAY. | HIGHWAY | 2, 4 | GOLDSBORO URBAN AREA MPO, EASTERN CAROLINA RPO | R-5853 | DIVISION 2, 4 | SCHEDULED FOR DELIVERY | T | 2025 | 2488000 | 2025 | 3040000 | 2027 | 8800000 | 14328000
WAYNE, JOHNSTON | US 70 | US 70 BYPASS TO WEST OF SR 2372 (EDWARDS ROAD / NORTH PEARL STREET). UPGRADE TO FREEWAY STANDARDS. | HIGHWAY | 4 | EASTERN CAROLINA RPO, GOLDSBORO URBAN AREA MPO, UPPER COASTAL PLAIN RPO | R-5829A | STATEWIDE MOBILITY | WILL BE REPRIORITIZED | T | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 40072000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 7908000 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 101600000 | 149580000
WILKES | WILKES COUNTY AIRPORT (UKF) | EXTEND RUNWAY TO 7,000 FEET. | AVIATION | 11 | HIGH COUNTRY RPO | AV-5894 | DIVISION 11 | SCHEDULED FOR DELIVERY | T | 2023 | 600000 |  |  | 2024 | 12300000 | 12900000
WILKES | NC 115 | US 421 TO 2ND STREET. WIDEN ROADWAY. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5759 | DIVISION 11 | SCHEDULED FOR DELIVERY | T | 2022 | 12615000 | 2022 | 900000 | 2024 | 31040000 | 44555000 | BUILD NC BOND FUNDING: $1.057 M FOR PRELIMINARY ENGINEERING, PAYBACK 2020-2034 (FY 2019 / YR 1 SALE); $1,129 FOR ROW, PAYBACK FY 2020-2034 (FY 2019 / YR1 SALE); $13M FOR CONSTRUCTION, PAYBACK FY 2024-2038 (FY 2024 / YR 6 SALE)
WILKES | NC 268 | SR 1966 TO FOUR LANES WEST OF SR 2026 (AUSTIN TRAPHILL ROAD). MODERNIZE ROADWAY. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5906 | DIVISION 11 | SCHEDULED FOR DELIVERY | BGLT5 | 2026 | 36000000 | 2026 | 600000 | 2029 | 52299000 | 88899000
WILKES | NEW ROUTE | NC 268 CONNECTOR, NC 18 TO US 421. CONSTRUCT MULTI-LANE FACILITY, PART ON NEW LOCATION. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-0616 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 18200000 | NOT FUNDED | 1100000 | NOT FUNDED | 132201000 | 151501000
WILKES | SR 1001 (OAKWOODS ROAD) | US 421 TO FOREST HILLS DRIVE. UPGRADE ROADWAY. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5772 | DIVISION 11 | SCHEDULED FOR DELIVERY | T | 2026 | 3000000 | 2026 | 1500000 | 2028 | 10448000 | 14948000
WILSON | NC 58 (NASH STREET NW) | SR 1330 (AIRPORT ROAD)/SR 1332 (LAKE WILSON ROAD). IMPROVE INTERSECTION. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | U-6111 | REGION A | SCHEDULED FOR DELIVERY | T | 2027 | 700000 | 2027 | 400000 | 2029 | 5400000 | 6500000
WILSON | SR 1309 (BLOOMERY ROAD) / SR 1382 (PACKHOUSE ROAD) | US 264 ALTERNATE TO NC 58. WIDEN AND UPGRADE FACILITY. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | U-5794 | DIVISION 4 | SCHEDULED FOR DELIVERY | T | 2023 | 1000000 | 2023 | 946000 | 2025 | 9199000 | 11145000
WILSON | US 264 ALTERNATE (RALEIGH ROAD PARKWAY) | SR 1320 (AIRPORT BOULEVARD) TO EAST OF SR 1165 (FOREST HILLS ROAD). SAFETY IMPROVEMENTS. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | U-5941 | REGION A | SCHEDULED FOR DELIVERY | T | 2026 | 12100000 | 2026 | 3900000 | 2028 | 11000000 | 27000000
WILSON | WILSON | WILSON CITY SIGNAL SYSTEM. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | U-5945 | NOT FUNDED | WILL BE REPRIORITIZED | BG5200 |  |  | NOT FUNDED | 700000 | NOT FUNDED | 6600000 | 7300000
YADKIN | NC 67 | US 601 IN BOONVILLE TO WEST MAIN STREET IN EAST BEND. MODERNIZE ROADWAY WITH INTERSECTION IMPROVEMENTS AT NEBO ROAD. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5914 | DIVISION 11 | SCHEDULED FOR DELIVERY | BGLT5 | 2026 | 9000000 | 2026 | 1000000 | 2028 | 39900000 | 49900000
YADKIN | SR 1314 (EAST MAIN STREET) | US 601 TO SR 1765 (UNIFI INDUSTRIAL ROAD) IN YADKINVILLE. MODERNIZE ROADWAY, INCLUDING IMPROVEMENTS AT THE US 601 AND VAN BUREN STREET INTERSECTIONS. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5909 | DIVISION 11 | SCHEDULED FOR DELIVERY | BGLT5 | 2026 | 1900000 | 2026 | 5800000 | 2028 | 4300000 | 12000000
YADKIN | SR 1605 (OLD US 421) | SR 1600 (FALCON ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5912 | DIVISION 11 | SCHEDULED FOR DELIVERY | T | 2023 | 600000 | 2023 | 100000 | 2024 | 1200000 | 1900000
YADKIN | US 601 | NC 67 TO (SR 1502/1503) COUNTRY CLUB ROAD. MODERNIZE ROADWAY AND IMPROVE SR 1134 (MACKIE ROAD) INTERSECTION. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5896 | NOT FUNDED | WILL BE REPRIORITIZED | T | NOT FUNDED | 2000000 | NOT FUNDED | 300000 | NOT FUNDED | 2100000 | 4400000
YADKIN | US 601 (SOUTH STATE STREET) | US 421 EASTBOUND RAMPS. INSTALL ROUNDABOUT. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5894 | REGION F | SCHEDULED FOR DELIVERY | NHP | 2024 | 300000 | 2024 | 100000 | 2026 | 3300000 | 3700000 | COORDINATE WITH U-5809.
YADKIN | US 601 (STATE STREET) | US 421 TO SR 1146 (LEE AVENUE). CONSTRUCT MEDIAN AND ROUNDABOUTS. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | U-5809 | DIVISION 11 | SCHEDULED FOR DELIVERY | T |  |  | 2023 | 800000 | 2024 | 11402000 | 12202000 | RIGHT-OF-WAY IN PROGRESS. COORDINATE WITH R-5894.
YADKIN, SURRY | NC 67, US 21 BUSINESS | COMMERCE STREET IN ELKIN TO NORTH BRIDGE STREET IN JONESVILLE. WIDEN ROADWAY, CONSTRUCT ROUNDABOUTS AT WEST MAIN STREET AND ELM STREET AND ELM STREET AND NORTH BRIDGE STREET, AND IMPROVE BICYCLE AND PEDESTRIAN CONNECTIONS. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5913A | DIVISION 11 | SCHEDULED FOR DELIVERY | BG5200 | 2023 | 1100000 | 2023 | 220000 | 2025 | 3300000 | 4620000

## Swap Projects Schedule Compare
REVISED DRAFT 2024-2033 STATE TRANSPORTATION IMPROVEMENT PROGRAM: PROJECTS ELIGIBLE FOR SWAPS
NOTES: COSTS AND SCHEDULES ARE AS OF AUGUST 4, 2022 AND ARE SUBJECT TO CHANGE. PRIORITIZATION STATUS IS BASED ON THE FIRST YEAR OF RIGHT-OF-WAY, UTILITIES, OR CONSTRUCTION FUNDING. IF THE FIRST YEAR OF RIGHT-OF-WAY, UTILITIES, OR CONSTRUCTION FUNDING IS SCHEDULED ON OR BEFORE FISCAL YEAR 2028, THE PROJECT IS CONSIDERED "SCHEDULED FOR DELIVERY" AND DOES NOT HAVE TO BE REPRIORITIZED.
BASIC PROJECT INFORMATION | [6 empty] | PRIORITIZATION INFORMATION |  |  |  |  | FISCAL YEAR PROJECT PHASE SCHEDULED TO START
COUNTY(S) | ROUTE/CITY | DESCRIPTION | MODE | DIVISION(S) | MPOs/RPOs | PROJECT ID | STI CATEGORY FUNDED | PRIORITIZATION SCORE AT THE TIME PROJECT WAS COMMITTED | COMMITTED STATUS CURRENT 2020-2029 STIP | PRIORITIZATION STATUS DRAFT 2024-2033 STIP (APRIL 2022) | PRIORITIZATION STATUS DRAFT 2024-2033 STIP (AUGUST 2022) | RIGHT-OF-WAY SCHEDULE CURRENT 2020-2029 STIP | RIGHT-OF-WAY SCHEDULE DRAFT 2024-2033 STIP (APRIL 2022) | RIGHT-OF-WAY SCHEDULE DRAFT 2024-2033 STIP (AUGUST 2022) | UTILITIES SCHEDULE CURRENT 2020-2029 STIP | UTILITIES SCHEDULE DRAFT 2024-2033 STIP (APRIL 2022) | UTILITIES SCHEDULE DRAFT 2024-2033 STIP (AUGUST 2022) | CONSTRUCTION SCHEDULE CURRENT 2020-2029 STIP | CONSTRUCTION SCHEDULE DRAFT 2024-2033 STIP (APRIL 2022) | CONSTRUCTION SCHEDULE DRAFT 2024-2033 STIP (AUGUST 2022)
ALAMANCE | BURLINGTON- ALAMANCE REGIONAL AIRPORT (BUY) | CONSTRUCT 100 FT PAVED OVERRUN AND MAKE SAFETY ENHANCEMENTS. | AVIATION | 7 | BURLINGTON-GRAHAM MPO | AV-5851 | DIVISION 7 | 75.69 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2024 | 2024 | 2024
ALAMANCE | LEE AVENUE | WEST LEBANON AVENUE TO SR 1454 (WEST HAGGARD AVENUE) IN ELON. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | BURLINGTON-GRAHAM MPO | EB-5988 | DIVISION 7 | 88.31 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | 2025 |  |  |  | 2026 | 2026 | 2026
ALAMANCE | I-40 / I-85 | SR 1158 (HUFFMAN MILL ROAD) INTERCHANGE. CONSTRUCT ADDITIONAL LEFT TURN LANE ON I-40 WESTBOUND RAMP AND IMPROVE OPERATIONS AT SR 1308 (GARDEN ROAD) INTERSECTION. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | I-6009 | STATEWIDE MOBILITY | 81.94 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
ALAMANCE | I-40 / I-85 | SR 1981 (TROLLINGWOOD-HAWFIELDS ROAD) IN MEBANE. UPGRADE INTERCHANGE. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | I-6059 | DIVISION 7 | 81.95 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
ALAMANCE | NC 119 | SR 1981 (TROLLINGWOOD-HAWFIELDS ROAD) / SR 2126 (OLD HILLSBOROUGH ROAD TO LOWES BOULEVARD IN MEBANE. WIDEN TO MULTILANES. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6013 | DIVISION 7 | 80.71 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024
ALAMANCE | NC 49 (ROXBORO ROAD) | SR 1928 (WILKINS ROAD) AND SR 1927 (BASON ROAD). UPGRADE K-TYPE INTERSECTION. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6183 | DIVISION 7 | 79.84 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
ALAMANCE | NC 54 (CHAPEL HILL ROAD) | SR 1445 (SOUTH O'NEAL STREET) IN BURLINGTON. RECONFIGURE INTERSECTION TO MAKE O'NEAL STREET THE THROUGH MOVEMENT WITH NC 54 EAST OF THE INTERSECTION. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6184 | DIVISION 7 | 79.82 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
ALAMANCE | NC 54 (EAST HARDEN STREET) | SR 1945 (RIVERBEND ROAD) / SR 2431 (JOHNSON STREET) INTERSECTIONIN GRAHAM. INTERSECTION IMPROVEMENTS. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6115A | DIVISION 7 | 88.11 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
ALAMANCE | NC 54 (EAST HARDEN STREET) | I-40 / I-85 INTERCHANGE IN GRAHAM. UPGRADE RAMP INTERSECTIONS. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6115B | REGION D | 79.56 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
ALAMANCE | NC 54 (EAST HARDEN STREET) | SR 2106 (WOODY DRIVE) IN GRAHAM. INTERSECTION IMPROVEMENTS. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6115C | REGION D | 83.48 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
ALAMANCE | NC 54 (EAST HARDEN STREET) | SR 2106 (WOODY DRIVE) AND SR 2107 (WHITTEMORE ROAD) INTERSECTIONS IN GRAHAM. UPGRADE PIPE CULVERTS 000271 AND 000297. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6115D | REGION D | 77.28 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2028 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY
ALAMANCE | NC 54 (WEST HARDEN STREET) | NC 49 (MAPLE AVENUE) IN BURLINGTON. INSTALL DUAL LEFT TURN LANES IN WESTBOUND DIRECTION. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6131 | REGION D | 78.51 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2028 | 2025 | 2025 | 2028 | 2025 | 2026 | 2030 | 2026
ALAMANCE | NC 62 | SR 1430 (RAMADA ROAD) TO US 70 (CHURCH STREET) IN BURLINGTON. WIDEN TO MULTILANES. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-5844 | DIVISION 7 | 69.22 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025
ALAMANCE | NC 62 (ALAMANCE ROAD) | SR 1155 (HATCHERY ROAD) / BONNIE LANE INTERSECTION IN BURLINGTON. INSTALL TRAFFIC SIGNAL AND ADD TURN LANES. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6114 | REGION D | 85.14 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
ALAMANCE | NC 87 (WEBB AVENUE) | SR 1515 (FLORA AVENUE). INSTALL TRAFFIC SIGNAL AND ADD TURN LANES. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6182 | DIVISION 7 | 80.27 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
ALAMANCE | SR 1455 (EAST HAGGARD AVENUE) | NC 87 (WEST WEBB AVENUE) / NC 100 (UNIVERSITY DRIVE) IN ELON. IMPROVE INTERSECTION. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6214 | DIVISION 7 | 63.46 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
ALAMANCE | SR 1716 (GRAHAM- HOPEDALE ROAD) | SR 1720 (WEST HANOVER ROAD) TO MORNINGSIDE DRIVE IN BURLINGTON. WIDEN TO MULTILANES WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6014 | DIVISION 7 | 80.16 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2025 | 2025 | 2025
ALAMANCE | SR 1716 (NORTH MAIN STREET) | SR 2396 (WEST PARKER STREET) IN GRAHAM. IMPROVE INTERSECTION. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6132 | DIVISION 7 | 84.5 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
ALAMANCE | US 70 (SOUTH CHURCH STREET) | TARLETON AVENUE TO FIFTH STREET IN BURLINGTON. WIDEN AND CONSTRUCT CENTER TURN LANE. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6009 | REGION D | 73.54 | P4.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2030
ALAMANCE | US 70 (SOUTH CHURCH STREET) | SR 1158 (HUFFMAN MILL ROAD) IN BURLINGTON. INTERSECTION IMPROVEMENTS. | HIGHWAY | 7 | BURLINGTON-GRAHAM MPO | U-6011 | REGION D | 73.47 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2025 | 2025 | 2025
ALEXANDER | NC 16 | CATAWBA RIVER TO US 64 IN TAYLORSVILLE. UPGRADE AND MODERNIZE TWO-LANE ROADWAY. | HIGHWAY | 12 | GREATER HICKORY MPO | U-6151 | NOT FUNDED | 68 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
ALEXANDER | US 64 | US 64 AND SR 1124. ADD LEFT TURN LANE ON WESTBOUND US 64/NC 90 | HIGHWAY | 12 | GREATER HICKORY MPO | U-6041 | DIVISION 12 | 75.76 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025
ALEXANDER, CATAWBA | NC 127 | SR 1400 (CLONINGER MILL ROAD) TO SR 1156 (RICHEY ROAD). | HIGHWAY | 12 | GREATER HICKORY MPO | R-3603A | DIVISION 12 | 76.56 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2026 | 2026 | 2026
ANSON | NEW ROUTE - WADESBORO BYPASS | US 52 NORTH OF WADESBORO TO US 74 EAST OF WADESBORO. CONSTRUCT FREEWAY ON NEW LOCATION. | HIGHWAY | 10 | ROCKY RIVER RPO | R-5878B | REGION E | 78.56 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2027 | 2027 | 2024 | 2027 | 2027 | 2027 | 2029 | 2029
ANSON | US 74 | NC 742 (GRAHAM STREET) TO ANSON HIGH SCHOOL ROAD. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 10 | ROCKY RIVER RPO | R-5871 | STATEWIDE MOBILITY | 85.64 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
ANSON | US 74 (ANDREW JACKSON HIGHWAY) | GRAHAM STREET TO SR 1749. CONSTRUCT MEDIAN. | HIGHWAY | 10 | ROCKY RIVER RPO | R-5798 | STATEWIDE MOBILITY | 67.64 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2026 | 2027 | 2026
ANSON | CSX SF LINE | CONSTRUCT SIDING EXTENSION IN POLKTON. | RAIL | 10 | ROCKY RIVER RPO | P-5750A | REGION E | 78.49 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 |  |  |  | 2024 | 2024 | 2024
ANSON | CSX SF LINE | SR 1469 (FREEDOM ROAD) INTERSECTION. CONSTRUCT GRADE SEPARATION. | RAIL | 10 | ROCKY RIVER RPO | P-5750B | REGION E | 78.49 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2026 | 2026 | 2026
ASHE | NC 88 | NC 88 TO NC 194. UPGRADE ROADWAY. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5832 | DIVISION 11 | 75.83 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2023 | 2022 | 2022 | 2023 | 2024 | 2024 | 2025
ASHE | US 221 BUSINESS | NC 194 AND SR 1248 (BEAVER CREEK SCHOOL ROAD) INTERSECTION. CONSTRUCT SUPERSTREET INTERSECTION. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5833 | NOT FUNDED | 65.55 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2027 | NOT FUNDED | NOT FUNDED | 2027 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
AVERY | NC 184 | NC 105 TO SR 1342 (HICKORY NUT GAP ROAD) IN BANNER ELK. WIDEN TO MULTI-LANES. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5902 | NOT FUNDED | 66.61 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
AVERY, MITCHELL | US 19E | MULTI-LANES EAST OF SPRUCE PINE TO SR 1106. WIDEN TO MULTI-LANES. | HIGHWAY | 11, 13 | HIGH COUNTRY RPO | R-2520A | DIVISION 11, 13 | 78.29 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY
BEAUFORT | WARREN FIELD (OCW) | ACQUIRE LAND FOR AND CONSTRUCT RUNWAY 5-23 EXTENSION AND TAXIWAY. | AVIATION | 2 | MID-EAST RPO | AV-5743 | DIVISION 2 | 83.45 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | 2028 |  |  |  | 2029 | 2029 | 2029
BEAUFORT | NC 32 | BRICK KILN ROAD. IMPROVE INTERSECTION. | HIGHWAY | 2 | MID-EAST RPO | R-5897 | NOT FUNDED | 74.52 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
BEAUFORT | SR 1306 (15TH STREET) | US 17 BUSINESS (CAROLINA AVENUE) TO BROWN STREET. WIDEN TO MULTI-LANES. | HIGHWAY | 2 | MID-EAST RPO | U-5860 | DIVISION 2 | 76.54 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2029 | 2026 | 2026 |  | 2026 | 2026 | AFTER 2029 | 2028 | 2028
BERTIE | NC 45 | US 17 AT MIDWAY TO SOUTHERN CITY LIMITS OF COLERAIN. | HIGHWAY | 1 | PEANUT BELT RPO | R-5809B | DIVISION 1 | 65.95 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2024 | 2023 | 2023 | 2024 | 2025 | 2025 | 2026
BLADEN | FIELD (EYF) CURTIS L BROWN JR | EXTEND RUNWAY TO 5500 FEET AND PARALLEL TAXIWAY. | AVIATION | 6 | MID-CAROLINA RPO | AV-5826 | DIVISION 6 | 88.04 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | [6 empty] | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
BRUNSWICK | NC 211 (NORTH HOWE STREET) | EAST OWEN STREET TO DOSHER HOSPITAL IN SOUTHPORT. CONSTRUCT SIDEWALK. | BIKE/PED | 3 | CAPE FEAR RPO | EB-5982 | DIVISION 3 | 87.49 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 |  |  |  | 2025 | 2025 | 2025
BRUNSWICK | NC 211 | SR 1112 (SUNSET HARBOR ROAD) TO NC 906 (MIDWAY ROAD). WIDEN ROADWAY. | HIGHWAY | 3 | CAPE FEAR RPO | R-5947 | NOT FUNDED | 82.61 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
BRUNSWICK | US 17 | NC 904. CONVERT INTERSECTION TO SUPERSTREET. | HIGHWAY | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | R-5851 | NOT FUNDED | 76.45 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2028 | NOT FUNDED | NOT FUNDED | 2028 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
BRUNSWICK | US 17 | US 17 BUSINESS SOUTH OF SHALLOTTE AND US 17 BUSINESS NORTH OF SHALLOTTE. CONVERT INTERSECTIONS TO SUPERSTREETS. | HIGHWAY | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | R-5857 | STATEWIDE MOBILITY | 64.25 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2025 | 2026 | 2025
BRUNSWICK | US 17 | NC 211. CONVERT INTERSECTION TO INTERCHANGE. | HIGHWAY | 3 | CAPE FEAR RPO, GRAND STRAND AREA TRANSPORTATION STUDY | U-5932 | STATEWIDE MOBILITY | 73.75 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
BRUNSWICK | US 17 (SHALLOTTE BYPASS) | SR 1357 (SMITH AVENUE). UPGRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | U-5862 | REGION B | 55.64 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2028 | 2028 |  | 2028 | 2028 | AFTER 2029 | 2030 | 2030
BRUNSWICK | US 17 (SHALLOTTE BYPASS) | US 17 BUSINESS SOUTH (MAIN STREET). UPGRADE EXISTING AT GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 3 | GRAND STRAND AREA TRANSPORTATION STUDY | U-6104 | NOT FUNDED | 77.69 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
BRUNSWICK, NEW HANOVER | SOUTHPORT - FORT FISHER | CONSTRUCT MOORING FACILITIES. | FERRY | 3 | CAPE FEAR RPO, WILMINGTON URBAN AREA MPO | F-5707 | REGION B | 73.89 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2025 | 2025 | 2025
BRUNSWICK, NEW HANOVER | SOUTHPORT-FORT FISHER | SOUTHPORT-FORT FISHER FERRY. CONSTRUCT RIVER CLASS FERRY. | FERRY | 3 | CAPE FEAR RPO, WILMINGTON URBAN AREA MPO | F-5705 | NOT FUNDED | 82.22 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | [6 empty] | 2029 | NOT FUNDED | NOT FUNDED
BUNCOMBE | DEAVERVIEW ROAD | US 19/23/74A (PATTON AVENUE) TO WESTMORE DRIVE IN ASHEVILLE. CONSTRUCT SIDEWALK. | BIKE/PED | 13 | FRENCH BROAD RIVER MPO | EB-5965 | DIVISION 13 | 87.31 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | 2026 |  |  |  | 2027 | 2027 | 2027
BUNCOMBE | MCDOWELL STREET CHOCTAW STREET | SOUTHSIDE AVENUE TO CHOCTAW STREET AT BILTMORE AVENUE. CONSTRUCT PEDESTRIAN IMPROVEMENTS. | BIKE/PED | 13 | FRENCH BROAD RIVER MPO | EB-5919 | DIVISION 13 | 57.72 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2022 |  |  |  | 2024 | 2024 | 2024
BUNCOMBE | NORTH RAD GREENWAY | CONSTRUCT MULTI-USE PATH ALONG RIVERSIDE DRIVE FROM HILL STREET TO US 19/23/70 AT BROADWAY | BIKE/PED | 13 | FRENCH BROAD RIVER MPO | EB-5822 | DIVISION 13 | 82.86 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 |  |  |  | 2025 | 2025 | 2025
BUNCOMBE | ASHEVILLE | US 19 (PATTON AVENUE) AND NC 63 (NEW LEICESTER HIGHWAY). CONSTRUCT FINAL INTERSECTION IMPROVEMENTS. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-5971B | NOT FUNDED | 80.26 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
BUNCOMBE | ASHEVILLE | NC 63 (NEW LEICESTER HIGHWAY), US 19/23 (PATTON AVENUE) TO NEWFOUND ROAD. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-5972 | NOT FUNDED | 72.87 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
BUNCOMBE | I-26 (US 19/US 23) | SR 1781 (BROADWAY STREET) TO US 25/70 | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | A-0010AA | REGION G | 53.64 | P3.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | 2030 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2031
BUNCOMBE | I-26/I-240 | NORTH OF I-40 TO SR 3548 (HAYWOOD ROAD). WIDEN TO SIX LANE FREEWAY. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-2513AC | REGION G | 73.84 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2023 | 2022 | 2022 | 2023 | 2024 | 2024 | 2024
BUNCOMBE | I-26/I-240 | I-26/I-40/I-240 FINAL INTERCHANGE IMPROVEMENTS | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-2513C | STATEWIDE MOBILITY | 52.72 | P3.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
BUNCOMBE | I-40 | I-40/SR 1228 (LIBERTY ROAD). CONVERT GRADE SEPARATION TO AN INTERCHANGE AND CONSTRUCT TWO LANE ROADWAY NORTH OF I-40 TO SR 1224 AND FOUR LANE ROADWAY SOUTH OF I-40 TO US 19/US 23/NC 151 WITH PARTS ON NEW LOCATION. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-4759 | STATEWIDE MOBILITY | 49.99 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2019 | 2019 | 2019 | 2021 | 2019 | 2019 | 2025 | 2025 | 2025
BUNCOMBE | I-40 | I-240 / US 74 ALTERNATE INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-6018 | NOT FUNDED | 78.89 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
BUNCOMBE | I-40 | SR 2838 (PORTERS COVE ROAD) INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-6021 | NOT FUNDED | 75.47 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 |  |  | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
BUNCOMBE | I-40 | SR 1200 (WIGGINS ROAD) TO SR 1224 (MONTE VISTA ROAD). ADD ADDITIONAL LANES. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-6054C | NOT FUNDED | 72.88 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
BUNCOMBE | I-40, I-26 | SR 3548 (HAYWOOD ROAD) TO US 19/23 AT SR 1781 (BROADWAY) | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-2513B | STATEWIDE MOBILITY | 46.63 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024
BUNCOMBE | NC 112 (SARDIS ROAD/ SANDHILL ROAD) | NC 191 (BREVARD ROAD) TO US 19/23 (SMOKEY PARK HIGHWAY). WIDEN ROADWAY. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-6047 | DIVISION 13 | 69.71 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2028 | 2025 | 2025 | 2028 | 2025 | 2028 | 2031 | 2028
BUNCOMBE | NC 191 (BREVARD ROAD - OLD HAYWOOD ROAD) | SR 3498 (LEDBETTER ROAD) TO NORTH OF BLUE RIDGE PARKWAY. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-3403B | NOT FUNDED | 62.57 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
BUNCOMBE | NC 81 (SWANNANOA RIVER ROAD) | SR 3214 (BILTMORE AVENUE) TO US 74A (SOUTH TUNNEL ROAD). WIDEN EXISTING ROADWAY. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-5832 | DIVISION 13 | 66.32 | P3.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2030
BUNCOMBE | NC 81 (SWANNANOA RIVER ROAD) | US 70 (TUNNEL ROAD) TO US 74 (SOUTH TUNNEL ROAD). UPGRADE ROADWAY. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-6046 | DIVISION 13 | 81.02 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY
BUNCOMBE | RIVERWAY MULTI-MODAL NETWORK | CRAVEN STREET BRIDGE IMPROVEMENTS OVER THE FRENCH BROAD RIVER | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-5019E | DIVISION 13 | 38.53 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2024 | 2024 | 2024
BUNCOMBE | SR 1332 (NORTH LOUISIANA AVENUE) | US 19/23 (PATTON AVENUE) TO SR 1338 (EMMA ROAD). MODERNIZE ROADWAY. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-6162 | DIVISION 13 | 82.09 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2025 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2025 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY
BUNCOMBE | SR 1477 (RIVERSIDE DRIVE) | SR 1517 (HILL STREET) TO SR 1781 (BROADWAY STREET) | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-2513D | DIVISION 13 | 75.56 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024
BUNCOMBE | SR 2002 (RICEVILLE ROAD) | US 70 (TUNNEL ROAD) TO SR 2285 (CLEAR VISTA LANE). UPGRADE ROADWAY. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-5837 | DIVISION 13 | 41.09 | P3.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
BUNCOMBE | SR 2500 (BLUE RIDGE ROAD) | CONVERT I-40/SR 2500 (BLUE RIDGE ROAD) GRADE SEPARATION TO INTERCHANGE. WIDEN SR 2500 (BLUE RIDGE ROAD) TO THREE LANES FROM US 70 TO SOUTH OF I-40 AND UPGRADE ROADWAY SOUTH OF I-40 TO SR 2713. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | I-4409 | DIVISION 13 | 79.71 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2025 | 2025 | 2025
BUNCOMBE | SR 3116 (MILLS GAP ROAD) | US 25 (HENDERSONVILLE ROAD) TO SR 3157 (WESTON ROAD). UPGRADE EXISTING ROADWAY. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-5834 | DIVISION 13 | 65.38 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2019 | 2019 | 2019 |  |  |  | 2024 | 2024 | 2024
BUNCOMBE | SR 3116 (MILLS GAP ROAD) | SR 3136 (CANE CREEK ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-6163 | DIVISION 13 | 79.86 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2024 | 2023 | 2023 | 2024 | 2023 | 2023 | 2024
BUNCOMBE | SR 3556 (AMBOYROAD/ MEADOW ROAD) | I-240 TO NC 81/SR 3214 (BILTMORE AVENUE). WIDEN TO MULTI-LANES WITH NEW BRIDGE OVER THE FRENCH BROAD RIVER. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-4739 | DIVISION 13 | 77.19 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2029 | 2028 | 2028
BUNCOMBE | US 25A (SWEETEN CREEK ROAD) | US 25 (HENDERSONVILLE ROAD) TO SR 3081 (ROCK HILL ROAD) | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-2801A | REGION G | 57.07 | P3.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2024 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | 2024 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2031
BUNCOMBE | WEAVERVILLE | US 19 BUSINESS (WEAVERVILLE HIGHWAY) AND SR 1740 (NEW STOCK ROAD). CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO | U-5973 | NOT FUNDED | 73.06 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 |  |  | 2029 |  |  | AFTER 2029 | NOT FUNDED | NOT FUNDED
BUNCOMBE, MADISON | US 25/70 | NORTH OF SR 1584 (TILLERY BRANCH ROAD) TO SR 1727 (MONTICELLO ROAD). UPGRADE ROADWAY TO SUPERSTREET. | HIGHWAY | 13 | FRENCH BROAD RIVER MPO, LAND-OF-SKY RPO | U-6173 | NOT FUNDED | 75.52 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
BURKE | COLLEGE STREET MULTIMODAL CONNECTOR | NORTH GREEN STREET TO US 70 IN MORGANTON. CONSTRUCT MULTI-USE PATH. | BIKE/PED | 13 | GREATER HICKORY MPO | EB-5978 | DIVISION 13 | 77.1 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2022 |  |  |  | 2024 | 2024 | 2024
BURKE | I-40 | SR 1734 (CAROLINA STREET SE)/SR 1826 - EXIT 111. REVISE INTERCHANGE. | HIGHWAY | 13 | GREATER HICKORY MPO | I-5008 | REGION G | 55.14 | P3.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
BURKE | I-40 | US 64 (BURKEMONT ROAD). IMPROVE INTERCHANGE. | HIGHWAY | 13 | GREATER HICKORY MPO | I-5009 | REGION G | 62.2 | P3.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
BURKE | I-40 | SR 1142 (JAMESTOWN ROAD) - EXIT 100. UPGRADE INTERCHANGE. | HIGHWAY | 13 | GREATER HICKORY MPO | I-5874 | REGION G | 63.79 | P3.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
BURKE | I-40 | SR 1712 (DREXEL ROAD). UPGRADE INTERCHANGE. | HIGHWAY | 13 | GREATER HICKORY MPO | I-5875 | REGION G | 55.81 | P3.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
BURKE | I-40 | SR 1761 (OLD HIGHWAY NC 10) - EXIT 116. UPGRADE INTERCHANGE AND REMOVE TWO-WAY TRAFFIC. | HIGHWAY | 13 | GREATER HICKORY MPO | I-5971 | STATEWIDE MOBILITY | 70.92 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
BURKE | I-40 | SR 1744 (MINERAL SPRINGS MOUNTAIN ROAD)/SR 1744 (ELDRED STREET SE) - EXIT 112. CONSTRUCT INTERCHANGE IMPROVEMENTS. | HIGHWAY | 13 | GREATER HICKORY MPO | I-5975 | NOT FUNDED | 66.12 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
BURKE | I-40 | EXIT 118 - SR 1761 (OLD NC 10). CONTRUCT INTERCHANGE IMPROVEMENTS. | HIGHWAY | 13 | GREATER HICKORY MPO | I-5990 | DIVISION 13 | 68.95 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2024 | 2025 | 2024
BURKE | I-40 | SR 1147 (CAUSBY ROAD). REDESIGN INTERCHANGE AND REMOVE TWO-WAY ON RAMP. | HIGHWAY | 13 | GREATER HICKORY MPO | I-6058 | NOT FUNDED | 73.06 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
BURKE | NC 126 | SR 1250 (WATERMILL ROAD) TO SR 1254 (FISH HATCHERY ROAD). MODERNIZE ROADWAY. | HIGHWAY | 13 | GREATER HICKORY MPO | U-6164 | NOT FUNDED | 77.08 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
BURKE | NC 181 | SR 1414 (ST MARY'S CHURCH ROAD) TO MORGANTON ETJ. WIDEN EXISTING ROADWAY. | HIGHWAY | 13 | GREATER HICKORY MPO | U-5836 | REGION G | 50.48 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY |  | 2028 | 2027 |  |  |  | 2029 | 2030 | 2029
BURKE | NC 181 | SR 1440 TO SR 1419. WIDEN TO 3-LANES. | HIGHWAY | 13 | GREATER HICKORY MPO | U-5978 | NOT FUNDED | 65.61 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
BURKE | US 64 (BURKEMONT AVENUE) | US 70 (W. FLEMING DRIVE) INTERSECTION. IMPROVE INTERSECTION. | HIGHWAY | 13 | GREATER HICKORY MPO | U-6123 | NOT FUNDED | 78.3 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
CABARRUS | CONCORD REGIONAL AIRPORT (JQF) | SOUTH DEVELOPMENT AREA APRON EXPANSION - PHASE II: APRON EXPANSION (DESIGN & CONSTRUCTION) | AVIATION | 10 | CABARRUS-ROWAN MPO | AV-5731 | REGION E | 71.46 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2023 | 2023 | 2025
CABARRUS | CONCORD REGIONAL AIRPORT (JQF) | EXTEND RUNWAY SAFETY AREA. | AVIATION | 10 | CABARRUS-ROWAN MPO | AV-5889 | NOT FUNDED | 90.9 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | WILL BE REPRIORITIZED | [6 empty] | AFTER 2029 | 2023 | NOT FUNDED
CABARRUS | CONCORD REGIONAL AIRPORT (JQF) | CONSTRUCT NORTH APRON EXPANSION. | AVIATION | 10 | CABARRUS-ROWAN MPO | AV-5892 | REGION E | 82.09 | NOT COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | [6 empty] | 2026 | NOT FUNDED | 2023
CABARRUS | BRUTON SMITH BLVD/ CONCORD MILLS BLVD/ PORTION OF | US 29 TO WEDDINGTON ROAD. CONSTRUCT SIDEWALK ON BOTH SIDES OF THE ROAD, INCLUDING A PORTION OF WEDDINGTON ROAD. | BIKE/PED | 10 | CABARRUS-ROWAN MPO | EB-5732 | DIVISION 10 | 73.32 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2023 | 2023 |  |  |  | 2024 | 2024 | 2024
CABARRUS | KANNAPOLIS | LITTLE TEXAS ROAD, LANE STREET TO DALE EARNHARDT BOULEVARD. CONSTRUCT SIDEWALK AND CURB AND GUTTER. | BIKE/PED | 10 | CABARRUS-ROWAN MPO | EB-5844 | DIVISION 10 | 86.77 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 |  |  |  | 2024 | 2024 | 2024
CABARRUS | GEORGE LILES PARKWAY | NC 49 TO SR 1304 (ROBERTA ROAD) | HIGHWAY | 10 | CABARRUS-ROWAN MPO | R-2246A | DIVISION 10 | 85.49 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2030
CABARRUS | NC 3 (DALE EARNHARDT BOULEVARD) | INTERSECTION OF NC 3 (DALE EARNHARDT BOULEVARD) AND US 29/601 (CANNON BOULEVARD). CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 10 | CABARRUS-ROWAN MPO | U-5761 | REGION E | 75.75 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2024 | 2024 | 2024
CABARRUS | NC 73 (DAVIDSON HIGHWAY) | EAST OF SR 1394 (POPLAR TENT ROAD) TO US 29. | HIGHWAY | 10 | CABARRUS-ROWAN MPO | R-5706B | REGION E | 71.2 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
CABARRUS | SR 1394 (POPLAR TENT ROAD) | EAST OF I-85 TO GEORGE LILES PARKWAY | HIGHWAY | 10 | CABARRUS-ROWAN MPO | U-3415A | DIVISION 10 | 73.37 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2026 | 2026 | 2027
CABARRUS | US 29 | REALIGN UNION CEMETERY ROAD TO INTERSECT US 29 AT ROCK HILL CHURCH ROAD AND CONSTRUCT IMPROVEMENTS ALONG US 29 FROM 0.6 MILE WEST OF ROCK HILL CHURCH ROAD TO JUST EAST OF ROCK HILL CHURCH ROAD. | HIGHWAY | 10 | CABARRUS-ROWAN MPO | U-5956 | REGION E | 79.13 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2025 | 2025 | 2025
CABARRUS, MECKLENBURG | POPLAR TENT ROAD | DERITA ROAD TO NC 73. WIDEN TO FOUR-LANES. | HIGHWAY | 10 | CABARRUS-ROWAN MPO, CHARLOTTE REGIONAL TPO | U-6029 | NOT FUNDED | 72.43 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
CALDWELL | SR 1001 (CONNELLY SPRINGS ROAD) | CATAWBA RIVER TO SR 1933 (SOUTH-WEST BOULEVARD) | HIGHWAY | 11 | GREATER HICKORY MPO | R-3430C | DIVISION 11 | 71.33 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2025 | 2026 | 2026 | 2025 | 2026 | 2029 | 2027 | 2029
CALDWELL | SR 1130 (CAJAH MOUNTAIN ROAD) | SR 1001 (CONNELLY SPRINGS ROAD) TO US 321A. MODERNIZE ROADWAY. | HIGHWAY | 11 | GREATER HICKORY MPO | U-6157 | DIVISION 11 | 76.71 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2025 | 2025 | 2025
CALDWELL | US 321 | SR 1002 (DUDLEY SHOALS ROAD) GRADE SEPARATION. CONSTRUCT RAMP ONTO US 321 SOUTHBOUND. | HIGHWAY | 11 | GREATER HICKORY MPO | U-6161 | DIVISION 11 | 72.96 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2028 | 2028 | 2028
CALDWELL | US 321 ALT | SR 1109 (PINEWOOD ROAD) TO SR 1106 (DUKE STREET). UPGRADE ROADWAY. | HIGHWAY | 11 | GREATER HICKORY MPO | U-6034 | DIVISION 11 | 78.95 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2026 | 2026 | 2026
CAMDEN | NC 343 | US 158 IN CAMDEN TO SR 1119 (SOUTH TROTMAN ROAD) IN SHILOH. MODERNIZE ROADWAY AND REPLACE BRIDGES 140017 AND 140018 IN CAMDEN COUNTY. | HIGHWAY | 1 | ALBEMARLE RPO | R-5807 | DIVISION 1 | 66.64 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2025 | 2024 | 2023 | 2025 | 2024 | 2025 | 2027 | 2026
CAMDEN, CURRITUCK | SR 1227/SR 1208 (SOUTH MILLS ROAD) SR 1224/SR 1223 | NC 343 IN CAMDEN COUNTY TO NC 168 IN CURRITUCK COUNTY. WIDEN AND INTERSECTION IMPROVEMENTS. | HIGHWAY | 1 | ALBEMARLE RPO | R-5717 | DIVISION 1 | 60.43 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2024 | 2024 | 2024
CARTERET | NC 24 | NC 58. INTERSECTION IMPROVEMENTS. | HIGHWAY | 2 | DOWN EAST RPO | R-5858 | STATEWIDE MOBILITY | 61.62 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2021 |  |  | 2021 |  |  | 2025 | 2025 | 2025
CARTERET | NC 58 (EMERALD DRIVE) | LOON STREET. INSTALL ROUNDABOUT. | HIGHWAY | 2 | DOWN EAST RPO | R-5884 | NOT FUNDED | 78.46 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
CARTERET | NC 58 (EMERALD DRIVE) | SR 1000 (COAST GUARD ROAD). INSTALL ROUNDABOUT. | HIGHWAY | 2 | DOWN EAST RPO | R-5886 | NOT FUNDED | 75.82 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2028 | NOT FUNDED | NOT FUNDED | 2028 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
CARTERET | NC 58 (EMERALD DRIVE) | MANGROVE DRIVE. UPGRADE INTERSECTION. | HIGHWAY | 2 | DOWN EAST RPO | R-5944 | DIVISION 2 | 83.23 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | 2027 | 2028 | 2028 | 2027 | AFTER 2029 | 2030 | 2029
CARTERET | SR 1175 (BRIDGES STREET) | SR 1243 (BARBOUR ROAD). REALIGN INTERSECTIONS. | HIGHWAY | 2 | DOWN EAST RPO | R-5941 | DIVISION 2 | 85.78 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | 2027 | 2028 | 2028 | 2027 | AFTER 2029 | 2030 | 2029
CARTERET | SR 1176 (BRIDGES STREET EXTENSION) | SR 1738 (BRIDGES STREET) TO SR 1147 (MCCABE ROAD). WIDEN EXISTING ROADWAY AND CONSTRUCT PART ON NEW LOCATION. | HIGHWAY | 2 | DOWN EAST RPO | R-5727 | DIVISION 2 | 74.42 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | AFTER 2029 | 2029 | 2029
CARTERET | US 70 (ARENDELL STREET) | 4TH STREET TO SR 1175 (RADIO ISLAND ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 2 | DOWN EAST RPO | U-5876 | STATEWIDE MOBILITY | 64.2 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
CARTERET | US 70 (CEDAR STREET) | US 70 (LIVE OAK STREET). CONSTRUCT ROUNDABOUT. | HIGHWAY | 2 | DOWN EAST RPO | R-5962 | NOT FUNDED | 80.32 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
CARTERET | US 70 (LIVE OAK STREET) | NC 101 TO SR 1429 (OLGA ROAD). ACCESS MANAGEMENT. | HIGHWAY | 2 | DOWN EAST RPO | R-5945 | DIVISION 2 | 82.08 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2029 | NOT FUNDED | 2027 | 2029 | NOT FUNDED | 2027 | AFTER 2029 | NOT FUNDED | 2029
CARTERET | US 70 (LIVE OAK STREET) | SR 1310 (LENNOXVILLE ROAD). UPGRADE INTERSECTION. | HIGHWAY | 2 | DOWN EAST RPO | R-5946 | DIVISION 2 | 81.15 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2028 | NOT FUNDED | 2027 | 2028 | NOT FUNDED | 2027 | AFTER 2029 | NOT FUNDED | 2029
CARTERET | US 70 (LIVE OAK STREET) | NC 101. CONSTRUCT ONE LANE ROUNDABOUT. | HIGHWAY | 2 | DOWN EAST RPO | U-6058 | REGION B | 69.12 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2025 | 2025 | 2025
CARTERET | US 70/NC 12 | SR 1429 (OLGA ROAD) TO SR 1350 (WHITEHURST ROAD). UPGRADE ROADWAY. | HIGHWAY | 2 | DOWN EAST RPO | R-4746 | NOT FUNDED | 80.43 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
CARTERET | NS/NCRR EC LINE | CONSTRUCT GRADE SEPARATION AT US 70 EASTBOUND AND WESTBOUND. CLOSE EXISTING AT-GRADE CROSSING NEAR NEWPORT. | RAIL | 2 | DOWN EAST RPO | P-5742 | NOT FUNDED | 77.02 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2027 | NOT FUNDED | NOT FUNDED |  | NOT FUNDED |  | AFTER 2029 | NOT FUNDED | NOT FUNDED
CARTERET, HYDE | NC 12 | CEDAR ISLAND - OCRACOKE FERRY. REPLACE M/V SILVER LAKE SOUND CLASS FERRY | FERRY | 1, 2 | ALBEMARLE RPO, DOWN EAST RPO | F-5704 | DIVISION 1, 2 | 70.84 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2025 | 2028 | 2025
CASWELL | NC 86 | US 158 TO VIRGINIA STATE LINE. CONSTRUCT PASSING LANES AND SHOULDER IMPROVEMENTS AT VARIOUS LOCATIONS, AND CONSTRUCT TURN LANES FROM SR 1300 (PARK SPRINGS ROAD) TO SOLID WASTE CONVENIENCE CENTER. | HIGHWAY | 7 | PIEDMONT TRIAD RPO | R-5822 | REGION D | 69.91 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
CASWELL | US 158 / NC 86 | SR 1572 (COUNTY HOME ROAD) TO SR 1734 (RP FUQUAY ROAD). CONSTRUCT PASSING LANES. | HIGHWAY | 7 | PIEDMONT TRIAD RPO | R-5926 | DIVISION 7 | 75.47 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
CATAWBA | HICKORY REGIONAL AIRPORT (HKY) | 600 FEET EXTENSION OF RUNWAY 6 - PHASE I AND II. | AVIATION | 12 | GREATER HICKORY MPO | AV-5741 | DIVISION 12 | 86.25 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2024 | 2024 | 2024
CATAWBA | HICKORY REGIONAL AIRPORT (HKY) | LAND ACQUISITION AND OBSTRUCTION REMOVAL. | AVIATION | 12 | GREATER HICKORY MPO | AV-5752 | DIVISION 12 | 67.95 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | 2026
CATAWBA | HICKORY | SR 1453 (SPRINGS ROAD) TO NC 127 | HIGHWAY | 12 | GREATER HICKORY MPO | U-2307B | DIVISION 12 | 75.46 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2028 | 2025 | 2024 | 2028 | 2025 | 2027 | 2031 | 2028
CATAWBA | I-40 | SR 1007 (LENOIR RHYNE BOULEVARD) INTERCHANGE. CONSTRUCT INTERCHANGE IMPROVEMENTS. | HIGHWAY | 12 | GREATER HICKORY MPO | I-5716 | STATEWIDE MOBILITY | 76.19 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2025 | 2026 | 2025
CATAWBA | I-40 | US 321 TO SR 1476 (FAIRGROVE CHURCH ROAD). WIDEN TO SIX LANES. | HIGHWAY | 12 | GREATER HICKORY MPO | I-5991A | STATEWIDE MOBILITY | 81.24 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 |  |  | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
CATAWBA | NC 127 | SR 1132 (HUFFMAN FARM ROAD) TO SR 1008 (ZION CHURCH ROAD). | HIGHWAY | 12 | GREATER HICKORY MPO | U-2530A | DIVISION 12 | 77.43 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2028 | 2025 | 2025 | 2028 | 2025 | 2027 | 2031 | 2027
CATAWBA | NC 127 (2ND STREET NORTHEAST, NORTH CENTER STREET) | 8TH AVENUE NORTHEAST TO SR 1327 (30TH AVENUE NORTHWEST). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 12 | GREATER HICKORY MPO | U-6135 | NOT FUNDED | 81.19 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
CATAWBA | SR 1005 (STARTOWN ROAD) | US 70 TO NC 10. WIDEN TO MULTI-LANES. | HIGHWAY | 12 | GREATER HICKORY MPO | R-5113 | DIVISION 12 | 73.03 | P4.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2031
CATAWBA | SR 1124 (33RD STREET SW) | SR 1124 (33RD STREET SW) AND (34TH STREET NW). REALIGN INTERSECTION. | HIGHWAY | 12 | GREATER HICKORY MPO | U-6042 | DIVISION 12 | 74.78 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | AFTER 2029 | 2029 | 2029
CATAWBA | SR 1453 (16TH STREET NE, 12TH AVE NE, SPRINGS ROAD | 9TH AVENUE NE TO SR 1504 (CHARLOTTE STREET). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 12 | GREATER HICKORY MPO | U-6176 | DIVISION 12 | 80.19 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY
CATAWBA, CALDWELL, BURKE | US 321 | NORTH OF US 70 IN HICKORY TO US 321A | HIGHWAY | 11, 12, 13 | GREATER HICKORY MPO | U-4700A | STATEWIDE MOBILITY | 47.67 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2021 | 2021 | 2021 |  |  |  | 2025 | 2025 | 2025
CATAWBA, LINCOLN | NC 150 | RELOCATED NC 16 (STIP PROJECT R-2206) TO EAST OF SR 1840 (GREENWOOD ROAD). WIDEN TO 4-LANES WITH A BYPASS OF THE TERRELL HISTORIC DISTRICT. | HIGHWAY | 12 | GREATER HICKORY MPO, GASTON-CLEVELAND-LINCOLN MPO | R-2307A | REGION F | 80.65 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2030
CHATHAM | SILER CITY MUNICIPAL AIRPORT (SCR) | EXTEND RUNWAY 22 AND PARALLEL TAXIWAY BY 500 FT, INCLUDING RELOCATION OF AIRPORT ROAD | AVIATION | 8 | TRIANGLE AREA RPO | AV-5816 | DIVISION 8 | 90.59 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
CHATHAM | SR 1107 (WEST 3RD STREET) | NORTH GARDEN AVENUE TO SR 1108 (NORTH CHATHAM AVENUE) IN SILER CITY. CONSTRUCT SIDEWALK. | BIKE/PED | 8 | TRIANGLE AREA RPO | EB-6006 | DIVISION 8 | 66.47 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 |  |  |  | 2026 | 2026 | 2026
CHATHAM | SR 2106 (EAST CARDINAL STREET); SOUTH 10TH AVENUE | SR 2016 (EAST CARDINAL STREET) FROM SR 2223 (MATTHEWS STREET) TO SOUTH 10TH AVENUE, AND SOUTH 10TH AVENUE FROM EAST CARDINAL STREET TO SR 2103 (EAST RALEIGH STREET) IN SILER CITY. CONSTRUCT SIDEWALK. | BIKE/PED | 8 | TRIANGLE AREA RPO | EB-6007 | NOT FUNDED | 63.62 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2026 | NOT FUNDED | NOT FUNDED |  | NOT FUNDED |  | 2028 | NOT FUNDED | NOT FUNDED
CHATHAM | NC 87 | NC 902 IN PITTSBORO TO US 64 BYPASS. WIDEN TO 12-FT LANES AND 4-FT PAVED SHOULDERS. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5961 | NOT FUNDED | 49.66 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2027 | NOT FUNDED | NOT FUNDED | 2027 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
CHATHAM | NEW ROUTE | US 64 BYPASS IN PITTSBORO TO US 15 / US 501. CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5930 | DIVISION 8 | 77.58 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024
CHATHAM | NEW ROUTE | US 15 / US 501 / NC 87 TO US 64 BUSINESS. CONSTRUCT 2-LANE ROADWAY ON NEW LOCATION. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5963 | DIVISION 8 | 77.58 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2027 | 2027 | 2027
CHATHAM | US 15 / US 501 | US 15 / US 501, NORTH OF US 64 BUSINESS TO POWELL PLACE LANE. MILL AND RESURFACE FROM NORTH OF US 64 BUSINESS TO LAUNIS STREET AND WIDEN FROM LAUNIS STREET TO POWELL PLACE LANE. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5724B | DIVISION 8 | 64.73 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2025 | 2025 | 2025
CHATHAM | US 64 (EAST 11TH STREET) | NORTH GLENN AVENUE TO EAST OF US 421 IN SILER CITY. UPGRADE ROADWAY TO INCLUDE MEDIAN FOR ACCESS CONTROL, SIDEWALKS, CROSSWALKS, BICYCLE LANES AND / OR MULTIUSE SIDEPATH. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5737 | REGION E | 49.46 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2026 | 2026 | 2026
CHATHAM, ORANGE | US 15 / US 501 | US 64 BYPASS TO SR 1919 (SMITH LEVEL ROAD). CONVERT REMAINING NON-SYNCHRONIZED SECTIONS OF FACILITY TO SYNCHRONIZED STREET. | HIGHWAY | 7, 8 | TRIANGLE AREA RPO, DURHAM-CHAPEL HILL-CARRBORO MPO | U-6192 | DIVISION 7, 8 | 75.98 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2030
CHATHAM, WAKE | US 64 | NC 751. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 5, 8 | TRIANGLE AREA RPO, CAPITAL AREA MPO | R-5887 | REGION C, E | 74.81 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2029 | NOT FUNDED | 2027 | 2029 | NOT FUNDED | 2027 | AFTER 2029 | NOT FUNDED | 2029
CHEROKEE | US 19/129 | GEORGIA STATE LINE TO US 64. WIDEN ROADWAY. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5861 | DIVISION 14 | 52.24 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2024 | 2024 | 2024
CHEROKEE | US 19/US 74/ US 129 | US 64 TO SR 1689 (CASINO PARKWAY). MODERNIZE ROADWAY. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5908 | DIVISION 14 | 66.24 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
CHEROKEE, MACON | US 74 | SR 1393 (WAKEFIELD ROAD) TO SR 1310 (WAYAH ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5920 | NOT FUNDED | 52.71 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
CLAY | US 64 | NC 175 TO SR 1349 (OLD HWY 64 EAST). WIDEN TO MULTI-LANE. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5922 | NOT FUNDED | 64.74 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
CLAY, CHEROKEE | US 64 | US 64 BUSINESS WEST OF HAYESVILLE TO EAST OF NC 141. WIDEN TO FOUR-LANES DIVIDED. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5847 | NOT FUNDED | 66.43 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
CLEVELAND | US 74 | US 74 BUSINESS TO NC 226. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-5713 | REGION F | 58.12 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2024 | 2024 | 2024
CLEVELAND | US 74 (DIXON BOULEVARD) | NC 150 (DEKALB STREET) INTERSECTION. CONSTRUCT INTERCHANGE. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-2567 | STATEWIDE MOBILITY | 79.53 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
CLEVELAND | US 74 (DIXON BOULEVARD) | INTERSECTION OF US 74 (DIXON BOULEVARD) AND NC 226 (EARL ROAD). CONSTRUCT IMPROVEMENTS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5929 | STATEWIDE MOBILITY | 82.78 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
CLEVELAND | US 74 SHELBY BYPASS | EAST OF NC 150 TO EXISTING US 74 WEST OF SR 2238 (LONG BRANCH ROAD). GRADING, STRUCTURE, PAVING. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-2707D | REGION F | 82.03 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2019 | 2019 | 2019 |  |  |  | 2024 | 2024 | 2024
CLEVELAND | US 74 SHELBY BYPASS | US 74 WEST OF SR 2238 TO WEST OF SR 1001 (STONEY POINT ROAD). GRADING, STRUCTURES, PAVING. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-2707E | REGION F | 81.4 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2019 | 2019 | 2019 |  |  |  | 2024 | 2024 | 2024
CLEVELAND, GASTON | I-85 | SOUTH CAROLINA STATE LINE TO US 74 | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | I-5985A | STATEWIDE MOBILITY | 80.26 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
COLUMBUS | NC 87 | NC 11 TO US 74/US 76 IN COLUMBUS COUNTY. | HIGHWAY | 6 | CAPE FEAR RPO | R-2561C | DIVISION 6 | 83.59 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
COLUMBUS | US 701 BYPASS | SR 1166 (PLEASANT PLAINS CHURCH ROAD) TO SR 1437 (VIRGIL AVENUE). | HIGHWAY | 6 | CAPE FEAR RPO | R-5020A | REGION C | 70.07 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2029 | 2027 | 2026
COLUMBUS | US 701 BYPASS | SR 1305 (COMPLEX STREET). UPGRADE INTERSECTION. | HIGHWAY | 6 | CAPE FEAR RPO | R-5952 | DIVISION 6 | 81.97 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2027 | 2025 | 2025 | 2027 | 2025 | 2027 | 2029 | 2027
COLUMBUS, ROBESON | US 74 | NC 41 NEAR LUMBERTON TO US 76 NEAR CHADBOURN. UPGRADE US 74 TO INTERSTATE STANDARDS. | HIGHWAY | 6 | CAPE FEAR RPO, LUMBER RIVER RPO | I-6011 | NOT FUNDED | 79.74 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2027 | NOT FUNDED | NOT FUNDED | 2027 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
CRAVEN | COASTAL CAROLINA REGIONAL AIRPORT (EWN) | RUNWAY EXTENSION. | AVIATION | 2 | NEW BERN AREA MPO | AV-5891 | NOT FUNDED | 96.34 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | [6 empty] | 2029 | NOT FUNDED | NOT FUNDED
CRAVEN | NC 43 CONNECTOR | US 17 BUSINESS TO SOUTH OF US17/US 70. | HIGHWAY | 2 | NEW BERN AREA MPO | R-4463A | REGION B | 70.15 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2020 | 2020 | 2020 |  |  |  | 2025 | 2025 | 2025
CRAVEN | NC 55 (NEUSE BOULEVARD) | US 17 BUSINESS (MLK BOULEVARD). CONSTRUCT ROUNDABOUT. | HIGHWAY | 2 | NEW BERN AREA MPO | U-5993 | REGION B | 69.91 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY |  | 2027 | 2026 |  |  |  | 2029 | 2029 | 2028
CRAVEN | SR 1763 (MILLER BOULEVARD) | SR 1756 (LAKE ROAD) TO OUTER BANKS DRIVE. WIDEN TO MULTI-LANES. | HIGHWAY | 2 | DOWN EAST RPO | U-3431 | DIVISION 2 | 77.99 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | 2026 | 2027 | 2027 | 2026 | 2029 | 2029 | 2028
CRAVEN | US 17 | NORTH OF NC 43 TO SR 1438 (SPRUILL TOWN ROAD). | HIGHWAY | 2 | DOWN EAST RPO | R-2513A | DIVISION 2 | 77.15 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2028 | 2028 | 2028
CRAVEN | US 17 | SR 1433 (ANTIOCH ROAD) TO NORTH OF NC 43. | HIGHWAY | 2 | DOWN EAST RPO, NEW BERN AREA MPO | R-3403B | REGION B | 71.98 | P4.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2026 | NOT FUNDED | 2027 | 2026 | NOT FUNDED | 2027 | 2028 | NOT FUNDED | 2029
CRAVEN | US 17 ALTERNATE (MARTIN LUTHER KING JR. BOULEVARD) | US 70 TO SR 1278 (TRENT ROAD). UGRADE TO SUPERSTREET. | HIGHWAY | 2 | NEW BERN AREA MPO | U-6198 | NOT FUNDED | 81.54 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
CRAVEN | US 70 | SR 1309 (GLENBURNIE ROAD). IMPROVE INTERCHANGE. | HIGHWAY | 2 | NEW BERN AREA MPO | U-6102 | NOT FUNDED | 75.74 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2027 | NOT FUNDED | NOT FUNDED | 2027 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
CUMBERLAND | FAYETTEVILLE | CROSS CREEK PARKS CONNECTOR TRAIL, NC 24 (BRAGG BOULEVARD) TO RAY AVENUE IN FAYETTEVILLE. CONSTRUCT GREENWAY. | BIKE/PED | 6 | FAYETTEVILLE AREA MPO | EB-5907 | DIVISION 6 | 88.89 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 |  |  |  | 2026 | 2026 | 2026
CUMBERLAND | NC 210 (MURCHISON ROAD) | LANGDON STREET TO US 401 BYPASS. MODERNIZE ROADWAY. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-5015 | NOT FUNDED | 45.37 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
CUMBERLAND | NC 24 (NORTH BRAGG BOULEVARD) | SR 1451 (MANCHESTER ROAD). CONSTRUCT INTERCHANGE. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-5930 | STATEWIDE MOBILITY | 79.86 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
CUMBERLAND | NC 24 / NC 87 | SR 1451 (MANCHESTER ROAD) TO NC 210 (LILLINGTON HIGHWAY). IMPROVE EXISTING MULTI-LANE FACILITY BY ADDING ACCESS MANAGEMENT AND OTHER IMPROVEMENTS. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-5802 | DIVISION 6 | 89.47 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
CUMBERLAND | NC 59 (SOUTH MAIN STREET) | SR 1243 (SHIPMAN ROAD) TO SR 1118 (PARKTON ROAD). WIDEN TO THREE LANES. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-6001 | REGION C | 69.08 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
CUMBERLAND | SR 1003 (CAMDEN ROAD) | PROPOSED FAYETTEVILLE OUTER LOOP (U-2519) TO NC 59 (HOPE MILLS ROAD) IN FAYETTEVILLE. WIDEN TO MULTI-LANES. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-3422 | DIVISION 6 | 79.05 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2024 | 2024 | 2024
CUMBERLAND | SR 1007 (ALL AMERICAN FREEWAY) | SR 1151 (OWEN DRIVE) TO NORTH OF SR 1437 (SANTA FE DRIVE). ADD ADDITIONAL LANES. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-4414 | REGION C | 66.78 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2028 | 2028 | 2027 | 2028 | 2028 | AFTER 2029 | 2030 | 2030
CUMBERLAND | SR 1104 (STRICKLAND BRIDGE ROAD) | US 401 TO FISHER ROAD. WIDEN ROADWAY. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-6210 | NOT FUNDED | 76.3 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2026 | NOT FUNDED | NOT FUNDED | 2026 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED
CUMBERLAND | SR 1112 (ROCKFISH ROAD) | SR 1102 (GILLIS HILL ROAD) TO CAMDEN ROAD. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-6072A | NOT FUNDED | 71.64 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
CUMBERLAND | SR 1219 (IRELAND DRIVE) | SR 1141 (CUMBERLAND ROAD) TO US 401 (RAEFORD ROAD). WIDEN ROADWAY. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-6213 | NOT FUNDED | 72.55 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
CUMBERLAND | SR 1400 (CLIFFDALE ROAD) | MCPHERSON CHURCH ROAD TO SR 1404 (MORGANTON ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-4404 | DIVISION 6 | 76.62 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2028 | 2028 | 2025 | 2028 | 2028 | AFTER 2029 | 2030 | 2030
CUMBERLAND | SR 1400 (CLIFFDALE ROAD) | SR 1411 (BUNCE ROAD) TO MCPHERSON CHURCH ROAD. ACCESS MANAGEMENT. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-6209 | DIVISION 6 | 91.84 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
CUMBERLAND | SR 1437 (SHAW RD) | NC 24/87 (BRAGG BLVD) TO NC 210 (MURCHISON ROAD). INTERCONNECT AND WIDEN TO MULTI-LANES. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-5101A | DIVISION 6 | 79.08 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2026 | 2026 | 2025 | 2026 | 2026 | 2028 | 2028 | 2028
CUMBERLAND | US 401 | US 401 BYPASS TO NORTH OF SLOCUMB ROAD. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-4403C | DIVISION 6 | 88.26 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2026 | 2026 | 2025 | 2026 | 2026 | 2029 | 2029 | 2029
CUMBERLAND | US 401 (RAEFORD ROAD) | EAST OF GLENSFORD DRIVE TO EAST OF ROBESON STREET. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-4405C | DIVISION 6 | 71.53 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2024 | 2024 | 2024
CUMBERLAND | US 401 (ROBESON STREET) | US 401 (RAEFORD ROAD) TO WALTER STREET. ACCESS MANAGEMENT. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-6152 | NOT FUNDED | 80.88 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
CUMBERLAND | US 401 BUSINESS | US 401 BUSINESS (MARTIN LUTHER KING, JR. FREEWAY) TO US 401 BYPASS. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-4403B | REGION C | 72.98 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2027 | 2027 | 2026 | 2027 | 2027 | 2029 | 2029 | 2029
CUMBERLAND | US 401 BUSINESS (SKIBO ROAD) | SR 1400 (CLIFFDALE ROAD). IMPROVE INTERSECTION | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-6133 | REGION C | 82.56 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2028 | NOT FUNDED | 2028 | 2028 | NOT FUNDED | 2028 | AFTER 2029 | NOT FUNDED | 2030
CUMBERLAND | FAYETTEVILLE AREA SYSTEM TRANSIT | EXPANSION BUS. | PUBLIC TRANSIT | 6 | FAYETTEVILLE AREA MPO | TA-6685 | DIVISION 6 | 85.56 | NOT COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2026 | 2026 | 2026
CUMBERLAND, HOKE | SR 1102 (GILLIS HILL ROAD) | FROM SR 1418 (LINDSAY ROAD) TO NORTH OF SR 1112 (STONEY POINT ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 6, 8 | FAYETTEVILLE AREA MPO | U-5798B | DIVISION 6, 8 | 73.48 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2025 | 2025 | 2025
CURRITUCK | NEW ROUTE | MID-CURRITUCK BRIDGE, COINJOCK TO COROLLA. NEW STRUCTURE OVER CURRITUCK SOUND AND UPGRADE APPROACHES. | HIGHWAY | 1 | ALBEMARLE RPO | R-2576 | DIVISION 1 | 36.85 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024
CURRITUCK, CAMDEN | US 158 (SHORTCUT ROAD) | EAST OF NC 34 (SHAWBORO ROAD) AT BELCROSS IN CAMDEN COUNTY TO US 158/NC 168 (CARATOKE HIGHWAY) IN CURRITUCK COUNTY. WIDEN TO MULTI-LANES. | HIGHWAY | 1 | ALBEMARLE RPO | R-2574 | REGION A | 72.84 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2026 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2026 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY
DARE | US 158 | CYPRESS KNEE LANE TO JEJAC STREET IN KITTY HAWK. CONSTRUCT SIDEWALK ON WEST SIDE. | BIKE/PED | 1 | ALBEMARLE RPO | EB-5848 | DIVISION 1 | 78.71 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | [6 empty] | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2025
DARE | US 158 | US 64-NC 12 TO EASTERN END OF CURRITUCK SOUND BRIDGE. ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 1 | ALBEMARLE RPO | R-3419 | STATEWIDE MOBILITY | 79.56 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
DARE | US 158 | NC 12. IMPROVE INTERSECTION. | HIGHWAY | 1 | ALBEMARLE RPO | R-4457 | NOT FUNDED | 72.69 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
DARE, HYDE | HATTERAS - SOUTH DOCK | CONSTRUCT PASSENGER FERRY. | FERRY | 1 | ALBEMARLE RPO | F-5706 | NOT FUNDED | 82.22 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | [6 empty] | 2027 | NOT FUNDED | NOT FUNDED
DAVIDSON | NC 109 | NC 109 IN DENTON TO I-85 IN THOMASVILLE. WIDEN TO MULTILANES. | HIGHWAY | 9 | HIGH POINT URBAN AREA MPO | R-4734 | DIVISION 9 | 57.58 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2028 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY
DAVIDSON | NC 8 (WINSTON ROAD) | 9TH STREET TO SR 1408 (BIESECKER ROAD) IN LEXINGTON. WIDEN TO MULTILANES. | HIGHWAY | 9 | HIGH POINT URBAN AREA MPO | U-5757 | REGION D | 63.17 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2019 | 2019 | 2019 |  |  |  | 2024 | 2024 | 2024
DAVIDSON | SR 1508 (HICKORY TREE ROAD) | US 52 / NC 8 / FUTURE I-285 TO NC 150. WIDEN TO MULTILANES. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-5786 | DIVISION 9 | 77.65 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2028 | 2028 | 2028
DAVIDSON | NCRR / NORFOLK SOUTHERN MAIN LINE | SR 2165 (TURNER STREET) IN THOMASVILLE. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722327S. | RAIL | 9 | HIGH POINT URBAN AREA MPO | P-5751 | DIVISION 9 | 84.85 | NOT COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2031
DAVIDSON | NORFOLK SOUTHERN | KIMBERLY CLARK IN LEXINGTON. CONSTRUCT LEAD. | RAIL | 9 | HIGH POINT URBAN AREA MPO | P-5722 | REGION D | 76.35 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2024 | 2024 | 2024
DAVIDSON | NORFOLK SOUTHERN | CROSSING 722306Y (EAST 7TH AVENUE) IN LEXINGTON. CONSTRUCT GRADE SEPARATION IN VICINITY OF 5TH STREET AND CLOSE CROSSING 722306Y. | RAIL | 9 | HIGH POINT URBAN AREA MPO | P-5731 | DIVISION 9 | 83.13 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2022 |  |  |  | 2026 | 2026 | 2022
DAVIE | NEW ROUTE | SR 1630 (BALTIMORE ROAD) TO I-40. CONSTRUCT 2-LANE EXTENSION OF BALTIMORE ROAD AND INTERCHANGE AT I-40. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-6187 | DIVISION 9 | 84.09 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2024 | 2023 | 2023 | 2024 | 2025 | 2025 | 2025
DAVIE | SR 1410 (FARMINGTON ROAD) | I-40 EASTBOUND RAMP AND US 158 INTERSECTION. CONSTRUCT ROUNDABOUTS. | HIGHWAY | 9 | NORTHWEST PIEDMONT RPO | R-5854 | DIVISION 9 | 74.8 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2025 | 2025 | 2025
DAVIE | US 601 | SR 1345 (BLAISE CHURCH ROAD) TO SR 1408 (CANA ROAD). WIDEN TO MULTILANES. | HIGHWAY | 9 | NORTHWEST PIEDMONT RPO | R-5736 | DIVISION 9 | 75.95 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2027 | 2026 | 2026 | 2027 | 2026 | 2028 | 2029 | 2028
DURHAM | NC 157 / SR 1322 (GUESS ROAD) | HILLCREST DRIVE TO SR 1407 (WEST CARVER STREET) IN DURHAM. CONSTRUCT SIDEWALKS ON BOTH SIDES. | BIKE/PED | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5834 | DIVISION 5 | 90.94 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | 2025 |  |  |  | 2026 | 2026 | 2026
DURHAM | NC 55 (ALSTON AVENUE) | SR 1171 (RIDDLE ROAD) TO CECIL STREET IN DURHAM. CONSTRUCT SIDEWALK ON EAST SIDE TO FILL IN MISSING GAPS. | BIKE/PED | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5835 | DIVISION 5 | 90.79 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | 2027 |  |  |  | 2028 | 2028 | 2028
DURHAM | I-40 | NC 55 (ALSTON AVENUE) TO NC 147 (DURHAM FREEWAY / TRIANGLE EXPRESSWAY) IN DURHAM. CONSTRUCT WESTBOUND AUXILIARY LANE. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-5707 | STATEWIDE MOBILITY | 49.78 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2028 | 2024 | 2024 | 2028 | 2024 | 2026 | 2031 | 2026
DURHAM | I-40, NC 54 | EAST OF LITTLE CREEK TO EAST OF I-40. UPGRADE ROADWAY CORRIDOR AND CONSTRUCT INTERCHANGE IMPROVEMENTS AT I-40. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5774F | STATEWIDE MOBILITY | 83.43 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
DURHAM | I-85 / US 15 | EAST OF SR 1827 (MIDLAND TERRACE) TO SR 1632 (RED MILL ROAD) IN DURHAM. ADD LANES. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-6010 | NOT FUNDED | 79.58 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
DURHAM | I-885 | I-40 TO NC 147 IN DURHAM. ADD LANES AND REHABILITATE PAVEMENT. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5934 | STATEWIDE MOBILITY | 76.98 | P4.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2028 |  |  | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029
DURHAM | NC 147 (DURHAM FREEWAY) | SR 1127 (WEST CHAPEL HILL STREET) TO BRIGGS AVENUE IN DURHAM. CONSTRUCT AUXILIARY LANES AND OPERATIONAL IMPROVEMENTS. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5937 | STATEWIDE MOBILITY | 71.23 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
DURHAM | NC 54 | EAST OF SR1110 (BARBEE CHAPEL ROAD) TO EAST OF LITTLE CREEK. UPGRADE ROADWAY CORRIDOR. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5774C | REGION C | 74.67 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
DURHAM | NC 55 | MERIDIAN PARKWAY TO I-40 INTERCHANGE IN DURHAM. ADD THIRD SOUTHBOUND LANE AND UPGRADE RAMP TERMINALS. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-6118 | NOT FUNDED | 81.5 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2028 | NOT FUNDED | NOT FUNDED | 2028 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
DURHAM | NC 98 (HOLLOWAY STREET) | SR 1938 (JUNCTION ROAD) TO SR 1919 (LYNN ROAD) IN DURHAM. CONSTRUCT SAFETY IMPROVEMENTS AND WIDEN TO ADD MEDIAN, BICYCLE LANES, SIDEWALKS, TRANSIT STOP IMPROVEMENTS, AND TRAFFIC SIGNALS WHERE NEEDED. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-6120 | DIVISION 5 | 93.16 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY
DURHAM | SR 1118 (FAYETTEVILLE ROAD) | WOODCROFT PARKWAY TO BARBEE ROAD IN DURHAM. WIDEN TO 4-LANE DIVIDED FACILITY WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-6021 | DIVISION 5 | 78.95 | P4.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2031
DURHAM | US 15 / US 501 | SR 1116 (GARRETT ROAD) IN DURHAM. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5717 | STATEWIDE MOBILITY | 47.21 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2026 | 2026 | 2026
DURHAM | US 15 / US 501 | I-40, SR (MOUNT MORIAH ROAD), AND SOUTHWEST DURHAM PARKWAY IN DURHAM. IMPROVE INTERCHANGE / INTERSECTION AREA. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-6067 | STATEWIDE MOBILITY | 77.57 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY
DURHAM | US 501 (ROXBORO ROAD) | SR 1448 (LATTA ROAD) / SR 1639 (INFINITY ROAD) INTERSECTION IN DURHAM. INTERSECTION IMPROVEMENTS. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5516 | REGION C | 63.11 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2026 | 2026 |  | 2026 | 2026 | 2027 | 2028 | 2028
DURHAM | US 70 (MIAMI BOULEVARD) | LYNN ROAD TO SR 1959 (SOUTH MIAMI BOULEVARD) / SR 1811 (SHERRON ROAD). | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5720A | STATEWIDE MOBILITY | 72.93 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
DURHAM | US 70 (MIAMI BOULEVARD) | SR 1959 (SOUTH MIAMI BOULEVARD) / SR 1811 (SHERRON ROAD) TO EAST OF SR 2095 (PAGE ROAD EXTENSION). | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5720B | STATEWIDE MOBILITY | 78.89 | P4.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2030
DURHAM | WOODCROFT PARKWAY EXTENSION | SR 1116 (GARRETT ROAD) TO NC 751 (HOPE VALLEY ROAD) IN DURHAM. CONSTRUCT ROADWAY ON NEW ALIGNMENT. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5823 | DIVISION 5 | 77.31 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025
DURHAM | NORFOLK SOUTHERN H LINE | EAST DURHAM RAILROAD SAFETY PROJECT. PROJECT WILL STRAIGHTEN EXISTING RAILROAD CURVATURE BETWEEN CP NELSON AND CP EAST DURHAM AND INCLUDES A COMBINATION OF GRADE SEPARATIONS AND CLOSURES AT ELLIS ROAD SOUTH END (734737A), GLOVER ROAD (734735L), AND WRENN | RAIL | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | P-5706 | STATEWIDE MOBILITY | 77.8 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2023 | 2022 | 2022 | 2023 | 2027 | 2028 | 2027
DURHAM | NORFOLK SOUTHERN H LINE | CROSSING 734742W AT SR 1121 (CORNWALLIS ROAD) IN DURHAM. CONSTRUCT GRADE SEPARATION. | RAIL | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO | P-5717 | REGION C | 68.07 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2024 | 2024 | 2024
DURHAM, WAKE | I-40 SR 1728 (WADE AVENUE) | NC 54 (EXIT 273) TO SR 1728 (WADE AVENUE), I-40 TO SR 1664 (BLUE RIDGE ROAD) CONVERT FACILITY TO A MANAGED FREEWAY WITH RAMP METERING AND OTHER ATM / ITS COMPONENTS. | HIGHWAY | 5 | DURHAM-CHAPEL HILL-CARRBORO MPO, CAPITAL AREA MPO | I-6006 | STATEWIDE MOBILITY | 83.91 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
EDGECOMBE | TARBORO EDGECOMBE AIRPORT (ETC) | RUNWAY EXTENSION. | AVIATION | 4 | UPPER COASTAL PLAIN RPO | AV-5897 | DIVISION 4 | 85.93 | NOT COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2028 | 2028 | 2028
EDGECOMBE | EAST RALEIGH BOULEVARD | US 64 TO ARLINGTON STREET IN ROCKY MOUNT. PEDESTRIAN IMPROVEMENTS. | BIKE/PED | 4 | ROCKY MOUNT URBAN AREA MPO | EB-5984 | DIVISION 4 | 59.29 | NOT COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2028 | 2028 | 2028
EDGECOMBE | NC 97 (ATLANTIC AVENUE) | US 64 TO EAST RALEIGH BOULEVARD IN ROCKY MOUNT. PEDESTRIAN IMPROVEMENTS. | BIKE/PED | 4 | ROCKY MOUNT URBAN AREA MPO | EB-5729 | DIVISION 4 | 59.1 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | [6 empty] | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
EDGECOMBE | US 258 | SR 1601 (COLONIAL ROAD) TO US 64. WIDEN ROADWAY. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | R-5949 | DIVISION 4 | 82.13 | NOT COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2029 | 2029 | 2029
EDGECOMBE, NASH | ROCKY MOUNT | US 301 BUSINESS, RIVER DRIVE TO MONK STREET IN ROCKY MOUNT. CONVERT ABANDONED RAILROAD TO MULTI-USE PATH. | BIKE/PED | 4 | ROCKY MOUNT URBAN AREA MPO | EB-5763 | DIVISION 4 | 83.14 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 |  |  |  | 2025 | 2025 | 2025
FORSYTH | SALEM CREEK GREENWAY | FORSYTH TECHNICAL COMMUNITY COLLEGE TO EXISTING GREENWAY AT MARKETPLACE MALL IN WINSTON-SALEM. CONSTRUCT GREENWAY. | BIKE/PED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-5812 | DIVISION 9 | 44.9 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2023 | 2023 | 2026
FORSYTH | SR 1122 (JONESTOWN ROAD) | EAST OF US 421 TO SR 1001 (COUNTRY CLUB ROAD) IN WINSTON-SALEM. CONSTRUCT SIDEWALK ON EAST SIDE AND WEST SIDE OF JONESTOWN RD. | BIKE/PED | 9 | WINSTON-SALEM URBAN AREA MPO | EB-5920 | DIVISION 9 | 82.01 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025
FORSYTH | I-40 | I-74 / US 311 TO SR 2643 (UNION CROSS ROAD). | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | I-5981A | STATEWIDE MOBILITY | 78.55 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2030 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
FORSYTH | I-40 | SR 2643 (UNION CROSS ROAD) TO NC 66. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | I-5981B | STATEWIDE MOBILITY | 78.55 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2030 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
FORSYTH | I-40 / US 311 | NC 109 (THOMASVILLE ROAD) / CLEMMONSVILLE ROAD SPLIT-DIAMOND INTERCHANGE IN WINSTON-SALEM. CONVERT HALF DIAMOND INTERCHANGE AT NC 109 TO FULL DIAMOND, AND REMOVE CONNECTOR ROADS AND HALF DIAMOND INTERCHANGE AT CLEMMONSVILLE ROAD | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | I-5880 | REGION D | 63.01 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2028 | 2023 | 2023 | 2028 | 2023 | 2025 | 2030 | 2025
FORSYTH | KERNERSVILLE SOUTHERN LOOP (PHASE I) | US 421 / BUSINESS 40 TO NC 66 (WEST MOUNTAIN STREET) IN KERNERSVILLE. WIDEN BIG MILL FARM ROAD AND SR 2649 (HOPKINS ROAD) AND CONSTRUCT INTERCHANGE AT US 421 / NC 150 / BUSINESS 40. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-5760 | DIVISION 9 | 74.47 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2025 | 2025 | 2025
FORSYTH | NC 65 (BETHANIA-RURAL HALL ROAD) | US 52 TO SR 3983 (NORTHRIDGE DRIVE) IN RURAL HALL. WIDEN TO MULTILANES. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-6005 | DIVISION 9 | 76.82 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2023 | 2022 | 2022 | 2023 | 2025 | 2025 | 2025
FORSYTH | NC 65 (BETHANIA-RURAL HALL ROAD) | SR 1647 (GLADE STREET) TO NC 66 IN RURAL HALL. WIDEN TO 3 LANES. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-6190 | DIVISION 9 | 64.65 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | 2027 | 2028 | 2028 | 2027 | AFTER 2029 | 2030 | 2029
FORSYTH | NC 66 (OLD HOLLOW ROAD) | HARLEY DRIVE TO US 158 IN WALKERTOWN. WIDEN TO MULTILANES. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-5824 | DIVISION 9 | 69.19 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2021 | 2021 | 2021 |  |  |  | 2024 | 2024 | 2024
FORSYTH | NEW ROUTE | PROPOSED GREAT WAGON ROAD FROM SHALLOWFORD ROAD (SR 1001) TO LEWISVILLE-VIENNA ROAD (SR 1308) IN LEWISVILLE. MULTILANE FACILITY ON NEW LOCATION WITH BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-5536 | DIVISION 9 | 64.35 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2024 | 2024 | 2024
FORSYTH | NEW ROUTE | FORUM PARKWAY CONNECTOR, SR 3955 (FORUM PARKWAY) TO NC 66 (UNIVERSITY PARKWAY) IN RURAL HALL. CONSTRUCT 2-LANE ROADWAY ON NEW LOCATION. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-5899 | DIVISION 9 | 57.2 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2024 | 2024 | 2024
FORSYTH | NEW ROUTE | SR 1969 (PINEY GROVE ROAD) TO NC 150 (NORTH MAIN STREET) IN KERNERSVILLE. CONSTRUCT TWO-LANE DIVIDED FACILITY WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-6003 | DIVISION 9 | 80.59 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2024 | 2024 | 2024
FORSYTH | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, US 158 TO SOUTH OF I-40 | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247A | NOT FUNDED | 76.38 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED
FORSYTH | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, SOUTH OF I-40 TO SOUTH OF US 421 INTERCHANGE | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247B | NOT FUNDED | 78.36 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED
FORSYTH | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, INTERCHANGE WITH US 421 AND INTERCHANGE WITH SR 1140 (PEACE HAVEN ROAD) | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247CA | REGION D | 78.36 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY
FORSYTH | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, NORTH OF US 421 INTERCHANGE TO SR 1348 (ROBINHOOD ROAD) | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247CB | REGION D | 78.36 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
FORSYTH | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, NORTH OF SR 1348 (MEADOWLARK DRIVE-ROBINHOOD ROAD) TO NC 67 | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247D | REGION D | 78.36 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
FORSYTH | NEW ROUTE (FUTURE NC 452) | WINSTON-SALEM NORTHERN BELTWAY, WESTERN SECTION, NC 67 TO SOUTH OF US 52 | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | R-2247EA | REGION D | 74.6 | P4.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2030
FORSYTH | SR 1103 (LEWISVILLE- CLEMMONS ROAD) | US 158 TO SR 1891 (PEACE HAVEN ROAD) IN CLEMMONS. ACCESS MANAGEMENT AND OPERATIONAL IMPROVEMENTS. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-6004 | DIVISION 9 | 79.26 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2024 | 2023 | 2023 | 2024 | 2025 | 2025 | 2026
FORSYTH | SR 1156 (LEWISVILLE- CLEMMONS ROAD) | SR 1103 (STYERS FERRY ROAD) TO SR 1101 (SHALLOWFORD ROAD) IN LEWISVILLE. WIDEN TO 3 LANES WITH BICYCLE AND PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-6189 | DIVISION 9 | 77.97 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | 2027 | 2028 | 2028 | 2027 | AFTER 2029 | 2030 | 2029
FORSYTH | SR 1969 (PINEY GROVE ROAD) | NORTH OF NELSON STREET TO SR 2031 (BROWN ROAD) IN KERNERSVILLE. WIDEN TO 3 LANES WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | U-6188 | DIVISION 9 | 82.73 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | 2027 | 2028 | 2028 | 2027 | AFTER 2029 | 2030 | 2029
FORSYTH | US 158 | MULTI-LANES NORTH OF US 421 / I-40 BUSINESS TO SR 1965 (BELEWS CREEK ROAD) | HIGHWAY | 9 | WINSTON-SALEM URBAN AREA MPO | R-2577A | REGION D | 61.54 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2024 | 2024 | 2024
FORSYTH, GUILFORD | US 158 | SR 1965 (BELEWS CREEK ROAD) IN FORSYTH COUNTY TO SR 2034 (ANTHONY ROAD) IN GUILFORD COUNTY | HIGHWAY | 7, 9 | WINSTON-SALEM URBAN AREA MPO, GREENSBORO URBAN AREA MPO | R-2577B | REGION D | 75.79 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY
FORSYTH, GUILFORD | US 421 (SALEM PARKWAY) | FUTURE I-74 IN KERNERSVILLE TO I-40 IN GUILFORD COUNTY. WIDEN TO 6 LANES. | HIGHWAY | 7, 9 | WINSTON-SALEM URBAN AREA MPO, GREENSBORO URBAN AREA MPO | U-6068 | NOT FUNDED | 77.04 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
FRANKLIN | TRIANGLE NORTH EXECUTIVE AIRPORT (LHZ) | CONSTRUCT RUNWAY EXTENSION, TO INCLUDE RELOCATION OF UTILITIES, NAVAID AND ROADWAYS. | AVIATION | 5 | CAPITAL AREA MPO | AV-5819 | DIVISION 5 | 89.63 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | 2026 |  |  |  | 2029 | 2029 | 2028
FRANKLIN | NC 56 | SR 1114 (PEACH ORCHARD ROAD) TO US 401 IN LOUISBURG. WIDEN TO 4 LANES. | HIGHWAY | 5 | KERR-TAR RPO | R-5893 | NOT FUNDED | 79.32 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
FRANKLIN | US 401 | SR 1103 (FLAT ROCK CHURCH ROAD / CLIFTON POND ROAD) TO SR 1700 (FOX PARK ROAD) SOUTH OF LOUISBURG | HIGHWAY | 5 | CAPITAL AREA MPO, KERR-TAR RPO | R-2814D | DIVISION 5 | 77.54 | P4.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2029 | NOT FUNDED | 2028 | 2029 | NOT FUNDED | 2028 | AFTER 2029 | NOT FUNDED | 2031
FRANKLIN | US 401 / NC 39 | NC 56 / NC 581 (NASH STREET) TO SR 1229 (MAIN STREET). WIDEN TO MULTILANES. | HIGHWAY | 5 | KERR-TAR RPO | R-3608 | REGION C | 74.32 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
FRANKLIN | US 401 / NC 39 (BICKETT BOULEVARD) | BURKE BOULEVARD TO NC 56 / NC 581 (NASH STREET) IN LOUISBURG. CONVERT 5-LANE SECTION TO 4-LANE DIVIDED FACILITY WITH BICYCLE / PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | 5 | KERR-TAR RPO | U-6024 | DIVISION 5 | 78.48 | P4.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2031
GASTON | CRAMERTON | SR 2014 (LAKEWOOD ROAD), SR 2565 (EAGLE ROAD) TO LAKE DRIVE. CONSTRUCT SIDEWALK AND PEDESTRIAN BRIDGE OVER SOUTH FORK RIVER INLET. | BIKE/PED | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5913 | DIVISION 12 | 53 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2022 | 2022 | 2025
GASTON | NC 279 (NEW HOPE ROAD) | US 29/74 (FRANKLIN BOULEVARD) TO HUNT AVENUE. CONSTRUCT SIDEWALK ON EAST SIDE OF NC 279 (NEW HOPE ROAD) FROM US 29/74 (FRANKLIN BOULEVARD) TO COURT DRIVE AND WEST SIDE OF NC 279 FROM COURT DRIVE TO HUNT AVENUE. | BIKE/PED | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5975 | DIVISION 12 | 91.05 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2024 | 2024 | 2024
GASTON | NC 279 (SOUTH NEW HOPE ROAD) | SR 2200 (ARMSTRONG PARK ROAD) TO SR 1255 (HUDSON BOULEVARD). CONSTRUCT MISSING SIDEWALK ON SOUTH SIDE OF NC 279. | BIKE/PED | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5743 | DIVISION 12 | 88.36 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2024 | 2024 | 2024
GASTON | SOUTH MARIETTA STREET/ HILLTOP DRIVE | HUDSON BOULEVARD TO CLYDE STREET. CONSTRUCT SIDEWALK ON ONE SIDE OF ROAD. | BIKE/PED | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5768 | DIVISION 12 | 36.98 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2023 |  |  |  | 2024 | 2024 | 2024
GASTON | SR 1255 (HUDSON BLVD) SR 2466 (REDBUD DR) | SR 1255 (HUDSON BOULEVARD) FROM SR 2200 (GASTON DAY SCHOOL ROAD) TO SR 2466 (REDBUD DRIVE). SR 2466 (REDBUD DRIVE) FROM SR 1255 (HUDSON BOULEVARD) TO NC 279 (SOUTH NEW HOPE ROAD). CONSTRUCT SIDEWALK ON ONE SIDE. | BIKE/PED | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5745 | DIVISION 12 | 56.83 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2023 |  |  |  | 2024 | 2024 | 2024
GASTON | SR 2044 (TUCKASEEGEE ROAD) MOUNT HOLLY | NC 273 TO MARINA VILLAGE DRIVE. CONSTRUCT SIDEWALK ON SOUTH SIDE. MARINA VILLAGE DRIVE NORTH TO BROOME STREET. CONSTRUCT SIDEWALK ON WEST SIDE. | BIKE/PED | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5912 | DIVISION 12 | 53.47 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2025 |  |  |  | 2024 | 2024 | 2027
GASTON | SR 2200 (COX ROAD) | I-85 TO COURT DRIVE. CONSTRUCT SIDEWALK ON BOTH SIDES OF SR 2200 (COX ROAD). | BIKE/PED | 12 | GASTON-CLEVELAND-LINCOLN MPO | EB-5976 | DIVISION 12 | 89.94 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2024 | 2024 | 2024
GASTON | I-85 | US 321 TO NC 273. WIDEN TO EIGHT LANES. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | I-5719 | STATEWIDE MOBILITY | 78.43 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024
GASTON | I-85 | US 74 TO US 321 | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | I-5985B | STATEWIDE MOBILITY | 79.82 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
GASTON | NC 27 (WEST CHARLOTTE AVENUE) | INTERSECTION OF NC 27 (WEST CHARLOTTE AVENUE) AND SR 2534 (HAWTHORNE STREET). CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5819 | DIVISION 12 | 69.04 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | 2028 |  | 2028 | 2028 | AFTER 2029 | 2030 | 2030
GASTON | NC 273 | SR 2525 (SOUTH POINT ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6150 | NOT FUNDED | 68.11 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2028 | NOT FUNDED | NOT FUNDED | 2028 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
GASTON | NC 274 (UNION ROAD) | OSCEOLA STREET TO NIBLICK DRIVE. UPGRADE ROADWAY. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5961 | REGION F | 75.18 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2024 | 2023 | 2023 | 2024 | 2025 | 2025 | 2027
GASTON | NC 275 | INTERSECTION OF NC 275 AND NC 274, INTERSECTION OF NC 275 AND SR 1327 (FAIRVIEW ROAD), AND INTERSECTION OF SR 1456 (WHITE JENKINS ROAD) AND SR 1327 (FAIRVIEW ROAD). IMPROVE INTERSECTIONS AND CLOSE INTERSECTION OF NC 275 AND SR 1456 (WHITE JENKINS ROAD) | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6078 | DIVISION 12 | 54.13 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2025 | 2024 | 2024 | 2025 | 2025 | 2025 | 2027
GASTON | NC 279 | NORTH OF SR 2275 (ROBINSON-CLEMMER ROAD) TO WEST OF NC 275 IN DALLAS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-2523B | REGION F | 73.78 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2028 | 2028 | 2028
GASTON | NC 279 (NEW HOPE ROAD) | SR 2478 (TITMAN ROAD) TO SR 2435 (UNION-NEW HOPE ROAD). WIDEN TO 4-LANES. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5821 | DIVISION 12 | 68.01 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2021 | 2023 | 2023 | 2026 | 2026 | 2026
GASTON | NC 279 (NORTH NEW HOPE ROAD) | US 29/74 (FRANKLIN BOULEVARD) INTERSECTION. ADD RIGHT TURN LANE FROM NC 279 (NORTH NEW HOPE ROAD) TO US 29/74 (FRANKLIN BOULEVARD). | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6138 | REGION F | 78.13 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY |  | 2025 | 2025 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026
GASTON | NC 7 | INTERSECTION OF NC 7/US 74 AND NC 7/US 29. CONSTRUCT NORTHBOUND THROUGH LANE AND INTERSECTION IMPROVEMENTS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5800 | REGION F | 57.83 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024
GASTON | SR 2200 (COX ROAD) | I-85 TO US 29/74. SELECTIVE WIDENING AND OPERATIONAL IMPROVEMENTS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6044 | DIVISION 12 | 87.59 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2025 | NOT FUNDED | 2025 | 2025 | NOT FUNDED | 2025 | 2028 | NOT FUNDED | 2028
GASTON | US 29 (FRANKLIN BOULEVARD) | US 29 (FRANKLIN BOULEVARD) AND NC 274. CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5965 | REGION F | 73.93 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2023 | 2022 | 2022 | 2023 | 2024 | 2024 | 2025
GASTON | US 29/74 (FRANKLIN BOULEVARD) | SR 2329 (REDBUD DRIVE) INTERSECTION. IMPROVE INTERSECTION AREA INCLUDING NEW GRADE-SEPARATED CROSSING OF US 29/74. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6141 | NOT FUNDED | 75.9 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
GASTON | US 29/74 (WILKINSON BOULEVARD) | MARKET STREET TO SR 2015 (ALBERTA AVENUE. WIDEN TO SIX LANES (INCLUDES REPLACEMENT OF BRDIGE 350082 OVER SOUTH FORK OF CATAWBA RIVER). | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6146 | REGION F | 68.21 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2024 | 2024 | 2024
GASTON | US 29/US 74 (FRANKLIN BOULEVARD) | SR 2200 (COX ROAD) TO 400 FEET EAST OF LINEBERGER ROAD. ADD LANE IN THE EASTBOUND DIRECTION. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6043 | DIVISION 12 | 73.71 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2023 | 2023 | 2022 | 2023 | 2023 | 2024 | 2025 | 2025
GASTON | US 321 (SOUTH YORK ROAD) | 19TH AVENUE TO CLYDE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5970 | REGION F | 78.42 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
GASTON | US 74 (WILKINSON BOULEVARD) | US 74 (WILKINSON BOULEVARD) AT NC 273 (PARK STREET). CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5959 | REGION F | 79.22 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
GATES, CHOWAN | NC 32 | NC 37 (GLIDEN ROAD) TO VIRGINIA STATE LINE. MODERNIZE ROADWAY. | HIGHWAY | 1 | ALBEMARLE RPO | R-5938 | DIVISION 1 | 71.81 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2030
GRAHAM | NC 143 | WEST BUFFALO CREEK TO NC 143 BUSINESS. UPGRADE CORRIDOR. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-2822B | REGION G | 62.05 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2025 | 2023 | 2023 | 2025 | 2023 | 2024 | 2028 | 2025
GRAHAM | NC 28 | SWAIN/GRAHAM COUNTY LINE AT LITTLE TENNESSEE RIVER TO WOODS ROAD AT FONTANA DAM VILLAGE. UPGRADE ROADWAY. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5839BA | DIVISION 14 | 60.17 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2027 | 2027 | 2024 | 2027 | 2027 | 2029 | 2029 | 2029
GRANVILLE | NC 56 (EAST C STREET) | SR 1215 (WEST LYON STATION ROAD) IN BUTNER. REALIGN INTERSECTION. | HIGHWAY | 5 | KERR-TAR RPO | U-6020 | DIVISION 5 | 79.47 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2025 | 2025 | 2025
GREENE | NC 58 (KINGOLD BOULEVARD) | SR 1105 (GREENRIDGE ROAD) TO CAROLINA DRIVE. UPGRADE ROADWAY. | HIGHWAY | 2 | EASTERN CAROLINA RPO | R-5898 | NOT FUNDED | 74.28 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2027 | NOT FUNDED | NOT FUNDED | 2027 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
GREENE | US 13 | SR 1104 (HULL ROAD). UPGRADE INTERSECTION. | HIGHWAY | 2 | EASTERN CAROLINA RPO | R-5943 | DIVISION 2 | 83.41 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | 2026 | 2028 | 2028 | 2026 | AFTER 2029 | 2030 | 2028
GREENE | US 13/US 258 | NC 91 TO US 258 SPLIT. UPGRADE TO FREEWAY. | HIGHWAY | 2 | EASTERN CAROLINA RPO | R-5942 | NOT FUNDED | 83.44 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | SURFACE MOVEMENT GUIDANCE AND CONTROL SYSTEM (SMGCS) UPDATE. | AVIATION | 7 | GREENSBORO URBAN AREA MPO | AV-5711 | STATEWIDE MOBILITY | 62.05 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2022 | 2022 | 2025
GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | RUNWAY 5R-23L GROUP VI UPGRADE. | AVIATION | 7 | GREENSBORO URBAN AREA MPO | AV-5715 | STATEWIDE MOBILITY | 60.28 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2024 | 2024 | 2024
GUILFORD | PIEDMONT TRIAD INTERNATIONAL AIRPORT (GSO) | TAXIWAY F. CONSTRUCT TAXIWAY INCLUDING BRIDGE OVER TED JOHNSON PARKWAY. | AVIATION | 7 | GREENSBORO URBAN AREA MPO | AV-5803 | STATEWIDE MOBILITY | 89.64 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2024 | 2024 | 2024
GUILFORD | BENJAMIN PARKWAY; WESTOVER TERRACE | BENJAMIN PARKWAY FROM ELAM AVENUE TO BATTLEGROUND AVENUE, AND WESTOVER TERRACE FROM BENJAMIN PARKWAY TO SEMINOLE DRIVE IN GREENSBORO. CONSTRUCT SIDEWALK ON BENJAMIN PARKWAY FROM ELAM AVENUE TO AYCOCK STREET, CONSTRUCT SIDEPATH ON BENJAMIN PARKWAY FROM AYC | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-5986 | DIVISION 7 | 89.12 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2022 |  |  |  | 2024 | 2024 | 2024
GUILFORD | CEDROW DRIVE | WEST OF I-74 TO EAST OF I-74 IN HIGH POINT. CONSTRUCT MULTIUSE FACILITY ACROSS I-74. | BIKE/PED | 7 | HIGH POINT URBAN AREA MPO | EB-5989 | DIVISION 7 | 86.25 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | 2025 |  |  |  | 2026 | 2026 | 2026
GUILFORD | GREEN VALLEY ROAD | FRIENDLY AVENUE TO WESTOVER TERRACE IN GREENSBORO. CONSTRUCT SIDEWALKS. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-5997 | DIVISION 7 | 62.04 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 |  |  |  | 2025 | 2025 | 2025
GUILFORD | HIGH POINT RAILROAD ESPLANADE | LIINDSAY STREET TO CENTENNIAL STREET IN HIGH POINT. CONSTRUCT GREENWAY. | BIKE/PED | 7 | HIGH POINT URBAN AREA MPO | EB-5990 | DIVISION 7 | 85.29 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | [6 empty] | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
GUILFORD | JOHNSON STREET | PARRIS AVENUE TO SR 1896 (EAST HARTLEY DRIVE) IN HIGH POINT. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | HIGH POINT URBAN AREA MPO | EB-5999 | DIVISION 7 | 59.45 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | [6 empty] | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
GUILFORD | LAWNDALE DRIVE | PISGAH CHURCH ROAD TO LAKE BRANDT ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-5995 | DIVISION 7 | 65.29 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 |  |  |  | 2025 | 2025 | 2025
GUILFORD | NC 68 (EASTCHESTER DRIVE) | CENTENNIAL STREET TO LASSITER DRIVE IN HIGH POINT. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | HIGH POINT URBAN AREA MPO | EB-5922 | DIVISION 7 | 58.71 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2025 | 2025 | 2025
GUILFORD | OLD BATTLEGROUND ROAD | LAKE BRANDT ROAD TO BICENTENNIAL GREENWAY IN GREENSBORO. CONSTRUCT MULTIUSE PATH. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-5987 | DIVISION 7 | 88.76 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 |  |  |  | 2025 | 2025 | 2025
GUILFORD | SPRING GARDEN STREET | SR 1008 (WEST MARKET STREET) TO POMONA DRIVE AND MERRITT DRIVE TO HOLDEN ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-5992 | DIVISION 7 | 66.74 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | [6 empty] | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
GUILFORD | SR 1001 (NORTH CHURCH STREET) | HENRY STREET / ELECTRA DRIVE TO LEES CHAPEL ROAD IN GREENSBORO. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-5996 | DIVISION 7 | 62.52 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | [6 empty] | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
GUILFORD | SR 1536 (PENNY ROAD) | CITY LAKE PARK TO PIEDMONT ENVIRONMENTAL CENTER IN HIGH POINT. CONSTRUCT MULTIUSE PATH. | BIKE/PED | 7 | HIGH POINT URBAN AREA MPO | EB-6000 | DIVISION 7 | 59.31 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | [6 empty] | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
GUILFORD | SR 2526 (SUMMIT AVENUE) | SULLIVAN STREET TO FOURTH STREET IN GREENSBORO. CONSTRUCT BICYCLE, PEDESTRIAN AND SAFETY IMPROVEMENTS. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-6009 | DIVISION 7 | 58.81 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | [6 empty] | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
GUILFORD | SUMMERFIELD SOUTH GREENWAY | US 220 TO CENTERFIELD ROAD IN SUMMERFIELD. CONSTRUCT MULTIUSE PATH. | BIKE/PED | 7 | GREENSBORO URBAN AREA MPO | EB-5900 | DIVISION 7 | 53.07 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2022 |  |  |  | 2024 | 2024 | 2024
GUILFORD | US 70 (WEST WENDOVER AVENUE) | NC 68 (EASTCHESTER DRIVE) TO GIBSON PARK ENTRANCE IN HIGH POINT. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | HIGH POINT URBAN AREA MPO | EB-6010 | DIVISION 7 | 58.11 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | [6 empty] | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
GUILFORD | I-40 | SR 1860 (MACY GROVE ROAD). CONVERT GRADE SEPARATION TO INTERCHANGE. | HIGHWAY | 7 | HIGH POINT URBAN AREA MPO | I-5980 | REGION D | 75.96 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2026 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2026 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY
GUILFORD | I-40 / BUSINESS 85 / US 29 / US 70 / US 220 | US 220 / SR 1398 (FREEMAN MILL ROAD) TO US 29 / US 70 / US 220 IN GREENSBORO. ADD LANES, IMPROVE SR 1007 (RANDLEMAN ROAD) AND ELM-EUGENE STREET INTERCHANGES, AND REPLACE NORFOLK-SOUTHERN RAILROAD BRIDGE OVERPASS EAST OF ELM-EUGENE STREET. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | I-5965 | STATEWIDE MOBILITY | 80.4 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
GUILFORD | I-40 / I-85 | SR 3056 (ROCK CREEK DAIRY ROAD) INTERCHANGE. UPGRADE INTERCHANGE AREA. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | I-6004 | STATEWIDE MOBILITY | 87.82 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
GUILFORD | I-40 / US 421 | SR 1850 (SANDY RIDGE ROAD) IN GREENSBORO. INTERCHANGE IMPROVEMENTS. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | I-5712 | STATEWIDE MOBILITY | 80.28 | P3.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2025 | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2025 | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027
GUILFORD | MCCONNELL ROAD | GORRELL STREET AND WILLOW HOPE STREET IN GREENSBORO. CONSTRUCT ROUNDABOUT. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6185 | DIVISION 7 | 79.8 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
GUILFORD | NC 62 | SR 1007 (RANDLEMAN ROAD). CONSTRUCT TURN LANES. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6212 | DIVISION 7 | 74.79 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
GUILFORD | NC 68 | SR 1523 (HICKSWOOD ROAD) TO SR 1556 (GALLIMORE DAIRY ROAD) IN HIGH POINT. UPGRADE TO SUPERSTREET. | HIGHWAY | 7 | HIGH POINT URBAN AREA MPO | U-5974 | REGION D | 76.71 | P4.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029
GUILFORD | NC 68 | SR 1556 (GALLIMORE DAIRY ROAD) TO TRIAD CENTER DRIVE IN GREENSBORO. UPGRADE CORRIDOR TO SUPERSTREET. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO, HIGH POINT URBAN AREA MPO | U-6122 | REGION D | 80.98 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
GUILFORD | NC 68 | SR 2129 (FOGLEMAN ROAD) TO SR 2017 / SR 2269 (ALCORN ROAD) IN OAK RIDGE. ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6127 | REGION D | 79.71 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
GUILFORD | PISGAH CHURCH ROAD | NORTH ELM STREET IN GREENSBORO. INTERSECTION IMPROVEMENTS. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-5842 | DIVISION 7 | 72.98 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 |  |  |  | 2024 | 2024 | 2024
GUILFORD | SR 1001 (CHURCH STREET) | US 220 (WENDOVER AVENUE) TO EAST CONE BOULEVARD IN GREENSBORO. ADD LANES. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-5851 | DIVISION 7 | 66.99 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | AFTER 2029 | 2030 | 2030
GUILFORD | SR 1001 (NORTH CHURCH STREET) | SR 2516 (ARCHERGATE ROAD) AND SR 2329 (SPENCER-DIXON ROAD) IN GREENSBORO. REALIGN INTERSECTION. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6186 | DIVISION 7 | 78.83 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
GUILFORD | SR 1007 (RANDLEMAN ROAD) | ELMSLEY DRIVE TO GLENDALE DRIVE IN GREENSBORO. WIDEN TO MULTLANES. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-5850 | DIVISION 7 | 67.14 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2025 | 2025 | 2025
GUILFORD | SR 1818 (JOHNSON STREET) / SR 1850 (SANDY RIDGE RO | SR 1820 (SKEET CLUB ROAD) TO SOUTH OF I-40 IN HIGH POINT. WIDEN TO FOUR LANES. | HIGHWAY | 7 | HIGH POINT URBAN AREA MPO | U-4758 | DIVISION 7 | 64.95 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2024 | 2024 | 2024
GUILFORD | SR 1850 (SANDY RIDGE ROAD) | I-40 TO SR 1008 (WEST MARKET STREET) IN GREENSBORO. WIDEN TO MULTILANES. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6045 | DIVISION 7 | 64.41 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | AFTER 2029 | 2030 | 2030
GUILFORD | SR 2085 (BENJAMIN PARKWAY / BRYAN BOULEVARD) | US 70 (WENDOVER AVENUE) TO HOLDEN ROAD IN GREENSBORO. ADD LANES. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-5852 | DIVISION 7 | 66.89 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2025
GUILFORD | SR 2085 (BRYAN BOULEVARD) | NEW GARDEN ROAD AT HORSEPEN CREEK ROAD IN GREENSBORO. INTERCHANGE IMPROVEMENTS, INCLUDING NEW RAMP FROM WESTBOUND NEW GARDEN ROAD TO WESTBOUND SR 2085. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6008 | DIVISION 7 | 85.18 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2029 | 2029 | 2029
GUILFORD | SR 2133 (PLEASANT RIDGE ROAD) | SR 2136 (FLEMING ROAD) IN SUMMERFIELD. CONSTRUCT TURN LANES. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6211 | DIVISION 7 | 75.28 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
GUILFORD | SR 2835 (MCKNIGHT MILL ROAD) | SR 2842 (MINORWOOD ROAD). UPGRADE INTERSECTION. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6181 | DIVISION 7 | 80.99 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
GUILFORD | US 220 (BATTLEGROUND AVENUE) | WESTRIDGE ROAD TO COTSWOLD AVENUE IN GREENSBORO. ADD LANES. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-5892 | REGION D | 57.29 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2028 | 2023 | 2023 | 2028 | 2023 | 2026 | 2030 | 2026
GUILFORD | US 29; US 70; US 220 | SR 4240 (GATE CITY BOULEVARD) TO SOUTH OF I-785 IN GREENSBORO. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS AND SAFETY ENHANCEMENTS, INCLUDING RAMP CLOSURES AND CONSOLIDATIONS, RECONFIGURE SR 2526 (SUMMIT AVENUE) / PHILLIPS AVENUE INTERCHANGE, AND REPLACE BRI | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6100 | NOT FUNDED | 79.78 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
GUILFORD | US 70 (WENDOVER AVENUE) | NC 68 (EASTCHESTER DRIVE) IN HIGH POINT TO SR 1541 (GUILFORD COLLEGE ROAD) IN GREENSBORO. WIDEN TO 6 LANES AND CONSTRUCT SIDEWALKS. | HIGHWAY | 7 | HIGH POINT URBAN AREA MPO, GREENSBORO URBAN AREA MPO | U-6121 | DIVISION 7 | 91.94 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
GUILFORD | US 70 / US 220 (WENDOVER AVENUE) | US 220 (BATTLEGROUND AVENUE) IN GREENSBORO. RECONFIGURE BATTLEGROUND AVENUE, LAWNDALE DRIVE, AND WESTOVER TERRACE BETWEEN FERNWOOD DRIVE AND WENDOVER AVENUE. IMPROVE TRAFFIC FLOW AND SAFETY. IMPROVE WENDOVER AVENUE CONNECTIONS AT WESTOVER TERRACE, BATTLEG | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6108 | REGION D | 86.6 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
GUILFORD | VARIOUS | LAWNDALE DRIVE AND PISGAH CHURCH ROAD IN GREENSBORO. INTERSECTION IMPROVEMENTS AT LAWNDALE ROAD AND PISGAH CHURCH ROAD, AT LAWNDALE ROAD AND MARTINSVILLE ROAD, AND AT MARTINSVILLE ROAD AND PISGAH CHURCH ROAD | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-5812 | DIVISION 7 | 80.82 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 |  |  |  | 2024 | 2024 | 2024
GUILFORD | WEST FRIENDLY AVENUE | PEMBROKE ROAD INTERSECTION AND GREEN VALLEY ROAD INTERSECTION IN GREENSBORO. CONSTRUCT INTERSECTION AND PEDESTRIAN IMPROVEMENTS. FROM PEMBROKE ROAD TO GREEN VALLEY ROAD, CONSTRUCT ROADWAY AND ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 7 | GREENSBORO URBAN AREA MPO | U-6129 | DIVISION 7 | 86.9 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
GUILFORD | NCRR / NORFOLK SOUTHERN MAIN LINE | HOSKINS STREET IN HIGH POINT. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722351T. | RAIL | 7 | HIGH POINT URBAN AREA MPO | P-5752 | DIVISION 7 | 56.74 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
GUILFORD | NCRR NORFOLK SOUTHERN | POMONA YARD. EXTEND AUXILIARY TRACK AND ADD POWER TURNOUTS. | RAIL | 7 | GREENSBORO URBAN AREA MPO | P-5714 | REGION D | 76.01 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2024 | 2024 | 2024
GUILFORD | NCRR NORFOLK SOUTHERN H LINE | SOUTH ENGLISH STREET IN GREENSBORO. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722955X. | RAIL | 7 | GREENSBORO URBAN AREA MPO | P-5747 | REGION D | 78.45 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2028 | 2025 |  |  |  | 2026 | 2031 | 2026
GUILFORD | NORFOLK SOUTHERN | JAMESTOWN SIDING IN JAMESTOWN. CONSTRUCT EXTENSION. | RAIL | 7 | HIGH POINT URBAN AREA MPO | P-5721 | STATEWIDE MOBILITY | 68.72 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2024 | 2024 | 2024
GUILFORD | NORFOLK SOUTHERN H LINE | CONSTRUCT GRADE SEPARATION AT FRANKLIN BOULEVARD CROSSING (722959A) IN GREENSBORO, AND CLOSE O'FERRELL STREET CROSSING (722961B). | RAIL | 7 | GREENSBORO URBAN AREA MPO | P-5709 | REGION D | 72.79 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2024 | 2024 | 2024
GUILFORD | NORFOLK SOUTHERN MAIN LINE | SR 1584 (YANCEYVILLE STREET) IN GREENSBORO. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 722542D. | RAIL | 7 | GREENSBORO URBAN AREA MPO | P-5735 | STATEWIDE MOBILITY | 82.97 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
GUILFORD | NORTH CAROLINA RAILROAD (NCRR) / NORFOLK SOUTHERN | SR 1424 (HILLTOP ROAD) IN GREENSBORO. CONVERT AT-GRADE CROSSING TO GRADE SEPARATION. | RAIL | 7 | GREENSBORO URBAN AREA MPO | P-5713 | STATEWIDE MOBILITY | 70.6 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2026 | 2024 | 2023 | 2026 | 2024 | 2025 | 2028 | 2026
GUILFORD, FORSYTH | I-40 | NC 66 TO US 421 / BUSINESS 40. | HIGHWAY | 7, 9 | HIGH POINT URBAN AREA MPO, WINSTON-SALEM URBAN AREA MPO | I-5981C | STATEWIDE MOBILITY | 78.55 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2030 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
HALIFAX | (IXA) HALIFAX NORTHAMPTON REGIONAL AIRPORT | CONSTRUCT TAXI LANE AND PREPARATION FOR ADDITIONAL T-HANGARS. | AVIATION | 4 | PEANUT BELT RPO | AV-5822 | DIVISION 4 | 68.48 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2024 | 2024 | 2024
HALIFAX | HALIFAX NORTHAMPTON REGIONAL AIRPORT (IXA) | CONSTRUCT TAXILANE AND APRON. | AVIATION | 4 | PEANUT BELT RPO | AV-5833 | DIVISION 4 | 69.25 | NOT COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2026 | 2026 | 2026
HALIFAX | EAST 10TH STREET | MARSHALL STREET TO PARKE AVENUE IN ROANOKE RAPIDS. CONSTRUCT SIDEWALK ON BOTH SIDES OF ROAD. | BIKE/PED | 4 | PEANUT BELT RPO | EB-5843 | DIVISION 4 | 89.01 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2025 | 2025 | 2025
HALIFAX, NORTHAMPTON | CSX A LINE | CONSTRUCT NEW MAIN TRACK BETWEEN MP A-80.7 AND MP A-82.4 INCLUDING REHABILITATION OF CSX SA-LINE BRIDGE OVER ROANOKE RIVER. NEW CONNECTION BETWEEN A-LINE AND SA-LINE AT MP A-80.7. RECONSTRUCT MAIN TRACK BETWEEN MP A-82.4 AND MP A-84.7. CREATE SECOND MAIN. | RAIL | 1, 4 | PEANUT BELT RPO | P-5741 | STATEWIDE MOBILITY | 82.2 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
HARNETT | NC 55 | NC 27 IN COATS TO SR 1006 (OLD STAGE ROAD (NORTH)). WIDEN ROADWAY. | HIGHWAY | 6 | MID-CAROLINA RPO | R-5953 | NOT FUNDED | 81.88 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
HARNETT | NC 87/24 | SR 1117 (NURSERY ROAD). INTERSECTION IMPROVEMENTS. | HIGHWAY | 6 | FAYETTEVILLE AREA MPO | U-5933 | STATEWIDE MOBILITY | 74.2 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY |  | 2024 | 2023 |  | 2024 | 2023 | 2025 | 2026 | 2025
HARNETT | US 401 (NORTH MAIN STREET) | PARKER LANE TO MCKINNEY PARKWAY. CONSTRUCT MEDIAN. | HIGHWAY | 6 | MID-CAROLINA RPO | R-5890 | REGION C | 81.35 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2025 | NOT FUNDED | 2028 | 2025 | NOT FUNDED | 2028 | AFTER 2029 | NOT FUNDED | 2030
HAYWOOD | US 19 (SOCO ROAD) | SR 1304 (FIE TOP ROAD AT GHOST TOWN IN THE SKY) TO BLUE RIDGE PARKWAY. MODERNIZE ROADWAY. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-6160 | NOT FUNDED | 66.08 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
HAYWOOD | US 23 BUSINESS (SOUTH MAIN STREET) | SR 1164 (HYATT CREEK ROAD) TO US 276 (PIGEON STREET). WIDEN TO MULTI-LANES. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-4712 | DIVISION 14 | 58.41 | P4.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2024 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | 2024 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2030
HAYWOOD | US 276 | SR 1134 (CRYMES COVE ROAD) AND RACCOON ROAD. INTERSECTION REALIGNMENT. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-6158 | DIVISION 14 | 68.8 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2030
HAYWOOD | US 276 (JONATHAN CREEK) | US 19 TO I-40 UPGRADE. MODERNIZE ROADWAY. | HIGHWAY | 14 | LAND-OF-SKY RPO, FRENCH BROAD RIVER MPO | R-5921 | DIVISION 14 | 65.19 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2024 | 2025 | 2024
HAYWOOD | US 276 (RUSS AVENUE) | US 23-74 (GREAT SMOKEY MOUNTAIN EXPRESSWAY) TO US 19 (DELLWOOD ROAD). ACCESS MANAGEMENT. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-6159 | DIVISION 14 | 68.44 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2030
HAYWOOD, BUNCOMBE | US 19, US 23 | SR 1836 (CHESTNUT MOUNTAIN ROAD) TO SR 1200 (WIGGINS ROAD). UPGRADE ROADWAY. | HIGHWAY | 13, 14 | FRENCH BROAD RIVER MPO | U-6048 | DIVISION 13, 14 | 61.98 | P4.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2030
HAYWOOD, JACKSON | US 23/US 74 (GREAT SMOKEY MOUNTAINS EXPRESSWAY) | SR 1777 (BALSAM VIEW DRIVE) TO SR 1158 (OLD BALSAM ROAD) MODERNIZE ROADWAY. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO, SOUTHWESTERN RPO | U-6172 | DIVISION 14 | 63.37 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
HENDERSON | BLYTHE STREET | BLYTHE STREET, US 64 (BREVARD ROAD) TO NC 191 (HAYWOOD ROAD). CONSTRUCT SIDEWALKS. | BIKE/PED | 14 | FRENCH BROAD RIVER MPO | EB-5860 | DIVISION 14 | 71.59 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | 2025 |  |  | 2025 | 2026 | 2027 | 2026
HENDERSON | GROVE STREET | BARNWELL STREET TO US 176 (SPARTANBURG HIGHWAY). CONSTRUCT SIDEWALK. | BIKE/PED | 14 | FRENCH BROAD RIVER MPO | EB-5963 | DIVISION 14 | 76.12 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | 2025 |  |  | 2025 | 2026 | 2027 | 2026
HENDERSON | I-26 | US 25 TO US 64 | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | I-4400A | NOT FUNDED | 71.27 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED |  | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
HENDERSON | I-26 | US 64 INTERCHANGE IMPROVEMENTS | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | I-4400BA | STATEWIDE MOBILITY | 63.02 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
HENDERSON | NC 191 | SR 1381 (MOUNTAIN ROAD) TO NC 280 SOUTH OF MILLS RIVER. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | R-2588B | DIVISION 14 | 64.31 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2024 | 2024 | 2024
HENDERSON | NC 225 (SOUTH MAIN STREET) | SOUTH MAIN STREET AT SOUTH KING STREET TO US 176. WIDEN BRIDGE 440143 TO 5-LANES. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-6049 | REGION G | 62.09 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2026 | 2023 | 2023 | 2026 | 2023 | 2026 | 2029 | 2026
HENDERSON | NC 280 (BOYLSTON HIGHWAY) | NC 191 (HAYWOOD ROAD) TO NC 191 (OLD HAYWOOD ROAD). CONSTRUCT ACCESS MANAGEMENT AND INTERSECTION IMPROVEMENTS. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-6124 | NOT FUNDED | 77.36 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
HENDERSON | SR 1127 (KANUGA ROAD) | US 25 BUSINESS (CHURCH STREET) TO SR 1123 (LITTLE RIVER ROAD). UPGRADE ROADWAY. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | R-5748 | DIVISION 14 | 64.88 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2028 | 2027 | 2027 | 2028 | 2027 | AFTER 2029 | 2031 | 2029
HENDERSON | SR 1170 (WHITE STREET) | SR 1171 (WILLOW ROAD) TO US 176 (SPARTANBURG HIGHWAY). REALIGN AND EXTEND ROADWAY. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-5886 | DIVISION 14 | 37.97 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2026 | 2023 | 2023 | 2026 | 2023 | 2026 | 2029 | 2026
HENDERSON | US 64 | SR 1180 (BLYTHE STREET) TO SR 1173 (WHITE PINE DRIVE)/SR 1186 (DANIEL DRIVE). WIDEN ROADWAY. | HIGHWAY | 14 | FRENCH BROAD RIVER MPO | U-5783 | REGION G | 53.45 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2024 | 2024 | 2024
HERTFORD | TRI-COUNTY AIRPORT (ASJ) | RUNWAY EXTENSION. | AVIATION | 1 | PEANUT BELT RPO | AV-5778 | DIVISION 1 | 77.04 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | [6 empty] | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
HERTFORD | TRI-COUNTY AIRPORT (ASJ) | CONSTRUCT ACCESS ROAD TO T-HANGARS. | AVIATION | 1 | PEANUT BELT RPO | AV-5878 | NOT FUNDED | 55.52 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | [6 empty] | 2027 | NOT FUNDED | NOT FUNDED
HERTFORD | US 13/NC 11 | NC 11/NC 561 INTERSECTION NEAR AHOSKIE TO US 13/US 158/NC 45 INTERSECTION NEAR WINTON. | HIGHWAY | 1 | PEANUT BELT RPO | R-5311B | REGION A | 74.38 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2030
HERTFORD | US 13/NC 42/NC 561 (MEMORIAL DRIVE) | PEACHTREE STREET TO NC 42. WIDEN TO MULTI-LANES. | HIGHWAY | 1 | PEANUT BELT RPO | R-5796 | REGION A | 78.38 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2024 | 2023 | 2023 | 2024 | 2025 | 2025 | 2025
HOKE | SR 1305 (WAYSIDE ROAD); SR 1418 (LINDSAY ROAD) | SR 1305, US 401 TO PLANK ROAD, AND SR 1418, US 401 TO SR 1406 (ROCKFISH ROAD). WIDEN TO MULTILANES. | HIGHWAY | 8 | FAYETTEVILLE AREA MPO | U-5753 | DIVISION 8 | 67.08 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2024 | 2024 | 2024
HOKE | SR 1406 (ROCKFISH ROAD); NEW ROUTE (GILLIS HILL RO | SR 1406 (ROCKFISH ROAD) FROM SR 1003 (CAMDEN ROAD) TO NORTH OF WESTFIELD DRIVE AND GILLIS HILL ROAD EXTENSION FROM NORTH OF WESTFIELD DRIVE TO SR 1418 (LINDSAY ROAD). WIDEN TO MULTI-LANES, PART ON NEW LOCATION. | HIGHWAY | 8 | FAYETTEVILLE AREA MPO | U-5857 | DIVISION 8 | 65.02 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2029 | 2029 | 2029
HOKE, MOORE | NC 211 | US 15 / US 501 IN ABERDEEN TO EAST OF SR 1244 (WEST PALMER STREET) / SR 1311 (MOCKINGBIRD HILL ROAD) IN RAEFORD. WIDEN TO MULTILANES. | HIGHWAY | 8 | LUMBER RIVER RPO, TRIANGLE AREA RPO | R-5709 | REGION E | 50.15 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2024 | 2024 | 2024
HOKE, SCOTLAND | US 401 | US 401 BUSINESS NORTH OF LAURINBURG TO US 401 BUSINESS EAST OF RAEFORD. CONSTRUCT PASSING LANES, TURN LANES, AND PAVED SHOULDERS. | HIGHWAY | 8 | LUMBER RIVER RPO, FAYETTEVILLE AREA MPO | R-3333 | NOT FUNDED | 47.26 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
IREDELL | STATESVILLE REGIONAL AIRPORT (SVH) | RELOCATE EAST AVIATION DRIVE TO ALLOW FOR FUTURE RUNWAY EXTENSION. | AVIATION | 12 | CHARLOTTE REGIONAL TPO | AV-5896 | DIVISION 12 | 87.84 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | 2026 |  |  |  | 2026 | 2027 | 2027
IREDELL | I-77 | I-77 AT SR 1302 (CORNELIUS ROAD). CONVERT GRADE SEPARATION TO INTERCHANGE. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | I-5962 | STATEWIDE MOBILITY | 79.3 | P4.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2026 | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2026 | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028
IREDELL | NC 115 | SR 1645 (OLD WILKESBORO ROAD) TO HARTNESS ROAD. WIDEN TO MULTI-LANES. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-5779 | REGION F | 58.22 | P3.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
IREDELL | NC 150 | INTERSECTION OF NC 150 AND SR 2399 (WIGGINS ROAD). REALIGN INTERSECTION. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-5780 | REGION F | 56.37 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2019 | 2019 | 2019 |  |  |  | 2024 | 2024 | 2024
IREDELL | NC 150 (OAK RIDGE FARM HIGHWAY) | NC 115 TO NC 801 (PARK AVENUE). WIDEN TO MULTI-LANES. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-5960 | REGION F | 70.71 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
IREDELL | NC 3 | CABARRUS-IREDELL COUNTY LINE TO SR 1147 (ROCKY RIVER ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-6145 | NOT FUNDED | 69.58 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
IREDELL | SR 1005 (OLD MOUNTAIN ROAD) | US 21/NC 115 (NORTH MAIN STREET) TO SR 1004 (BUFFALO SHOALS ROAD). WIDEN TO FOUR LANES WITH A MEDIAN. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-6175 | NOT FUNDED | 83.49 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
IREDELL | SR 1100 (BRAWLEY SCHOOL ROAD) | I-77 TO US 21 | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | R-3833C | DIVISION 12 | 70.46 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2019 | 2019 | 2019 | 2019 | 2019 |  | 2024 | 2024 | 2024
IREDELL | SR 1109 (WILLIAMSON ROAD) | I-77 TO SR 1100 (BRAWLEY SCHOOL ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | R-5100A | DIVISION 12 | 79.21 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2020 | 2020 | 2020 | 2022 | 2022 | 2022 | 2025 | 2025 | 2025
IREDELL | SR 1109 (WILLIAMSON ROAD) | SR 1100 (BRAWLEY SCHOOL ROAD) TO NC 150. WIDEN TO MULTI-LANES. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | R-5100B | DIVISION 12 | 79.78 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2019 | 2019 | 2019 | 2022 | 2022 | 2022 | 2025 | 2025 | 2025
IREDELL | SR 1246 (FAIRVIEW ROAD) | EXTEND SR 1246 (FAIRVIEW ROAD) OVER I-77 TO CONNECT WITH SR 1206 (ALCOVE ROAD) AND CONSTRUCT PARALLEL NORTH-SOUTH CONNECTOR ROADS TO SR 1109 (WILLIAMSON ROAD). | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-5817 | DIVISION 12 | 83.46 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2025 | 2025 | 2025
IREDELL | SR 1305 (OATES ROAD - MIDNIGHT LANE) | US 21 (CHARLOTTE HIGHWAY) TO SR 1474 (BLUEFIELD ROAD). WIDEN TO THREE-LANES WITH OVERPASS OVER I-77. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-5816 | DIVISION 12 | 85.81 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | 2026 | 2023 | 2026 | 2026 | 2029 | 2029 | 2029
IREDELL | US 21 | INTERSECTION OF US 21 AND SR 2375 (HOUSTON ROAD)/SR 1312 (FLOWER HOUSE ROAD). REALIGN AND SIGNALIZE. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | R-5711 | REGION F | 60.97 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2025 | 2025 | 2025
IREDELL | US 21 - NC 115 | CEDAR LANE IN TROUTMAN TO BARIUM LANE IN BARIUM SPRINGS. WIDEN TO MULTI-LANES. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | R-2522 | REGION F | 75.51 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
IREDELL | US 21 (CHARLOTTE HIGHWAY) | NC 150 (PLAZA DRIVE) TO SR 1245 (MEDICAL PARK ROAD). WIDEN TO 4-LANES DIVIDED. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-6037 | DIVISION 12 | 83.96 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | AFTER 2029 | 2030 | 2030
IREDELL | US 64 (DAVIE AVENUE) | US 64 (DAVIE AVENUE) AND US 21 (SULLIVAN ROAD). CONVERT 5-APPROACH INTERSECTION TO A SINGLE LANE ROUNDABOUT. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO | U-5964 | REGION F | 74.01 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2026 | 2026 | 2026
IREDELL, CATAWBA | NC 150 | EAST OF SR 1840 (GREENWOOD ROAD) IN CATAWBA COUNTY TO WEST OF SR 1303/SR 1180 (PERTH ROAD/DOOLIE ROAD) IN IREDELL COUNTY. WIDEN TO 4-LANES. SR 1383/SR 1180 TO US 21 IN IREDELL COUNTY. WIDEN TO 6-LANES. | HIGHWAY | 12 | CHARLOTTE REGIONAL TPO, GREATER HICKORY MPO | R-2307B | REGION F | 61.09 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2025 | 2025 | 2025
JACKSON | NC 107 | 500 FEET SOUTH OF SR 1135 (SHOOK COVE ROAD) TO 1000 FEET NORTH OF THE LAKE TUCKASEEGEE DAM. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5841A | DIVISION 14 | 58.2 | P4.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2030
JACKSON | NC 107 (US 23 BUSINESS) | NC 116 TO US 23 BUSINESS. US 23 BUSINESS, SR 1432 (SKYLAND DRIVE) TO MUNICIPAL DRIVE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5600 | REGION G | 59.13 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2025 | 2025 | 2025
JACKSON | US 64 | NC 107 INTERSECTION. IMPROVE INTERSECTION AND ADD AUXILLARY LANE FROM PEBBLE CREEK DRIVE TO US 64/NC 107 INTERSECTION. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5881 | NOT FUNDED | 68.64 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
JACKSON | US 74 (GREAT SMOKEY MOUNTAINS EXPRESSWAY) | US 441 GATEWAY INTERCHANGE TO SR 1391 (WEST PINEY MOUNTAIN ROAD). MODERNIZE ROADWAY, INCLUDING REPLACEMENT OF BRIDGE 490043 OVER THE TUCKASEGEE RIVER. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5907 | DIVISION 14 | 69.58 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2030
JOHNSTON | EAST CLAYTON CONNECTOR GREENWAY | SR 2851 (EAST FRONT STREET) TO SR 1902 (GLEN LAUREL ROAD). CONSTRUCT GREENWAY. | BIKE/PED | 4 | CAPITAL AREA MPO | EB-6016 | DIVISION 4 | 55.82 | NOT COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | 2027 |  |  |  | 2028 | 2028 | 2028
JOHNSTON | MOUNTAINS TO SEA TRAIL | FOX RIDGE ROAD TO NEUSE RIVER BRIDGE. CONSTRUCT GREENWAY. | BIKE/PED | 4 | CAPITAL AREA MPO | EB-6017 | DIVISION 4 | 55.67 | NOT COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | [6 empty] | 2028 | NOT FUNDED | 2028
JOHNSTON | CLAYTON | CLAYTON SIGNAL SYSTEM. | HIGHWAY | 4 | CAPITAL AREA MPO | U-5943 | REGION A | 77.73 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2025 | 2025 | 2025
JOHNSTON | I-95 | US 70 BUSINESS. UPGRADE INTERCHANGE. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | I-5972 | REGION A | 70.46 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2024 | 2024 | 2024
JOHNSTON | I-95 | US 701/NC 96. CONSTRUCT INTERCHANGE. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | I-5974 | REGION A | 65.06 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2026 | 2026 | 2025 | 2026 | 2026 | 2028 | 2028 | 2028
JOHNSTON | I-95 | SR 1007 (BROGDEN ROAD). IMPROVE INTERCHANGE. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | I-6061 | DIVISION 4 | 55.36 | NOT COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2027 | NOT FUNDED | 2027 | 2027 | NOT FUNDED | 2027 | 2029 | NOT FUNDED | 2029
JOHNSTON | I-95 | SR 2339 (BAGLEY ROAD). IMPROVE INTERCHANGE. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | I-6062 | DIVISION 4 | 51.75 | NOT COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2027 | NOT FUNDED | 2027 | 2027 | NOT FUNDED | 2027 | 2029 | NOT FUNDED | 2029
JOHNSTON | NC 210 | NC 50 TO SR 1330 (RALEIGH ROAD). UPGRADE TO SUPERSTREET. | HIGHWAY | 4 | CAPITAL AREA MPO | U-6203 | DIVISION 4 | 87.32 | NOT COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | 2026 | 2027 | 2027 | 2026 | 2029 | 2029 | 2028
JOHNSTON | NC 242 | SR 1168 (TARHEEL ROAD) TO I-40. WIDEN ROADWAY. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | R-5761 | DIVISION 4 | 25.28 | NOT COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2028 | NOT FUNDED | 2027 | 2028 | NOT FUNDED | 2027 | AFTER 2029 | NOT FUNDED | 2029
JOHNSTON | NC 42 | NC 50 TO US 70 BUSINESS. WIDEN TO MULTI-LANES. | HIGHWAY | 4 | CAPITAL AREA MPO | R-3410 | REGION A | 74.87 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2029 | 2029 | 2029
JOHNSTON | NC 42 | SR 1003 (BUFFALO ROAD) TO WILSON COUNTY LINE. MODERNIZE ROADWAY. | HIGHWAY | 4 | CAPITAL AREA MPO, UPPER COASTAL PLAIN RPO | U-5998 | DIVISION 4 | 50.21 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2026 | 2025 | 2027 | 2026 | 2025 | 2029 | 2028 | 2027
JOHNSTON | NEW ROUTE | SR 1010 (CLEVELAND ROAD) TO NC 42. CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | 4 | CAPITAL AREA MPO | U-6208 | DIVISION 4 | 82.2 | NOT COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | 2027 | 2028 | 2028 | 2027 | AFTER 2029 | 2030 | 2029
JOHNSTON | SR 1003 (BUFFALO ROAD) | US 70 TO SR 1934 (OLD BEULAH ROAD). WIDEN TO THREE LANES. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | R-5718 | DIVISION 4 | 68.33 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2025 | 2025 | 2025
JOHNSTON | SR 1010 (CLEVELAND ROAD) | NC 42 TO SR 1555 (BARBER MILL ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 4 | CAPITAL AREA MPO | U-6216 | DIVISION 4 | 77.48 | NOT COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | 2027 | 2028 | 2028 | 2027 | AFTER 2029 | 2030 | 2029
JOHNSTON | SR 1501 (SWIFT CREEK ROAD) | AIRPORT INDUSTRIAL DRIVE TO DRIVEWAY JUST NORTH OF JOHNSTON COUNTY AIRPORT. WIDEN ROADWAY. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | R-5950 | DIVISION 4 | 76.17 | NOT COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | 2027 | 2028 | 2028 | 2027 | AFTER 2029 | 2030 | 2029
JOHNSTON | US 301/NC 39/NC 96 | SR 1623 (BOOKER DAIRY ROAD) TO SR 2302 (RICKS ROAD). CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | U-5726 | DIVISION 4 | 80.26 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2025 | 2025 | 2027 | 2025 | 2025 | AFTER 2029 | 2027 | 2027
JOHNSTON | US 70 | US 301 TO I-95. ACCESS MANAGEMENT. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | R-5795 | REGION A | 72.94 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2028 | NOT FUNDED | 2027 | 2028 | NOT FUNDED | 2027 | AFTER 2029 | NOT FUNDED | 2029
JOHNSTON | US 70 | WEST OF SR 2372 (EDWARDS ROAD / NORTH PEARL STREET) TO EAST OF SR 2314 (PONDFIELD ROAD). UPGRADE TO FREEWAY STANDARDS. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | R-5829B | STATEWIDE MOBILITY | 77.64 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
JOHNSTON | JOHNSTON COUNTY | PURCHASE EXPANSION VEHICLES. | PUBLIC TRANSIT | 4 | UPPER COASTAL PLAIN RPO, CAPITAL AREA MPO | TA-6720 | DIVISION 4 | 86.67 | NOT COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2026 | 2026 | 2026
JOHNSTON | NS/NCRR H LINE | CONSTRUCT GRADE SEPARATION AT SR 1553 (SHOTWELL ROAD). CLOSE EXISTING AT-GRADE CROSSING IN CLAYTON. | RAIL | 4 | CAPITAL AREA MPO | P-5743 | NOT FUNDED | 82.09 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2027 | NOT FUNDED | NOT FUNDED |  | NOT FUNDED |  | AFTER 2029 | NOT FUNDED | NOT FUNDED
JOHNSTON, WAKE | US 70 BUSINESS | GREENFIELD PARKWAY TO NC 42. UPGRADE ROADWAY TO SUPERSTREET. | HIGHWAY | 4, 5 | CAPITAL AREA MPO | U-6113 | NOT FUNDED | 79.27 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
JOHNSTON, WAKE | VARIOUS | BUS RAPID TRANSIT SERVICE, GARNER TO CLAYTON. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | PUBLIC TRANSIT | 4, 5 | CAPITAL AREA MPO | TO-6166D | REGION A, C | 80.37 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2025 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2025 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY
LEE | RALEIGH EXECUTIVE JETPORT (TTA) | RUNWAY 21 AND RUNWAY 3 BYPASS TAXIWAY. CONSTRUCT AIRPLANE RUN-UP LANE AT EACH END OF TAXIWAY. | AVIATION | 8 | TRIANGLE AREA RPO | AV-5899 | DIVISION 8 | 73.4 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2024 | 2024 | 2024
LEE | MCIVER STREET | MOORE STREET TO OAKWOOD AVENUE IN SANFORD. CONSTRUCT SIDEWALKS. | BIKE/PED | 8 | TRIANGLE AREA RPO | EB-6003 | NOT FUNDED | 69.24 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | [6 empty] | 2026 | NOT FUNDED | NOT FUNDED
LEE | NC 42 (WICKER STREET) | LEGION DRIVE TO NORTH OF HIGH RIDGE DRIVE AT KIWANIS FAMILY PARK IN SANFORD. CONSTRUCT MULTIUSE PATH. | BIKE/PED | 8 | TRIANGLE AREA RPO | EB-5742 | DIVISION 8 | 47.53 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2024 | 2024 | 2024
LEE | SR 1002 (CHARLOTTE AVENUE) | CHATHAM STREET TO SR 1002 (11TH STREET) IN SANFORD. CONSTRUCT SIDEWALKS AND IMPLEMENT ROAD DIET WITH BICYCLE LANES. | BIKE/PED | 8 | TRIANGLE AREA RPO | EB-6002 | DIVISION 8 | 68.42 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2025 | 2025 | 2025
LEE | NEW ROUTE | SR 1133 (LEE AVENUE) TO EXISTING COMMERCE DRIVE IN SANFORD. CONSTRUCT 2-LANE EXTENSION OF COMMERCE DRIVE. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5960 | DIVISION 8 | 60.36 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | AFTER 2029 | 2030 | 2030
LEE | SR 1237 (CARTHAGE STREET) | SR 1152 (FIRE TOWER ROAD) TO NC 42 (WICKER STREET) IN SANFORD. WIDEN ROADWAY. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5709 | DIVISION 8 | 64.4 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2024 | 2024 | 2024
LEE | SR 1521 (KELLY DRIVE) | SR 1519 (NASH STREET) TO NORTHEAST OF CENTRAL CAROLINA COMMUNITY COLLEGE. CONSTRUCT 3-LANE REALIGNMENT OF KELLY DRIVE. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5959 | DIVISION 8 | 67.87 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2025 | 2025 | 2025
LEE | US 1 / US 15 / US 501 | SOUTH OF SR 1198 (BRYAN DRIVE) TO SR 1237 (CARTHAGE STREET) IN SANFORD. UPGRADE TO SUPERSTREET AND RELOCATE NC 78 (TRAMWAY ROAD). | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5727 | REGION E | 47.34 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2024 | 2023 | 2022 | 2024 | 2023 | 2026 | 2026 | 2026
LEE | US 1 / US 15 / US 501 | US 15 / US 501 (WHITE HILL ROAD) / SR 1179 (ROCKY FORK CHURCH ROAD) TO SOUTH OF SR 1198 (BRYAN DRIVE). UPGRADE TO SUPERSTREET. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5975 | REGION E | 76.71 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2024 | 2023 | 2022 | 2024 | 2023 | 2026 | 2026 | 2026
LEE | US 421 BUSINESS / NC 87 | US 1 / US 15 / US 501 TO FORMER ATLANTIC COAST LINE RAILROAD CROSSING EAST OF WASHINGTON AVENUE IN SANFORD. RECONSTRUCT AS A "COMPLETE STREET" WITH IMPROVEMENTS SUCH AS MEDIANS, SIDEWALKS, BICYCLE FACILITIES, AND STREETSCAPING. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5722 | REGION E | 68.99 | P4.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2030
LENOIR | SR 1569 (CAREY ROAD EXTENSION) | SR 1572 (ROUSE ROAD) TO US 258. CONSTRUCT MULTI-LANES ON NEW LOCATION. | HIGHWAY | 2 | EASTERN CAROLINA RPO | U-3618 | DIVISION 2 | 75.77 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2028 | 2028 | 2028
LENOIR | US 70 | SR 1227 (JIM SUTTON ROAD)/SR 1252 (WILLIE MEASLEY ROAD). CONSTRUCT AT GRADE INTERSECTION TO INTERCHANGE | HIGHWAY | 2 | EASTERN CAROLINA RPO | R-5813 | NOT FUNDED | 71.07 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2026 | NOT FUNDED | NOT FUNDED | 2026 | NOT FUNDED | NOT FUNDED | 2028 | NOT FUNDED | NOT FUNDED
LENOIR | US 70 (FUTURE I-42) | SR 1522 (ALBERT SUGGS ROAD) TO NC 148 (HARVEY PARKWAY). | HIGHWAY | 2 | EASTERN CAROLINA RPO | R-2553B | NOT FUNDED | 71.64 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
LENOIR | US 70 (FUTURE I-42) | NC 148 (HARVEY PARKWAY) TO US 70 EAST OF NC 58. | HIGHWAY | 2 | EASTERN CAROLINA RPO | R-2553C | STATEWIDE MOBILITY | 67.28 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
LENOIR, GREENE | US 258 | SR 1101 (BROWNTOWN ROAD) TO SR 2010 (C. F. HARVEY PARKWAY). WIDEN TO MULTI-LANES. | HIGHWAY | 2 | EASTERN CAROLINA RPO | R-5814 | DIVISION 2 | 81.18 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2029 | NOT FUNDED | 2027 | 2029 | NOT FUNDED | 2027 | AFTER 2029 | NOT FUNDED | 2029
LINCOLN | NC 150 | US 321 AT LINCOLNTON TO US 321 BYPASS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | R-0617C | NOT FUNDED | 73.11 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
LINCOLN | NC 16 | SR 1389 (FAIRFIELD FOREST ROAD) TO SR 1379 (WEBBS ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6144 | NOT FUNDED | 69.77 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
LINCOLN | NC 16 BUSINESS | NC 16 BUSINESS, SR 1373 (CAMPGROUND ROAD), SR 1386 (WILL PROCTOR ROAD). REALIGN OFFSET INTERSECTIONS. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-5962 | REGION F | 74.17 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2026 | 2026 | 2026
LINCOLN | NC 16 BYPASS | SR 1380 (OPTIMIST CLUB ROAD) INTERSECTION. UPGRADE AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6134 | REGION F | 82.08 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2024 | 2023 | 2023 | 2024 | 2024 | 2026 | 2026
LINCOLN | NC 27 (EAST MAIN STREET) | US 321 BUS TO NC 150 (EAST). CONSTRUCT ACCESS MANAGEMENT AND INTERSECTION IMPROVEMENTS. INCLUDES CONSTRUCTION OF NORTHBOUND TURN LANE FROM SR 1294 (LITHINA INN ROAD) TO NC 27 (E MAIN STREET) AND WIDENING OF BRIDGE #540042 OVER SEABOARD RR ON NC 150. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6140 | REGION F | 76.14 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
LINCOLN | NC 73 | SR 1383 (INGLESIDE FARM ROAD) TO NC 16. WIDEN TO MULTI-LANES. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6139 | NOT FUNDED | 77.93 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
LINCOLN | NC 73 EXTENSION | US 321 TO SR 1356 (CAMP CREEK ROAD) CONSTRUCT MULTI-LANES ON NEW LOCATION. | HIGHWAY | 12 | GASTON-CLEVELAND-LINCOLN MPO | U-6142 | NOT FUNDED | 71.42 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
LINCOLN, MECKLENBURG | NC 73 | NC 16 TO VANCE ROAD EXTENSION/BEATTIES FORD ROAD. | HIGHWAY | 10, 12 | GASTON-CLEVELAND-LINCOLN MPO, CHARLOTTE REGIONAL TPO | R-5721A | REGION E, F | 73.14 | P4.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2024 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2026 | 2024 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2026 | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029
MACON | MACON COUNTY AIRPORT | EXTEND RUNWAY. | AVIATION | 14 | SOUTHWESTERN RPO | AV-5850 | DIVISION 14 | 65.48 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2029 | 2028 | 2028 |  |  |  | 2029 | 2029 | 2029
MACON | EAST MAIN ST/US 441 BUS | NC 28 (HIGHLANDS ROAD). CONSTRUCT SIDEWALK LOOP. | BIKE/PED | 14 | SOUTHWESTERN RPO | EB-5964 | DIVISION 14 | 66.39 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 |  |  |  | 2024 | 2024 | 2024
MACON | US 23/US 441 | SR 1652 (WIDE HORIZON DRIVE)/SR 1152 (BELDEN CIRCLE) TO SR 1649 (PRENTISS BRIDGE ROAD). | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5734B | NOT FUNDED | 63.27 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2025 | NOT FUNDED | NOT FUNDED | 2025 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED
MACON | US 23/US 441 | SR 1649 (PRENTISS BRIDGE ROAD) TO GEORGIA STATE LINE. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-5734C | NOT FUNDED | 65.88 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
MADISON | MARSHALL | US 25/70, SR 1601 (DERINGER DRIVE) TO BEGINNING OF INGLE'S PARKING LOT. CONSTRUCT SIDEWALKS, INSTALL CROSSWALKS, ADA RAMPS, PEDESTRIAN SIGNAL AND PEDESTRIAN REFUGE. | BIKE/PED | 13 | LAND-OF-SKY RPO | EB-5918 | DIVISION 13 | 63.39 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2022 | 2022 | 2024
MADISON | US 25 | US 25/70 BUSINESS (NORTH MAIN STREET) TO SR 1143 (BRUSH CREEK ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 13 | LAND-OF-SKY RPO | R-5837 | NOT FUNDED | 61.01 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
MADISON | US 25/70 | EAST OF SR 1392 (SKYWAY DRIVE) TO US 25/70 BUSINESS (NORTH MAIN STREET). MODERNIZE ROADWAY. | HIGHWAY | 13 | LAND-OF-SKY RPO | R-5924 | NOT FUNDED | 73.29 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
MARTIN | EAST MAIN STREET | BOULEVARD STREET TO RIVER ROAD IN WILLIAMSTON. INSTALL SIDEWALKS AND CURB RAMPS. | BIKE/PED | 1 | MID-EAST RPO | EB-5979 | DIVISION 1 | 84.07 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | [6 empty] | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027
MARTIN | US 13/US 17 | MAIN STREET IN WILLIAMSTON. IMPROVE INTERSECTION. | HIGHWAY | 1 | MID-EAST RPO | R-5879 | REGION A | 74.03 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2025 | NOT FUNDED | 2025 | 2025 | NOT FUNDED | 2025 | 2027 | NOT FUNDED | 2027
MARTIN | US 17 | SR 1119 (RALPH TAYLOR ROAD) TO SR 1205 (HOLLY CREEK ROAD). ACCESS MANAGEMENT. | HIGHWAY | 1 | MID-EAST RPO | R-5810 | DIVISION 1 | 63.86 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2025 | 2025 | 2025
McDOWELL | FONTA FLORA TRAIL | US 70 TO RESISTOFLEX ROAD. CONSTRUCT GREENWAY. | BIKE/PED | 13 | FOOTHILLS RPO | EB-5916 | DIVISION 13 | 66.7 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 |  |  |  | 2024 | 2024 | 2024
McDOWELL | NC 226 | US 221 TO NC 226A. WIDEN ROADWAY TO 3 LANES. | HIGHWAY | 13 | FOOTHILLS RPO | R-5923 | NOT FUNDED | 74.32 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
McDOWELL | US 221 | NORTH OF I-40 TO SR 1153 (GOOSE CREEK ROAD) | HIGHWAY | 13 | FOOTHILLS RPO | R-0204E | DIVISION 13 | 65.27 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2029 | 2028 | 2028
McDOWELL | US 221 BUSINESS | US 221/NC 226 TO GEORGIA AVENUE. WIDEN EXISTING ROADWAY. | HIGHWAY | 13 | FOOTHILLS RPO | U-5835 | DIVISION 13 | 64.56 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2025 | 2025 | 2025
MECKLENBURG | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT (CLT) | CONSTRUCT FOURTH PARALLEL RUNWAY. | AVIATION | 10 | CHARLOTTE REGIONAL TPO | AV-5879 | STATEWIDE MOBILITY | 99.64 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2024 | 2024 | 2024
MECKLENBURG | CHARLOTTE DOUGLAS INTERNATIONAL AIRPORT (CLT) | EXPAND CONCOURSE A (PHASE II). | AVIATION | 10 | CHARLOTTE REGIONAL TPO | AV-5893 | REGION E | 75.67 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2025 | 2025 | 2025
MECKLENBURG | IRWIN CREEK GREENWAY EASTERN EXTENSION | EXISTING IRWIN CREEK GREENWAY TO HAMILTON STREET. CONSTRUCT GREENWAY. | BIKE/PED | 10 | CHARLOTTE REGIONAL TPO | EB-5970 | DIVISION 10 | 87.66 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | [6 empty] | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028
MECKLENBURG | JETTON STREET | GRIFFITH STREET TO POTTS STREET. CONSTRUCT SIDEWALK ON SOUTH SIDE OF JETTON STREET. | BIKE/PED | 10 | CHARLOTTE REGIONAL TPO | EB-5971 | DIVISION 10 | 86.24 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2025 | 2025 | 2025
MECKLENBURG | NC 51 MULTI-USE PATH | TRADE STREET TO INDEPENDENCE POINTE PARKWAY. CONSTRUCT MULTI-USE PATH ON SOUTH SIDE OF NC 51. | BIKE/PED | 10 | CHARLOTTE REGIONAL TPO | EB-5969 | DIVISION 10 | 88.76 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2025 | 2025 | 2025
MECKLENBURG | ARDREY KELL ROAD | US 521 (JOHNSTON ROAD) TO SR 3624 (REA ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6167 | NOT FUNDED | 81.53 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
MECKLENBURG | BAILEY ROAD EXTENSION | US 21 (STATESVILLE ROAD) TO FUTURE NORTHCROSS DRIVE EXTENSION. CONSTRUCT 2 LANE ROADWAY ON NEW LOCATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6171 | NOT FUNDED | 78.48 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
MECKLENBURG | CHARLOTTE | SR 2940 (EASTWAY DRIVE) AND SHAMROCK DRIVE. CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5803 | DIVISION 10 | 90.22 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2024 |  |  |  | 2025 | 2025 | 2025
MECKLENBURG | I-277 | KENILWORTH AVENUE TO NORTH DAVIDSON STREET AND US 74 (INDEPENDENCE BOULEVARD) FROM I-277 TO PECAN AVENUE. UPGRADE INTERCHANGES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6022A | NOT FUNDED | 77.92 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
MECKLENBURG | I-485 | I-485 AND NC 16 (PROVIDENCE ROAD). CONSTRUCT INTERCHANGE IMPROVEMENTS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-5963 | STATEWIDE MOBILITY | 74.93 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
MECKLENBURG | I-485 | NC 51 (PINEVILLE-MATTHEWS ROAD) INTERCHNAGE. IMPROVE INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6015 | NOT FUNDED | 83.78 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
MECKLENBURG | I-485 | NC 49 (SOUTH TRYON STREET) INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6019 | NOT FUNDED | 78.39 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
MECKLENBURG | I-77 | NC 73 INTERCHANGE. UPGRADE EXISTING INTERCHANGE TO SPLIT DIAMOND CONFIGURATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-5715 | STATEWIDE MOBILITY | 82.46 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 |  | 2023 | 2023 | 2025 | 2026 | 2025
MECKLENBURG | I-77 | SOUTH CAROLINA STATE LINE TO I-277/US 74 (BELK FREEWAY). WIDEN EXISTING FREEWAY TO TEN LANES BY CONSTRUCTING MANAGED LANES, RECONSTRUCT I-77/I-277 (BELK FREEWAY) INTERCHANGE, AND INSTALL RAMP METERS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-5718A | STATEWIDE MOBILITY | 89.36 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
MECKLENBURG | I-77 | I-85 INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6014 | STATEWIDE MOBILITY | 88.45 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
MECKLENBURG | I-77 | US 21/SR 2108 (SUNSET ROAD) INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6056 | NOT FUNDED | 73 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
MECKLENBURG | I-85 | I-485 INTERCHANGE NORTHEAST OF CHARLOTTE. IMPROVE INTERCHANGE | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6012 | STATEWIDE MOBILITY | 90.25 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
MECKLENBURG | I-85 | NC 24 (W.T. HARRIS BOULEVARD) INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6013 | STATEWIDE MOBILITY | 89.47 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
MECKLENBURG | I-85 | I-485 INTERCHANGE WEST OF CHARLOTTE. IMPROVE INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6016 | STATEWIDE MOBILITY | 82.69 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
MECKLENBURG | I-85 | SR 2472 (MALLARD CREEK CHURCH ROAD) INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6017 | NOT FUNDED | 79.4 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
MECKLENBURG | I-85 | NC 16 (BROOKSHIRE BOULEVARD) INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6020 | NOT FUNDED | 76 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
MECKLENBURG | I-85 | SR 2480 (SUGAR CREEK ROAD) INTERCHANGE. IMPROVE INTERCHANGE | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | I-6053 | NOT FUNDED | 79.27 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
MECKLENBURG | NC 115 (OLD STATESVILLE ROAD) | NC 24 (HARRIS BOULEVARD) TO I-485. WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5772 | REGION E | 68.21 | P4.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2030
MECKLENBURG | NC 16 (BROOKSHIRE BOULEVARD) | I-85 TO IDAHO DRIVE. ADD WESTBOUND THROUGH LANE ON NC 16 BETWEEN A POINT WEST OF IDAHO DRIVE AND I-85. CONVERT NC 16 AND IDAHO DRIVE INTERSECTION TO AN INTERCHANGE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5955B | REGION E | 79.68 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | PROJECT SEGMENT NOT LISTED IN 2020-2029 STIP | 2024 | 2025 | PROJECT SEGMENT NOT LISTED IN 2020-2029 STIP | 2024 | 2025 | PROJECT SEGMENT NOT LISTED IN 2020-2029 STIP | 2026 | 2028
MECKLENBURG | NC 160 | SOUTH CAROLINA LINE TO NC 49 (SOUTH TRYON ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5766A | REGION E | 21.53 | P3.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2025 | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2025 | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028
MECKLENBURG | NC 160 | NC 49 (SOUTH TRYON ROAD) TO I-485. WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5766B | REGION E | 59.6 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2025 | 2024 | 2024 | 2025 | 2027 | 2027 | 2028
MECKLENBURG | NC 27 (FREEDOM DRIVE) | SR 1644 (TODDVILLE ROAD) TO SR 1600 (MOORES CHAPEL ROAD). WIDEN TO 4-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5957 | REGION E | 71.61 | P4.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2026 | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2026 | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028
MECKLENBURG | NC 49 & BACK CREEK CHURCH ROAD | NC 49, JOHN KIRK DRIVE TO I-485. WIDEN EXISTING ROADWAY. REALIGN BACK CREEK CHURCH ROAD ON NEW LOCATION TO THE NC 49 AND MALLARD CREEK CHURCH ROAD INTERSECTION. CLOSE EXISTING AT GRADE RAIL CROSSING AT NC 49 AND BACK CREEK CHURCH ROAD. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5768 | REGION E | 58.75 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2023 | 2026 | 2022 | 2023 | 2026 | 2025 | 2025 | 2029
MECKLENBURG | NC 51 | MATTHEWS TOWNSHIP PARKWAY TO SR 3128 (LAWYERS ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5007 | REGION E | 67.27 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
MECKLENBURG | NC 51 (MATTHEWS TOWNSHIP PARKWAY) | SR 3356 (SARDIS ROAD) TO SR 1010 (EAST JOHN STREET/ MONROE ROAD). WIDEN EXISTING ROADWAY. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5763 | REGION E | 63.62 | P3.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2026 | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2026 | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029
MECKLENBURG | NC 73 | NC 115 TO SR 2693 (DAVIDSON-CONCORD ROAD). | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | R-2632AB | REGION E | 72.3 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2026 | 2026 | 2026
MECKLENBURG | NC 73 | VANCE ROAD EXTENSION/BEATTIES FORD ROAD TO SR 5544 (WEST CATAWBA AVENUE). | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | R-5721B | REGION E | 75.42 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2026 | 2026 | 2026
MECKLENBURG | NC 73 (SAM FURR ROAD) | SR 5544 (WEST CATAWBA AVENUE) TO SR 2316 (NORTHCROSS DRIVE). WIDEN EXISTING ROADWAY. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5765 | REGION E | 70.45 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2026 | 2026 | 2026
MECKLENBURG | NEW ROUTE | SR 3168 (SAM NEWELL ROAD) TO SR 5215 (NORTHEAST PARKWAY. CONSTRUCT MULTI-LANES ON NEW LOCATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6166 | NOT FUNDED | 83.28 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
MECKLENBURG | SR 1009 (JOHN STREET-OLD MONROE ROAD) | SR 3448-SR 3474 (TRADE STREET) TO WEST OF I-485. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-4714AA | DIVISION 10 | 73.8 | P3.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2030
MECKLENBURG | SR 1441 (CAROWINDS BOULEVARD EXTENSION) | NC 49 (SOUTH TRYON STREET TO NC 160 (STEELE CREEK ROAD). CONSTRUCT TWO LANE DIVIDED ROADWAY ON NEW LOCATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6168 | NOT FUNDED | 80.89 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
MECKLENBURG | SR 2136 (GILEAD ROAD) | US 21 (STATESVILLE ROAD) TO NC 115. WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5807 | DIVISION 10 | 84.68 | P4.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2030
MECKLENBURG | SR 2467 (MALLARD CREEK ROAD) | SR 2472 (MALLARD CREEK CHURCH ROAD) TO BREEZEWOOD DRIVE. WIDEN TO FOUR-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6028 | DIVISION 10 | 84.28 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2026 | 2026 | 2025 | 2026 | 2026 | 2027 | 2028 | 2028
MECKLENBURG | SR 3440 (MCKEE ROAD) EXTENSION | SR 3448 (PLEASANT PLAINS ROAD) TO SR 1009 (JOHN STREET) | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-4713A | DIVISION 10 | 80.28 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2020 | 2020 | 2020 | 2021 | 2021 | 2021 | 2024 | 2024 | 2024
MECKLENBURG | SR 3687 (PARK ROAD) | JOHNSTON ROAD TO NC 51 (PINEVILLE-MATTHEWS ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6165 | NOT FUNDED | 83.4 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
MECKLENBURG | SR 4979 (BALLANTYNE COMMONS PARKWAY) | ANNALEXA LANE TO WILLIAMS POND LANE. WIDEN TO FOUR-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6030 | NOT FUNDED | 77.91 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
MECKLENBURG | SR 5544 (WEST CATAWBA AVENUE) | NC 73 (SAM FURR ROAD) TO SR 2151 (JETTON ROAD). WIDEN TO FOUR-LANES DIVIDED. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | R-2555B | DIVISION 10 | 74.94 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2025 | 2025 | 2025
MECKLENBURG | US 21 | SR 2136 (GILEAD ROAD) TO HOLLY POINT DRIVE. WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5771 | REGION E | 55.27 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2025 | 2025 | 2025
MECKLENBURG | US 21 (STATESVILLE ROAD) | NORTHCROSS CENTER COURT TO SR 2147 (WESTMORELAND ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5767 | REGION E | 59.31 | P3.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2026 | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2026 | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029
MECKLENBURG | US 521 (LANCASTER HIGHWAY/ JOHNSTON ROAD) | SOUTH CAROLINA STATE LINE TO SR 4979 (BALLANTYNE COMMONS PARKWAY). WIDEN TO MULTILANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6109 | REGION E | 76.49 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2026 | 2026 | 2026
MECKLENBURG | US 74 | SHARON FOREST DRIVE AND HARRIS BOULEVARD/VILLAGE LAKE DRIVE INTERSECTION AREA. CONSTRUCT GRADE SEPARATION AT SHARON FOREST DRIVE AND INTERCHANGE AT VILLAGE LAKE DRIVE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2509AA | STATEWIDE MOBILITY | 60.36 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | PROJECT SEGMENT NOT LISTED IN 2020-2029 STIP | 2027 | 2024 | PROJECT SEGMENT NOT LISTED IN 2020-2029 STIP | 2027 | 2024 | PROJECT SEGMENT NOT LISTED IN 2020-2029 STIP | 2030 | 2027
MECKLENBURG | US 74 | SARDIS ROAD AND SAM NEWELL ROAD INTERSECTION AREA. CONSTRUCT INTERCHANGES AT SARDIS ROAD NORTH AND SAM NEWELL ROAD, CONSTRUCT EXTENSION OF SARDIS ROAD NORTH FROM US 74 TO AREQUIPA DRIVE EXTENSION, AND CONSTRUCT EXTENSION OF AREQUIPA DRIVE FROM SARDIS ROA | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2509AB | STATEWIDE MOBILITY | 60.36 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | PROJECT SEGMENT NOT LISTED IN 2020-2029 STIP | 2028 | 2024 | PROJECT SEGMENT NOT LISTED IN 2020-2029 STIP | 2028 | 2024 | PROJECT SEGMENT NOT LISTED IN 2020-2029 STIP | 2030 | 2027
MECKLENBURG | US 74 | INDEPENDENCE POINTE PARKWAY. CONSTRUCT ROADWAY ON NEW LOCATION FROM WINDSOR SQUARE DRIVE TO NC 51 (MATTHEWS TOWNSHIP PARKWAY). | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2509AC | STATEWIDE MOBILITY | 60.36 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | PROJECT SEGMENT NOT LISTED IN 2020-2029 STIP | 2028 | 2024 | PROJECT SEGMENT NOT LISTED IN 2020-2029 STIP | 2028 | 2024 | PROJECT SEGMENT NOT LISTED IN 2020-2029 STIP | 2030 | 2027
MECKLENBURG | US 74 | MATTHEWS-MINT HILL ROAD INTERSECTION AREA. CONSTRUCT INTERCHANGE AT MATTHEWS-MINT HILL ROAD AND EXTENSION OF NORTHEAST PARKWAY FROM OVERCASH DRIVE TO WAITING STREET. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2509AD | STATEWIDE MOBILITY | 60.36 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | PROJECT SEGMENT NOT LISTED IN 2020-2029 STIP | 2027 | 2024 | PROJECT SEGMENT NOT LISTED IN 2020-2029 STIP | 2027 | 2024 | PROJECT SEGMENT NOT LISTED IN 2020-2029 STIP | 2030 | 2027
MECKLENBURG | US 74 | WEST OF IDLEWILD ROAD TO WALLACE LANE. ADD GENERAL PURPOSE AND EXPRESS LANES AND CONSTRUCT EXPRESS LANE INTERCHANGE ON WEST SIDE OF CONFERENCE DRIVE. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2509B | STATEWIDE MOBILITY | 60.36 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | PROJECT SEGMENT NOT LISTED IN 2020-2029 STIP | 2028 | 2024 | PROJECT SEGMENT NOT LISTED IN 2020-2029 STIP | 2028 | 2024 | PROJECT SEGMENT NOT LISTED IN 2020-2029 STIP | 2030 | 2027
MECKLENBURG | US 74 | WALLACE LANE TO SARDIS ROAD. ADD GENERAL PURPOSE AND EXPRESS LANES AND CONSTRUCT EXPRESS LANE INTERCHANGE AT SARDIS ROAD. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2509C | STATEWIDE MOBILITY | 60.36 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | PROJECT SEGMENT NOT LISTED IN 2020-2029 STIP | 2028 | 2024 | PROJECT SEGMENT NOT LISTED IN 2020-2029 STIP | 2028 | 2024 | PROJECT SEGMENT NOT LISTED IN 2020-2029 STIP | 2030 | 2027
MECKLENBURG | US 74 | SARDIS ROAD TO I-485. ADD GENERAL PURPOSE AND EXPRESS LANES, CONSTRUCT EXPRESS LANE INTERCHANGES AT I-485 AND EAST SIDE OF CONFERENCE DRIVE, AND RECONSTRUCT INTERCHANGE AT NC 51 (MATTHEWS TOWNSHIP PARKWAY). | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2509D | STATEWIDE MOBILITY | 60.36 | P3.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | PROJECT SEGMENT NOT LISTED IN 2020-2029 STIP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT SEGMENT NOT LISTED IN 2020-2029 STIP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | PROJECT SEGMENT NOT LISTED IN 2020-2029 STIP | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
MECKLENBURG | US 74 (INDEPENDENCE BOULEVARD) | I-277 TO WEST OF IDLEWILD ROAD. WIDEN ROADWAY TO ALLOW FOR TWO-WAY EXPRESS LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6103 | STATEWIDE MOBILITY | 79.64 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2031 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
MECKLENBURG | US 74 PARALLEL ROUTES | KREFELD DRIVE, AREQUIPA DRIVE, AND INDEPENDENCE POINTE PARKWAY. CONSTRUCT MULTIPLE SEGMENTS, PART ON NEW LOCATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-2509E | NOT FUNDED | N/A | P3.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | PROJECT SEGMENT NOT LISTED IN 2020-2029 STIP | NOT FUNDED | NOT FUNDED | PROJECT SEGMENT NOT LISTED IN 2020-2029 STIP | NOT FUNDED | NOT FUNDED | PROJECT SEGMENT NOT LISTED IN 2020-2029 STIP | NOT FUNDED | NOT FUNDED
MECKLENBURG | CLANTON ROAD | EXTEND CLANTON ROAD TO US 29/74 (WILKINSON BOULEVARD) WITH A GRADE SEPARATION OF NORFOLK SOUTHERN RAILROAD AND CLOSE THE DONALD ROSS ROAD CROSSING. | RAIL | 10 | CHARLOTTE REGIONAL TPO | P-5730 | REGION E | 79.55 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 |  |  |  | 2025 | 2025 | 2025
MECKLENBURG, CABARRUS | NC 73 (DAVIDSON HIGHWAY) | EAST OF SR 2693 (DAVIDSON-CONCORD ROAD) TO EAST OF SR 1394 (POPLAR TENT ROAD). | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | R-5706A | REGION E | 76.01 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2026 | 2026 | 2026
MECKLENBURG, CABARRUS | SR 2467 (MALLARD CREEK ROAD)/ SR 1445 (DERITA ROAD | I-485 TO CONCORD MILLS BOULEVARD (SR 2894). WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO, CABARRUS-ROWAN MPO | U-6032 | DIVISION 10 | 78.02 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2025 | 2025 | 2025
MITCHELL | NC 226 | BLUE RIDGE PARKWAY TO SR 1274 (SUMMIT AVENUE). WIDEN TO 3-LANES. | HIGHWAY | 13 | HIGH COUNTRY RPO | R-5804 | NOT FUNDED | 64.63 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
MONTGOMERY | NC 109 | SR 1127 (HEARNE FARM ROAD) TO SR 1174 (PEE DEE ROAD). | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-5826B | DIVISION 8 | 62.96 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2026 | 2026 | 2026
MONTGOMERY | NC 24 / NC 27 | NC 73 TO TROY BYPASS. WIDEN TO MULTILANES. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-2527 | REGION E | 65.5 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2019 | 2019 | 2019 |  |  |  | 2024 | 2024 | 2024
MOORE | SR 2055 (NORTH POPLAR STREET) | JOHNSON STREET TO US 1 (SANDHILLS BOULEVARD) IN ABERDEEN. CONSTRUCT SIDEWALK. | BIKE/PED | 8 | TRIANGLE AREA RPO | EB-6001 | DIVISION 8 | 71.97 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY |  |  | 2024 |  |  |  | 2025 | 2025 | 2025
MOORE | VARIOUS | CONSTRUCT PEDESTRIAN IMPROVEMENTS AT 5 INTERSECTIONS AND ONE MID-BLOCK LOCATION IN THE CENTRAL BUSINESS DISTRICT OF ABERDEEN. | BIKE/PED | 8 | TRIANGLE AREA RPO | EB-6005 | NOT FUNDED | 69.1 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | [6 empty] | 2026 | NOT FUNDED | NOT FUNDED
MOORE | NC 211 | NC 73 IN WEST END TO WEST OF SR 1241 (HOLLY GROVE SCHOOL ROAD). WIDEN TO MULTILANES. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5726 | REGION E | 50.38 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2025 | 2025 | 2025
MOORE | NC 24 / NC 27 | SR 1006 (GLENDON-CARTHAGE ROAD) IN CARTHAGE. IMPROVE INTERSECTION AND ADJACENT INTERSECTIONS OF EACH FACILITY WITH US 15 / US 501. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5929 | DIVISION 8 | 78.55 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2025 | 2025 | 2025
MOORE | NC 24 / NC 27 | COURTHOUSE WEST OF NC 22 (MCNEILL STREET) TO US 15 / US 501 IN CARTHAGE. WIDEN TO THREE LANES WITH CURB AND GUTTER AND BICYCLE / PEDESTRIAN ACCOMMODATIONS. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-3628 | REGION E | 46.08 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2025 | 2025 | 2025
MOORE | NC 5 | US 1 IN ABERDEEN TO THE INTERSECTION OF TROTTER DRIVE / BLAKE BOULEVARD IN PINEHURST. WIDEN TO MULTILANES. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5756 | REGION E | 66.43 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2025 | 2025 | 2025
MOORE | NC 5 (BEULAH HILL ROAD) | INTERSECTION OF TROTTER DRIVE / BLAKE BOULEVARD TO NC 211 IN PINEHURST. ADD TURN LANES, SIGNAL IMPROVEMENTS, AND OTHER OPERATIONAL IMPROVEMENTS ALONG CORRIDOR AS APPROPRIATE. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5892 | REGION E | 73.43 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2028 | NOT FUNDED | 2028 | 2028 | NOT FUNDED | 2028 | AFTER 2029 | NOT FUNDED | 2030
MOORE | NC 690 (LOBELIA ROAD) | US 1 IN VASS TO CUMBERLAND COUNTY LINE. UPGRADE ROADWAY, TO INCLUDE TURN LANES AT VARIOUS LOCATIONS AND SOME REALIGNMENT. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5824 | REGION E | 64.82 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2025 | 2025 | 2025
MOORE | US 1 (SANDHILLS BOULEVARD) | SR 1112 (ROSELAND ROAD) TO KNIGHT STREET IN ABERDEEN. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5815A | REGION E | 60.89 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2027 | 2027 | 2027
MOORE | US 1 (SANDHILLS BOULEVARD) | KNIGHT STREET IN ABERDEEN TO OLD US 1 IN SOUTHERN PINES, TO INCLUDE SR 1112 (ROSELAND ROAD) REALIGNMENT AT US1 AND RADII IMPROVEMENT I AT US 15 / US 501 / NC 211. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5815B | REGION E | 60.89 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2025 | 2025 | 2025
MOORE | US 15 / US 501 | NC 2 AND NC 211 TRAFFIC CIRCLE IN PINEHURST TO NC 73. WIDEN TO MULTILANES. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5927 | DIVISION 8 | 82.34 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2029 | 2029 | 2029
MOORE | US 15 / US 501 | SR 1905 (VOIT GILMORE LANE) IN SOUTHERN PINES TO SR 1208 PAGE ROAD IN PINEHURST. UPGRADE SR 1208 INTERSECTION AND CONSTRUCT IMPROVEMENTS TO PINEHURST TRAFFIC CIRCLE AND APPROACHES. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5976 | DIVISION 8 | 77.87 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2026 | 2026 | 2026
MOORE | US 15 / US 501 / NC 211 | SR 1205 / SR 1309 (MORGANTON ROAD) IN SOUTHERN PINES. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 8 | TRIANGLE AREA RPO | R-5891 | REGION E | 77.44 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2029 | NOT FUNDED | 2027 | 2029 | NOT FUNDED | 2027 | AFTER 2029 | NOT FUNDED | 2029
MOORE | US 15 / US 501 / NC 211 | US 1 (SANDHILLS BOULEVARD) IN ABERDEEN TO BRUCEWOOD ROAD IN SOUTHERN PINES. ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 8 | TRIANGLE AREA RPO | U-5814 | REGION E | 54.1 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2025 | 2025 | 2025
MOORE, MONTGOMERY | NC 24 / NC 27 | I-73 / I-74 / US 220 TO SR 1644 (OLD GLENDON ROAD). MODERNIZE ROADWAY. | HIGHWAY | 8 | TRIANGLE AREA RPO, PIEDMONT TRIAD RPO | R-5932 | NOT FUNDED | 75.07 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2027 | NOT FUNDED | NOT FUNDED | 2027 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
NASH | US 301 BUSINESS (CHURCH STREET) | US 64 TO NC 97 (RALEIGH BOULEVARD) OVERPASS. CONSTRUCT STREETSCAPE IMPROVEMENTS. ADD SIDEWALK AND BICYCLE LANES. | BIKE/PED | 4 | ROCKY MOUNT URBAN AREA MPO | EB-5761 | DIVISION 4 | 50.35 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 |  |  |  | 2025 | 2025 | 2025
NASH | US 64 BUSINESS (THOMAS STREET) | SR 1005 (EAST RALEIGH BOULEVARD TO US 64 BUSINESS (SUNSET AVENUE) IN ROCKY MOUNT. ADD PEDESTRIAN SIGNALS. | BIKE/PED | 4 | ROCKY MOUNT URBAN AREA MPO | EB-5905 | DIVISION 4 | 54.29 | NOT COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | [6 empty] | 2027 | NOT FUNDED | 2027
NASH | NC 43 | SR 1613 (WOODRUFF AVENUE) TO I-95. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | U-2561C | DIVISION 4 | 78.27 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2027 | 2026 | 2028 | 2027 | 2026 | AFTER 2029 | 2029 | 2028
NASH | NC 48 | SR 1524 (RED OAK/BATTLEBORO ROAD) TO NC 4. WIDEN TO MULTI-LANES. | HIGHWAY | 4 | ROCKY MOUNT URBAN AREA MPO | U-5911 | DIVISION 4 | 78.3 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2025 | 2025 | 2026 | 2025 | 2025 | 2028 | 2027 | 2027
NASH | TAR RIVER TRANSIT | ENLARGE DRIVERS BREAKROOM | PUBLIC TRANSIT | 4 | ROCKY MOUNT URBAN AREA MPO | TD-5281 | DIVISION 4 | 62.69 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2025 | 2025 | 2025
NASH, EDGECOMBE | US 64 | NC 58 (WASHINGTON STREET), EXIT 459, TO SR 1233 (THOMAS ROAD) OVERPASS. UPGRADE TO INTERSTATE STANDARDS. | HIGHWAY | 4 | ROCKY MOUNT URBAN AREA MPO | U-6149 | NOT FUNDED | 72.52 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
NEW HANOVER | INTERNATIONAL (ILM) WILMINGTON | INCREASE WIDTH OF ALL TAXIWAYS. | AVIATION | 3 | WILMINGTON URBAN AREA MPO | AV-5796 | NOT FUNDED | 80.16 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | [6 empty] | 2026 | NOT FUNDED | NOT FUNDED
NEW HANOVER | WILIMINGTON INTERNATION (ILM) | TAXIWAY J IMPROVEMENTS. | AVIATION | 3 | WILMINGTON URBAN AREA MPO | AV-5886 | NOT FUNDED | 83.2 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | [6 empty] | 2027 | NOT FUNDED | NOT FUNDED
NEW HANOVER | WILMINGTON INTERNATIONAL (ILM) | EXPAND THE GENERAL AVIATION APRON. | AVIATION | 3 | WILMINGTON URBAN AREA MPO | AV-5795 | STATEWIDE MOBILITY | 74.79 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | [6 empty] | 2029 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY
NEW HANOVER | WILMINGTON INTERNATIONAL (ILM) | TAXIWAY IMPROVEMENTS. | AVIATION | 3 | WILMINGTON URBAN AREA MPO | AV-5798 | STATEWIDE MOBILITY | 77.04 | P4.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | [6 empty] | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028
NEW HANOVER | WILMINGTON INTERNATIONAL (ILM) | WIDEN NORTH-SOUTH TAXIWAY SYSTEM. | AVIATION | 3 | WILMINGTON URBAN AREA MPO | AV-5799 | NOT FUNDED | 81.55 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | [6 empty] | 2027 | NOT FUNDED | NOT FUNDED
NEW HANOVER | WILMINGTON INTERNATIONAL AIRPORT (ILM) | REHABILITATE RUNWAY. | AVIATION | 3 | WILMINGTON URBAN AREA MPO | AV-5885 | NOT FUNDED | 87.48 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | [6 empty] | 2027 | NOT FUNDED | NOT FUNDED
NEW HANOVER | SR 1219 (SOUTH 17TH STREET) | HARBOUR DRIVE TO SHIPYARD BOULEVARD. CONSTRUCT MULTI-USE PATH. | BIKE/PED | 3 | WILMINGTON URBAN AREA MPO | EB-5600 | DIVISION 3 | 82.7 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2024 | 2024 |  |  |  | 2022 | 2024 | 2024
NEW HANOVER | NC 132 (COLLEGE ROAD) | SR 1272 (NEW CENTRE DRIVE) TO US 117 (SHIPYARD BOULEVARD). ACCESS MANAGEMENT AND TRAVEL TIME IMPROVEMENTS. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5702A | STATEWIDE MOBILITY | 78.96 | P4.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2024 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | 2024 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2030
NEW HANOVER | NC 132 (COLLEGE ROAD) | US 117 (SHIPYARD BOULEVARD) TO US 421 (CAROLINA BEACH ROAD). ACCESS MANAGEMENT AND TRAVEL TIME IMPROVEMENTS. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5702B | NOT FUNDED | 76.52 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2025 | NOT FUNDED | NOT FUNDED | 2025 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
NEW HANOVER | NC 132 (COLLEGE ROAD) | US 76 (OLEANDER DRIVE). INTERSECTION IMPROVEMENTS. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5704 | STATEWIDE MOBILITY | 86.4 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
NEW HANOVER | NC 132 (COLLEGE ROAD) | SR 2048 (GORDON ROAD) TO SR 1272 (NEW CENTRE DRIVE). UPGRADE ROADWAY. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5881 | STATEWIDE MOBILITY | 77.97 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
NEW HANOVER | NC 133 (CASTLE HAYNE ROAD) | I-140/US 17 (WILMINGTON BYPASS) TO SR 1310 (DIVISION DRIVE) IN WILMINGTON. WIDEN TO MULTI-LANES | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5863 | NOT FUNDED | 69.3 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2025 | NOT FUNDED | NOT FUNDED | 2025 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
NEW HANOVER | NC 133 (CASTLE HAYNE ROAD) | NORTH 23RD STREET. CONSTRUCT A ROUNDABOUT. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5954 | REGION B | 72.72 | P4.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2025 | NOT FUNDED | 2025 | 2025 | NOT FUNDED | 2025 | 2027 | NOT FUNDED | 2027
NEW HANOVER | SR 1175 (KERR AVENUE) | SR 1175 (KERR AVENUE) INTERCHANGE AT US 74 (MLK, JR. PARKWAY). | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-3338C | REGION B | 57.71 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2029 | 2027 | 2026
NEW HANOVER | SR 1175 (KERR AVENUE) | SR 1411 (WRIGHTSVILLE AVENUE) TO US 76 (OLEANDER DRIVE). CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-6201 | DIVISION 3 | 84.12 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | AFTER 2029 | 2030 | 2030
NEW HANOVER | SR 1209 (INDEPENDENCE BOULEVARD EXTENSION) | RANDALL PARKWAY TO US 74 (MLK, JR. PARKWAY) IN WILMINGTON. MULTI-LANES ON NEW LOCATION. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-4434 | DIVISION 3 | 85 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2027 | 2026 | 2024 | 2027 | 2026 | 2028 | 2029 | 2028
NEW HANOVER | SR 2048 (GORDON ROAD) | US 17 (MARKET STREET) TO I-40. WIDEN ROADWAY. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-6202 | DIVISION 3 | 80.14 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2024 | 2024 | 2024
NEW HANOVER | US 17 BUSINESS (MARKET STREET) | CSX RAILROAD TO CINEMA DRIVE; JACKSONVILLE STREET TO NORTH OF US 117/NC 132 (COLLEGE ROAD). | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-4902B | REGION B | 57.54 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY |  | 2027 | 2027 |  | 2027 | 2027 | 2029 | 2029 | 2029
NEW HANOVER | US 17 BUSINESS (MARKET STREET) | NORTH OF US 117/NC 132 (COLLEGE ROAD) TO STATION ROAD. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-4902C | STATEWIDE MOBILITY | 45.25 | P3.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029
NEW HANOVER | US 421 | US 421 (BURNETT AVENUE) TO US 117 (SHIPYARD BOULEVARD) IN WILMINGTON. UPGRADE ROADWAY. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5729REG | REGION B | 69.83 | P3.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029
NEW HANOVER | US 421 | US 117 (SHIPYARD BOULEVARD). INTERSECTION IMPROVEMENTS. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5729SW | STATEWIDE MOBILITY | 45.25 | P3.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029
NEW HANOVER | US 421 (CAROLINA BEACH ROAD) | NC 132 (SOUTH COLLEGE ROAD) TO SANDERS ROAD IN WILMINGTON. WIDEN EXISTING ROADWAY AND CONSTRUCT FLYOVERS AT US 421 AND NC 132. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5790 | DIVISION 3 | 58.74 | P3.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029
NEW HANOVER | US 421 (SOUTH FRONT STREET) | US 17 BUSINESS/US 76/US 421 (CAPE FEAR MEMORIAL BRIDGE) TO US 421 (BURNETT BOULEVARD) IN WILMINGTON. WIDEN TO MULTI-LANES. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5734 | REGION B | 74.21 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY
NEW HANOVER | US 74 | US 17/US 421 IN WILMINGTON. CONSTRUCT A FLY-OVER AND FREE FLOW RAMP AT INTERCHANGE. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5731 | STATEWIDE MOBILITY | 77.64 | P4.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2024 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2026 | 2024 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2026 | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028
NEW HANOVER | US 74 (EASTWOOD ROAD) | SR 1409 (MILITARY CUTOFF ROAD) INTERSECTION IN WILMINGTON. CONVERT AT-GRADE INTERSECTION TO AN INTERCHANGE. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5710 | STATEWIDE MOBILITY | 58.84 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2025 | 2026 | 2025
NEW HANOVER | US 74 (MARTIN LUTHER KING, JR. PARKWAY) | US 117/NC 132 (COLLEGE ROAD) IN WILMINGTON. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5792 | DIVISION 3 | 56.53 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 |  | 2024 | 2024 | 2026 | 2026 | 2026
NEW HANOVER | US 76 (OLEANDER DRIVE) | GREENVILLE LOOP ROAD AND GREENVILLE AVENUE. UPGRADE INTERSECTION. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-6128 | NOT FUNDED | 74.84 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
NEW HANOVER | WILMINGTON | WILMINGTON CITYWIDE SIGNAL SYSTEM. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-6199 | DIVISION 3 | 88.33 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | AFTER 2029 | 2030 | 2030
NORTHAMPTON | NC 305 | SEABOARD TOWN LIMITS TO HERTFORD COUNTY LINE. UPGRADE ROADWAY. | HIGHWAY | 1 | PEANUT BELT RPO | R-5757 | DIVISION 1 | 31.78 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2023 | 2022 | 2022 | 2023 | 2024 | 2024 | 2024
NORTHAMPTON | NC 46 | NC 48 IN GASTON TO THE VIRGINIA STATE LINE. UPGRADE AND WIDEN EXISTING FACILITY. | HIGHWAY | 1 | PEANUT BELT RPO | R-5739 | DIVISION 1 | 33.89 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2025 | 2025 | 2025
ONSLOW | ALBERT J. ELLIS AIRPORT (OAJ) | EXTEND RUNWAY 23 AND TAXIWAY A. | AVIATION | 3 | JACKSONVILLE URBAN AREA MPO | AV-5806 | REGION B | 81.44 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2025 | 2025 | 2025
ONSLOW | NC 210 | US 17 TO SOUTH OF SR 1518 (OLD FOLKSTONE ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5949 | REGION B | 80.24 | P4.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2030
ONSLOW | NC 24 | US 258 (RICHLANDS HIGHWAY) INTERSECTION. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5716 | STATEWIDE MOBILITY | 50.06 | P3.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029
ONSLOW | NC 24 (LEJEUNE BOULEVARD) | NC 53 (WESTERN BOULEVARD) IN JACKSONVILLE. UPGRADE INTERSECTION AND DRAINAGE. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5508 | STATEWIDE MOBILITY | 75.28 | P3.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029
ONSLOW | NC 24 (LEJEUNE BOULEVARD) | NC 24 BUSINESS (JOHNSON BOULEVARD) TO NC 172. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5741 | REGION B | 56.16 | P3.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
ONSLOW | NC 24 (WEST CORBETT AVENUE) | BELGRADE-SWANSBORO ROAD TO FRONT STREET. CONSTRUCT SUPERSTREET. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | R-5885 | NOT FUNDED | 77.44 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2027 | NOT FUNDED | NOT FUNDED | 2027 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
ONSLOW | NC 53 | NC 53: FROM US 17 (MARINE BOULEVARD) TO SR 2716 (EXCHANGE DRIVE). | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-4007E | STATEWIDE MOBILITY | 81.73 | P3.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029
ONSLOW | NC 53 (WESTERN BOULEVARD) | US 17 (MARINE BOULEVARD) TO NC 24 (LEJEUNE BOULEVARD) IN JACKSONVILLE. CONSTRUCT ACCESS MANAGEMENT IMPROVEMENTS. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5736 | REGION B | 59.53 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2019 | 2027 | 2027 |  | 2027 | 2027 | 2029 | 2029 | 2029
ONSLOW | NC 53 (WESTERN BOULEVARD) | SR 2714 (JACKSONVILLE PARKWAY). IMPROVE INTERSECTION. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5789 | REGION B | 55.76 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2025 | 2025 | 2025
ONSLOW | NC 53 (WESTERN BOULEVARD) | SR 1308 (GUM BRANCH ROAD) TO US 17 (MARINE BOULEVARD). UPGRADE TO SUPERSTREET. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-6081 | NOT FUNDED | 81.4 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2026 | NOT FUNDED | NOT FUNDED | 2026 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
ONSLOW | SR 1308 (BELL FORK ROAD) | SR 1403 (COUNTRY CLUB ROAD/HARGETT STREET). IMPROVE INTERSECTION. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-6082 | DIVISION 3 | 85.09 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2027 | 2027 | 2027
ONSLOW | SR 1308 (GUM BRANCH ROAD) | SR 1322 (SUMMERSILL SCHOOL ROAD) TO SR 1324 (RAMSEY ROAD). | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5793A | DIVISION 3 | 93 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
ONSLOW | SR 1308 (GUM BRANCH ROAD) | SR 1324 (RAMSEY ROAD) TO SR 1390 (COUNTRY CLUB BOULEVARD). | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5793B | DIVISION 3 | 89.56 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
ONSLOW | SR 1308 (GUM BRANCH ROAD) | WILLIAMSBURG PARKWAY TO INDIAN DRIVE. UPGRADE TO SUPERSTREET. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-6200 | NOT FUNDED | 84.35 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2028 | NOT FUNDED | NOT FUNDED | 2028 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
ONSLOW | SR 1336 (HENDERSON ROAD) | SR 1308 (GUM BRANCH ROAD) TO NC 53 (WESTERN BOULEVARD). UPGRADE TO SUPERSTREET. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5903 | DIVISION 3 | 86.61 | NOT COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2029 | NOT FUNDED | 2028 | 2029 | NOT FUNDED | 2028 | AFTER 2029 | NOT FUNDED | 2030
ONSLOW | SR 1509 (QUEENS CREEK ROAD) | JONES ROAD TO SR 1565 (SMALLWOOD ROAD). WIDEN ROADWAY. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | R-5948 | NOT FUNDED | 82.44 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2027 | NOT FUNDED | NOT FUNDED | 2027 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
ONSLOW | SR 2714 | NC 53 (WESTERN BOULEVARD) TO SR 1324 (RAMSEY ROAD). | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5791A | DIVISION 3 | 81.59 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2026 | 2026 | 2026
ONSLOW | SR 2715 (TRADE STREET) | NC 53 (WESTERN BOULEVARD) TO MCDANIEL DRIVE IN JACKSONVILLE. CONSTRUCT ROADWAY ON NEW LOCATION. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5787 | DIVISION 3 | 85.51 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2025 | 2025 | 2025
ONSLOW | US 17 | US 17 BUSINESS (MARINE BOULEVARD). UPGRADE AT-GRADE INTERSECTION TO PARTIAL INTERCHANGE. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5951 | REGION B | 74.57 | P4.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2027 | NOT FUNDED | 2028 | 2027 | NOT FUNDED | 2028 | AFTER 2029 | NOT FUNDED | 2030
ONSLOW | US 17 | NC 172 (SNEADS FERRY ROAD/SR 1518 (OLD FOLKSTONE ROAD). INSTALL SUPER-STREET WITH INTERSECTION IMPROVEMENTS. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-6065 | STATEWIDE MOBILITY | 69.41 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2028 | 2024 | 2024 | 2028 | 2024 | 2026 | 2030 | 2026
ONSLOW | US 17 | MCDANIEL DRIVE /WORKSHOP LANE. UPGRADE INTERSECTION. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-6107 | STATEWIDE MOBILITY | 81.31 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
ONSLOW | US 17 (WILMINGTON HIGHWAY) | SR 1130 (OLD MAPLEHURST ROAD) IN JACKSONVILLE. CONSTRUCT INTERCHANGE AND ASSOCIATED IMPROVEMENTS TO MCAS NEW RIVER MAIN GATE. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5735 | REGION B | 59.54 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | 2027 |  | 2027 | 2027 | 2029 | 2029 | 2029
ONSLOW | US 17 BUSINESS (MARINE BOULEVARD) | SR 1308 (BELL FORK ROAD) IN JACKSONVILLE. IMPROVE INTERSECTION. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5728 | REGION B | 69.85 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2025 | 2025 | 2025
ONSLOW | US 17 BUSINESS (MARINE BOULEVARD) | SR 1336 (HENDERSON DRIVE). IMPROVE INTERSECTION. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5950 | REGION B | 75.29 | P4.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2025 | NOT FUNDED | 2025 | 2025 | NOT FUNDED | 2025 | 2027 | NOT FUNDED | 2027
ONSLOW | US 258/NC 24 (RICHLANDS HIGHWAY) | SR 1212 (PONY FARM ROAD) TO SR 1213 (BLUE CREEK ROAD). CONSTRUCT SUPERSTREET. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-5739 | REGION B | 57.34 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY |  | 2027 | 2027 |  | 2027 | 2027 | 2029 | 2029 | 2029
ONSLOW | US 258/NC 24 (RICHLANDS HIGHWAY) | SR 1329 (RHODESTOWN FIRE DEPARTMENT ROAD). IMPROVE INTERSECTION. | HIGHWAY | 3 | JACKSONVILLE URBAN AREA MPO | U-6148 | NOT FUNDED | 72.1 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2028 | NOT FUNDED | NOT FUNDED | 2028 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
ORANGE | BARNES STREET | KING STREET TO SR 1005 (JONES FERRY ROAD) IN CARRBORO. CONSTRUCT SIDEWALK. | BIKE/PED | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5890 | DIVISION 7 | 61.04 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 |  |  |  | 2025 | 2025 | 2025
ORANGE | NC 54 | ANDERSON PARK TO JAMES STREET IN CARRBORO. CONSTRUCT MULTIUSE PATH ON NORTH SIDE OF NC 54. | BIKE/PED | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5994 | DIVISION 7 | 65.44 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
ORANGE | SR 1005 (JONES FERRY ROAD) | DAVIE ROAD TO SR 1010 (WEST MAIN STREET) IN CARRBORO. CONSTRUCT SIDEWALK ON NORTH SIDE. | BIKE/PED | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5880 | DIVISION 7 | 71.96 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 |  |  |  | 2025 | 2025 | 2025
ORANGE | SR 1780 (ESTES DRIVE) | SR 1772 (NORTH GREENSBORO STREET) TO SOUTH OF NORFOLK-SOUTHERN RR TRACKS IN CARRBORO | BIKE/PED | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5886A | DIVISION 7 | 67.25 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 |  |  |  | 2026 | 2026 | 2026
ORANGE | SR 1780 (ESTES DRIVE) | SOUTH OF NORFOLK-SOUTHERN RR TRACKS TO NC 86 (MARTIN LUTHER KING, JR. BLVD) IN CHAPEL HILL | BIKE/PED | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5886B | DIVISION 7 | 67.25 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 |  |  |  | 2025 | 2025 | 2025
ORANGE | US 15 / US 501 | WILLOW DRIVE TO SR 1741 / SR 1838 (OLD DURHAM-CHAPEL HILL ROAD) IN CHAPEL HILL. CONSTRUCT MULTIUSE PATHS. | BIKE/PED | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | EB-5998 | DIVISION 7 | 60.78 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2026 | 2026 | 2026
ORANGE | I-40 | NC 86 UPGRADE TO SUPERSTREET FROM NORTHWOOD DRIVE TO RAMP C/D AT I-40 INTERCHANGE. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-3306AC | REGION D | 75.84 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2028 | 2024 | 2024 | 2028 | 2024 | 2026 | 2030 | 2026
ORANGE | I-85 | SR 1009 (SOUTH CHURTON STREET) IN HILLSBOROUGH. INTERCHANGE IMPROVEMENTS. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-5967 | STATEWIDE MOBILITY | 77.36 | P4.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2031
ORANGE | I-85 | NC 86 IN HILLSBOROUGH. UPGRADE INTERCHANGE. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-5984 | STATEWIDE MOBILITY | 83.8 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
ORANGE | NC 54 | SR 1006 (ORANGE GROVE ROAD) TO SR 1107 / SR 1937 (OLD FAYETTEVILLE ROAD). CONSTRUCT OPERATIONAL IMPROVEMENTS, INCLUDING BICYCLE/PEDESTRIAN ACCOMMODATIONS | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | R-5821A | REGION D | 71.07 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
ORANGE | SR 1009 (SOUTH CHURTON STREET) | I-40 TO ENO RIVER IN HILLSBOROUGH. WIDEN TO MULTILANES. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5845 | DIVISION 7 | 50.53 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2027 | 2028 | 2026 | 2027 | 2028 | 2029 | 2029 | 2031
ORANGE | US 15 / US 501 | NC 86 (SOUTH COLUMBIA STREET). INTERCHANGE IMPROVEMENTS. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5304A | NOT FUNDED | 76.47 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
ORANGE | US 15 / US 501 | NC 86 (SOUTH COLUMBIA STREET) TO NC 54 (RALEIGH ROAD). CAPACITY IMPROVEMENTS , WITH SIDEWALKS, WIDE OUTSIDE LANES AND TRANSIT ACCOMMODATIONS. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5304B | NOT FUNDED | 76.95 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
ORANGE | US 15 / US 501 | NC 54 (RALEIGH ROAD). TO SR 1742 (EPHESUS CHURCH ROAD). CAPACITY IMPROVEMENTS , WITH SIDEWALKS, WIDE OUTSIDE LANES AND TRANSIT ACCOMMODATIONS. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5304D | NOT FUNDED | 77.7 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
ORANGE | US 15 / US 501 | SR 1902 (MANNING DRIVE). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5304E | NOT FUNDED | 79.48 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
ORANGE | GO TRIANGLE | UNC HOSPITALS AREA IN CHAPEL HILL. CONSTRUCT NEIGHBORHOOD TRANSIT CENTER TRANSFER STATION. 400; 405; 420; 800; 805; CRX; FCX | PUBLIC TRANSIT | 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | TD-5284 | REGION D | 72.78 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2024 | 2024 | 2024
ORANGE, DURHAM | I-85 | WEST OF SR 1006 (ORANGE GROVE ROAD) IN ORANGE COUNTY TO WEST OF SR 1400 (SPARGER ROAD) IN DURHAM COUNTY. ADD LANES. | HIGHWAY | 5, 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | I-0305 | STATEWIDE MOBILITY | 81.68 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
ORANGE, DURHAM | NC 54 | WEST OF US 15 / US 501 IN ORANGE COUNTY TO EAST OF SR 1110 (BARBEE CHAPEL ROAD) IN DURHAM COUNTY. UPGRADE ROADWAY CORRIDOR. | HIGHWAY | 5, 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5774B | REGION C, D | 75.18 | P4.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2030
ORANGE, DURHAM | US 15 / US 501 | SR 1742 (EPHESUS CHURCH ROAD) TO I-40. CORRIDOR CAPACITY IMPROVEMENTS. | HIGHWAY | 5, 7 | DURHAM-CHAPEL HILL-CARRBORO MPO | U-5304F | NOT FUNDED | 79.79 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
PASQUOTANK | US 17 (HUGHES BOULEVARD) | SR 1308 (CHURCH STREET) TO US 17 BUSINESS (NORTH ROAD STREET). ACCESS MANAGEMENT. | HIGHWAY | 1 | ALBEMARLE RPO | U-5940 | REGION A | 78.59 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | 2025 | 2026 | 2026 | 2025 | 2028 | 2028 | 2027
PASQUOTANK | US 17 BUSINESS | SR 1145 (OAK STUMP ROAD). IMPROVE INTERSECTION. | HIGHWAY | 1 | ALBEMARLE RPO | U-5939 | REGION A | 79.28 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025
PENDER | HENDERSON FIELD (ACZ) | APRON EXPANSION. | AVIATION | 3 | CAPE FEAR RPO | AV-5815 | DIVISION 3 | 82.86 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2024 | 2024 | 2024
PENDER | NC 210 | SR 1560 (WATTS LANDING ROAD). CONSTRUCT ROUNDABOUT. | HIGHWAY | 3 | CAPE FEAR RPO | R-5899 | NOT FUNDED | 73.74 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2028 | NOT FUNDED | NOT FUNDED | 2028 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
PENDER | NC 50/NC 210 | SR 1534 (BELT ROAD). CONSTRUCT ROUNDABOUT. | HIGHWAY | 3 | CAPE FEAR RPO | R-5900 | NOT FUNDED | 72.45 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
PENDER | NC 53 | US 117 BUSINESS (WALKER STREET/WILMINGTON STREET). IMPROVE INTERSECTION. | HIGHWAY | 3 | CAPE FEAR RPO | R-5701 | REGION B | 59.73 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2027 | 2027 | 2027
PENDER | NC 53 | US 117 BYPASS TO STAG PARK ROAD. WIDEN TO THREE LANES. | HIGHWAY | 3 | CAPE FEAR RPO | R-5850 | DIVISION 3 | 82.39 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2025 | 2025 | 2025
PENDER | US 17 | NC 210 (SURF CITY). INTERSECTION IMPROVEMENT AT US 17 AND NC 210 NEAR SURF CITY. | HIGHWAY | 3 | CAPE FEAR RPO | R-5877 | NOT FUNDED | 75.91 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2028 | NOT FUNDED | NOT FUNDED | 2028 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
PENDER | US 17 | US 17 FROM SR 1582 (WASHINGTON ACRES ROAD) TO VISTA LANE. CONVERT TO SUPERSTREET. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | U-5732 | REGION B | 59.68 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2029 | 2027 | 2026
PENDER, NEW HANOVER | US 17 | US 17 BYPASS SOUTH OF HAMPSTEAD TO NC 210. | HIGHWAY | 3 | WILMINGTON URBAN AREA MPO | R-3300A | REGION B | 77.66 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2027 | 2027 | 2027
PERQUIMANS | SR 1300 (NEW HOPE ROAD) | WOODLAND CHURCH ROAD TO WOODVILLE ROAD (SR 1329). MODERNIZE ROADWAY. | HIGHWAY | 1 | ALBEMARLE RPO | R-5939 | DIVISION 1 | 69.9 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2030
PERQUIMANS | US 17 | SR 1336 (HARVEY POINT ROAD) AND SR 1338 (WAYNE FORK ROAD). CONVERT AT-GRADE INTERSECTION TO AN INTERCHANGE. | HIGHWAY | 1 | ALBEMARLE RPO | R-5869A | DIVISION 1 | 77.15 | NOT COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2027 | NOT FUNDED | 2028 | 2027 | NOT FUNDED | 2028 | 2029 | NOT FUNDED | 2030
PERQUIMANS | US 17 | SR 1300 (NEW HOPE ROAD). CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 1 | ALBEMARLE RPO | R-5869B | DIVISION 1 | 67 | NOT COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2027 | NOT FUNDED | 2028 | 2027 | NOT FUNDED | 2028 | 2029 | NOT FUNDED | 2030
PERSON | PERSON COUNTY EXECUTIVE AIRPORT (TDF) | EXTEND RUNWAY TO TOTAL LENGTH OF 7000 FT, CONSTRUCT TAXIWAY EXTENSION AND RELOCATE SR 1311 (CATES MILL ROAD). | AVIATION | 5 | KERR-TAR RPO | AV-5818 | DIVISION 5 | 89.23 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2029 | 2028 | 2028
PERSON | US 501 | SOUTH OF US 158 TO NC 157. | HIGHWAY | 5 | KERR-TAR RPO | U-5969A | DIVISION 5 | 78.31 | P4.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | 2030 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029
PERSON | US 501 | NC 157 TO SR 1596 (WEST MOREHEAD STREET) | HIGHWAY | 5 | KERR-TAR RPO | U-5969B | REGION C | 74.38 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2025 | 2025 | 2025
PERSON | US 501 / NC 49 | SR 1596 (WEST MOREHEAD STREET) TO SR 1601 (NORTH MAIN STREET) | HIGHWAY | 5 | KERR-TAR RPO | U-5969C | REGION C | 74.5 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2025 | 2025 | 2025
PITT | NC 11 (MEMORIAL DRIVE) | NC 43 (WEST FIFTH STREET) TO SR 1128 (DAVENPORT FARM ROAD) IN GREENVILLE. CONSTRUCT SIDEWALK. | BIKE/PED | 2 | GREENVILLE URBAN AREA MPO | EB-5981 | NOT FUNDED | 88.61 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2028 | NOT FUNDED | NOT FUNDED |  | NOT FUNDED |  | 2029 | NOT FUNDED | NOT FUNDED
PITT | US 264-A (GREENVILLE BOULEVARD) | US 264-A TO US 13 (DICKINSON AVENUE) IN GREENVILLE. CONSTRUCT SIDEWALK AND CURB AND GUTTER. | BIKE/PED | 2 | GREENVILLE URBAN AREA MPO | EB-5980 | NOT FUNDED | 88.99 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2027 | NOT FUNDED | NOT FUNDED |  | NOT FUNDED |  | 2028 | NOT FUNDED | NOT FUNDED
PITT | GREENVILLE | GREENVILLE SIGNAL SYSTEM. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-5952 | REGION B | 74.51 | P4.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY |  |  |  | 2026 | NOT FUNDED | 2026 | 2028 | NOT FUNDED | 2028
PITT | NC 33 | SR 1755 (BLACKJACK-SIMPSON ROAD) TO SR 1760 (MOBLEYS BRIDGE ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO, MID-EAST RPO | U-6215 | NOT FUNDED | 80.24 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
PITT | NC 33 (10TH STREET) | OXFORD ROAD TO SR 1702 (EVANS STREET). ACCESS MANAGEMENT. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-6125 | NOT FUNDED | 79.79 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
PITT | NC 43 | SR 1708 (FIRETOWER ROAD) TO SR 1711 (WORTHINGTON ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-5991 | DIVISION 2 | 74.37 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2029 | 2029 | 2029
PITT | NC 43 (CHARLES BOULEVARD) | US 264A (GREENVILLE BOULEVARD) TO SR 1726 (BELLS FORK ROAD). ACCESS MANAGEMENT. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-6147 | NOT FUNDED | 73.24 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
PITT | SR 1203 (ALLEN ROAD) | SR 1467 (STANTONSBURG ROAD) TO US 13 (DICKINSON AVENUE EXTENSION). WIDEN TO MULTI-LANES. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-5875 | DIVISION 2 | 74.42 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2025 | 2024 | 2024
PITT | SR 1467 (STANTONSBURG ROAD) | SR 1204 (B'S BARBEQUE ROAD) TO NC 11 (MEMORIAL DRIVE). ACCESS MANAGEMENT. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-6195 | NOT FUNDED | 86.44 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
PITT | SR 1700 (EVANS STREET/ OLD TAR ROAD) | SR 1711 (WORTHINGTON ROAD) IN WINTERVILLE TO US 264 ALTERNATE (GREENVILLE BOULEVARD) IN GREENVILLE. WIDEN TO MULTI-LANES. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-2817 | DIVISION 2 | 75.81 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2025 | 2025 | 2025
PITT | SR 1702 (EVANS STREET) | SR 1155 (RED BANKS ROAD) TO WEST 5TH STREET. ACCESS MANAGEMENT. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-6196 | NOT FUNDED | 82.19 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
PITT | SR 1704 (FOURTEENTH STREET) | RED BANKS ROAD TO SR 1708 (FIRETOWER ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-5917 | DIVISION 2 | 72.7 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2019 | 2019 | 2019 | 2026 | 2024 | 2024 | 2028 | 2026 | 2026
PITT | SR 1708 (FIRETOWER ROAD) | WEST OF EAST ARLINGTON BOULEVARD TO SR 1704 (FOURTEENTH STREET) IN GREENVILLE. WIDEN TO MULTI-LANES. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-5785 | DIVISION 2 | 85.42 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2024 | 2024 |  | 2024 | 2024 | 2028 | 2026 | 2026
PITT | SR 1708 (FIRETOWER ROAD) | SR 1704 (FOURTEENTH STREET) TO NC 33 (EAST 10TH STREET) IN GREENVILLE. WIDEN TO MULTI-LANES. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-5870 | DIVISION 2 | 75.75 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2025 | 2024 |  | 2025 | 2024 | 2028 | 2027 | 2026
PITT | SR 1711 (WORTHINGTON ROAD) | SR 1725 (COUNTY HOME ROAD). UPGRADE INTERSECTION. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-6197 | DIVISION 2 | 81.97 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2028 | NOT FUNDED | 2027 | 2028 | NOT FUNDED | 2027 | AFTER 2029 | NOT FUNDED | 2029
PITT | US 13 (MEMORIAL DRIVE) | NC 43 (5TH STREET). UPGRADE INTERSECTION. | HIGHWAY | 2 | GREENVILLE URBAN AREA MPO | U-5730 | REGION B | 68.94 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2025 | 2025 | 2025
POLK | I-26 | CONSTRUCT IMPROVEMENTS ON NC 108 AT EXIT 67. | HIGHWAY | 14 | FOOTHILLS RPO | I-4729B | REGION G | 49.92 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2019 | 2019 | 2019 |  | 2028 | 2027 | 2029 | 2030 | 2029
POLK | NC 9 | US 74 TO NC 108. ADD PAVED SHOULDERS. | HIGHWAY | 14 | FOOTHILLS RPO | R-5840 | DIVISION 14 | 59.46 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2025 | 2025 | 2025
POLK | US 74 | NC 108 INTERCHANGE. IMPROVE INTERCHANGE. | HIGHWAY | 14 | FOOTHILLS RPO | R-5873 | STATEWIDE MOBILITY | 77.96 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2024 |  |  | 2024 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
RANDOLPH | REGIONAL AIRPORT (HBI) ASHEBORO | CONSTRUCT TAXILANE EXTENSION, EXTEND ACCESS ROAD, AND CONSTRUCT NEW ACCESS ROAD. | AVIATION | 8 | PIEDMONT TRIAD RPO | AV-5858 | DIVISION 8 | 69.59 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2025 | 2025 | 2025
RANDOLPH | SR 1950 (WEST NAOMI STREET) | WEST ACADEMY STREET TO US 220 BUSINESS (SOUTH MAIN STREET) IN RANDLEMAN. CONSTRUCT SIDEWALK, IMPLEMENT ROAD DIET, AND INSTALL RAISED CROSSWALK AND MEDIAN. | BIKE/PED | 8 | PIEDMONT TRIAD RPO | EB-5898 | DIVISION 8 | 53.21 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2024 |  |  |  | 2023 | 2023 | 2024
RANDOLPH | US 64 / NC 49 (EAST DIXIE DRIVE) | EXECUTIVE WAY TO CENTERPOINT PLAZA SHOPPING CENTER IN ASHEBORO. CONSTRUCT SIDEWALK. | BIKE/PED | 8 | PIEDMONT TRIAD RPO | EB-6004 | DIVISION 8 | 69.81 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2024 | 2024 | 2024
RANDOLPH | I-85 | SR 1009 (SOUTH MAIN STREET) IN ARCHDALE. INTERCHANGE IMPROVEMENTS. | HIGHWAY | 8 | HIGH POINT URBAN AREA MPO | U-5770 | REGION E | 58.24 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2025 | 2025
RANDOLPH | NC 159 (ZOO PARKWAY) | RIDGE STREET IN ASHEBORO. IMPROVE INTERSECTION. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-5958 | DIVISION 8 | 68.8 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2023 | 2022 | 2022 | 2023 | 2025 | 2025 | 2025
RANDOLPH | NC 42 | SR 2237 (EAST SALISBURY STREET) TO NORTH OF US 64 / NC 49 (DIXIE DRIVE) IN ASHEBORO. WIDEN TO THREE LANES. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | U-5743 | REGION E | 51.44 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2024 | 2024 | 2024
RANDOLPH | NC 42 (EAST SALISBURY STREET) | SR 2189 (MARTIN LUTHER KING, JR. DRIVE) / NORTH RANDOLPH AVENUE TO SR 2237 (EAST SALISBURY STREET) IN ASHEBORO. IMPROVE CORRIDOR. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-5957 | NOT FUNDED | 70.12 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2026 | NOT FUNDED | NOT FUNDED | 2026 | NOT FUNDED | NOT FUNDED | 2028 | NOT FUNDED | NOT FUNDED
RANDOLPH | NC 49 | SR 1174 (WAYNICK MEADOW ROAD) TO SOUTH OF SR 1193 (OLD NC 49). WIDEN TO MULTILANES. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-5931 | NOT FUNDED | 75.54 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2027 | NOT FUNDED | NOT FUNDED | 2027 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
RANDOLPH | NC 62 | SR 3252 (SURRETT DRIVE) IN TRINITY TO SR 1009 (NORTH MAIN STREET) IN ARCHDALE. MODERNIZE ROADWAY. | HIGHWAY | 8 | HIGH POINT URBAN AREA MPO | U-6191 | DIVISION 8 | 78.73 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2029 | 2029 | 2029
RANDOLPH | SR 1009 (SOUTH MAIN STREET) | WEST OF COLUMBUS AVENUE TO SR 3182 (COMANCHE ROAD/TARHEEL ROAD). MILLING AND RESURFACING. | HIGHWAY | 8 | HIGH POINT URBAN AREA MPO | U-5770A | REGION E | 58.24 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | PROJECT SEGMENT NOT LISTED IN DRAFT 2024-2033 STIP (APRIL 2022) |  | 2022 | PROJECT SEGMENT NOT LISTED IN DRAFT 2024-2033 STIP (APRIL 2022) |  | 2025 | PROJECT SEGMENT NOT LISTED IN DRAFT 2024-2033 STIP (APRIL 2022) | 2023
RANDOLPH | SR 1009 (SOUTH MAIN STREET) | WEST OF COLUMBUS AVENUE TO SR 3182 (COMANCHE ROAD/TARHEEL ROAD). CONSTRUCT DDI AND RCI IMPROVEMENTS. | HIGHWAY | 8 | HIGH POINT URBAN AREA MPO | U-5770B | REGION E | 58.24 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | PROJECT SEGMENT NOT LISTED IN DRAFT 2024-2033 STIP (APRIL 2022) |  | 2022 | PROJECT SEGMENT NOT LISTED IN DRAFT 2024-2033 STIP (APRIL 2022) |  | 2025 | PROJECT SEGMENT NOT LISTED IN DRAFT 2024-2033 STIP (APRIL 2022) | 2025
RANDOLPH | SR 1547 (FINCH FARM ROAD) | SR 3106 (KENNEDY ROAD) TO I-85 IN TRINITY. WIDEN TO MULTILANES. | HIGHWAY | 8 | HIGH POINT URBAN AREA MPO | U-5308 | DIVISION 8 | 65.31 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2025 | 2025 | 2025
RANDOLPH | SR 1712 (PINEVIEW STREET) | WEST OF SYLVAN STREET TO US 220 BUSINESS IN ASHEBORO. WIDEN TO MULTILANES. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | U-5711 | DIVISION 8 | 61.04 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2024 | 2024 | 2024
RANDOLPH | US 220 BUSINESS | SR 2123 (CAUDLE ROAD) TO SR 2270 (US 311 EXTENSION) IN RANDLEMAN. WIDEN TO 4-LANE DIVIDED FACILITY. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | U-6006 | DIVISION 8 | 76.02 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2026 | 2026 | 2026
RANDOLPH | US 220 BUSINESS (NORTH FAYETTEVILLE STREET) | SR 2269 (VISION DRIVE) TO SR 2149 (HUB MORRIS ROAD). WIDEN TO MULTILANES. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-5956A | NOT FUNDED | 73.58 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
RANDOLPH | US 220 BUSINESS (NORTH FAYETTEVILLE STREET) | SR 2149 (HUB MORRIS ROAD) TO SR 2123 (CAUDLE ROAD). WIDEN TO MULTILANES. | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-5956B | NOT FUNDED | 58.46 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
RANDOLPH | US 64 | SR 1409 (LAKE PARK ROAD) TO ASHEBORO BYPASS | HIGHWAY | 8 | PIEDMONT TRIAD RPO | R-2220DA | REGION E | 68.77 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | 2027 | 2028 | 2028 | 2027 | AFTER 2029 | 2030 | 2029
RANDOLPH, GUILFORD | SR 1577 / SR 1004 (ARCHDALE ROAD) | US 311 (MAIN STREET) TO EAST OF SPRINGWOOD LANE IN ARCHDALE. WIDEN TO MULTILANES. | HIGHWAY | 7, 8 | HIGH POINT URBAN AREA MPO | U-3400 | DIVISION 7, 8 | 63.29 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2026 | 2026 | 2026
RANDOLPH, GUILFORD | SR 1595 / SR 4053 (SURRETT DRIVE) | I-85 IN TRINITY TO SR 1300 (WEST FAIRFIELD ROAD) IN HIGH POINT. WIDEN TO MULTILANES. | HIGHWAY | 7, 8 | HIGH POINT URBAN AREA MPO | U-5864 | DIVISION 7, 8 | 37.71 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2026 | 2026 | 2024 | 2026 | 2026 | 2029 | 2029 | 2029
RICHMOND | RICHMOND COUNTY AIRPORT (RCZ) | EXTEND RUNWAY 14-32 TO 5500 FEET. | AVIATION | 8 | LUMBER RIVER RPO | AV-5763 | DIVISION 8 | 39.28 | P3.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | [6 empty] | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
RICHMOND | SR 1639 (SPRING STREET); SR 1615 (SOUTH MAIN STREE | SPRING STREET FROM SR 1640 (WIREGRASS ROAD) TO NC 177 AND MAIN STREET FROM BRIDGES STREET TO NC 38 IN HAMLET. CONSTRUCT SIDEWALKS. | BIKE/PED | 8 | LUMBER RIVER RPO | EB-6018 | DIVISION 8 | 46.63 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 |  |  | 2024 | 2025 | 2025 | 2025
RICHMOND | US 1 | US 74 BUSINESS TO NORTH OF SR 1606 (FOX ROAD) | HIGHWAY | 8 | LUMBER RIVER RPO | R-2501BC | NOT FUNDED | 46.85 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
RICHMOND | US 1 | SR 1640 (WIREGRASS ROAD) TO LOCH LAURIN LANE. WIDEN TO MULTILANES. | HIGHWAY | 8 | LUMBER RIVER RPO | R-5928 | DIVISION 8 | 80.65 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2029 | 2029 | 2029
RICHMOND | US 1 (PROPOSED) /SR 1516 (GREENE STREET) | US 220 TO US 1 IN ROCKINGHAM. WIDEN TO 3-LANE FACILITY AND RE-ROUTE US 1 ALONG PROJECT. | HIGHWAY | 8 | LUMBER RIVER RPO | U-6027 | DIVISION 8 | 74.06 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2025 | 2025 | 2025
RICHMOND | US 74 / FUTURE I-74 | US 1 (EXIT 311). INTERCHANGE IMPROVEMENTS. | HIGHWAY | 8 | LUMBER RIVER RPO | I-5979 | DIVISION 8 | 49.23 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2024 | 2024 | 2024
RICHMOND | VARIOUS | US 74 BUSINESS TO SR 1426 (ABERDEEN ROAD). CONSTRUCT TWO LANE FACILITY UTILIZING SECTIONS OF SR 1641 (CLEMMER ROAD) AND SR 1645 (MT. OLIVE CHURCH ROAD), REMAINDER ON NEW LOCATION. | HIGHWAY | 8 | LUMBER RIVER RPO | U-5706 | DIVISION 8 | 65.06 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2026 | 2026 | 2026
ROBESON | LUMBERTON REGIONAL AIRPORT (LBT) | RUNWAY 13-31. CONSTRUCT TAXIWAYS. | AVIATION | 6 | LUMBER RIVER RPO | AV-5901 | DIVISION 6 | 83.79 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | [6 empty] | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
ROBESON | NC 711 (THIRD STREET) | SR 1563 (UNION CHAPEL ROAD) TO WALMART SHOPPING CENTER/JOHNES ROAD IN PEMBROKE. CONSTRUCT SIDEWALKS. | BIKE/PED | 6 | LUMBER RIVER RPO | EB-6013 | DIVISION 6 | 84.09 | NOT COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2028 | 2028 |  |  |  | 2028 | 2029 | 2029
ROBESON | I-95 | CONSTRUCT WEIGH IN MOTION STATION. | HIGHWAY | 6 | LUMBER RIVER RPO | I-5987AA | REGION C | N/A | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2025 | 2025 | 2025
ROBESON | NC 20 | SR 1743 (COVINGTON FARM ROAD) TO I-95. WIDEN TO MULTI-LANES. | HIGHWAY | 6 | LUMBER RIVER RPO | R-5904 | NOT FUNDED | 81.1 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
ROBESON | NC 41 (EAST ELIZABETHTOWN ROAD) | SR 2110 (SNAKE ROAD) TO SYCAMORE LANE. WIDEN EXISTING ROADWAY. | HIGHWAY | 6 | LUMBER RIVER RPO | R-5888 | REGION C | 83.25 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2027 | NOT FUNDED | 2028 | 2027 | NOT FUNDED | 2028 | AFTER 2029 | NOT FUNDED | 2030
ROBESON | NC 41 (MARTIN LUTHER KING DRIVE) | US 74 TO MARION ROAD. WIDEN ROADWAY. | HIGHWAY | 6 | LUMBER RIVER RPO | R-5951 | NOT FUNDED | 82 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2027 | NOT FUNDED | NOT FUNDED | 2027 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
ROBESON | NC 711 | SR 1340 (ODOM STREET-PHILADELPHUS ROAD) IN PEMBROKE TO SR 1557 (REDMOND ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 6 | LUMBER RIVER RPO | R-4428 | REGION C | 74.6 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
ROBESON | SR 1945 (MEADOW ROAD) | SR 1984 (LINKHAW ROAD). IMPROVE INTERSECTION. | HIGHWAY | 6 | LUMBER RIVER RPO | R-5954 | NOT FUNDED | 79.38 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2026 | NOT FUNDED | NOT FUNDED | 2026 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
ROBESON | SR 1997 (FAYETTEVILLE ROAD) | I-95 TO FARRINGTON STREET. WIDEN ROADWAY. | HIGHWAY | 6 | LUMBER RIVER RPO | R-5955 | NOT FUNDED | 76.48 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2026 | NOT FUNDED | NOT FUNDED | 2026 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED
ROBESON | SR 1997 (FAYETTEVILLE ROAD) | FARRINGTON STREET TO EAST 22ND STREET. WIDEN TO MULTI-LANES. | HIGHWAY | 6 | LUMBER RIVER RPO | U-5797 | DIVISION 6 | 74.29 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024
ROBESON | US 74 | CONVERT AT-GRADE INTERSECTION OF US 74 AND SR 2225 (CREEK ROAD) TO GRADE SEPARATION. | HIGHWAY | 6 | LUMBER RIVER RPO | I-6011A | DIVISION 6 | 79.74 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2027 | 2025 | 2025 | 2027 | 2025 | 2027 | 2028 | 2027
ROCKINGHAM | ROCKINGHAM COUNTY / NC SHILOH AIRPORT (SIF) | CONSTRUCT T-HANGAR TAXILANES FOR ADDITION OF T-HANGARS. | AVIATION | 7 | PIEDMONT TRIAD RPO | AV-5898 | DIVISION 7 | 80.26 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2025 | 2025 | 2025
ROCKINGHAM | ROCKINGHAM COUNTY AIRPORT (SIF) | EXTEND RUNWAY TO 5500 FT. | AVIATION | 7 | PIEDMONT TRIAD RPO | AV-5852 | DIVISION 7 | 75.47 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | [6 empty] | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
ROCKINGHAM | FUTURE I-73 / US 220 | US 311 / NC 135 INTERCHANGE. REPLACE BRIDGE 780074 AND UPGRADE INTERCHANGE. | HIGHWAY | 7 | PIEDMONT TRIAD RPO | I-5898 | REGION D | 55.61 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2025 | 2025 | 2025
ROCKINGHAM | NC 65 / NC 87 | WEST OF SR 2371 (OLD COUNTY HOME ROAD) IN WENTWORTH TO SR 1001 (SANDY CROSS ROAD) / SR 1998 (WENTWORTH STREET) | HIGHWAY | 7 | PIEDMONT TRIAD RPO | R-5766A | DIVISION 7 | 80.25 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2026 | 2026 | 2026
ROCKINGHAM | NC 65 / NC 87 | SR 1001 (SANDY CROSS ROAD) / SR 1998 (WENTWORTH STREET) TO SR 2413 (VANCE STREET EXTENSION) | HIGHWAY | 7 | PIEDMONT TRIAD RPO | R-5766B | DIVISION 7 | 78.94 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2026 | 2026 | 2026
ROCKINGHAM | NC 65 / NC 87 | SR 2413 (VANCE STREET EXTENSION) TO US 158 / US 29 BUSINESS IN REIDSVILLE | HIGHWAY | 7 | PIEDMONT TRIAD RPO | R-5766C | DIVISION 7 | 74.7 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2026 | 2026 | 2026
ROCKINGHAM | US 311 / NC 14 (SOUTH VAN BUREN ROAD) | SR 2066 (KINGS HIGHWAY) IN EDEN. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 7 | PIEDMONT TRIAD RPO | U-5893 | REGION D | 59.99 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2028 | 2024 | 2024 | 2028 | 2024 | 2026 | 2030 | 2026
ROCKINGHAM, GUILFORD | NC 65 / NC 68 | NC 65 IN STOKESDALE (SOUTHERNMOST INTERSECTION) TO US 220 / FUTURE I-73. WIDEN TO MULTILANES. | HIGHWAY | 7 | PIEDMONT TRIAD RPO, GREENSBORO URBAN AREA MPO | R-5823 | DIVISION 7 | 77.81 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2024 | 2022 | 2022 | 2024 | 2024 | 2024 | 2026
ROCKINGHAM, GUILFORD | US 29 (FUTURE I-785) | SR 2565 (HICONE ROAD) IN GREENSBORO TO US 158 / NC 14 IN REIDSVILLE. UPGRADE CORRIDOR TO INTERSTATE STANDARDS. | HIGHWAY | 7 | PIEDMONT TRIAD RPO, GREENSBORO URBAN AREA MPO | R-5889 | REGION D | 77.53 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2026 | NOT FUNDED | 2028 | 2026 | NOT FUNDED | 2028 | 2029 | NOT FUNDED | 2031
ROWAN | SR 2739 (NORTH MAIN STREET) | 12TH STREET TO 22ND STREET IN KANNAPOLIS. CONSTRUCT SIDEWALK. | BIKE/PED | 9 | CABARRUS-ROWAN MPO | EB-5921 | DIVISION 9 | 70.76 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 |  |  |  | 2025 | 2025 | 2025
ROWAN | THIRD STREET GREENWAY | 3RD STREET TO YADKIN RIVER IN SPENCER. CONSTRUCT ALTERNATE ROUTE, INCLUDING SPUR FROM GRANTS CREEK. | BIKE/PED | 9 | CABARRUS-ROWAN MPO | EB-5861 | DIVISION 9 | 81.7 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2022 | 2022 | 2024
ROWAN | NEW ROUTE | AIRPORT PARKWAY, SR 1710 (HARRISON ROAD) NEAR US 70 / US 601 (JAKE ALEXANDER BOULEVARD) TO SR 2539 (PEACH ORCHARD ROAD) AT US 29 IN SALISBURY. CONSTRUCT 2-LANE ROADWAY ON MULTILANE RIGHT OF WAY. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | U-5901 | DIVISION 9 | 73.11 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | 2027 | 2028 | 2028 | 2027 | AFTER 2029 | 2030 | 2030
ROWAN | US 29 | NC 152 IN CHINA GROVE. RAMP AND INTERSECTION IMPROVEMENTS. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | U-6130 | REGION D | 78.61 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
ROWAN | US 52 | PROPOSED MISENHEIMER BYPASS TO PROPOSED ROCKWELL BYPASS. WIDEN TO MULTILANES. | HIGHWAY | 9 | CABARRUS-ROWAN MPO | R-5860 | DIVISION 9 | 58.36 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | 2027 | 2028 | 2028 | 2027 | AFTER 2029 | 2030 | 2029
ROWAN | NORFOLK SOUTHERN | CITY OF SALISBURY. UPGRADE STATION BUILDING, EXPAND WAITING SPACE AND SURFACE PARKING. | RAIL | 9 | CABARRUS-ROWAN MPO | P-5733 | DIVISION 9 | 74.4 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | 2025 |  |  |  | 2026 | 2026 | 2026
ROWAN | RAILROAD NORFOLK SOUTHERN | NS MAINLINE IN ROWAN COUNTY. CONSTRUCT TRACK IMPROVEMENTS, SECOND PLATFORM, PEDESTRIAN UNDERPASS, SITEWORK, RETAINING WALL AND SIGNAL EQUIPMENT. | RAIL | 9 | CABARRUS-ROWAN MPO | P-5726 | REGION D | 50.92 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2024 | 2024 | 2024
ROWAN, CABARRUS | SR 2739 (NORTH MAIN STREET / SOUTH MAIN STREET) | SR 2000 (JACKSON PARK ROAD) / NORTH LOOP ROAD IN KANNAPOLIS TO SR 1211 (KIMBALL ROAD) IN CHINA GROVE. UPGRADE ROADWAY INCORPORATING BICYCLE LANES AND SIDEWALKS. | HIGHWAY | 9, 10 | CABARRUS-ROWAN MPO | U-6062 | DIVISION 9, 10 | 69.79 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2031
RUTHERFORD | THERMAL BELT RAIL TRAIL IN RUTHERFORDTON. | CONSTRUCT SIDEWALK CONNECTIONS TO THERMAL BELT RAIL TRAIL ALONG VICTORY DRIVE, ALLEN STREET/RAILROAD STREET, PINE STREET, BROADWAY, EAST LIBERTY STREET/BEAVER STREET, MAIN STREET, AND WESTVIEW STREET | BIKE/PED | 13 | FOOTHILLS RPO | EB-5966 | DIVISION 13 | 84.73 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | 2025 |  |  |  | 2026 | 2026 | 2026
RUTHERFORD | NC 108 (CHARLOTTE STREET) | NC 108 (MAPLE STREET), SOUTH WASHINGTON STREET, MONFREDO STREET INTERSECTION IN RUTHERFORDTON. IMPROVE INTERSECTION. | HIGHWAY | 13 | FOOTHILLS RPO | R-5916 | NOT FUNDED | 78.95 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
RUTHERFORD | US 221 | NORTH OF US 74 BYPASS TO SOUTH OF US 74 BUSINESS | HIGHWAY | 13 | FOOTHILLS RPO | R-2233BA | DIVISION 13 | 69.43 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | 2024 | 2025 | 2025 | 2024 | 2028 | 2028 | 2027
RUTHERFORD | US 221 | NORTH OF SR 1366 (ROPER LOOP ROAD) TO SR 1325 (NANNEY TOWN ROAD). WIDEN TO MULTI-LANES. | HIGHWAY | 13 | FOOTHILLS RPO | R-2597A | NOT FUNDED | 69.79 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
RUTHERFORD | US 221 | SR 2201 (THUNDER ROAD) / SR 1005 (COXE ROAD) INTERSECTION. IMPROVE INTERSECTION. | HIGHWAY | 13 | FOOTHILLS RPO | R-5880 | NOT FUNDED | 71.5 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
RUTHERFORD | US 221A (EAST MAIN STREET) | KENTUCKY STREET/OAKLAND ROAD INTERSECTION IN RUTHERFORDTON. IMPROVE INTERSECTION | HIGHWAY | 13 | FOOTHILLS RPO | R-5918 | NOT FUNDED | 78.03 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
RUTHERFORD | US 64 (EAST MOUNTAIN STREET) | NORTH WASHINGTON STREET INTERSECTION IN RUTHERFORDTON. IMPROVE INTERSECTION. | HIGHWAY | 13 | FOOTHILLS RPO | R-5917 | NOT FUNDED | 78.76 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
SAMPSON | CLINTON SAMPSON COUNTY AIRPORT (CTZ) | OVERLAY RUNWAY TO ACCOMMODATE LARGER AIRCRAFT. | AVIATION | 3 | MID-CAROLINA RPO | AV-5823 | DIVISION 3 | 36.29 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2025 | 2025 | 2025
SAMPSON | BEAMAN STREET | NORTH BOULEVARD TO SAMPSON REGIONAL MEDICAL CENTER IN CLINTON. CONSTRUCT SIDEWALK. | BIKE/PED | 3 | MID-CAROLINA RPO | EB-6011 | NOT FUNDED | 86.35 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2026 | NOT FUNDED | NOT FUNDED |  | NOT FUNDED |  | 2027 | NOT FUNDED | NOT FUNDED
SAMPSON | NC 24 (SOUTHWEST BOULEVARD/MLK JR BOULEVARD) | BUTLER ROAD/TRAM ROAD. IMPROVE INTERSECTION. | HIGHWAY | 3 | MID-CAROLINA RPO | U-6126 | NOT FUNDED | 78.76 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2028 | NOT FUNDED | NOT FUNDED | 2028 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
SAMPSON, DUPLIN | NC 24 | SR 1935 (CECIL ODIE ROAD) IN SAMPSON COUNTY TO I-40 IN DUPLIN COUNTY. | HIGHWAY | 3 | MID-CAROLINA RPO, EASTERN CAROLINA RPO | R-2303F | NOT FUNDED | 79.51 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
SCOTLAND | LAURINBURG- MAXTON AIRPORT (MEB) | CONSTRUCT 1500 FT RUNWAY EXTENSION. | AVIATION | 8 | LUMBER RIVER RPO | AV-5854 | DIVISION 8 | 72.48 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2024 | 2024 | 2024
SCOTLAND | SR 1108 (WEST BOULEVARD) | SR 1105 (TURNPIKE ROAD) TO GLASGOW DRIVE AND EAST OF US 15 / US 401 / US 501 TO SUNSET DRIVE IN LAURINBURG. | BIKE/PED | 8 | LUMBER RIVER RPO | EB-5872A | DIVISION 8 | 80.45 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2024 |  |  |  | 2023 | 2023 | 2024
SCOTLAND | US 401 BUSINESS (SOUTH MAIN STREET | PLAZA ROAD TO CREPE MYRTLE AVENUE IN LAURINBURG. CONSTRUCT SIDEWALKS | BIKE/PED | 8 | LUMBER RIVER RPO | EB-6015B | DIVISION 8 | 69.82 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 |  |  |  | 2025 | 2025 | 2025
SCOTLAND | US 15 / US 401 | SOUTH CAROLINA STATE LINE TO SOUTH OF SR 1105 (TURNPIKE ROAD) IN LAURINBURG. WIDEN TO MULTILANES. | HIGHWAY | 8 | LUMBER RIVER RPO | U-5977 | REGION E | 74.09 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2029 | NOT FUNDED | 2028 | 2029 | NOT FUNDED | 2028 | AFTER 2029 | NOT FUNDED | 2030
SCOTLAND, RICHMOND | US 74 / FUTURE I-74 | US 74 BUSINESS EAST OF HAMLET TO US 74 BUSINESS WEST OF LAURINBURG. UPGRADE CORRIDOR TO INTERSTATE STANDARDS. | HIGHWAY | 8 | LUMBER RIVER RPO | I-6055 | REGION E | 77.85 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2029 | NOT FUNDED | 2027 | 2029 | NOT FUNDED | 2027 | AFTER 2029 | NOT FUNDED | 2030
STANLY | STANLY COUNTY AIRPORT (VUJ) | ACQUIRE LAND FOR EXPANSION AND PERFORM ESA TO DETERMINE STATUS OF STRUCTURES ON PROPERTY. CLEAR AND GRUBB LAND REQUIRED FOR EXPANSION AND DEMOLISH HOUSES ON PROPERTY ACQUIRED. | AVIATION | 10 | ROCKY RIVER RPO | AV-5817 | DIVISION 10 | 90.54 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | 2025 |  |  |  | 2027 | 2027 | 2027
STANLY | ALBEMARLE | US 52, WEST MAIN STREET TO SNUGGES STREET. CONSTRUCT SIDEWALK ON EAST SIDE OF ROAD | BIKE/PED | 10 | ROCKY RIVER RPO | EB-5841 | DIVISION 10 | 89.95 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | 2025 |  |  |  | 2026 | 2026 | 2026
STANLY | NORTH SECOND AVENUE | PARK RIDGE TO SALISBURY AVENUE. CONSTRUCT SIDEWALKS, ADA RAMPS, AND CROSSWALKS. | BIKE/PED | 10 | ROCKY RIVER RPO | EB-5972 | DIVISION 10 | 82.78 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2026 | 2026 |  |  |  | 2026 | 2027 | 2027
STANLY | SALISBURY AVENUE | US 52 TO NORTH SECOND STREET. CONSTRUCT BIKE LANES. | BIKE/PED | 10 | ROCKY RIVER RPO | EB-5973 | DIVISION 10 | 80.93 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2025 | 2025 | 2025
STANLY | US 52 BUSINESS RAMP | NC 24/27 TO SECOND STREET. CONSTRUCT SIDEWALK ALONG US 52 BUSINESS RAMP | BIKE/PED | 10 | ROCKY RIVER RPO | EB-5974 | NOT FUNDED | 79.21 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2028 | NOT FUNDED | NOT FUNDED |  | NOT FUNDED |  | 2029 | NOT FUNDED | NOT FUNDED
SURRY | MOUNT AIRY | S. SOUTH STREET, WORTH STREET TO ROCKFORD STREET. ROCKFORD STREET, PENN STREET TO US 52. WORTH STREET, SOUTH STREET TO US 52. CONSTRUCT SIDEWALK. | BIKE/PED | 11 | NORTHWEST PIEDMONT RPO | EB-5845 | DIVISION 11 | 84.85 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 |  |  |  | 2024 | 2024 | 2024
SURRY | US 21 BUSINESS (NORTH BRIDGE STREET) | NC 268 (CC CAMP ROAD) TO HIGHLAND AVENUE. CONSTRUCT SIDEWALK ON WEST SIDE OF ROADWAY. | BIKE/PED | 11 | NORTHWEST PIEDMONT RPO | EB-5961 | DIVISION 11 | 84.05 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 |  |  |  | 2024 | 2024 | 2024
SURRY | NC 103 (EAST PINE STREET) | SR 1742 (QUAKER ROAD) INTERSECTION. IMPROVE INTERSECTION. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5895 | NOT FUNDED | 74.27 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2026 | NOT FUNDED | NOT FUNDED | 2026 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
SURRY | NC 89 (WEST PINE STREET) | SR 1397 (ROUND PEAK CHURCH ROAD) INTERSECTION. IMPROVE INTERSECTION. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5901 | NOT FUNDED | 67.81 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2027 | NOT FUNDED | NOT FUNDED | 2027 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED
SURRY | NC 89 (WEST PINE STREET) | SR 1387 (TOAST ROAD) TO SR 1396 (PINE RIDGE ROAD). MODERNIZE ROADWAY AND IMPROVE INTERSECTION AT SR 1396 (PINE RIDGE ROAD). | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5905 | DIVISION 11 | 79.63 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2028 | 2028 | 2028
SURRY | US 601 | I-74 TO SR 1104 (CODY TRAIL). WIDEN TO 4-LANES. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5836 | DIVISION 11 | 56.42 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2026 | 2026 | 2026
SWAIN | US 19 | SR 1152 (HUGHES BRANCH ROAD) IN BRYSON CITY TO SR 1195 (US 19A). MODERNIZE ROADWAY. | HIGHWAY | 14 | SOUTHWESTERN RPO | R-4751 | NOT FUNDED | 64.12 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
TRANSYLVANIA | BREVARD | CONSTRUCT BICYCLE AND PEDESTRIAN BRIDGE FROM CITY OF BREVARD EXISTING SHARED USE PATH ACROSS DAVIDSON RIVER. | BIKE/PED | 14 | LAND-OF-SKY RPO | EB-5858 | DIVISION 14 | 71.61 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2022 |  |  |  | 2024 | 2024 | 2024
TRANSYLVANIA | SR 1540 (WILSON ROAD) | SR 1504 (OLD US 64) TO US 276. UPGRADE ROADWAY. | HIGHWAY | 14 | LAND-OF-SKY RPO | R-5763 | DIVISION 14 | 56.62 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2024 | 2024 | 2024
TRANSYLVANIA | US 178 | SR 1156 (MAIN STREET) IN ROSMAN TO SR 1133 (MIDDLEFORK ROAD) MODERNIZE ROADWAY. | HIGHWAY | 14 | LAND-OF-SKY RPO | R-5919 | DIVISION 14 | 65.42 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
TRANSYLVANIA | US 64 | US 276, NC 280 INTERSECTION. CONSTRUCT INTERSECTION IMPROVEMENTS. | HIGHWAY | 14 | LAND-OF-SKY RPO | R-5799 | REGION G | 73.97 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2024 | 2024 | 2024
TRANSYLVANIA | US 64 (SOUTH BROAD STREET) | US 64 BUSINESS (SOUTH CALDWELL STREET), SR 1116 (NORTH COUNTRY CLUB ROAD) INTERSECTION. IMPROVE INTERSECTION ALIGNMENT. | HIGHWAY | 14 | LAND-OF-SKY RPO | R-5882 | NOT FUNDED | 67.18 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
TRANSYLVANIA | US 64, US 276 | FORTUNE COVE ROAD TO US 64 BUSINESS (NORTH CALDWELL STREET). CONSTRUCT MEDIAN AND ACCESS CONTROL MEASURES. | HIGHWAY | 14 | LAND-OF-SKY RPO | R-5800 | REGION G | 70.58 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2027 | 2023 | 2023 | 2027 | 2023 | 2025 | 2029 | 2025
TYRRELL | US 64 | COLUMBIA TO ALLIGATOR RIVER BRIDGE. MODERNIZE ROADWAY. | HIGHWAY | 1 | ALBEMARLE RPO | R-5940 | DIVISION 1 | 68.73 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2030
UNION | CHARLOTTE-MONROE EXECUTIVE AIRPORT (EQY) | RELOCATE AND WIDEN THE EXISTING PARALLEL TAXIWAY SECTION BETWEEN THE EXISTING RAMP AND THE RUNWAY 5 TAXIWAY EXTENSION. | AVIATION | 10 | CHARLOTTE REGIONAL TPO | AV-5814 | DIVISION 10 | 91.84 | P4.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | [6 empty] | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028
UNION | NC 16 (PROVIDENCE ROAD SOUTH) | SR 1316 (REA ROAD EXTENSION) TO SR 1307 (BONDS GROVE CHURCH RD). WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5769A | REGION E | 73.52 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2025 | 2024 | 2024 | 2025 | 2024 | 2027 | 2028 | 2027
UNION | NC 16 (PROVIDENCE ROAD SOUTH) | SR 1307 (BONDS GROVE CHURCH RD) TO SR 3530 (WAXHAW PARKWAY) IN WAXHAW. WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5769B | REGION E | 65.97 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2025 | 2024 | 2024 | 2025 | 2024 | 2027 | 2028 | 2027
UNION | NC 84 | NC 16 TO SR 1008 (WAXHAW-INDIAN TRAIL ROAD) IN WESLEY CHAPEL. CONSTRUCT FOUR LANE ROADWAY, PART ON NEW LOCATION. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-3467 | REGION E | 56.08 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | 2024 |  | 2026 | 2024 | 2029 | 2029 | 2027
UNION | SR 1004 (LAWYERS ROAD) | I-485 TO SR 1524 (STEVENS MILL ROAD). WIDEN ROADWAY TO FOUR LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6170 | NOT FUNDED | 79.56 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
UNION | SR 1009 (CHARLOTTE AVENUE) | SEYMOUR STREET TO NC 200 (DICKERSON BOULEVARD). WIDEN TO FOUR-LANES DIVIDED. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6031 | DIVISION 10 | 78.62 | P4.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2030
UNION | SR 1009 (JOHN STREET-OLD MONROE ROAD) | WEST OF MORNINGSIDE MEADOW LANE TO EAST OF SR 1377 (WESLEY CHAPEL-STOUTS ROAD) | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-4714B | DIVISION 10 | 90.54 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2021 | 2021 | 2021 | 2021 | 2021 | 2021 | 2024 | 2024 | 2024
UNION | SR 1009 (OLD MONROE ROAD) | SR 1377 (WESLEY CHAPEL-STOUTS ROAD) TO SR 1349 (AIRPORT ROAD). | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-6169 | NOT FUNDED | 79.76 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
UNION | US 601 | EXISTING US 74 TO THE MONROE BYPASS. WIDEN TO MULTI-LANES. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-4024 | REGION E | 74.43 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2027 | NOT FUNDED | 2028 | 2027 | NOT FUNDED | 2028 | AFTER 2029 | NOT FUNDED | 2030
UNION | US 74 | US 601 INTERCHANGE. CONSTRUCT IMPROVEMENTS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5723 | STATEWIDE MOBILITY | 69.81 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 |  |  | 2023 |  |  | 2025 | 2025 | 2025
UNION | US 74 | NC 200 (DICKERSON BOULEVARD) TO SR 1007 (ROCKY RIVER ROAD). WIDEN EXISTING ROADWAY. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5764 | REGION E | 78.93 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2025 | 2025 |  | 2025 | 2025 | 2027 | 2028 | 2028
UNION | US 74 | INTERSECTION OF US 74 AND SECREST SHORTCUT ROAD. CONSTRUCT IMPROVEMENTS. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5931 | STATEWIDE MOBILITY | 84.12 | P4.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2024 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2025 |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2025 | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028
UNION | US 74 (ROOSEVELT BLVD) | REALIGN JAMES HAMILTON ROAD TO INTERSECT WITH SR 1514 (ROCKY RIVER ROAD) AT MYERS ROAD. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-5703B | STATEWIDE MOBILITY | 70.85 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 |  |  |  | 2025 | 2026 | 2025
UNION | CSX SF LINE | SR 1377 (WESLEY CHAPEL STOUTS ROAD). CONSTRUCT GRADE SEPERATION. | RAIL | 10 | CHARLOTTE REGIONAL TPO | P-5744 | STATEWIDE MOBILITY | 82.3 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2027 | 2027 | 2027
UNION, MECKLENBURG | IDLEWILD ROAD | SR 3175 (STALLINGS ROAD) TO SR 1524 (STEVENS MILL ROAD). WIDEN EXISTING ROADWAY. | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-4913 | DIVISION 10 | 72.08 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2027 | 2026 | 2026 | 2027 | 2026 | 2028 | 2029 | 2028
UNION, MECKLENBURG | SR 1009 (JOHN STREET-OLD MONROE ROAD) | EAST OF I-485 TO WEST OF MORNINGSIDE MEADOW LANE | HIGHWAY | 10 | CHARLOTTE REGIONAL TPO | U-4714AC | DIVISION 10 | 73.8 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2019 | 2019 | 2019 |  | 2019 | 2019 | 2024 | 2024 | 2024
VANCE | SR 1162 (DABNEY DRIVE) | COBLE BOULEVARD TO US 158 BUSINESS IN HENDERSON. CORRIDOR UPGRADE. | HIGHWAY | 5 | KERR-TAR RPO | U-5890 | DIVISION 5 | 68.9 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | 2026 | 2027 | 2027 | 2026 | 2029 | 2029 | 2028
WAKE | SR 1012 (WESTERN BOULEVARD) | CONSTRUCT BICYCLE / PEDESTRIAN TUNNEL IMMEDIATELY WEST OF SR 1321 (AVENT FERRY ROAD) IN RALEIGH. | BIKE/PED | 5 | CAPITAL AREA MPO | EB-5718 | DIVISION 5 | 84.15 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | [6 empty] | 2025 | 2025 | 2025
WAKE | SR 1637 (CHURCH STREET) | SR 3014 (MORRISVILLE-CARPENTER ROAD) TO DURHAM COUNTY LINE IN MORRISVILLE. CONSTRUCT SIDEWALKS TO FILL IN GAPS. | BIKE/PED | 5 | CAPITAL AREA MPO | EB-5838 | DIVISION 5 | 90.2 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 |  |  |  | 2024 | 2024 | 2024
WAKE | I-40 | I-440 / US 1 / US 64 INTERCHANGE IN RALEIGH. RECONSTRUCT INTERCHANGE. | HIGHWAY | 5 | CAPITAL AREA MPO | I-5703 | STATEWIDE MOBILITY | 80.78 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2027 | 2026 | 2026 | 2027 | 2026 | 2026 | 2027 | 2026
WAKE | I-40 | SR 1002 (AVIATION PARKWAY) TO SR 1652 (HARRISON AVENUE) IN CARY. CONSTRUCT AUXILIARY LANES IN BOTH DIRECTIONS. | HIGHWAY | 5 | CAPITAL AREA MPO | I-5966 | STATEWIDE MOBILITY | 78.83 | P4.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2030
WAKE | I-40 / US 64 | I-440 / US 1 / US 64 TO SR 1370 (LAKE WHEELER ROAD) IN RALEIGH. ADD LANES. | HIGHWAY | 5 | CAPITAL AREA MPO | I-5701 | STATEWIDE MOBILITY | 77.63 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2027 | 2026 | 2026 | 2027 | 2026 | 2026 | 2027 | 2026
WAKE | I-440 / US 1 | SR 2000 (WAKE FOREST ROAD) IN RALEIGH. INTERCHANGE IMPROVEMENTS. | HIGHWAY | 5 | CAPITAL AREA MPO | I-5708 | STATEWIDE MOBILITY | 78.54 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2019 | 2019 | 2019 | 2020 |  |  | 2025 | 2025 | 2025
WAKE | I-440 / US 1 | US 70 (GLENWOOD AVENUE) IN RALEIGH. CONSTRUCT INTERCHANGE IMPROVEMENTS, REVISE US 70 INTERSECTION WITH SR 1670 (BLUE RIDGE ROAD) / SR 1820 (LEAD MINE ROAD), AND REPLACE BRIDGE 910494 ON SR 1670. | HIGHWAY | 5 | CAPITAL AREA MPO | I-5870 | STATEWIDE MOBILITY | 74.15 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
WAKE | I-440 / US 1 | US 401 (CAPITAL BOULEVARD) IN RALEIGH. INTERCHANGE IMPROVEMENTS. | HIGHWAY | 5 | CAPITAL AREA MPO | I-5970 | STATEWIDE MOBILITY | 73.83 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
WAKE | I-540 | US 70 TO SR 1829 (LEESVILLE ROAD) IN RALEIGH. CONSTRUCT EASTBOUND AUXILIARY LANE. | HIGHWAY | 5 | CAPITAL AREA MPO | I-5968 | STATEWIDE MOBILITY | 76.37 | P4.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2030
WAKE | I-87 / US 64 / US 264 | US 64 BUSINESS (WENDELL BOULEVARD) TO US 264. WIDEN TO 6 LANES. | HIGHWAY | 5 | CAPITAL AREA MPO | I-6005 | STATEWIDE MOBILITY | 84.87 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
WAKE | I-87 / US 64 / US 264 | SR 2233 (SMITHFIELD ROAD). CONVERT INTERCHANGE TO DIVERGING DIAMOND. | HIGHWAY | 5 | CAPITAL AREA MPO | I-6007 | STATEWIDE MOBILITY | 83.42 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
WAKE | NC 50 (CREEDMOOR ROAD) | I-540 TO NORTH OF NC 98. WIDEN TO MULTILANE DIVIDED ROADWAY. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5891 | REGION C | 73.13 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
WAKE | NC 55 (WILLIAMS STREET) | US 1 TO NORTH OF SR 1160 (OLIVE CHAPEL ROAD). CONVERT EXISTING MULTILANES TO MEDIAN DIVIDED SECTION AND WIDEN REMAINING 2-LANE SECTIONS TO MULTILANES. | HIGHWAY | 5 | CAPITAL AREA MPO | U-2901B | REGION C | 62.77 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | AFTER 2029 | 2031 | 2031
WAKE | NEW ROUTE | SR 1613 (MCCRIMMON PARKWAY) TO NC 540 IN MORRISVILLE. CONSTRUCT MULTILANE FACILITY ON NEW LOCATION. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5966 | REGION C | 74.91 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | AFTER 2029 | 2030 | 2030
WAKE | SR 1002 (AVIATION PARKWAY) | NC 54 TO I-40 IN MORRISVILLE. WIDEN TO MULTILANES WITH INTERCHANGE MODIFICATIONS AT I-40. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5811 | DIVISION 5 | 77.89 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2029 | 2028 | 2026 | 2029 | 2028 | 2026 | AFTER 2029 | 2030 | 2028
WAKE | SR 1010 (TEN-TEN ROAD) | APEX PEAKWAY IN APEX TO SR 1300 (KILDARE FARM ROAD) IN CARY. WIDEN TO MULTILANES. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5825 | DIVISION 5 | 78.01 | P4.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2027 | NOT FUNDED | 2028 | 2027 | NOT FUNDED | 2028 | AFTER 2029 | NOT FUNDED | 2031
WAKE | SR 1115 (AVENT FERRY ROAD) | SR 1116 (CASS HOLT ROAD) TO NC 55 BYPASS IN HOLLY SPRINGS. WIDEN TO MULTILANES, WITH INTERSECTION IMPROVEMENTS AT SR 1116 (CASS HOLT ROAD), SR 1101 (PINEY GROVE-WILBON ROAD) AND NC 55 BYPASS. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5889 | DIVISION 5 | 73.25 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2029 | 2028 | 2026 | 2029 | 2028 | 2026 | AFTER 2029 | 2029 | 2028
WAKE | SR 1152 (HOLLY SPRINGS ROAD) | SR 1010 (TEN-TEN ROAD) TO SR 3977 (CARY PARKWAY). IMPROVE INTERSECTIONS AT SR 1010, SR 1379 (PENNY ROAD), AND SR 3977. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6217 | DIVISION 5 | 93.07 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2029 | NOT FUNDED | 2028 | 2029 | NOT FUNDED | 2028 | AFTER 2029 | NOT FUNDED | 2031
WAKE | SR 1664 (DURALEIGH ROAD) | SR 3009 (EDWARDS MILL ROAD) IN RALEIGH. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6193 | DIVISION 5 | 93.41 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2029 | NOT FUNDED | 2027 | 2029 | NOT FUNDED | 2027 | AFTER 2029 | NOT FUNDED | 2029
WAKE | SR 1728 (WADE AVENUE) | I-40 TO I-440 IN RALEIGH. ADD LANES. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5936 | STATEWIDE MOBILITY | 71.67 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
WAKE | US 1 | I-540 TO NORTH OF SR 2006 (DURANT ROAD) IN RALEIGH. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5307A | STATEWIDE MOBILITY | 71.16 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2026 | 2025 | 2025 | 2026 | 2025 | 2025 | 2026 | 2025
WAKE | US 1 | NORTH OF SR 2006 (DURANT ROAD) IN RALEIGH TO NORTH OF SR 2045 (BURLINGTON MILLS ROAD) IN WAKE FOREST. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5307B | REGION C | 74.76 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2026 | 2027 | 2025 | 2026 | 2027 | 2027 | 2028 | 2029
WAKE | US 1 | NORTH OF SR 2045 (BURLINGTON MILLS ROAD) TO SOUTH OF NC 98 BUSINESS IN WAKE FOREST. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5307C | REGION C | 74.63 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2027 | 2027 | 2025 | 2027 | 2027 | 2027 | 2029 | 2029
WAKE | US 1 | SOUTH OF NC 98 BUSINESS TO SR1909 (PURNELL ROAD) / SR 1931 (HARRIS ROAD) IN WAKE FOREST. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5307D | REGION C | 81.16 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY
WAKE | US 1 | NC 55 IN APEX TO US 64 IN CARY. ADD LANES. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6066 | STATEWIDE MOBILITY | 74.6 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2028 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2025 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY
WAKE | US 401 | SR 1467 / SR 2839 (ALLEN STREET) TO SR 1010 (TEN-TEN ROAD). ADD LANES. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5746 | REGION C | 63.12 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY |  |  |  | 2022 | 2022 | 2022 | 2023 | 2023 | 2024
WAKE | US 401 | NC 55 / NC 42 IN FUQUAY-VARINA. IMPROVE US 401 INTERSECTION WITH NC 55 / NC 42. PROJECT WILL INCLUDE IMPROVEMENTS TO NC 55 INTERSECTION WITH NC 42, AND CONSTRUCTION OF CONNECTOR FROM NC 55 TO SR 5056 (JUDD PARKWAY). | HIGHWAY | 5 | CAPITAL AREA MPO | U-5751 | REGION C | 62.74 | P3.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
WAKE | US 401 | SR 1010 (TEN-TEN ROAD). CONVERT EXISTING SIGNALIZED INTERSECTION TO SQUARE-LOOP INTERCHANGE. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6112 | REGION C | 83.34 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
WAKE | US 401 | SR 1375 (SIMPKINS ROAD) TO SR 2538 (MECHANICAL BOULEVARD) IN GARNER. WIDEN TO 6 LANES AND CONVERT TO SUPERSTREET. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6116 | NOT FUNDED | 81.38 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
WAKE | US 64 | WEST OF SR 1308 (LAURA DUNCAN ROAD) TO US 1 IN APEX AND CARY. CORRIDOR UPGRADE AND IMPROVEMENTS. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5301 | STATEWIDE MOBILITY | 79.44 | P4.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2026 | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2026 | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029
WAKE | US 70 | I-540 TO HILLBURN DRIVE IN RALEIGH. ADD LANES AND CONVERT TO SUPERSTREET. | HIGHWAY | 5 | CAPITAL AREA MPO | U-2823 | STATEWIDE MOBILITY | 73.76 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
WAKE | US 70 / NC 50 | SR 2026 (HAMMOND ROAD) / SR 2812 (TIMBER DRIVE) IN GARNER. CONVERT AT-GRADE INTERSECTION TO INTERCHANGE. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5744 | REGION C | 62.83 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | AFTER 2029 | 2030 | 2030
WAKE | VARIOUS | TOWN OF MORRISVILLE. CONSTRUCT TOWNWIDE ITS / SIGNAL SYSTEM. | HIGHWAY | 5 | CAPITAL AREA MPO | U-5967 | REGION C | 74.62 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY |  |  |  | 2025 | 2025 | 2025 | 2026 | 2026 | 2026
WAKE | VARIOUS | APEX TOWNWIDE SIGNAL SYSTEM. UPGRADE EXISTING INFRASTRUCTURE AND INSTALL NEW FIBER, CONTROLLERS, SIGNALS, AND OTHER EQUIPMENT AS NECESSARY. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6117 | NOT FUNDED | 80.39 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2028 | NOT FUNDED | NOT FUNDED | 2028 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
WAKE | VARIOUS | RALEIGH CITYWIDE SIGNAL SYSTEM. UPGRADE SOFTWARE FOR EXISTING ITS SYSTEM. | HIGHWAY | 5 | CAPITAL AREA MPO | U-6119 | REGION C | 79.28 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2025 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2025 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY
WAKE | VARIOUS | GARNER CITYWIDE SIGNAL SYSTEM | HIGHWAY | 5 | CAPITAL AREA MPO | U-6194 | DIVISION 5 | 93.14 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2028 | NOT FUNDED | 2027 | 2028 | NOT FUNDED | 2027 | AFTER 2029 | NOT FUNDED | 2028
WAKE | VARIOUS | TRIANGLE TOWN CENTER. CONSTRUCT TRANSIT CENTER AND PARK-AND-RIDE FACILITY. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TD-5307 | DIVISION 5 | 95.38 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2022 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  | NOT FUNDED |  | 2023 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY
WAKE | VARIOUS | BUS RAPID TRANSIT SERVICE, MORRISVILLE TO CARY. CONSTRUCT INFRASTRUCTURE, PURCHASE VEHICLES, AND ESTABLISH SERVICE. | PUBLIC TRANSIT | 5 | CAPITAL AREA MPO | TO-6166A | REGION C | 80.37 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2025 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2025 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY
WAKE | CSX | CROSSING 643351A AT SR 1415 (NORTHEAST MAYNARD ROAD) IN CARY. CONSTRUCT GRADE SEPARATION. | RAIL | 5 | CAPITAL AREA MPO | P-5718 | REGION C | 66.73 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
WAKE | CSX S LINE | CONSTRUCT GRADE SEPARATION AT SR 2052 (ROGERS ROAD EXTENSION) CROSSING (633905Y) IN WAKE FOREST. | RAIL | 5 | CAPITAL AREA MPO | P-5707 | REGION C | 56.36 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027: 2024; 2028: 2024; 2029: 2024
WAKE | CSX S LINE | SR 2108 (MILLBROOK ROAD) IN RALEIGH. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 630605A. | RAIL | 5 | CAPITAL AREA MPO | P-5737 | STATEWIDE MOBILITY | 77.72 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2024 | 2024 | 2024
WAKE | CSX S LINE | SR 1415 (WEST MAYNARD ROAD) IN CARY. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 643400U. | RAIL | 5 | CAPITAL AREA MPO | P-5739 | NOT FUNDED | 75.99 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2027 | NOT FUNDED | NOT FUNDED |  | NOT FUNDED |  | 2029 | NOT FUNDED | NOT FUNDED
WAKE | NORFOLK SOUTHERN H LINE | CONSTRUCT GRADE SEPARATION AT HARRISON AVENUE CROSSING (734755X) IN CARY. | RAIL | 5 | CAPITAL AREA MPO | P-5708 | REGION C | 61.77 | P4.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
WAKE | NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN H LINE | SR 2713 (VANDORA SPRINGS ROAD) IN GARNER. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 735324J. | RAIL | 5 | CAPITAL AREA MPO | P-5738 | NOT FUNDED | 77.64 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2026 | NOT FUNDED | NOT FUNDED |  | NOT FUNDED |  | 2028 | NOT FUNDED | NOT FUNDED
WAKE | NORTH CAROLINA RAILROAD / NORFOLK SOUTHERN H LINE | SR 1655 (TRINITY ROAD) IN CARY. CONSTRUCT GRADE SEPARATION AND CLOSE CROSSING 630657S. | RAIL | 5 | CAPITAL AREA MPO | P-5734 | STATEWIDE MOBILITY | 83.07 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2025 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  | FUNDED FOR PRELIMINARY ENGINEERING ONLY |  | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
WAKE | NORTH CAROLINA RAILROAD; NORFOLK SOUTHERN H LINE; | BERYL ROAD CROSSING IN RALEIGH. EXTEND BERYL ROAD TO ROYAL AVENUE, AND CLOSE CROSSING 630647L. | RAIL | 5 | CAPITAL AREA MPO | P-5736 | NOT FUNDED | 78.07 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2026 | NOT FUNDED | NOT FUNDED |  | NOT FUNDED |  | 2027 | NOT FUNDED | NOT FUNDED
WAKE, DURHAM | US 70 (GLENWOOD AVENUE) | WEST OF SR 3067 (T.W. ALEXANDER DRIVE) TO I-540 IN RALEIGH. UPGRADE ROADWAY TO IMPROVE CAPACITY, SAFETY AND TRAFFIC OPERATIONS INCLUDING INTERCHANGES AT VARIOUS LOCATIONS. | HIGHWAY | 5 | CAPITAL AREA MPO, DURHAM-CHAPEL HILL-CARRBORO MPO | U-5518 | STATEWIDE MOBILITY | 74.73 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2026 | 2025 | 2025 | 2026 | 2025 | 2025 | 2026 | 2025
WAKE, JOHNSTON | I-40; I-87; I-440; US 1 / US 64 | I-40 FROM SR 1728 (WADE AVENUE) TO NC 42, I-440, I-87 FROM I-40 TO I-540, US 1 FROM NC 540 TO I-40. CONVERT FACILITIES TO MANAGED FREEWAYS, TO INCLUDE RAMP METERING. | HIGHWAY | 4, 5 | CAPITAL AREA MPO | U-6101 | NOT FUNDED | 81.22 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
WAKE, JOHNSTON | NEW ROUTE (FUTURE NC 540) | EASTERN WAKE FREEWAY / TRIANGLE EXPRESSWAY SOUTHEAST EXTENSION (RALEIGH OUTER LOOP), I-40 TO US 64 / US 264 BYPASS. FREEWAY ON NEW LOCATION. | HIGHWAY | 4, 5 | CAPITAL AREA MPO | R-2829 | STATEWIDE MOBILITY | 82.45 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2026 | 2025 | 2026 | 2026 | 2025 | 2026 | 2028 | 2026
WASHINGTON | SR 1106 (MORATTOCK ROAD) | SR 1100 (LONG RIDGE ROAD) TO NC 32 SOUTH. MODERNIZE ROADWAY. | HIGHWAY | 1 | ALBEMARLE RPO | R-5937 | DIVISION 1 | 73.16 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2030
WASHINGTON | SR 1126 (ROPER NEWLAND ROAD) | SR 1128 (A CANAL ROAD) TO SR 1183 (SHORE DRIVE). MODERNIZE ROADWAY. | HIGHWAY | 1 | ALBEMARLE RPO | R-5936 | DIVISION 1 | 76.22 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2026 | 2026 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2026 | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028
WATAUGA | US 421 (KING STREET) MULTI-USE PATH | GROVE STREET TO BROOKSHIRE ROAD. CONSTRUCT MULTI-USE PATH. | BIKE/PED | 11 | HIGH COUNTRY RPO | EB-5983 | DIVISION 11 | 53.22 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 |  |  |  | 2025 | 2025 | 2025
WATAUGA | NC 105 | SR 1136 (CLARKS CREEK ROAD) TO SR 1107 (NC 105 BYPASS) IN BOONE. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-2566B | REGION F | 76.19 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2024 | 2024 | 2025
WATAUGA | SR 1514 (BAMBOO ROAD); SR 1523 (WILSON RIDGE) | US 421/US 221 TO SR 1522 (DEERFIELD ROAD). MODERNIZE ROADWAY. | HIGHWAY | 11 | HIGH COUNTRY RPO | U-5810 | DIVISION 11 | 61.04 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2024 | 2024 | 2024
WATAUGA | SR 1522 (DEERFIELD ROAD) | STATE FARM ROAD TO SR 1523 (WILSON RIDGE ROAD). UPGRADE ROADWAY. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5830 | DIVISION 11 | 77.77 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025
WATAUGA | US 321 | DEERFIELD ROAD AND MEADOWVIEW ROAD. REALIGN OFFSET INTERSECTION. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5874 | NOT FUNDED | 75.22 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
WATAUGA | US 421 | SR 1180 (POPLAR GROVE CONNECTOR). CONSTRUCT ROUNDABOUT. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5872 | STATEWIDE MOBILITY | 79.62 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | FUNDED FOR PRELIMINARY ENGINEERING ONLY
WATAUGA | US 421 | TENNESSEE LINE TO US 321-US 421 JUNCTION NEAR VILAS. WIDEN TO MULTI-LANES. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5903 | NOT FUNDED | 65.32 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
WATAUGA | US 421 (DANIEL BOONE PARKWAY) | US 321/421 WEST OF BOONE TO NC 105 | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5915A | NOT FUNDED | 59.3 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | PROJECT SEGMENT NOT LISTED IN 2020-2029 STIP | PROJECT SEGMENT NOT LISTED IN DRAFT 2024-2033 STIP (APRIL 2022) | NOT FUNDED | PROJECT SEGMENT NOT LISTED IN 2020-2029 STIP | PROJECT SEGMENT NOT LISTED IN DRAFT 2024-2033 STIP (APRIL 2022) | NOT FUNDED | PROJECT SEGMENT NOT LISTED IN 2020-2029 STIP | PROJECT SEGMENT NOT LISTED IN DRAFT 2024-2033 STIP (APRIL 2022) | NOT FUNDED
WATAUGA | US 421 (DANIEL BOONE PARKWAY) | NC 105 TO US 221/321 SOUTH OF BOONE | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5915B | DIVISION 11 | 59.3 | NOT COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | PROJECT SEGMENT NOT LISTED IN 2020-2029 STIP | PROJECT SEGMENT NOT LISTED IN DRAFT 2024-2033 STIP (APRIL 2022) | 2028 | PROJECT SEGMENT NOT LISTED IN 2020-2029 STIP | PROJECT SEGMENT NOT LISTED IN DRAFT 2024-2033 STIP (APRIL 2022) | 2028 | PROJECT SEGMENT NOT LISTED IN 2020-2029 STIP | PROJECT SEGMENT NOT LISTED IN DRAFT 2024-2033 STIP (APRIL 2022) | 2031
WATAUGA | US 421 (DANIEL BOONE PARKWAY) | US 221/321 TO US 221/421 EAST OF BOONE | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5915C | NOT FUNDED | 59.3 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | PROJECT SEGMENT NOT LISTED IN 2020-2029 STIP | PROJECT SEGMENT NOT LISTED IN DRAFT 2024-2033 STIP (APRIL 2022) | NOT FUNDED | PROJECT SEGMENT NOT LISTED IN 2020-2029 STIP | PROJECT SEGMENT NOT LISTED IN DRAFT 2024-2033 STIP (APRIL 2022) | NOT FUNDED | PROJECT SEGMENT NOT LISTED IN 2020-2029 STIP | PROJECT SEGMENT NOT LISTED IN DRAFT 2024-2033 STIP (APRIL 2022) | NOT FUNDED
WATAUGA | US 421/US 321 | US 321/US 421 JUNCTION NEAR VILAS TO SR 1107 (105 BYPASS) - TERMINI OF PROPOSED DANIEL BOONE PARKWAY (R-5915). WIDEN TO MULTI-LANES. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-2615 | REGION F | 73.42 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2028 | 2027 | 2024 | 2028 | 2027 | 2027 | 2031 | 2030
WAYNE | MOUNT OLIVE MUNICIPAL AIRPORT (W40) | EXTEND RUNWAY TO 5500 FEET. | AVIATION | 4 | EASTERN CAROLINA RPO | AV-5811 | DIVISION 4 | 89.69 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2027: 2029; 2028: FUNDED FOR PRELIMINARY ENGINEERING ONLY; 2029: 2027
WAYNE | WAYNE EXECUTIVE JETPORT (GWW) | EXTEND RUNWAY. | AVIATION | 4 | GOLDSBORO URBAN AREA MPO | AV-5843 | DIVISION 4 | 84.74 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2027: 2029; 2028: FUNDED FOR PRELIMINARY ENGINEERING ONLY; 2029: FUNDED FOR PRELIMINARY ENGINEERING ONLY
WAYNE | GOLDSBORO | BERKELEY BOULEVARD, US 70 BUSINESS (EAST ASH STREET) TO SR 1900 (ELM STREET) IN GOLDSBORO. CONSTRUCT SIDEWALK ON EAST SIDE. | BIKE/PED | 4 | GOLDSBORO URBAN AREA MPO | EB-5850 | DIVISION 4 | 83.16 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027: 2025; 2028: 2025; 2029: 2025
WAYNE | NC 581 (BILL LANE BOULEVARD) | ARRINGTON BRIDGE ROAD TO NC 111. MODERNIZE ROADWAY. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-6207 | DIVISION 4 | 76.66 | NOT COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | 2027 | 2028 | 2028 | 2027 | AFTER 2029 | 2030 | 2029
WAYNE | SR 1556 (WAYNE MEMORIAL DRIVE) | SR 1003 (NEW HOPE ROAD) TO PROPOSED US 70 BYPASS IN GOLDSBORO. WIDEN TO MULTI-LANES. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-4753 | DIVISION 4 | 80.98 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2019 | 2019 | 2019 |  |  |  | 2025 | 2025 | 2025
WAYNE | SR 1556 (WAYNE MEMORIAL DRIVE) | COUNTRY DAY ROAD TO NEW HOPE ROAD. ACCESS MANAGEMENT. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-6204 | DIVISION 4 | 81.83 | NOT COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | 2026 | 2028 | 2028 | 2026 | AFTER 2029 | 2030 | 2028
WAYNE | SR 1556 (WAYNE MEMORIAL DRIVE) | US 70 BYPASS TO SR 1572 (SAULSTON ROAD). WIDEN ROADWAY. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-6205 | DIVISION 4 | 80.32 | NOT COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029
WAYNE | SR 1713 (MILLER'S CHAPEL ROAD) | US 70 TO SR 1712 (THOROUGHFARE ROAD). MODERNIZE ROADWAY. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-6206 | DIVISION 4 | 77.09 | NOT COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | 2027 | 2028 | 2028 | 2027 | AFTER 2029 | 2030 | 2029
WAYNE | US 117 (FUTURE I-795) | NORTH OF SR 1135 (COUNTRY CLUB ROAD) TO SOUTH OF SR 1129 (SOUTH LANDFILL ROAD). | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO, EASTERN CAROLINA RPO | U-3125C | REGION A | 81.08 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2026 | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2026 | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028
WAYNE | US 117 (FUTURE I-795) | SOUTH OF SR 1129 (SOUTH LANDFILL ROAD) TO SOUTH OF SR 1927 (GENOA ROAD). | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-3125D | REGION A | 75.02 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2029
WAYNE | US 117 (FUTURE I-795) | SOUTH OF SR 1927 (GENOA ROAD) TO NORTH OF NC 581 (ARRINGTON BRIDGE ROAD). | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-3125E | NOT FUNDED | 75.02 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
WAYNE | US 117 (FUTURE I-795) | NORTH OF NC 581 (ARRINGTON BRIDGE ROAD) TO I-795. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-3125F | NOT FUNDED | 75.02 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
WAYNE | US 13 (BERKELEY BOULEVARD) | WIDEN TO MULTI-LANES FROM SR 1003 (NEW HOPE ROAD) TO US 70 BYPASS WITH INTERSECTION IMPROVEMENT AT SR1572 (SAULSTON ROAD) | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-3609B | REGION A | 68.64 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2025 | 2025 | 2025
WAYNE | US 70 | SR 1711 (NORTH OAK FOREST ROAD). IMPROVE INTERSECTION. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-6110 | REGION A | 77.91 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2026 | 2025 | 2025 | 2026 | 2025 | 2027 | 2028 | 2027
WAYNE | US 70 BUSINESS (EAST ASH STREET) | SR 1579 (BERKELEY BOULEVARD) EAST TO US 70 IN GOLDSBORO. WIDEN TO MULTI-LANES. | HIGHWAY | 4 | GOLDSBORO URBAN AREA MPO | U-4407 | REGION A | 58.69 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2028 | 2028 | 2026 | 2028 | 2028 | 2026 | AFTER 2029 | 2030 | 2028
WAYNE, GREENE | US 13 | SR 1572 (SAULSTON ROAD) TO SR 1700 (RODELL BARROW ROAD). MODERNIZE ROADWAY. | HIGHWAY | 2, 4 | GOLDSBORO URBAN AREA MPO, EASTERN CAROLINA RPO | R-5853 | DIVISION 2, 4 | 80.23 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2025 | 2025 | 2027 | 2025 | 2025 | 2029 | 2027 | 2027
WAYNE, JOHNSTON | US 70 | US 70 BYPASS TO WEST OF SR 2372 (EDWARDS ROAD / NORTH PEARL STREET). UPGRADE TO FREEWAY STANDARDS. | HIGHWAY | 4 | EASTERN CAROLINA RPO, GOLDSBORO URBAN AREA MPO, UPPER COASTAL PLAIN RPO | R-5829A | STATEWIDE MOBILITY | 75.24 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2025 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2025 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2027 | NOT FUNDED | FUNDED FOR PRELIMINARY ENGINEERING ONLY
WILKES | WILKES COUNTY AIRPORT (UKF) | EXTEND RUNWAY TO 7,000 FEET. | AVIATION | 11 | HIGH COUNTRY RPO | AV-5894 | DIVISION 11 | 57.94 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2023 |  |  |  | 2024 | 2024 | 2024
WILKES | NC 115 | US 421 TO 2ND STREET. WIDEN ROADWAY. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5759 | DIVISION 11 | 65.17 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2022 | 2022 | 2022 | 2022 | 2024 | 2024 | 2024
WILKES | NC 268 | SR 1966 TO FOUR LANES WEST OF SR 2026 (AUSTIN TRAPHILL ROAD). MODERNIZE ROADWAY. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5906 | DIVISION 11 | 77.94 | NOT COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2029 | 2029 | 2029
WILKES | NEW ROUTE | NC 268 CONNECTOR, NC 18 TO US 421. CONSTRUCT MULTI-LANE FACILITY, PART ON NEW LOCATION. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-0616 | NOT FUNDED | 65.13 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2026 | NOT FUNDED | NOT FUNDED | 2026 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED
WILKES | SR 1001 (OAKWOODS ROAD) | US 421 TO FOREST HILLS DRIVE. UPGRADE ROADWAY. | HIGHWAY | 11 | HIGH COUNTRY RPO | R-5772 | DIVISION 11 | 60.54 | P4.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2025 | 2026 | 2026 | 2025 | 2026 | 2028 | 2027 | 2028
WILSON | NC 58 (NASH STREET NW) | SR 1330 (AIRPORT ROAD)/SR 1332 (LAKE WILSON ROAD). IMPROVE INTERSECTION. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | U-6111 | REGION A | 77.29 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2025 | 2028 | 2027 | 2025 | 2028 | 2027 | AFTER 2029 | 2030 | 2029
WILSON | SR 1309 (BLOOMERY ROAD) / SR 1382 (PACKHOUSE ROAD) | US 264 ALTERNATE TO NC 58. WIDEN AND UPGRADE FACILITY. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | U-5794 | DIVISION 4 | 65.67 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2022 | 2022 | 2023 | 2022 | 2022 | 2023 | 2025 | 2025 | 2025
WILSON | US 264 ALTERNATE (RALEIGH ROAD PARKWAY) | SR 1320 (AIRPORT BOULEVARD) TO EAST OF SR 1165 (FOREST HILLS ROAD). SAFETY IMPROVEMENTS. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | U-5941 | REGION A | 77.69 | P5.0 COMMITTED | WILL BE REPRIORITIZED | SCHEDULED FOR DELIVERY | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2026 | 2028 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2026 | AFTER 2029 | FUNDED FOR PRELIMINARY ENGINEERING ONLY | 2028
WILSON | WILSON | WILSON CITY SIGNAL SYSTEM. | HIGHWAY | 4 | UPPER COASTAL PLAIN RPO | U-5945 | NOT FUNDED | 70.97 | P5.0 COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2025 |  |  | 2025 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
YADKIN | NC 67 | US 601 IN BOONVILLE TO WEST MAIN STREET IN EAST BEND. MODERNIZE ROADWAY WITH INTERSECTION IMPROVEMENTS AT NEBO ROAD. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5914 | DIVISION 11 | 59.96 | NOT COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027 | 2027 | 2026 | 2027 | 2027 | 2026 | AFTER 2029 | 2029 | 2028
YADKIN | SR 1314 (EAST MAIN STREET) | US 601 TO SR 1765 (UNIFI INDUSTRIAL ROAD) IN YADKINVILLE. MODERNIZE ROADWAY, INCLUDING IMPROVEMENTS AT THE US 601 AND VAN BUREN STREET INTERSECTIONS. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5909 | DIVISION 11 | 75.92 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2028 | 2028 | 2028
YADKIN | SR 1605 (OLD US 421) | SR 1600 (FALCON ROAD) INTERSECTION. CONSTRUCT ROUNDABOUT. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5912 | DIVISION 11 | 65.58 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024
YADKIN | US 601 | NC 67 TO (SR 1502/1503) COUNTRY CLUB ROAD. MODERNIZE ROADWAY AND IMPROVE SR 1134 (MACKIE ROAD) INTERSECTION. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5896 | NOT FUNDED | 69.86 | NOT COMMITTED | WILL BE REPRIORITIZED | WILL BE REPRIORITIZED | 2029 | NOT FUNDED | NOT FUNDED | 2029 | NOT FUNDED | NOT FUNDED | AFTER 2029 | NOT FUNDED | NOT FUNDED
YADKIN | US 601 (SOUTH STATE STREET) | US 421 EASTBOUND RAMPS. INSTALL ROUNDABOUT. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5894 | REGION F | 79 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2026 | 2026 | 2026
YADKIN | US 601 (STATE STREET) | US 421 TO SR 1146 (LEE AVENUE). CONSTRUCT MEDIAN AND ROUNDABOUTS. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | U-5809 | DIVISION 11 | 65.08 | P3.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2027: 2023; 2027: 2024; 2028: 2025; 2029: 2024
YADKIN, SURRY | NC 67, US 21 BUSINESS | COMMERCE STREET IN ELKIN TO NORTH BRIDGE STREET IN JONESVILLE. WIDEN ROADWAY, CONSTRUCT ROUNDABOUTS AT WEST MAIN STREET AND ELM STREET AND ELM STREET AND NORTH BRIDGE STREET, AND IMPROVE BICYCLE AND PEDESTRIAN CONNECTIONS. | HIGHWAY | 11 | NORTHWEST PIEDMONT RPO | R-5913A | DIVISION 11 | 65.23 | P5.0 COMMITTED | SCHEDULED FOR DELIVERY | SCHEDULED FOR DELIVERY | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2025 | 2025 | 2025

## Fund Sources
Fund Source | Fund Type | Description | Subject to STI
3037 | Federal | Job Assistance and Reverse Commute | No
5303 | Federal | Metropolitan Planning (FMPL) | No
5305 | Federal | FTA Discretionary Grant Funds | No
5307 | Federal | Urbanized Area Formula Program (FUZ) | No
5309 | Federal | Capital Program - Bus Earmark (FBUS) | No
5310 | Federal | Elderly and Persons with Disability (FEPD) | No
5311 | Federal | Non Urbanised Area Formula Program (FNU) | No
5312 | Federal | FUZ 5312 | No
5316 | Federal | Job Assistance And Reverse Commute (JARC) | No
5317 | Federal | New Freedom Program | No
5337 | Federal | Urbanized Area Formula Program (FUZ) | No
5339 | Federal | Capital Program - Bus Earmark (FBUS) | No
5339(b) | Federal | Capital Program - Bus Earmark (FBUS) - Discretionary Grant | No
ADHS | Federal | Appalachian Development Highway System | No
ADHSL | Federal | Appalachian Development Highway System (Local Access Roads) | No
ADTAP | Federal | Appalachian Development portion of 5311 - Non Urbanised Area Formula Program (FNU) | No
ARP | Federal | American Rescue Plan | No
BA | State | Bonus Allocation | No
BFP | Federal | Federal Bridge Improvement Program - Formula | Yes
BFPOFF | Federal | Federal Bridge Improvement Program - Formula (Off System) | Yes
BG | Federal | Surface Transportation Block Grant Program (Uncategorized) | Yes
BG5200 | Federal | Surface Transportation Block Grant Program (5K - 200K) | Yes
BGANY | Federal | Surface Transportation Block Grant Program (Any Area) | Yes
BGBA | Federal | Surface Transportation Block Grant Program (Bonus Allocation) | No
BGDA | Federal | Surface Transportation Block Grant Program (Direct Attributable) | Yes
BGDACV | Federal | COVID Relief Funds | Yes
BGIM | Federal | Surface Transportation Block Grant Program (Interstate Maintenance) | Yes
BGLT5 | Federal | Surface Transportation Block Grant Program (Less than 5K) | Yes
BGOFF | Federal | Surface Transportation Block Grant Program (Off System) | Yes
BOND R | Other | Revenue Bond | No
BRGI | Federal | Bridge Inspection | Yes
CARES | Federal | CARES Act Funding | No
CMAQ | Federal | Congestion Mitigation | No
CRP550 | Federal | Carbon Reduction Program - (5K - 50K) | No
CRPANY | Federal | Carbon Reduction Program - Any Area | No
CRPDA | Federal | Carbon Reduction Program - Direct Attributable (All MPOs) | No
CRPLT5 | Federal | Carbon Reduction Program - (Less than 5K) | No
DOD | Federal | Department of Defense | No
DP | Federal | Discretionary or Demonstration | No
ER | Federal | Emergency Relief | No
ERFO | Federal | Emergency Relief for Federally Owned Roads | No
FED | Federal | Unidentified Federal Funding | No
FEDT | Federal | Undesignated Federal Transit Funding | No
FF | Federal | FEDERAL FERRY | Yes
FLAP | Federal | Federal Lands Access Program (Park Roads) | No
FLPF | Federal | Federal Lands Program (Forest Roads) | No
FLTP | Federal | Federal Lands Transportation Program | No
FMOD | Federal | Fixed Guideway Modifications | Yes
FSPR | Federal | State Planning and Research | No
FTTP | Federal | Federal Tribal Transportation Program | No
FUZ | Federal | Capital Program - Bus Earmark (5309) | No
HF | State | Highway Fund | No
HFB | State | Highway Fund Bridge Replacement Program | Yes
HIB | Federal | Highway Infrastructure Bridge Replacement | Yes
HP | Federal | High Priority | Yes
HRRR | Federal | High Risk Rural Roads | Yes
HSIP | Federal | HIGHWAY SAFETY IMPROVEMENT PROGRAM | Yes
L | Other | Local | No
NEVI | Federal | National Electric Vehicle Infrasructure Program Funds | Yes
NHFP | Federal | National Highway Freight Program | Yes
NHP | Federal | National Highway Performance Program | Yes
NHPB | Federal | National Highway Performance Program(Bridge) | Yes
NHPBA | Federal | National Highway Performance Program(Bonus Allocation) | No
NHPIM | Federal | National Highway Performance Program (Interstate Maintenance) | Yes
NRT | Federal | National Recreation Trails | Yes
O | Other | Local, Non Federal or State Funds | No
PROTCT | Federal | PROTECT Formula Program (Promoting Resilient Operations…) | Yes
RR | Federal | Rail-Highway Safety | Yes
RTAP | Federal | Rural Transit Assistance Program | No
S | State | State | No
S(M) | State | State Match for STP-DA or Garvee Projects | Yes
S(M)BA | State | State Match for Bonus Allocation Projects using Federal funds | No
SBG | Federal | Scenic Byway Grant | Yes
SF | State | Ferries | Yes
SMAP | State | Operating Assistance and State Maintenance | No
SRTS | Federal | Safe Roads to School | Yes
SSO | Federal | Safety System Oversight | No
STHSR | Federal | Stimulus High Speed Rail | No
T | State | Highway Trust Funds | Yes
T(DA) | State | Highway Trust Funds - Fund Swaps for DA Projects | Yes
TA | Federal | Transportation Alternatives Program (Uncategorized) | Yes
TA5200 | Federal | Transportation Alternatives Program (5K - 200K) | Yes
TAANY | Federal | Transportation Alternatives Program (Any Area) | Yes
TADA | Federal | Transportation Alternatives Program (Direct Attributable) | Yes
TALT5 | Federal | Transportation Alternatives Program (Less than 5K) | Yes
TAP | Federal | Transportation Alternatives Program (Uncategorized) | Yes
TAPDA | Federal | Transportation Alternatives Program (Direct Attributable) | Yes